## MyWells Drilling Comp
NOOP Document Date | FWR Document Date | PAC Name | Region Name | Field Name | Well Name | Well Type | Rig Name | Rig Type | Water Depth (m) | Total Well Depth MD Plan (m) | Total Well Depth TVD Plan (m) | AFE Cost Dry (usd) | AFE Cost Success (usd) | AFE Days Dry | AFE Days Success | AFE Cost (usd) | AFE Days | Special Status | Alternative Well Name | Tree Type | Spud Date | Well Start Date Time | Well End Date Time | Meterage Drilled (m) | Water Depth Category | Total Well Depth MD Actual (m) | Total Well Depth TVD Actual (m) | Final Cost Dry (usd) | Final Cost Success (usd) | Final Days Dry | Final Days Success | Final Cost (usd) | Final Days | Well NPT Percentage WOW (%) | Well NPT Percentage (%) | Drilling Min Standard | DMS | Plan DDPTF (days/1000ft) | Plan DDPTF | Plan DCPF (usd/ft) | Plan DCPF | Plan WCPF (usd/ft) | Plan WCPF | Actual DDPTF (days/1000ft) | Actual DDPTF | Actual DCPF (usd/ft) | Actual DCPF | Actual WCPF (usd/ft) | Actual WCPF | Completion Days Plan | Completion Cost Plan | Completion Min Standard | Plan CDPTF (days/1000ft) | Plan CCPF (usd/ft) | Completion Days Actual | Completion Cost Actual | Actual CDPTF (days/1000ft) | Actual CCPF (usd/ft) | Producing Formation | Pressure Temperature | Completion Type | Smart Well | ESP | Tubing Size (inch) | Zones | Number Of String | Tubing Material | Sand Control Length (ft) | PDG | OH Inflow Control | Completion Material | Completion Fluid Weight (ppg) | Completion Fluid Type | Chemical Injection Valve | Intelligent Gas Lift | Availability
2023-03-07 | 2023-11-02 | VESTIGO | PM | LARUT | LARUT A-26ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 4127.49 | 2338.05 | N/A | N/A | N/A | N/A | 6560000 | 14.29 | NO | N/A | DRY TREE | 2023-08-25 | 2023-08-24 19:00 | 2023-09-07 05:00 | 4026.63 | SHALLOW WATER | 4121.5 | 2333.55 | N/A | N/A | N/A | N/A | 4668369 | 13.42 | 8.01 | 8.01 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 1.3 | yes | 325 | yes | 454 | [5 empty] | 1.81 | 1318987.36 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 65.62 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-03-07 | 2024-01-03 | VESTIGO | PM | LARUT | LARUT-A09ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3407.5 | 1961.86 | N/A | N/A | N/A | N/A | 7120000 | 17.85 | NO | N/A | DRY TREE | 2023-10-21 | 2023-10-21 01:30 | 2023-11-14 02:30 | 3665.13 | SHALLOW WATER | 3760 | 2047.8 | N/A | N/A | N/A | N/A | 4734531 | 12.6 | 0 | 0 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 1.18 | yes | 329 | yes | 444 | [5 empty] | 1.72 | 1220042.76 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 72.182 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-03-07 | 2023-11-21 | VESTIGO | PM | LARUT | LARUT-A29ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3003.4 | 2625.4 | N/A | N/A | N/A | N/A | 6779320 | 13.52 | NO | N/A | DRY TREE | 2023-08-08 | 2023-08-06 19:00 | 2023-09-22 06:00 | 2871.13 | SHALLOW WATER | 2966 | 2622.8 | N/A | N/A | N/A | N/A | 5474865 | 16 | 34.32 | 34.32 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 2.43 | yes | 601 | yes | 830 | [5 empty] | 1.34 | 1326979.37 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 131.24 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-03-07 | 2023-08-23 | VESTIGO | PM | LARUT | LARUT-A24 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 2292.82 | 1977.19 | N/A | N/A | N/A | N/A | 4563572.58 | 9.51 | SIDETRACK | N/A | DRY TREE | 2023-06-28 | 2023-06-28 07:00 | 2023-07-08 | 2200.13 | SHALLOW WATER | 2295 | 1980.27 | N/A | N/A | N/A | N/A | 3572118 | 9.71 | 2.15 | 2.15 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 1.88 | yes | 484 | yes | 693 | [5 empty] | 1.73 | 1081149.58 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 55.777 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-24 | 2024-01-19 | VESTIGO | PM | LARUT | LARUT-A01ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3914.35 | 2534.7 | N/A | N/A | N/A | N/A | 8235192 | 17.9 | NO | N/A | DRY TREE | 2023-10-06 | 2023-10-04 08:30 | 2023-11-22 20:30 | 3138.13 | SHALLOW WATER | 3233 | 2511.69 | N/A | N/A | N/A | N/A | 8072116 | 25.46 | 12.07 | 12.07 | SW DEV ST 2HS OHPDL | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1400 | yes | 2.41 | yes | 725 | yes | 1014 | [5 empty] | 5.48 | 2303835.68 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 207.52 | False |  | L80 13CR | 9.2 | KCL | NO | NO | Exist
2023-02-24 | 2023-11-09 | VESTIGO | PM | LARUT | LARUT-A30ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3253.5 | 1981.75 | N/A | N/A | N/A | N/A | 5350000 | 11.62 | NO | N/A | DRY TREE | 2023-08-02 | 2023-07-31 08:30 | 2023-09-11 22:00 | 3310.13 | SHALLOW WATER | 3405 | 2042.65 | N/A | N/A | N/A | N/A | 3884000 | 11.15 | 1.68 | 1.68 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 1.4 | yes | 366 | yes | 489 | [5 empty] | 1.45 | 977143.36 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 141.083 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-24 | 2023-12-13 | VESTIGO | PM | LARUT | LARUT A-36ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 4156.72 | 2171.3 | N/A | N/A | N/A | N/A | 7175927 | 15.48 | NO | N/A | DRY TREE | 2023-09-27 | 2023-06-02 03:00 | 2023-11-07 19:00 | 4161.13 | SHALLOW WATER | 4256 | 2205.85 | N/A | N/A | N/A | N/A | 7033425 | 21.64 | 7.51 | 7.51 | SW DEV C3 MONOBORE | SW DEV C3 | Yes | 2.2 | Yes | 915 | Yes | 1290 | yes | 1.64 | yes | 458 | yes | 534 | [5 empty] | 1.69 | 993710.05 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 108.273 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-23 | 2023-11-21 | VESTIGO | PM | LARUT | LARUT-A23ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3198.27 | 2060.55 | N/A | N/A | N/A | N/A | 5184350 | 11.24 | NO | N/A | DRY TREE | 2023-08-14 | 2023-08-13 02:30 | 2023-09-26 15:15 | 3005.13 | SHALLOW WATER | 3100 | 2097.55 | N/A | N/A | N/A | N/A | 3886398 | 10.55 | 5.53 | 5.53 | SW DEV ST 2HS MONOBORE | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1200 | yes | 1.44 | yes | 392 | yes | 532 | [5 empty] | 1.4 | 889555.54 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 62.339 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-09 | 2023-09-27 | VESTIGO | PM | LARUT | LARUT A-35 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 5658 | 2334.8 | N/A | N/A | N/A | N/A | 9780000 | 20.94 | NO | N/A | DRY TREE | 2023-05-30 | 2023-05-29 22:00 | 2023-07-31 08:30 | 5526.13 | SHALLOW WATER | 5621 | 2317 | N/A | N/A | N/A | N/A | 11405366 | 37.5 | 0.34 | 0.34 | SW DEV C3 MONOBORE | SW DEV C3 | Yes | 2.2 | Yes | 915 | Yes | 1290 | yes | 1.71 | yes | 432 | yes | 529 | [5 empty] | 2.6 | 1866911.13 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 42.653 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-09 | 2023-11-21 | VESTIGO | PM | LARUT | LARUT-A31ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 3198.27 | 2060.55 | N/A | N/A | N/A | N/A | 5184350 | 11.24 | RE-SPUD | N/A | DRY TREE | 2023-08-14 | 2023-08-13 | 2023-09-26 | 3005.13 | SHALLOW WATER | 3100 | 2097.43 | N/A | N/A | N/A | N/A | 3886398 | 10.55 | 5.5 | 5.5 | SW DEV ST 2HS OHPDL | SW DEV ST 2HS | Yes | 2.4 | Yes | 795 | Yes | 1400 | yes | 2.7 | yes | 709 | yes | 917 | [5 empty] | 7.75 | 3082902.75 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 823.2882 | False |  | L80 13CR | 9.2 | KCL | NO | NO | Exist
2023-02-09 | 2023-09-07 | VESTIGO | PM | LARUT | LARUT A-34 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 60 | 4112.23 | 2024.08 | N/A | N/A | N/A | N/A | 8214591 | 17.58 | NO | N/A | DRY TREE | 2023-05-23 | 2023-05-21 18:00 | 2023-07-13 | 3930.13 | SHALLOW WATER | 4025 | 1998.44 | N/A | N/A | N/A | N/A | 6690870 | 21.57 | 2.08 | 2.08 | SW DEV C3 MONOBORE | SW DEV C3 | Yes | 2.2 | Yes | 915 | Yes | 1290 | yes | 1.63 | yes | 413 | yes | 507 | [5 empty] | 2 | 1233995.02 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 108.273 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-05-14 | 2019-10-09 | VESTIGO | SK | ANJUNG KECIL | AJK-A2ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.5 | 2504 | 1713 | N/A | N/A | N/A | N/A | 8100000 | 20.5 | NO | N/A | DRY TREE | 2019-07-12 | 2019-05-30 18:00 | 2019-08-31 00:30 | 2439.35 | SHALLOW WATER | 2545 | 1712 | N/A | N/A | N/A | N/A | 6081416 | 21.14 | 6.6 | 6.6 | SW DEV C4 OHSAS/OHPDL | SW DEV C4 | Yes | 2.5 | Yes | 1010 | Yes | 1705 | yes | 1.49 | yes | 383 | yes | 728 | [5 empty] | 6.5 | 2155737 |  |  | CARBONATE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 187.3779 | False | ICD | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-05-07 | 2019-09-12 | PCSB | SK | ANJUNG | ANJUNG-A3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 76 | 2364.06 | 1974.91 | N/A | N/A | N/A | N/A | 15765611.55 | 44.83 | NO | N/A | DRY TREE | 2019-06-12 | 2019-06-11 06:00 | 2019-08-13 06:30 | 2227.92 | SHALLOW WATER | 2347.7 | 1976.89 | N/A | N/A | N/A | N/A | 15622645.61 | 43.3 | 13.11 | 13.11 | SW DEV C4 OHPDL | SW DEV C4 | Yes | 2.5 | Yes | 1010 | Yes | 1705 | 2.34 | 2.34 | 747 | 747 | 1802 | 1802 | [5 empty] | 12.65 | 3107335.53 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | L80 13CR | 0 | True |  | SUPER 13CR | 10.3 | NACOOH | NO | NO | Exist
2018-09-26 | 2019-03-22 | SHELL | SB | GEMILANG | GEMILANG-1 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 1022.25 | 2885.71 | 2693.69 | 23400000 | 31480000 | 34.2 | 45.3 | N/A | N/A | NO | N/A | N/A | 2018-12-11 | 2018-11-11 21:00 | 2018-12-27 21:00 | 1838.46 | DEEP WATER | 2885.71 | 2668.7 | N/A | 31500000 | N/A | 45.3 | N/A | N/A | 11.65 | 11.65 | No DMS category. Having value but not sure refering which version | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2018-08-21 | 2018-12-28 | REPSOL | PM | BUNGA ORKID | BOB-9(J) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.6 | 4530.1 | 2190 | N/A | N/A | N/A | N/A | 14900000 | 42.14 | NO | N/A | DRY TREE | 2018-09-11 | 2018-09-04 19:00 | 2018-11-07 01:30 | 4652.6 | SHALLOW WATER | 4745 | 2222.84 | N/A | N/A | N/A | N/A | 13977440 | 63.27 | 33.55 | 19.07 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 18 | 4000000 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2237.5328 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2018-08-02 | N/A | REPSOL | PM | BUNGA PAKMA | BPA-6 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 4278 | 3029 | N/A | N/A | N/A | N/A | 8366634 | 22 | NO | N/A | DRY TREE | 2018-08-14 | 2018-08-12 20:00 | 2018-09-03 | 4177.13 | SHALLOW WATER | 4278 | 3029 | N/A | N/A | N/A | N/A | 6700000 | 21.17 | 8.3 | 8.3 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 6.51 | 2629741 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 63.9764 | True | NONE | L80 13CR | 6.84 | BASE OIL/DIESEL | NO | NO | Exist
2018-07-19 | 2018-11-16 | SHELL | SK | RERAMA | RERAMA-1 | EXPLORATION/APPRAISAL | NAGA-7 | JACK UP | 60.65 | 1829.02 | 1430.36 | 9517000 | 13400000 | 22.43 | 30.29 | N/A | N/A | NO | N/A | N/A | 2018-09-08 | 2018-09-03 20:30 | 2018-09-27 17:45 | 1376.1 | SHALLOW WATER | 1467.54 | 1467.54 | 5640000 | N/A | 23.89 | N/A | N/A | N/A | 4.23 | 4.23 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2018-06-17 | 2018-08-22 | REPSOL | PM | BUNGA PAKMA | BPA-4 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 4887 | 3353 | N/A | N/A | N/A | N/A | 14232446 | 33.29 | NO | N/A | DRY TREE | 2018-06-18 | 2018-06-18 09:30 | 2018-08-12 20:00 | 4849.13 | SHALLOW WATER | 4950 | 3422 | N/A | N/A | N/A | N/A | 11240000 | 33.3 | 8.09 | 8.03 | SW DEV C2 PM - MONOBORE | SW DEV C2 | Yes | 3.2 | Yes | 1300 | Yes | 1600 | Yes | 1.97 | Yes | 669 | Yes | 757 | [5 empty] | 6.57 | 1902000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 63.9764 | True | NONE | L80 13CR | 6.84 | BASE OIL/DIESEL | NO | NO | Exist
2018-04-11 | 2018-07-05 | REPSOL | SB | KINABALU | KNDW-D08 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3801.89 | 2426.7 | N/A | N/A | N/A | N/A | 14724389 | 30.34 | NO | N/A | N/A | 2018-04-25 | 2018-04-25 08:00 | 2018-05-17 02:00 | 3806.77 | SHALLOW WATER | 3901.25 | 2425.78 | N/A | N/A | N/A | N/A | 9031731 | 21.75 | 1.3 | 1.3 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2018-04-01 | 2018-07-05 | REPSOL | PM | BUNGA PAKMA | BPA-1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 3268 | 2947.1 | N/A | N/A | N/A | N/A | 12440000 | 30.7 | NO | N/A | N/A | 2018-04-12 | 2018-04-12 | 2018-05-06 | 3154.13 | SHALLOW WATER | 3255 | 2926 | N/A | N/A | N/A | N/A | 8530528 | 24 | 14 | 14 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2018-03-29 | 2018-06-25 | PCSB | SB | SAMARANG | SM-37ST | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 47 | 3049.38 | 2295.03 | N/A | N/A | N/A | N/A | 10498894 | 40.21 | NO | N/A | DRY TREE | 2018-05-04 | 2018-05-04 | 2018-05-20 | 2740.57 | SHALLOW WATER | 2822.31 | 2110.94 | N/A | N/A | N/A | N/A | 5170000 | 22.1 | 0.28 | 0.28 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 6.29 | 2046460 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 | 600 | False | NONE | 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-03-22 | 2018-06-20 | REPSOL | SB | KINABALU | KNDW-D16 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 2133.8 | 1977.14 | N/A | N/A | N/A | N/A | 10567967 | 21 | NO | N/A | N/A | 2018-04-10 | 2018-04-09 14:00 | 2018-04-24 09:00 | 2005.18 | SHALLOW WATER | 2099.66 | 1933.86 | N/A | N/A | N/A | N/A | 6043404 | 14.83 | 0.13 | 0.13 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2018-02-21 | 2018-05-03 | REPSOL | SB | KINABALU | KNDW-D02 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 4323.97 | 3669.03 | N/A | N/A | N/A | N/A | 15840192 | 36.98 | NO | N/A | N/A | 2018-03-09 | 2018-03-08 14:00 | 2018-04-09 13:00 | 4203.9 | SHALLOW WATER | 4298.38 | 3667.03 | N/A | N/A | N/A | N/A | 13783161.02 | 31.96 | 3.46 | 3.46 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2017-10-13 | 2018-06-19 | ROC OIL | SK | J4 | J4-A09 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 53.64 | 1956.11 | 1956.11 | N/A | N/A | N/A | N/A | 11610000 | 24.48 | NO | N/A | N/A | 2018-01-01 | 2017-12-31 | 2018-04-19 | 2120.7 | SHALLOW WATER | 2217.31 | 1630.57 | N/A | N/A | N/A | N/A | 8668774 | 33.63 | 7.52 | 7.24 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2017-04-03 | 2017-11-10 | ROC OIL | SK | D21 | D21-A7ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 50.59 | 3913.44 | 2294.18 | N/A | N/A | N/A | N/A | 11189579 | 27.45 | NO | N/A | N/A | 2017-07-03 | 2017-06-27 12:00 | 2017-09-14 | 3817.13 | SHALLOW WATER | 3913.44 | 2294.26 | N/A | N/A | N/A | N/A | 14508177 | 47.83 | 25.72 | 25.7 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2017-04-01 | 2017-09-11 | REPSOL | PM | BUNGA ORKID | NBO-4 | EXPLORATION/APPRAISAL | ENSCO-52 | JACK UP | 54.7 | 4174 | 2471 | 25018081 | 25018081 | 70.26 | 70.26 | N/A | N/A | SIDETRACK | N/A | N/A | 2017-05-20 09:30 | 2017-05-14 10:30 | 2017-08-08 09:00 | 3145.3 | SHALLOW WATER | 3230 | 2009 | N/A | 20595074 | N/A | 54.94 | N/A | N/A | 13.27 | 13.25 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2017-03-27 | 2017-11-13 | ROC OIL | SK | D21 | D21-P1 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 50.59 | 2796.71 | 2183.18 | N/A | N/A | N/A | N/A | 11000000 | 23.29 | NO | N/A | N/A | 2017-05-17 17:15 | 2017-05-12 08:30 | 2017-09-12 04:00 | 2677.23 | SHALLOW WATER | 2773.54 | 2158.06 | N/A | N/A | N/A | N/A | 10427402 | 29.15 | 10.25 | 10.25 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2017-02-03 | 2017-06-21 | PETROFAC | PM | WEST DESARU | WD-A17ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 65.8 | 2830 | 1604 | N/A | N/A | N/A | N/A | 7142000 | 23.9 | NO | N/A | DRY TREE | 2017-05-04 | 2017-05-04 | 2017-05-26 | 2738.74 | SHALLOW WATER | 2848 | 1608 | N/A | N/A | N/A | N/A | 6940000 | 22.2 | 2.82 | 2.82 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 8.82 | 3317397.69 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 2-7/8" | 1.0 | SINGLE | L80 13CR | 0 | False |  | L80 13CR | 9.1 | NACL | NO | NO | Exist
2016-06-09 | 2017-03-09 | NOEX | SK | LAYANG | LAYANG-2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 87 | 4028 | 3635 | N/A | N/A | N/A | N/A | 23294644 | 46.81 | SIDETRACK | N/A | N/A | 2016-08-04 | 2016-08-04 | 2017-01-07 12:00 | 4232.8 | SHALLOW WATER | 4350 | 3663 | N/A | N/A | N/A | N/A | 25292683 | 83.41 | 0.46 | 0.46 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2016-03-07 | 2016-05-12 | EMEPMI | PM | GUNTONG | GUNTONG-C14ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 2240 | 1978 | N/A | N/A | N/A | N/A | 13600000 | 24.6 | SIDETRACK | N/A | N/A | 2016-03-22 | 2016-03-22 | 2016-04-03 | 2143 | SHALLOW WATER | 2240 | 1978 | N/A | N/A | N/A | N/A | 11500000 | 13.6 | 3.5 | 3.5 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2016-02-12 | 2016-04-21 | EMEPMI | PM | GUNTONG | GUNTONG-C05ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 2565 | 2021 | N/A | N/A | N/A | N/A | 19820000 | 26 | NO | N/A | N/A | 2016-02-21 | 2016-02-21 | 2016-03-11 | 2470 | SHALLOW WATER | 2567 | 2021 | N/A | N/A | N/A | N/A | 11700000 | 19.25 | 0.78 | 0.78 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2015-11-30 | 2016-02-24 | EMEPMI | PM | GUNTONG | GUNTONG-C10 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 3310 | 1954 | N/A | N/A | N/A | N/A | 11600000 | 21.1 | SIDETRACK | N/A | N/A | 2015-12-13 12:00 | 2015-12-13 12:00 | 2016-01-10 | 3208 | SHALLOW WATER | 3305 | 1948 | N/A | N/A | N/A | N/A | 9300000 | 21.04 | 12.7 | 12.7 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2015-08-21 | 2015-11-06 | PCSB | SB | SAMARANG | SAMARANG EAST-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 10.06 | 2900.94 | 2232.25 | 15563188.7 | 15563188.7 | 26.4 | 26.4 | N/A | N/A | NO | N/A | N/A | 2015-09-08 08:00 | 2015-09-03 | 2015-10-14 | 2982.81 | SHALLOW WATER | 3023.47 | 2262.72 | N/A | 15120935.36 | N/A | 37.17 | N/A | N/A | 5.38 | 5.38 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2015-01-22 | 2015-08-13 | PCSB | SK | BAYAN | BAYAN-220 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 29.26 | 2282.84 | 1427.92 | N/A | N/A | N/A | N/A | 20890000 | 23.38 | NO | N/A | DRY TREE | 2015-05-07 | 2015-05-06 | 2015-07-07 | 2014.32 | SHALLOW WATER | 2093.57 | 1236.21 | N/A | N/A | N/A | N/A | 11194140.52 | 28.86 | 8.63 | 5.91 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2014-12-17 | 2015-07-14 | PCSB | SK | BAYAN | BAYAN-221 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 29.26 | 2199.33 | 1261.2 | N/A | N/A | N/A | N/A | 19106060.88 | 26.2 | SIDETRACK | N/A | N/A | 2015-03-10 | 2015-03-03 | 2015-06-15 | 1776.29 | SHALLOW WATER | 1855.53 | 1256.63 | N/A | N/A | N/A | N/A | 16347000 | 31.9 | 41.7 | 41.7 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2014-12-05 | 2015-06-18 | PCSB | SK | BAYAN | BAYAN-223 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 29.26 | 2582.14 | 1360.26 | N/A | N/A | N/A | N/A | 20340000 | 28 | NO | N/A | DRY TREE | 2015-02-18 09:00 | 2015-02-15 04:45 | 2015-04-16 | 2539.26 | SHALLOW WATER | 2615.15 | 1357.51 | N/A | N/A | N/A | N/A | 63600000 | 41.35 | 27.7 | 27.7 | SW DEV C1 | SW DEV C1 | Yes | 2.2 | Yes | 830 | Yes | 1395 | No |  | No |  | No | [27 empty] | Exist
2014-12-01 | N/A | SHELL | SB | SOUTH FURIOUS | SF-16S2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 49.07 | 1471.5 | 1122.52 | N/A | N/A | N/A | N/A | 113600000 | 56.8 | SIDETRACK | N/A | N/A | 2015-01-31 | 2015-01-31 | 2015-02-18 | 1397.9 | SHALLOW WATER | 1490.09 | 1134.72 | N/A | N/A | N/A | N/A | 36039203 | 69.5 | 2.74 | 2.74 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2014-10-23 | 2015-04-21 | EMEPMI | PM | TELOK | TELOK-B4 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 63.6 | 2746 | 2134 | N/A | N/A | N/A | N/A | 25500000 | 47.2 | NO | N/A | DRY TREE | 2014-11-10 09:00 | 2014-11-09 07:30 | 2015-03-12 17:00 | 2601.53 | SHALLOW WATER | 2710 | 2107.2 | N/A | N/A | N/A | N/A | 21232400 | 30.4 | 9.74 | 9.74 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 4.18 | 3161620.82 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 5.0 | DUAL | L80 13CR | 2490 | True | NONE | L80 13CR | 9.5 | NACL | NO | NO | Exist
2014-08-04 | 2015-05-21 | EMEPMI | PM | TELOK | TELOK-B6 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 63.6 | 2370 | 1160 | N/A | N/A | N/A | N/A | 25900000 | 40.3 | NO | N/A | N/A | 2014-11-06 11:00 | 2014-11-05 | 2015-03-12 05:00 | 2332.53 | SHALLOW WATER | 2441 | 1175.89 | N/A | N/A | N/A | N/A | 21609800 | 28.44 | 5.41 | 5.41 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2014-06-26 | 2014-10-15 | SAPURA OMV | PM | EAST BELUMUT | EB A-08ST1 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 3377.77 | 1167.65 | N/A | N/A | N/A | N/A | 14391370 | 24.98 | NO | N/A | N/A | 2014-08-12 | 2014-08-12 12:00 | 2014-08-28 14:00 | 3306.3 | SHALLOW WATER | 3423 | 1167.12 | N/A | N/A | N/A | N/A | 9056198 | 16.08 | 6.93 | 6.93 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
2014-06-26 | 2014-12-22 | EMEPMI | PM | TELOK | TELOK-B3 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 63.6 | 1546 | 882 | N/A | N/A | N/A | N/A | 17800000 | 26.5 | NO | N/A | DRY TREE | 2014-09-22 00:30 | 2014-09-21 | 2014-11-05 | 1441.53 | SHALLOW WATER | 1550 | 886 | N/A | N/A | N/A | N/A | 14856000 | 22.02 | 2.6 | 2.6 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 5.3 | 1946000 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 7" | 1.0 | SINGLE | L80 13CR | 36 | True | NONE | L80 13CR | 9 | NACL | NO | NO | Exist
2014-06-24 | 2014-09-22 | SAPURA OMV | PM | EAST BELUMUT | EB-A05ST2 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 4035 | 1168 | N/A | N/A | N/A | N/A | 19393900 | 34.5 | SIDETRACK | N/A | N/A | N/A | 2014-07-16 18:00 | 2014-08-12 12:00 | 3614.3 | SHALLOW WATER | 3731 | 1165.7 | N/A | N/A | N/A | N/A | 15185289 | 26.75 | 23.73 | 23.64 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
2013-11-20 | N/A | SHELL | SK | D12 | D12-101A | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-105 | JACK UP | 49.68 | 3280.34 | 2142.33 | N/A | N/A | N/A | N/A | 103628205 | 59.8 | NO | N/A | N/A | 2013-12-12 14:00 | 2013-12-12 14:00 | 2014-03-19 06:00 | 3300.52 | SHALLOW WATER | 3399.88 | 2202.99 | N/A | N/A | N/A | N/A | 19165255 | 49.72 | 10.06 | 3.06 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2013-04-25 | 2013-10-31 | KPOC | SB | KAMUNSU EAST | KME-2 | EXPLORATION/APPRAISAL | ENSCO-8504 | SEMI-SUB | 808.5 | 3412 | 2661 | 72109491 | 72109491 | 56 | 56 | N/A | N/A | SIDETRACK | N/A | N/A | N/A | 2013-07-17 | 2013-09-10 15:30 | 2729.1 | DEEP WATER | 3564 | 2627 | N/A | 68000000 | N/A | 55.65 | N/A | N/A | 15.58 | 10.13 | DW EXP C2 | DW EXP C2 | Yes | 4.4 | Yes | 4200 | Yes | 6400 | 2.56 | 2.56 | 2562 | 2562 | 5031 | 5031 | [26 empty] | Exist
2012-07-02 | 2012-09-13 | IPC | SB | BERANGAN | BERANGAN-1 | EXPLORATION/APPRAISAL | OFFSHORE COURAGEOUS | JACK UP | 66.4 | 1709 | 1709 | 13436690 | 30582432 | 31.7 | 72.2 | N/A | N/A | NO | N/A | N/A | 2012-07-28 | 2012-07-25 | 2012-08-18 16:30 | 1608.6 | SHALLOW WATER | 1709 | 1708.6 | 12953589 | N/A | 25 | N/A | N/A | N/A | 7.83 | 7.83 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
2012-05-17 | 2012-09-13 | IPC | SB | TIGA PAPAN | TIGA PAPAN-5 | EXPLORATION/APPRAISAL | OFFSHORE COURAGEOUS | JACK UP | 51.4 | 2055 | 1702 | 15083307 | 23734249 | 31.7 | 51.5 | N/A | N/A | NO | N/A | N/A | 2012-07-07 | 2012-07-03 | 2012-07-25 08:00 | 1619.6 | SHALLOW WATER | 1705 | 1704.22 | 11783404 | N/A | 25.7 | N/A | N/A | N/A | 6.4 | 1.2 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
2011-10-25 | 2012-02-28 | IPC | PM | BERTAM | BERTAM-2 | EXPLORATION/APPRAISAL | OFFSHORE COURAGEOUS | JACK UP | 76 | 1892 | 1892 | 15420217.74 | 23562502.64 | 41.2 | 64.6 | N/A | N/A | NO | N/A | N/A | 2011-11-28 | 2011-11-18 | 2012-01-15 14:00 | 1774 | SHALLOW WATER | 1884 | 1884 | N/A | 20860000 | N/A | 61.04 | N/A | N/A | 33.89 | 29.73 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
2007-11-11 | 2014-10-02 | SAPURA OMV | PM | EAST BELUMUT | EB A-01 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 2400 | 1199 | N/A | N/A | N/A | N/A | 14682018 | 25.06 | SIDETRACK | N/A | N/A | N/A | 2014-08-28 14:00 | 2014-09-16 12:00 | 3265.3 | SHALLOW WATER | 3382 | 1163.23 | N/A | N/A | N/A | N/A | 9962841 | 18.92 | 6.61 | 6.28 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Missing
N/A | 2017-05-01 | COASTAL ENERGY KBM (CEKBM) | PM | ZAITUN | ZAITUN-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 56.08 | 1605.3 | 1299.3 | 3386000 | 3386000 | 12.79 | 12.79 | N/A | N/A | SIDETRACK | N/A | N/A | 2017-03-20 | 2017-03-18 07:15 | 2017-03-31 10:00 | 1511.73 | SHALLOW WATER | 1603.78 | 1298.57 | 2212132.22 | N/A | 11.08 | N/A | N/A | N/A | 13.44 | 13.44 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
N/A | N/A | SHELL | SB | MALIKAI | MLK-123 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 2499.24 | 1327.03 | N/A | N/A | N/A | N/A | 21952443 | 34.29 | NO | N/A | N/A | 2016-11-19 | 2016-11-19 | 2017-05-13 | 1358.88 | DEEP WATER | 1890.28 | 1555.32 | N/A | N/A | N/A | N/A | 15827000 | 42.22 | 20 | 12.48 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2014-05-23 | COASTAL ENERGY KBM (CEKBM) | PM | MERANTI | MERANTI M3 | APPRAISAL CUM DEV/DEVELOPMENT | ATWOOD MANTA | JACK UP | 58.52 | 2626.94 | 2195.37 | N/A | N/A | N/A | N/A | 8088505 | 23.65 | SIDETRACK | N/A | N/A | 2013-12-28 | 2013-12-25 | 2014-01-19 | 1948.8 | SHALLOW WATER | 2042.37 | 1293.51 | N/A | N/A | N/A | N/A | 11636127 | 23.65 | 59.74 | 59.74 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2015-06-04 | PETROFAC | PM | WEST DESARU | WD-A16 | APPRAISAL CUM DEV/DEVELOPMENT | TRIDENT-9 | JACK UP | 64.8 | 2418 | 1557.8 | N/A | N/A | N/A | N/A | 11924077.8 | 25.04 | NO | N/A | DRY TREE | N/A | 2015-02-08 15:00 | 2015-03-18 20:30 | 2292.4 | SHALLOW WATER | 2400 | 1549.88 | N/A | N/A | N/A | N/A | 9172386.69 | 26.79 | 26.91 | 26.91 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [6 empty] | 9.28 | 4787728 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | GRE | 0 | True |  | 25CR | 11.5 | NACL/NABR | NO | NO | Exist
N/A | 2017-05-01 | COASTAL | PM | MERPAUH | MERPAUH-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 57.3 | 2685.16 | 2323.07 | 6018075 | 7482000 | 23.57 | 31.79 | N/A | N/A | SIDETRACK | N/A | N/A | 2017-02-01 | 2017-01-15 | 2017-03-15 | 2429.75 | SHALLOW WATER | 2525.14 | 2267.91 | N/A | 8019345 | N/A | 39.3 | N/A | N/A | 31.55 | 31.55 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2014-07-08 | COASTAL ENERGY KBM (CEKBM) | PM | BANANG | BANANG-B4 | APPRAISAL CUM DEV/DEVELOPMENT | ATWOOD MANTA | JACK UP | 58.21 | 2707.1 | 2199.94 | N/A | N/A | N/A | N/A | 8827944 | 18.09 | NO | N/A | N/A | 2014-03-30 | 2014-03-28 | 2014-06-05 | 2622.07 | SHALLOW WATER | 2716.25 | 2206.98 | N/A | N/A | N/A | N/A | 9909129 | 27.44 | 17.85 | 17.85 | No DMS category | No | No |  | No |  | No |  | No |  | No |  | No | [27 empty] | Exist
2026-03-10 | 2026-03-10 15:01 | VESTIGO | SK | KMSE | KMSE-A06 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 85 | 1324.73 | 1201 | N/A | N/A | N/A | N/A | 5435175 | 9.84 | NO | N/A | DRY TREE | 2024-05-01 | 2024-05-01 18:00 | 2024-06-06 04:30 | 1181.93 | SHALLOW WATER | 1300 | 1198.44 | N/A | N/A | N/A | N/A | 3656659 | 9.84 | 0.53 | 0.53 | SW DEV SLIM HOLE (WITHOUT OFFLINE CAPABILITY RIG) |  | 1.4 |  | 550 |  | 1380 |  | 1.26 |  | 546 |  | 916 |  | 3.07 | 1919565 | OHSAS/OHPDL | 0.7 | 373 | 2.2 | 1432394 | 0.52 | 336 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 2-7/8" | 2 | SINGLE | L80 | 80 | True | NONE | L80 | 9.4 | NACL | NO | NO | Missing
2026-03-10 | 2026-03-10 15:28 | VESTIGO | SK | KMSE | LIMAU WEST - 1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 85 | 3570.04 | 1171.38 | N/A | N/A | N/A | N/A | 8806704 | 17.35 | NO | N/A | DRY TREE | 2024-04-27 | 2024-04-27 12:30 | 2024-05-29 06:00 | 3495.93 | SHALLOW WATER | 3614 | 1188.83 | N/A | N/A | N/A | N/A | 8945584 | 20.24 |  |  | SW DEV SLIM HOLE (WITHOUT OFFLINE CAPABILITY RIG) |  | 1.4 |  | 550 |  | 870 |  | 1.12 |  | 488 |  | 776 |  | 4.83 | 3122577 | OHSAS/OHPDL | 0.7 | 373 | 6.29 | 3303881 | 0.53 | 279 | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | NO | NO | 2-7/8" | 2 | SINGLE | L80 | 320 | True | NONE | L80 | 9 |  |  |  | Missing
2026-02-25 | 2026-02-25 10:51 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI-C1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 63.6118 | 3887.724 | 1842.8543 | N/A | N/A | N/A | N/A | 14430000 | 32.9 | NO | N/A | DRY TREE | 2023-10-23 | 2023-10-22 16:30 | 2024-06-16 | 3781.335 | SHALLOW WATER | 3887.724 | 1842.85 | N/A | N/A | N/A | N/A | 15360215.34 | 42.06 | 9.8 | 9.8 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.6 |  | 652 |  | 1262 |  | 8.47 | 3564239 | CH | 1 | 390 | 19.25 | 5279510.93 | 1.51 | 435 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1 | SINGLE | L80 13CR | 247 | True | NONE | L80 13CR | 8.5 | KCL | NO | NO | Missing
2026-02-20 | 2026-02-20 09:37 | PCSB | PM | GANSAR | GANSAR-A3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 77.5 | 3138.53 | 2982 | N/A | N/A | N/A | N/A | 19522616.46 | 33.19 | NO | N/A | DRY TREE | 2024-05-13 | 2024-05-13 19:30 | 2024-10-02 15:15 | 3747.3 | SHALLOW WATER | 3142 | 2987.05 | N/A | N/A | N/A | N/A | 17379643.58 | 34.12 | 10.44 | 10.44 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3040 |  | 2.28 |  | 1127.34 |  | 1413.57 |  | 4.71 | 3987671 | MONOBORE | 0.3 | 159 | 3.71 | 2589208 | 0.3 | 210.59 | SANDSTONE | HPHT | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1 | SINGLE | L80 13CR | 12.07 | True | NONE | L80 13CR | 8.35 | SEAWATER/DRILLWATER | NO | NO | Missing
2026-02-20 | 2026-02-20 09:52 | PCSB | PM | GANSAR | GANSAR-A4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 77.5 | 4075 | 2974 | N/A | N/A | N/A | N/A | 20441192.39 | 33.16 | NO | N/A | DRY TREE | 2024-05-23 | 2024-05-22 19:30 | 2024-11-03 | 4049.45 | SHALLOW WATER | 4173.65 | 2966 | N/A | N/A | N/A | N/A | 16449360.15 | 33.44 | 1.06 | 1.06 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3040 |  | 2.25 |  | 1055.15 |  | 1236.67 |  | 5.17 | 4428397 | MONOBORE | 0.3 | 159 | 3.1 | 2075596 | 0.23 | 156.22 | SANDSTONE | HPHT | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1 | SINGLE | L80 13CR | 46.6 | True | NONE | L80 13CR | 8.35 | SEAWATER/DRILLWATER | NO | NO | Missing
2026-02-20 | 2026-02-20 09:19 | PCSB | PM | GANSAR | GANSAR-A2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 77.5 | 4442.77 | 2903 | N/A | N/A | N/A | N/A | 21404747.91 | 38.53 | NO | N/A | DRY TREE | 2024-05-19 | 2024-05-19 11:15 | 2024-11-04 21:45 | 4337.8 | SHALLOW WATER | 4462 | 2927.6 | N/A | N/A | N/A | N/A | 19474168.11 | 34.88 | 1.61 | 1.61 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3040 |  | 2.17 |  | 1129 |  | 1368 |  | 5.38 | 4844550 | MONOBORE | 0.3 | 159 | 4.04 | 3213389 | 0.28 | 226 | SANDSTONE | HPHT | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 2 | SINGLE | L80 13CR | 175.2 | True | NONE | L80 13CR | 8.35 | SEAWATER/DRILLWATER | NO | NO | Missing
2026-02-19 | 2026-02-19 13:46 | ENQUEST | PM | SELIGI | SEE-35 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 73 | 3100 | 1384 | N/A | N/A | N/A | N/A | 11950000 | 32.9 | NO | N/A | DRY TREE | 2024-04-03 | 2024-04-02 22:00 | 2024-05-06 | 2862 | SHALLOW WATER | 3026 | 1341 | N/A | N/A | N/A | N/A | 10461000 | 34.08 | 5.04 | 4.68 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.2 |  | 672 |  | 1114 |  | 14.16 | 4261000 | CH | 1 | 390 | 8.75 | 2801222 | 0.9 | 283 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | DUAL | L80 13CR | 49.215 | True | INNER STRING WITH SSD | L80 13CR | 9 | KCL | NO | NO | Missing
2026-02-19 | 2026-02-19 14:11 | ENQUEST | PM | SELIGI | SEE-36 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 73 | 2200 | 1407 | N/A | N/A | N/A | N/A | 7900000 | 20.71 | NO | N/A | DRY TREE | 2024-05-10 | 2024-05-10 08:00 | 2024-06-08 | 1953.2 | SHALLOW WATER | 2120 | 1365.9 | N/A | N/A | N/A | N/A | 5627700 | 17.56 | -1 | 0.89 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.2 |  | 370 |  | 879 |  | 8.82 | 2753130 | CH | 1 | 390 | 5.59 | 2002200 | 0.8 | 288 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 29 | True | INNER STRING WITH SSD | L80 | 8.7 | NACL | NO | NO | Missing
2026-02-19 | 2026-02-19 13:57 | ENQUEST | PM | SELIGI | SEE-34 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 73 | 3400 | 1408 | N/A | N/A | N/A | N/A | 10400000 | 28.41 | NO | N/A | DRY TREE | 2024-05-07 | 2024-05-07 | 2024-06-13 02:00 | 3077 | SHALLOW WATER | 3250 | 1365 | N/A | N/A | N/A | N/A | 6862700 | 19.52 | -1 | 0.85 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.2 |  | 411 |  | 680 |  | 11.73 | 3208731 | CH | 1 | 390 | 4.84 | 1751081 | 0.5 | 165 | SANDSTONE | NORMAL | CASED HOLE |  |  | 3-1/2" | 1 | SINGLE | L80 | 22 | True | NONE | L80 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Missing
2026-02-13 | 2026-02-13 16:22 | PCSB | PM | GUNTONG | BINDU-A1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 61 | 4898 | 1650 | N/A | N/A | N/A | N/A | 18350000 | 31.67 | NO | N/A | DRY TREE | 2024-11-28 | 2024-11-28 12:06 | 2025-03-17 12:06 | 4691 | SHALLOW WATER | 4795 | 1645.33 | N/A | N/A | N/A | N/A | 18349998 | 31.76 | 8.57 | 8.57 | DW DEV C3 (DRY TREE) |  | 5.1 |  | 1525 |  |  |  | 3.1 |  | 1251 |  | 1585 |  | 7.01 | 4692308 |  |  |  | 7 | 4692308 | 0.5 | 316 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | 1 ZONE | NO | 3-1/2" | 1 | SINGLE | L80 | 1011 | True |  | L80 | 9.3 | NACL | NO | 1 | Missing
2026-02-13 | 2026-02-13 16:39 | PCSB | PM | GUNTONG | BINDU-A2 ADDENDUM | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 61 | 3657 | 1636 | N/A | N/A | N/A | N/A | 22600000 | 49.5 | NO | N/A | DRY TREE | 2024-11-23 | 2024-11-23 16:23 | 2025-02-05 16:24 | 3460 | SHALLOW WATER | 3564 | 1667 | N/A | N/A | N/A | N/A | 28900000 | 71.9 | 31 | 31 | DW DEV C3 (DRY TREE) |  | 5.1 |  | 1525 |  |  |  | 3.5 |  | 1597 |  | 2502 |  | 4.96 | 4400000 |  |  |  | 6.7 | 4359347 | 0.6 | 336 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | 1 ZONE | NO | 5-1/2" | 1 | SINGLE | L80 13CR | 57 |  | NONE | L80 13CR |  |  | NO | NO | Missing
2026-01-21 | 2026-01-21 14:44 | PCSB | PM | N/A | BEKANTAN-1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 63 | 1770 | 1466 | 33267382.85 | 38613257.01 | 57.11 | 65.69 | N/A | N/A | NO | N/A | DRY TREE | 2024-10-06 | 2024-10-02 21:00 | 2024-12-03 17:00 | 1546.36 | SHALLOW WATER | 1641 | 1407.93 | N/A | 34124353.14 | N/A | 61.83 | 34124353.14 | 61.83 | 15.67 | 11.89 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.37 |  | 2109.02 |  | 4903.89 | [27 empty] | Missing
2026-01-09 | 2026-03-27 14:24 | PCSB | PM | TABU | TABU-B30ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63 | 2667.62 | 1910.3 | N/A | N/A | N/A | N/A | 12883878 | 32.9 | NO | N/A | DRY TREE | 2026-01-22 | 2025-11-27 12:00 | 2026-02-07 14:00 | 1875.42 | SHALLOW WATER | 2590 | 1910.85 | N/A | N/A | N/A | N/A | 10663197.58 | 24.25 | 10.22 | 9.49 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.3 |  | 627.98 |  | 1733 |  | 11 | 3137958 | CH | 1 | 390 | 6.19 | 4227503 | 0.96 | 595.56 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 |  | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-12-19 | 2025-12-19 14:48 | PCSB | PM | N/A | ROSEBAY-1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 62 | 1965 | 1873.35 | 20923574 | 21506598.97 | 46.4 | 48.5 | N/A | N/A | NO | N/A | DRY TREE | 2024-12-03 | 2025-12-03 12:00 | 2025-12-28 05:30 | 1871.2 | SHALLOW WATER | 1965 | 1889.09 | 13876206.96 | N/A | 24.52 | N/A | 13876206.96 | 24.52 | 9.95 | 0 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 0.9 |  | 438 |  | 1503 | [27 empty] | Missing
2025-12-13 | 2026-02-24 12:16 | PCSB | PM | TABU | TABU-B13ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.3 | 2795.3 | 1662 | N/A | N/A | N/A | N/A | 10299985 | 13 | NO | N/A | DRY TREE | 2025-12-27 | 2025-11-15 21:00 | 2026-01-18 15:00 | 637 | SHALLOW WATER | 2082 | 1696.34 | N/A | N/A | N/A | N/A | 10920185.79 | 28.58 | 34 | 25.77 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 2.3 |  | 1404.3 |  | 4457 |  | 11.04 | 5486258 | CH | 1 | 390 | 4.52 | 2663648 | 0.95 | 538 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1 | SINGLE | L80 |  | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-12-12 | 2025-12-12 11:00 | POSCO | PM | PM524 | MAWAR MERAH-1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 60.29 | 1340 | 1340 | 12175007 | 13013435 | 21.4 | 24.7 | N/A | N/A | NO | N/A | DRY TREE | 2025-05-01 | 2025-04-24 08:15 | 2025-05-12 20:30 | 1294.91 | SHALLOW WATER | 1390 | 1386.79 | 11000000 | N/A | 22.4 | N/A | 11000000 | 22.4 | 0 | 5.4 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 1.58 |  | 654.63 |  | 2682.68 | [27 empty] | Missing
2025-12-03 | 2025-12-03 10:14 | PCSB | PM | IRONG BARAT | IRONG BARAT-C04ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 65.7 | 2840 | 929.05 | N/A | N/A | N/A | N/A | 12399997 | 28 | NO | N/A | DRY TREE | 2025-09-19 | 2025-04-12 | 2025-10-04 05:00 | 1345.7 | SHALLOW WATER | 2546.7 | 878.32 | N/A | N/A | N/A | N/A | 9727865.41 | 22.22 | 2.88 | 2.88 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 2.85 |  | 1215.62 |  | 2221.6 |  | 8.72 | 4607537 | OHSAS/OHPDL | 0.7 | 373 | 3.32 | 1777077.33 | 0.4 | 318.8 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN |  |  | 3-1/2" | 2 | SINGLE | L80 | 410 |  |  | L80 13CR | 9.7 | CACL2 |  |  | Missing
2025-12-02 | 2025-12-02 14:43 | SHELL | SK | F22 | F22-101 | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE TOM PROSSER | JACK UP | 92.3544 | 3121.76 | 2057.4 | N/A | N/A | N/A | N/A | 44370000 | 52.58 | NO | N/A | DRY TREE | 2024-11-20 | 2024-11-14 | 2025-01-23 06:30 | 2945.2 | SHALLOW WATER | 3082.1 | 2078.9 | N/A | N/A | N/A | N/A | 50320000 | 70.27 | 24.3 | 1.9 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.69 |  | 2043 |  | 4849 |  | 10.25 | 13770000 | OHSAS/OHPDL | 0.7 | 373 | 13.52 | 15560000 | 1.33 | 1538 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1 | SINGLE | SUPER 13CR |  | True | NONE | SUPER 13CR | 10.7 | NACL/NABR | NO | NO | Missing
2025-12-02 | 2025-12-02 11:12 | SHELL | SK | F27 | F27-101 | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE TOM PROSSER | JACK UP | 97.536 | 2606.04 | 1351.79 | N/A | N/A | N/A | N/A | 41950000 | 49.23 | NO | N/A | DRY TREE | 2024-09-13 | 2024-08-24 | 2024-11-14 | 2528.47 | SHALLOW WATER | 2667 | 1354.63 | N/A | N/A | N/A | N/A | 41960000 | 50.7 | 20.22 | 4.87 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.78 |  | 2189 |  | 3768 |  | 9.51 | 13730000 | OHSAS/OHPDL | 0.7 | 373 | 13.73 | 10320000 | 1.59 | 1406 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1 | SINGLE | SUPER 13CR |  | True | NONE | SUPER 13CR | 11.2 | NACL/NABR | NO | NO | Missing
2025-12-02 | 2025-12-02 14:53 | SHELL | SK | SELASIH | SELASIH-101 | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE TOM PROSSER | JACK UP | 89.3064 | 2693.21 | 1367.94 | N/A | N/A | N/A | N/A | 41870000 | 49.94 | NO | N/A | DRY TREE | 2025-01-31 | 2025-01-23 06:30 | 2025-03-30 12:45 | 2554.4 | SHALLOW WATER | 2688.3 | 1366.5 | N/A | N/A | N/A | N/A | 50750000 | 66.26 | 17.01 | 11.05 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.47 |  | 2450 |  | 6055 |  | 9.62 | 13460000 | OHSAS/OHPDL | 0.7 | 373 | 13.59 | 18150000 | 1.5 | 206 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1 | SINGLE | SUPER 13CR |  | True | NONE | SUPER 13CR | 10.7 | NACL/NABR | NO | NO | Missing
2025-12-01 | 2026-04-02 10:57 | PCSB | PM | DUYONG BARAT | MERANSI-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 72.2 | 2764 | 2623 | N/A | 17934434.85 | N/A | 32.84 | N/A | N/A | NO | N/A | DRY TREE | 2026-01-26 | 2026-01-17 09:30 | 2026-02-25 02:30 | 2763 | SHALLOW WATER | 2763 | 2620 | N/A | 17788859.45 | N/A | 38.71 | 17788859.45 | 38.71 | 15.98 | 5.49 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.06 |  | 677 |  | 1353 | [27 empty] | Missing
2025-11-26 | 2025-11-27 07:09 | PCSB | SK | N/A | SILUNGEN-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 120 | 1803 | 1803 | 25210477.68 | 25210477.68 | 50.93 | 50.93 | N/A | N/A | NO | N/A | WET TREE | 2024-08-24 | 2024-08-20 07:00 | 2024-10-03 11:30 | 1659 | SHALLOW WATER | 1779 | 1778.97 | N/A | 19532150.26 | N/A | 38.73 | 19532150.26 | 38.73 | 1.29 | 1.1 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.1 |  | 1768 |  | 2809 | [27 empty] | Missing
2025-11-13 | 2025-11-13 10:53 | SHELL | SK | MLNGX | LEMANG-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 69.49 | 1588.92 | 1588.89 | 20280000 | 24530000 | 30.13 | 41.07 | N/A | N/A | NO | N/A | DRY TREE | 2024-06-14 | 2024-06-07 22:30 | 2024-07-11 05:30 | 1482.55 | SHALLOW WATER | 1588.92 | 1588.89 | 21560000 | N/A | 33.29 | N/A | 21560000 | 33.29 | 7.73 | 6.2 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.23 |  | 2385 |  | 4432 | [27 empty] | Missing
2025-11-13 | 2025-11-13 10:45 | SHELL | SK | MLNGX | LATOK-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 78.94 | 1616.66 | 1616.58 | 20700000 | 24900000 | 31.38 | 41.93 | N/A | N/A | NO | N/A | DRY TREE | 2024-05-04 | 2024-04-28 14:00 | 2024-06-07 22:30 | 1501.14 | SHALLOW WATER | 1616.66 | 1616.58 | 25250000 | N/A | 40.35 | N/A | 25250000 | 40.35 | 11.7 | 11.2 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.94 |  | 3467 |  | 5126 | [27 empty] | Missing
2025-11-13 | 2025-11-13 10:59 | SHELL | SK | MLNGX | HABANERO-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 80.47 | 2468.88 | 2274.2 | 23900000 | 28100000 | 35.42 | 46.16 | N/A | N/A | NO | N/A | DRY TREE | 2024-07-16 | 2024-07-11 05:30 | 2024-08-24 | 2351.53 | SHALLOW WATER | 2468.88 | 2274.2 | 27690000 | N/A | 43.77 | N/A | 27690000 | 43.77 | 9.76 | 9.21 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.14 |  | 2196 |  | 3589 | [27 empty] | Missing
2025-11-11 | 2025-11-11 16:22 | PCSB | SK | D18 | D18-C310B | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 36.5 | 2909 | 1636.87 | N/A | N/A | N/A | N/A | 13486616.4 | 24.52 | NO | N/A | DRY TREE | 2024-12-13 | 2024-12-13 21:00 | 2025-02-13 18:00 | 2882 | SHALLOW WATER | 2882 | 1638.13 | N/A | N/A | N/A | N/A | 12880451.49 | 29.25 | 0.71 | 0.57 | SW DEV C1 |  | 2.2 |  | 830 |  |  |  | 1.11 |  | 622 |  | 1307 | [27 empty] | Missing
2025-11-11 | 2025-11-11 15:15 | PCSB | SK | D18 | D18-D406B | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 35 | 2221 | 1839 | N/A | N/A | N/A | N/A | 15671794.69 | 26.33 | NO | N/A | DRY TREE | 2024-09-14 | 2024-09-11 18:00 | 2024-10-19 12:00 | 1953 | SHALLOW WATER | 1953 | 1662.88 | N/A | N/A | N/A | N/A | 12383323.13 | 27.12 | 16.09 | 12 | SW DEV C1 |  | 2.2 |  | 830 |  |  |  | 2.31 |  | 812 |  | 1865 | [27 empty] | Missing
2025-11-11 | 2025-11-12 11:12 | PCSB | SK | D18 | D18-C312A | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 36.5 | 2666 | 1628.92 | N/A | N/A | N/A | N/A | 15903912.72 | 27.01 | NO | N/A | DRY TREE | 2024-12-17 | 2024-12-17 09:00 | 2025-05-03 18:00 | 2626 | SHALLOW WATER | 2626 | 1592.69 | N/A | N/A | N/A | N/A | 13072854.89 | 34.12 | 7.23 | 5.4 | SW DEV C1 |  | 2.2 |  | 830 |  |  |  | 1.72 |  | 766 |  | 1441 | [27 empty] | Missing
2025-11-11 | 2025-11-12 11:24 | PCSB | SK | D18 | D18-C312B | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 36.5 | 3610 | 1548 | N/A | N/A | N/A | N/A | 16623102.78 | 27.34 | NO | N/A | DRY TREE | 2024-12-21 | 2024-12-21 | 2025-04-13 06:00 | 3854 | SHALLOW WATER | 3854 | 1620.9 | N/A | N/A | N/A | N/A | 17781645.14 | 44.61 | 3.06 | 3.25 | SW DEV C1 |  | 2.2 |  | 830 |  |  |  | 1.48 |  | 707 |  | 1489 | [27 empty] | Missing
2025-11-11 | 2025-11-11 19:39 | PCSB | SK | SINSING | SINSING-2 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 116 | 3275 | 2065 | 45130000 | 54460000 | 89.39 | 115.77 | N/A | N/A | NO | N/A | DRY TREE | 2024-05-27 | 2024-05-20 | 2024-08-20 09:00 | 2263 | SHALLOW WATER | 2379 | 1517.55 | 45245959.35 | N/A | 92 | N/A | 45245959.35 | 92 | 4.1 | 4.1 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.99 |  | 1325 |  | 3635 | [27 empty] | Missing
2025-11-11 | 2025-11-11 16:05 | PCSB | SK | D18 | D18-C310A | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 36.5 | 2835 | 2093 | N/A | N/A | N/A | N/A | 14678307.9 | 25.08 | NO | N/A | DRY TREE | 2024-12-10 | 2024-12-10 | 2025-03-11 03:00 | 2929 | SHALLOW WATER | 2929 | 2157.55 | N/A | N/A | N/A | N/A | 13766596.32 | 36.75 | 16.58 | 16.13 | SW DEV C1 |  | 2.2 |  | 830 |  |  |  | 1.21 |  | 663 |  | 1413 | [27 empty] | Missing
2025-11-10 | 2025-11-10 16:50 | PCSB | SK | D18 | D18-D406A | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 35 | 2341 | 1740 | N/A | N/A | N/A | N/A | 12465003.2 | 23.23 | NO | N/A | DRY TREE | 2024-09-20 | 2024-09-20 06:00 | 2024-11-08 23:59 | 2700 | SHALLOW WATER | 2700 | 1925.46 | N/A | N/A | N/A | N/A | 12030367.22 | 28.12 | 11.59 | 11.59 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.51 |  | 510 |  | 1313 |  | 7.94 |  | CH | 1 | 390 | 123 | 952908.59 | 123 | 123 |  | NORMAL | CASED HOLE | 5 ZONE | 2 | 2-7/8" | 3 | DUAL | L80 | 121 | True | AICV | 15CR |  | NABR | 4 | 5 | Missing
2025-11-06 | 2025-11-06 10:04 | SHELL | SK | MENGKUDU | MENGKUDU-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 93.27 | 2983.5 | 2827.3 | 23350000 | 30110000 | 31.75 | 45.29 | N/A | N/A | NO | N/A | DRY TREE | 2025-05-06 | 2025-05-01 | 2025-06-17 05:30 | 2073.55 | SHALLOW WATER | 2203.7 | 2096.1 | N/A | 26660000 | N/A | 47.23 | 26660000 | 47.23 | 5.47 | 5.34 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.66 |  | 2697 |  | 3919 | [27 empty] | Missing
2025-11-06 | 2025-11-06 15:17 | PCSB | PM | IRONG BARAT | IRONG BARAT-C14ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 65.7 | 1540 | 858 | N/A | N/A | N/A | N/A | 11522157 | 23.42 | SIDETRACK | N/A | DRY TREE | 2025-09-07 | 2025-04-08 20:30 | 2025-09-14 16:00 | 990 | SHALLOW WATER | 1540 | 858.66 | N/A | N/A | N/A | N/A | 6241112.62 | 13.31 | 0 | 0 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 2.09 |  | 896.44 |  | 1737.69 |  | 9.01 | 5650791 | OHSAS/OHPDL | 0.7 | 373 | 2.15 | 1951974 | 0.42 | 395.98 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1 | SINGLE | L80 | 327 |  | ICD | L80 13CR | 8.7 | CACL2 | NO |  | Missing
2025-11-02 | 2025-11-05 20:02 | HML | SB | SOUTH FURIOUS | SFJT-D02 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1027.31 | 860.3 | N/A | N/A | N/A | N/A | 6806517.3 | 7 | NO | N/A | DRY TREE | 2024-11-20 | 2024-11-19 13:30 | 2024-11-30 12:00 | 3144 | SHALLOW WATER | 1006 | 2320 | N/A | N/A | N/A | N/A | 4897287 | 10.9 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 1.9 |  | 793.1 |  | 1484 |  | 3.55 | 2384074.06 | OHSAS/OHPDL | 0.7 | 373 | 4.2 | 2279939 | 1.3 | 690.9 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 265 | True | INNER STRING WITH SSD | L80 | 8.6 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 20:13 | HML | SB | SOUTH FURIOUS | SFJT-D03 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1823.68 | 721.27 | N/A | N/A | N/A | N/A | 7983611.8 | 14.54 | NO | N/A | DRY TREE | 2024-11-06 | 2024-11-05 06:00 | 2025-12-23 | 1689.9 | SHALLOW WATER | 1749.5 | 701.3 | N/A | N/A | N/A | N/A | 10493732 | 30.31 | 16.6 | 16.6 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 4.4 |  | 1341 |  | 1828.2 |  | 4.56 | 2631371.54 | OHSAS/OHPDL | 0.7 | 373 | 5 | 2796573 | 0.87 | 487 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 1084 | True | NONE | L80 | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 22:27 | HML | SB | SOUTH FURIOUS | SFJT-D08 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1316.12 | 8840 | N/A | N/A | N/A | N/A | 6805901.29 | 11.94 | NO | N/A | DRY TREE | 2025-03-03 | 2025-03-02 07:00 | 2025-03-15 03:00 | 1234.4 | SHALLOW WATER | 1294 | 834 | N/A | N/A | N/A | N/A | 5622057.8 | 18.9 |  | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.3 |  | 806.1 |  | 1323.9 |  | 3.31 | 2069301.01 | OHSAS/OHPDL | 0.7 | 373 | 3.3 | 2199057.8 | 0.8 | 517.8 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1 | SINGLE | L80 1CR | 361 | True | NONE | L80 1CR | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 22:42 | HML | SB | SOUTH FURIOUS | SFJT-D11 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1121.64 | 896.5 | N/A | N/A | N/A | N/A | 8354179.44 | 18.5 | NO | N/A | DRY TREE | 2024-09-17 | 2024-09-14 15:30 | 2024-10-24 | 1044 | SHALLOW WATER | 1103 | 884.2 | N/A | N/A | N/A | N/A | 9979862 | 26.9 | 11.4 | 11.4 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 3 |  | 2.8 |  | 2283.7 |  | 3.56 | 3005763 | OHSAS/OHPDL | 0.7 | 373 | 9.2 | 3928602 | 1384.7 | 1085 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 1CR | 749 | True | INNER STRING WITH SSD | L80 1CR | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 19:48 | HML | SB | SOUTH FURIOUS | SFJT-D01 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1153.4 | 896.5 | N/A | N/A | N/A | N/A | 9361904.85 | 18.5 | NO | N/A | DRY TREE | 2024-09-26 | 2024-09-26 | 2024-12-07 | 1071 | SHALLOW WATER | 1131 | 896 | N/A | N/A | N/A | N/A | 7046945.1 | 16.75 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.4 |  | 851 |  | 1359.9 |  | 3.7 | 2331027.97 | OHSAS/OHPDL | 0.7 | 373 | 4.3 | 2637161 | 0.8 | 508.9 | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER & CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 218 | True | INNER STRING WITH SSD | L80 | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 20:50 | HML | SB | SOUTH FURIOUS | SFJT-D07 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1883.94 | 1014.7 | N/A | N/A | N/A | N/A | 8953806.06 | 19.9 | NO | N/A | DRY TREE | 2024-12-23 | 2024-12-23 | 2025-02-22 12:00 | 1836.4 | SHALLOW WATER | 1896 | 895 | N/A | N/A | N/A | N/A | 9308160 | 25.9 | 7 | 5 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 3.5 |  | 857.8 |  | 1261.7 |  | 3.95 | 2307879.8 | OHSAS/OHPDL | 0.7 | 373 | 4.3 | 2979588 | 0.6 | 403.9 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 2045 | True | NONE | L80 | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 20:25 | HML | SB | SOUTH FURIOUS | SFJT-D04 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1415.94 | 1086.41 | N/A | N/A | N/A | N/A | 8452276.03 | 17.77 | NO | N/A | DRY TREE | 2024-12-27 | 2024-12-27 10:30 | 2025-02-08 04:00 | 1377.5 | SHALLOW WATER | 1437 | 1105 | N/A | N/A | N/A | N/A | 7627922 | 19.2 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.2 |  | 715.1 |  | 1091.6 |  |  |  | OHSAS/OHPDL | 0.7 | 373 | 5.3 | 3183510 | 0.9 | 512.2 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" |  |  | L80 | 1492 | True | INNER STRING WITH SSD | L80 | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 22:19 | HML | SB | SOUTH FURIOUS | SFJT-D09 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1316.12 | 840.75 | N/A | N/A | N/A | N/A | 6805901.29 | 11.94 | NO | N/A | DRY TREE | 2025-01-01 | 2024-12-31 08:30 | 2025-03-25 21:00 | 1564.4 | SHALLOW WATER | 1624 | 939 | N/A | N/A | N/A | N/A | 7890699.4 | 18.9 | 14.2 | 14.2 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.7 |  | 901.4 |  | 1480.4 |  | 3.31 | 2069301.01 | OHSAS/OHPDL | 0.7 | 373 | 4.3 | 3086410.3 | 0.8 | 579.1 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 1CR | 792 | True | NONE | L80 1CR | 8.7 | KCL | NO | NO | Missing
2025-11-02 | 2025-11-05 20:35 | HML | SB | SOUTH FURIOUS | SFJT-D06 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 1993.8 | 1004.4 | N/A | N/A | N/A | N/A | 7764513.67 | 15.04 | NO | N/A | DRY TREE | 2025-01-16 | 2025-01-15 09:00 | 2026-03-02 07:00 | 1921.5 | SHALLOW WATER | 1981 | 1004 | N/A | N/A | N/A | N/A | 6604148.9 | 15.98 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 1.8 |  | 611.1 |  | 1016 |  | 4.19 | 2207965.25 | OHSAS/OHPDL | 0.7 | 373 | 4.2 | 2632032.01 | 0.7 | 404.7 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 833 | True | NONE | L80 | 8.7 | KCL | NO | NO | Missing
2025-10-31 | 2025-11-06 10:14 | SHELL | SK | MISAI KUCING | MISAI KUCING-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 80 | 2174 | 2174 | 22600000 | 28200000 | 31 | 41.75 | N/A | N/A | NO | N/A | DRY TREE | 2025-04-04 | 2025-03-30 12:45 | 2025-05-01 | 1248.2 | SHALLOW WATER | 1365.5 | 1365.5 | 21660000 | N/A | 31.47 | N/A | 21660000 | 31.47 | 14.39 | 14.11 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.36 |  | 3529 |  | 5288 | [27 empty] | Missing
2025-10-29 | 2025-10-29 14:35 | PTTEP | SK | CHENDA | CHENDA-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 48 | 1342 | 1317 | 16991457 | 17416457 | 32.8 | 33.63 | N/A | N/A | NO | N/A | N/A | 2024-12-14 | 2024-12-29 16:00 | 2026-02-14 17:00 | 1262 | SHALLOW WATER | 1342 | 1317 | N/A | 23460848 | N/A | 62.39 | 23460848 | 62.39 | 60.3 | 2.5 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 2.4 |  | 1131 |  | 5666 | [27 empty] | Missing
2025-10-29 | 2025-11-05 11:08 | PCSB | PM | IRONG BARAT | IRONG BARAT-C16ST4 | APPRAISAL CUM DEV/DEVELOPMENT | GUNNLOD | JACK UP | 61 | 3363 | 1058 | N/A | N/A | N/A | N/A | N/A | 36.4 | SIDETRACK | N/A | DRY TREE | 2025-07-20 | 2025-04-26 12:00 | 2025-09-05 | 2145.2 | SHALLOW WATER | 3134.2 | 1038.39 | N/A | N/A | N/A | N/A | 23641247.58 | 50.65 | 44.61 | 44.61 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1550 |  | 2.65 |  | 1301.53 |  | 3080.21 |  | 4.82 | 13100000 | OHGP | 1 | 451 |  |  | 2.72 | 1267.36 | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2 | SINGLE | L80 |  | False | NONE | L80 | 8.7 | CACL2 | NO | NO | Missing
2025-10-27 | 2025-10-27 16:31 | PTTEP | SK | D9 | D9-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 34.1 | 3235 | 3235 | N/A | 28621700 | N/A | 56.55 | N/A | N/A | NO | N/A | DRY TREE | 2025-02-21 | 2025-02-14 17:00 | 2025-03-30 09:15 | 3116.7 | SHALLOW WATER | 3181 | 3180 | N/A | 22528386 | N/A | 43.68 | 22528386 | 43.68 | 1.53 | 1.43 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.89 |  | 892 |  | 2203 | [27 empty] | Missing
2025-10-27 | 2025-11-12 10:38 | PTTEP | SK | NANGKA | NANGKA-2 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 70.7 | 4668 | 3273 | 53382212 | N/A | 106.8 | N/A | N/A | N/A | NO | N/A | DRY TREE | 2024-05-15 | 2024-05-08 10:30 | 2024-08-16 | 4647.8 | SHALLOW WATER | 4751 | 3313.46 | N/A | 50591368.87 | N/A | 99.56 | 50591368.87 | 99.56 | 23.54 | 23.5 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 3.7 |  | 1562 |  | 3246 | [27 empty] | Missing
2025-10-23 | 2025-10-23 10:53 | PCSB | SB | ZOISIT | ZOISIT DEEP-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 46.7 | 1980 | 1830 | N/A | 35222520.29 | N/A | 66.56 | N/A | N/A | SIDETRACK | N/A | N/A | 2024-11-09 | 2024-11-03 21:00 | 2025-01-23 20:45 | 1810.3 | SHALLOW WATER | 1888.42 | 1629.93 | N/A | 37488717.23 | N/A | 80.99 | 37488717.23 | 80.99 | 19.84 | 9.25 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.19 |  | 2057.33 |  | 2841.78 | [27 empty] | Missing
2025-10-23 | 2025-10-23 10:31 | PCSB | SB | MEGAH | MEGAH-1 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 2810.6 | 5448 | 5448 | 91803738.13 | 124014523.71 | 73.55 | 109.31 | N/A | N/A | NO | N/A | N/A | 2024-11-23 | 2024-11-10 | 2025-03-04 07:00 | 2363.4 | DEEP WATER | 5200 | 5199.91 | N/A | 112347131.85 | N/A | 114.29 | 112347131.85 | 114.29 | 32.9 | 31.58 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 5.63 |  | 5287 |  | 9886 | [27 empty] | Missing
2025-10-23 | 2025-10-23 09:48 | PCSB | SB | N/A | BILIT DEEP-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 55.6 | 3058 | 2405 | N/A | 39083800.55 | N/A | 79.9 | N/A | N/A | NO | N/A | N/A | 2025-01-28 | 2025-01-23 08:45 | 2025-03-26 | 3023.02 | SHALLOW WATER | 3110 | 2405.66 | N/A | 27097532.67 | N/A | 61.14 | 27097532.67 | 61.14 | 7.77 | 2.1 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.08 |  | 1206 |  | 2150 | [27 empty] | Missing
2025-10-16 | 2025-10-16 07:54 | ROC OIL | SK | D21 | D21-A7 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 50.6 | 4195 | 2103 | N/A | N/A | N/A | N/A | 19968000 | 40.53 | SUSPEND | N/A | DRY TREE | 1970-01-01 | 2024-03-18 06:00 | 2024-04-25 |  | SHALLOW WATER |  |  | N/A | N/A | N/A | N/A | 11733630 | 18.8 | 7.3 | 7.3 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | No |  | No |  | No |  | 8.75 | 5693000 | OHSAS/OHPDL | 0.7 | 373 | [21 empty] | Missing
2025-10-07 | 2025-10-07 18:19 | PCSB | SK | KASAWARI | KASAWARI-A6RDR1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | TENDER ASSISTED DRILLING RIG (TADR) | 108 | 3134 | 2627 | N/A | N/A | N/A | N/A | 67140690.64 | 94.54 |  | N/A | DRY TREE | 2024-05-01 | 2024-04-30 10:00 | 2024-08-03 03:00 | 2837.2 | SHALLOW WATER | 3222 | 2759.07 | N/A | N/A | N/A | N/A | 55562607.49 | 84.59 |  |  | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 5.1 |  | 3180 |  | 4713 |  |  |  | CH | 1 | 390 |  |  | 1.42 | 1462 | [17 empty] | Missing
2025-10-03 | 2025-12-11 11:28 | PCSB | SK | BENDAI | BENDAI-2 ST1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 49.5 | 3019 | 2295 | N/A | 20671452.88 | N/A | 51 | N/A | N/A | NO | N/A | DRY TREE | 2025-09-16 | 2025-09-03 15:00 | 2025-10-16 18:00 | 4464 | SHALLOW WATER | 3019 | 2293.09 | N/A | 17217536.72 | N/A | 43.12 | 17217536.72 | 43.12 | 4.81 | 4.18 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 0.81 |  | 466 |  | 808 | [27 empty] | Missing
2025-10-02 | 2025-12-24 22:22 | HML | PM | BUNGA RAYA | BSA-3ST1 (NWBR I50L) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 53 | 4641 | 2011 | N/A | N/A | N/A | N/A | 16777835.36 | 37.05 | NO | N/A | DRY TREE | 2025-10-13 | 2025-07-29 16:15 | 2025-10-27 | 1633 | SHALLOW WATER | 2236 | 2136 | N/A | N/A | N/A | N/A | 14058573.4 | 33.58 | 12.4 | 12.4 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.29 |  | 599 |  | 2624 |  | 5.02 | 3389499 | CH | 1 | 390 | 4.63 | 1977929.66 | 0.5 | 369 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1 | SINGLE | L80 13CR | 113 | True | NONE | L80 13CR | 6.8 | KCL | NO | NO | Missing
2025-10-01 | 2025-12-21 23:12 | PCSB | PM | TABU | TABU-A2ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 4100 | 1892 | N/A | N/A | N/A | N/A | 7000000 | 20.5 | NO | N/A | DRY TREE | 2025-10-03 | 2025-06-14 08:00 | 2025-10-22 09:00 | 2171 | SHALLOW WATER | 4115 | 1895.91 | N/A | N/A | N/A | N/A | 23322518.38 | 53.73 | 29.19 | 28.57 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 5.45 |  | 2381.37 |  | 3359 |  | 7 | 2802641.52 | OHSAS/OHPDL | 0.7 | 373 | 9.62 | 3380715.42 | 0.85 | 481.7 | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 2 | SINGLE | L80 |  | False | INNER STRING WITH SSD | L80 | 8.6 | NACL | NO | NO | Missing
2025-09-29 | 2025-09-29 11:50 | PCSB | SK | MANJAKANI | MANJAKANI-1 | EXPLORATION/APPRAISAL | NAGA 6 | JACK UP | 60.6 | 1430 | 1430 | 26127715.1 | 28527116.52 | 46.12 | 52.16 | N/A | N/A | NO | N/A | N/A | 2024-06-28 | 2024-06-17 | 2024-07-21 15:45 | 939.2 | SHALLOW WATER | 1030 | 1030 | 17115824.7 | N/A | 33.91 | N/A | 17115824.7 | 33.91 | 3.51 | 0.03 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.95 |  | 2936 |  | 3719 | [27 empty] | Missing
2025-09-29 | 2025-09-29 18:15 | PCSB | PM | IRAMA NORTH | IRAMA NORTH-1ST1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 63 | 1992 | 1911.7 | 16671418.06 | 18079671 | 23.93 | 21.93 | N/A | N/A | NO | N/A | N/A | 2024-09-11 | 2024-09-11 | 2024-09-29 18:00 | 1955.3 | SHALLOW WATER | 2050 | 1967.5 | 13289463.07 | N/A | 18.25 | N/A | 13289463.07 | 18.25 | 1.26 | 1.26 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.44 |  | 1035 |  | 1585 | [27 empty] | Missing
2025-09-29 | 2025-09-29 18:51 | PCSB | SK | CEMUMAR | CEMUMAR-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 80 | 2780 | 2780 | 38724972.79 | 46857596.69 | 71.7 | 81.2 | N/A | N/A | SIDETRACK | N/A | N/A | 2024-06-08 | 2025-06-02 17:00 | 2024-08-31 09:00 | 4462.5 | SHALLOW WATER | 2425 | 2424.17 | 41581244.76 | N/A | 89.67 | N/A | 41581244.76 | 89.67 | 17.77 | 14.9 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.01 |  | 2062 |  | 2659 | [27 empty] | Missing
2025-09-29 | 2025-09-29 18:00 | PCSB | PM | IRAMA NORTH | IRAMA NORTH-1 | EXPLORATION/APPRAISAL | PVD-6 | JACK UP | 63 | 2340 | 1930 | 26805261.15 | 31692656.14 | 52.99 | 65.75 | N/A | N/A |  | N/A | N/A | 2024-08-17 | 2024-08-13 13:00 | 2024-10-02 21:00 | 2118.8 | SHALLOW WATER | 2213.5 | 1862.01 | 18150404.23 | N/A | 32.08 | N/A | 18150404.23 | 32.08 | 4.64 | 3.86 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.92 |  | 1288 |  | 1409 | [27 empty] | Missing
2025-09-29 | 2025-09-29 12:08 | PCSB | PM | AMARYLLIS | AMARYLLIS-1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 63.1 | 1851 | 1765 | 22011317.7 | 32624226.33 | 27.04 | 54.19 | N/A | N/A | SIDETRACK | N/A | N/A | 2024-07-06 | 2024-06-29 17:00 | 2024-08-13 13:00 | 3947 | SHALLOW WATER | 2670 | 1691.42 | 24569844.31 | N/A | 44.83 | N/A | 24569844.31 | 44.83 | 0.61 | 0.61 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.29 |  | 635 |  | 1408 | [27 empty] | Missing
2025-09-25 | 2025-09-25 19:05 | PCSB | SK | KALUNG EMAS | KALUNG EMAS-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 62 | 1230 | 1230 | 24796362.04 | 39341642.04 | 51.32 | 84.84 | N/A | N/A | NO | N/A | N/A | 2024-05-24 | 2024-10-05 16:00 | 2024-06-17 18:00 | 1057.48 | SHALLOW WATER | 1230.42 | 1230.35 | 17780943.53 | N/A | 38.08 | N/A | 17780943.53 | 38.08 | 0.68 | 0.68 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.02 |  | 2012 |  | 3373 | [27 empty] | Missing
2025-09-17 | 2025-09-18 15:32 | PCSB | PM | IRONG BARAT | IRONG BARAT-C05ST1 | APPRAISAL CUM DEV/DEVELOPMENT | GUNNLOD | JACK UP | 65.7 | 3852 | 1164 | N/A | N/A | N/A | N/A | 16635000 | 38.79 |  | N/A | DRY TREE | 2025-06-24 | 2025-04-15 04:15 | 2025-07-20 | 2112 | SHALLOW WATER | 3997 | 1199.31 | N/A | N/A | N/A | N/A | 16634029.94 | 38.7 | 23.55 | 23.45 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1580 |  | 1.95 |  | 938.96 |  | 2271.77 |  | 17.58 | 10315000 | OHGP | 1 | 451 | 14.11 | 3050853.15 | 1.68 | 808.09 | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1 | SINGLE | L80 | 50 | False | NONE | L80 | 9.1 | CACL2 | NO | NO | Missing
2025-09-13 | 2025-09-13 13:54 | PCSB | PM | TABU | TABU-A1ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 2136 | 1949 | N/A | N/A | N/A | N/A | 8469087.75 | 20.2 |  | N/A | DRY TREE | 2025-07-05 | 2025-05-28 21:30 | 2025-07-20 | 670 | SHALLOW WATER | 2140 | 1952 | N/A | N/A | N/A | N/A | 9231065.62 | 25.77 | 9.12 | 8.54 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 3.93 |  | 1890.42 |  | 4175.5 |  | 6.7 | 2733184 | CH | 1 | 390 | 7.4 | 2493142.78 | 1.13 | 383.77 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4 | SINGLE | L80 | 203.422 | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-09-12 | 2025-12-09 10:21 | PCSB | SB | SAMARANG | SM-F98ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 10.9 | 1641 | 1424 | N/A | N/A | N/A | N/A | 11513121.35 | 20.07 | NO | N/A | DRY TREE | 2025-10-06 | 2025-10-01 | 2025-10-14 16:00 | 1264.25 | SHALLOW WATER | 1624 | 1433 | N/A | N/A | N/A | N/A | 5462933.62 | 11.58 | 5.2 | 5.2 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 1.36 |  | 553 |  | 1317 |  | 1.78 |  | MONOBORE | 0.3 | 159 | 1.42 | 1262340.82 | 0.27 | 225 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 6 | SINGLE | L80 13CR | 1283 | False | NONE | L80 13CR | 8.5 | KCL | NO | NO | Missing
2025-09-12 | 2025-09-12 23:01 | IPC | PM | BERTAM | BERTAM A-21 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 74.7 | 5089 | 1656 | N/A | N/A | N/A | N/A | 22953673 | 56 | NO | N/A | DRY TREE | 2025-05-07 | 2025-05-07 13:00 | 2025-07-13 04:00 | 5084 | SHALLOW WATER | 5202 | 1651 | N/A | N/A | N/A | N/A | 24611055 | 69.63 | 0.9 | 0.9 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 3.3 |  | 1129 |  | 1442 |  | 11.7 | 5909954 | OHSAS/OHPDL | 0.7 | 373 | 10.96 | 4620836 | 0.64 | 271 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1 | SINGLE | L80 | 500 | False | ICD | L80 | 8.3 | SEAWATER/DRILLWATER | NO | NO | Missing
2025-09-10 | 2025-11-28 23:28 | HML | PM | BUNGA RAYA | BSA-15ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 53 | 4619 | 1981 | N/A | N/A | N/A | N/A | 4481905.42 | 11.81 | NO | N/A | DRY TREE | 2025-08-10 | 2025-08-09 17:00 | 2025-10-04 | 5630 | SHALLOW WATER | 4642 | 2011 | N/A | N/A | N/A | N/A | 21663681.47 | N/A | 0.0004 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1830 |  | 1.97 |  | 791 |  | 1191 |  | 5.02 | 4472275.99 | CH | 1 | 390 |  |  | 0.3 | 192 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1 | SINGLE | L80 13CR | 105 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Missing
2025-09-09 | 2025-11-05 22:35 | HML | SB | SOUTH FURIOUS | SFJT-D10 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 17.7 | 952 | 885.8 | N/A | N/A | N/A | N/A | 6732123.42 | 10.8 | NO | N/A | DRY TREE | 2024-10-01 | 2024-09-30 | 2024-10-30 | 876.4 | SHALLOW WATER | 936 | 877.5 | N/A | N/A | N/A | N/A | 5181611.9 | 12.3 | 2 | 2 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.5 |  | 961.8 |  | 1687.8 |  | 3.5 | 2137522.63 | OHSAS/OHPDL | 0.7 | 373 | 3.7 | 2228748 | 1.3 | 726 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2 | SINGLE | L80 1CR | 777 | True | INNER STRING WITH SSD | L80 1CR | 8.7 | KCL | NO | NO | Missing
2025-09-09 | 2025-09-09 17:53 | ROC OIL | SK | D21 | D21-A3 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 50.6 | 3342 | 2154 | N/A | N/A | N/A | N/A | 15855000 | 33.8 | NO | N/A | DRY TREE | 2024-02-19 | 2024-01-29 15:00 | 2024-03-13 | 2635 | SHALLOW WATER | 3393 | 2182 | N/A | N/A | N/A | N/A | 17213820 | 41.53 | 19 | 17.6 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.52 |  | 720 |  | 1991 |  | 9.6 | 4743837 | CH | 1 | 390 | 7.57 | 3765352 | 0.68 | 436 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 13CR | 67 | True | NONE | L80 13CR | 10 | NABR |  |  | Missing
2025-09-09 | 2025-11-27 17:51 | ROC OIL | SK | D21 | D21-A11 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 50.6 | 2835 | 2182 | N/A | N/A | N/A | N/A | 13470000 | 28.63 | NO | N/A | DRY TREE | 2024-03-28 | 2024-02-10 | 2024-04-14 02:00 | 1203 | SHALLOW WATER | 2850 | 2196 | N/A | N/A | N/A | N/A | 10957337.74 | 25.04 | 6.2 | 6.2 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.43 |  | 721 |  | 2685 |  | 8.6 | 4493672 | CH | 1 | 390 | 7.07 | 3493929.61 | 0.8 | 374 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 13CR |  | True | NONE | L80 13CR | 9.6 | NACL/NABR |  |  | Missing
2025-09-04 | 2026-02-04 21:38 | VESTIGO | PM | TNAG | TBK-B6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 71.5 | 2999.27 | 2810 | N/A | N/A | N/A | N/A | 8308169.65 | 13.37 | NO | N/A | DRY TREE | 2025-11-15 | 2025-11-14 04:00 | 2025-12-13 04:00 | 2858.72 | SHALLOW WATER | 2975 | 2822.02 | N/A | N/A | N/A | N/A | 7828516 | 19.44 | 30 | 1 | SW DEV SLIM HOLE (WITH OFFLINE CAPABILITY RIG) |  | 1.1 |  | 420 |  | 555 |  | 1.25 |  | 479 |  | 865 |  | 1.58 | 2339486 | MONOBORE | 0.3 | 159 | 1.22 | 1975957 | 0.12 | 202 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" |  | SINGLE | L80 13CR |  | False | NONE | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Missing
2025-09-04 | 2025-12-03 10:20 | PCSB | SB | SAMARANG | SM-F95ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 10.91 | 2340.44 | 1801.58 | N/A | N/A | N/A | N/A | 13572596.94 | 27.34 | SIDETRACK | N/A | DRY TREE | 2025-09-24 | 2025-09-11 05:15 | 2025-10-14 19:00 | 1902.2 | SHALLOW WATER | 2318.2 | 1781.4 | N/A | N/A | N/A | N/A | 6444621.28 | 16.91 | 6.41 | 6.41 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 0.91 |  | 430 |  | 1574 |  | 2.08 | 1204819 | CHGP | 2 | 789 | 1.82 | 1131194 | 0.24 | 149 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4 | SINGLE | L80 13CR | 80 | False | NONE | L80 13CR | 8.5 | NACL | NO | NO | Missing
2025-09-04 | 2026-02-04 21:54 | VESTIGO | PM | TNAG | TBK-B7 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 71.5 | 3008.99 | 2809 | N/A | N/A | N/A | N/A | 8911407.65 | 13.55 | NO | N/A | DRY TREE | 2025-11-20 | 2025-11-19 23:30 | 2025-12-09 14:00 | 2889.72 | SHALLOW WATER | 3006 | 2821.16 | N/A | N/A | N/A | N/A | 5537649 | 9.56 | 2 | 2 | SW DEV SLIM HOLE (WITH OFFLINE CAPABILITY RIG) |  | 1.1 |  | 420 |  | 555 |  | 0.78 |  | 386 |  | 614 |  | 1.6 | 2156264 | MONOBORE | 0.3 | 159 | 1.86 | 2065920 | 0.19 | 209 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" |  | SINGLE | L80 13CR |  | False | NONE | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Missing
2025-08-26 | 2025-08-26 13:42 | HESS | PM | BUNGA KANGSAR | BUNGA KANGSAR-A5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64.9224 | 4239.1584 | 1898.904 | N/A | N/A | N/A | N/A | 17596713.87 | 35.28 | NO | N/A | DRY TREE | 2023-02-12 | 2023-02-12 06:00 | 2025-06-24 17:30 | 4172.4377 | SHALLOW WATER | 4282.44 | 1917.8687 | N/A | N/A | N/A | N/A | 27416870.86 | 216.41 | 27.98 | 12.84 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.76 |  | 756 |  | 2076 |  | 10.02 | 4510582 | OHSAS/OHPDL | 0.7 | 373 | 16.79 | 17662452.03 | 1.46 | 611 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1 | SINGLE | L80 13CR | 30 | True | NONE | L80 13CR | 8.5 | KCL | NO | NO | Missing
2025-08-20 | 2025-08-21 10:06 | PCSB | PM | IRONG BARAT | IRONG BARAT-C12ST2 | APPRAISAL CUM DEV/DEVELOPMENT | GUNNLOD | JACK UP | 65.7 | 3057 | 1067 | N/A | N/A | N/A | N/A | 22573193 | 46.21 | SIDETRACK | N/A | DRY TREE | 2025-05-06 | 2025-04-15 | 2025-06-22 15:00 | 1560.54 | SHALLOW WATER | 3023.5 | 1067 | N/A | N/A | N/A | N/A | 26673494.62 | 52 | 43.81 | 48.52 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1580 |  | 3.49 |  | 1425.86 |  | 2432.66 |  | 17.21 | 9501217 | OHGP | 1 | 451 | 11.06 | 6137292.27 | 1.11 | 949.91 | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | 2 ZONE | NO | 3-1/2" | 2 | SINGLE | L80 | 500 | False |  | L80 |  |  |  | 2 | Missing
2025-08-14 | 2025-11-21 17:08 | PCSB | PM | BEKOK | BEKOK DEEP-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 70 | 2821 | 2801 | N/A | 27071469.72 | N/A | 50.51 | N/A | N/A | NO | N/A | DRY TREE | 2025-08-23 | 2025-08-13 08:15 | 2025-09-28 15:15 | 2701.3 | SHALLOW WATER | 2803 | 2782.96 | N/A | 23496222.34 | N/A | 46.29 | 23496222.34 | 46.29 | 5.06 | 1.69 | SW HT |  | 3.5 |  | 2280 |  | 3980 |  | 1.23 |  | 766 |  | 2201 | [27 empty] | Missing
2025-08-14 | 2025-11-11 19:28 | PCSB | SB | SAMARANG | SAMARANG-F78ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 10.9 | 2055.78 | 1778.33 | N/A | N/A | N/A | N/A | 14956278.38 | 26.15 | SIDETRACK | N/A | DRY TREE | 2025-09-01 | 2025-08-26 | 2025-09-19 10:00 | 1869.39 | SHALLOW WATER | 2061.26 | 1783.3 | N/A | N/A | N/A | N/A | 6668681.27 | 19.93 | 19.97 | 19.65 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 1.1 |  | 408 |  | 1672.67 |  | 2.06 | 1568611 | CHGP | 2 | 789 | 5.8 | 1957413.38 | 0.81 | 289 | SANDSTONE | NORMAL |  | NO | NO | 3-1/2" |  | SINGLE | L80 13CR |  | False |  |  | 8.5 | SEAWATER/DRILLWATER |  |  | Missing
2025-07-24 | 2025-08-15 20:33 | HML | PM | BUNGA PAKMA | BPA-8 (PAKMA NOSE) | APPRAISAL CUM DEV/DEVELOPMENT | JU NAGA IV | JACK UP | 58 | 5315 | 2635 | N/A | N/A | N/A | N/A | 25075234.9 | 49.69 |  | N/A | DRY TREE | 2025-05-04 | 2025-05-04 09:00 | 2025-06-15 | 5043 | SHALLOW WATER | 5250 | 2618 | N/A | N/A | N/A | N/A | 24011674.05 | 61.23 | 13.88 | 13.88 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.9 |  | 718 |  | 1196.3 |  | 4.52 | 4709214.96 | CH | 1 | 390 | 5.6 | 5102919.16 | 0.33 | 302 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 3 | SINGLE | L80 13CR | 68.3 | False | NONE | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Missing
2025-07-15 | 2025-08-08 09:20 | SHELL | SK | MARJORAM | MARJORAM-102 | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE VIKING | DRILLSHIP | 887 | 2682 | 2066 | N/A | N/A | N/A | N/A | 78590000 | 51.25 | NO | N/A | WET TREE | 2025-03-16 | 2025-03-16 15:30 | 2025-06-08 15:00 | 1850 | DEEP WATER | 2826 | 2097 | N/A | N/A | N/A | N/A | 61400000 | 40.42 | 15.6 | 15.6 | DW DEV C2 (WET TREE) |  | 4 |  | 3640 |  | 8010 |  | 3.09 |  | 3775 |  | 10119 |  | 11.01 | 24710000 | SUBSEA | 1.3 | 1449 | 13.9 | 24510000 | 1.5 | 2644 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1 | SINGLE | 25CR | 1481 | True | NONE | 25CR | 10.2 | NACL/NABR | NO | NO | Missing
2025-07-15 | 2025-07-16 11:17 | SHELL | SK | MARJORAM | MARJORAM-101 | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE VIKING | DRILLSHIP | 891.6 | 2750.5 | 2134 | N/A | N/A | N/A | N/A | 77510000 | 49 | NO | N/A | WET TREE | 2025-03-14 | 2025-03-04 07:00 | 2025-05-16 21:30 | 1872 | DEEP WATER | 2789 | 2134 | N/A | N/A | N/A | N/A | 75600000 | 55.92 | 18.56 | 18.27 | DW DEV C2 (WET TREE) |  | 4 |  | 3640 |  | 8010 |  | 2.55 |  | 3436 |  | 12313 |  | 11.15 | 25170000 | SUBSEA | 1.3 | 1449 | 17.18 | 27640000 | 1.88 | 3021 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1 | SINGLE | 25CR | 1648 | True | NONE | 25CR | 10.2 | NACL/NABR | NO | NO | Missing
2025-07-11 | 2025-10-02 13:58 | ENQUEST | PM | SELIGI | SEG-30 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 73 | 2878.3 | 2286 | N/A | N/A | N/A | N/A | 10669048.2 | 26.39 |  | N/A | DRY TREE | 2025-07-13 | 2025-07-09 05:45 | 2025-08-26 19:00 | 2640 | SHALLOW WATER |  |  | N/A | N/A | N/A | N/A | 9207561 | 24.32 | 6.94 | 3.38 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.6 |  | 523 |  | 1032 |  | 10.39 | 4192950.8 | CH | 1 | 390 | 5.96 | 3038708.88 | 0.5 | 226 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 52.5 | True | NONE | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Missing
2025-07-11 | 2025-10-01 12:09 | ENQUEST | PM | SELIGI | SEG-29 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 73 | 3027.6 | 1325 | N/A | N/A | N/A | N/A | 11011582 | 28.16 |  | N/A | DRY TREE | 2025-07-14 | 2025-07-09 | 2025-08-21 20:00 | 2845 | SHALLOW WATER | 3032 | 1327.68 | N/A | N/A | N/A | N/A | 9358745 | 24.47 | 0.34 | 0.34 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1 |  | 352 |  | 976 |  | 11.7 | 5038674 | CH | 1 | 390 | 9.58 | 4372785 | 0.8 | 339 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | DUAL | L80 | 96 | True | NONE | L80 | 8.9 | NACL | NO | NO | Missing
2025-07-11 | 2025-07-24 15:32 | ENQUEST | PM | SELIGI | SEC-41ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 73 | 3296.44 | 1653.53 | N/A | N/A | N/A | N/A | 14276250 | 32.36 | NO | N/A | DRY TREE | 2025-03-27 | 2025-03-25 12:00 | 2025-05-24 13:30 | 3832 | SHALLOW WATER | 3356 | 1646.2 | N/A | N/A | N/A | N/A | 17540387 | 61 | 28.2 | 26 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.5 |  | 725 |  | 1405 |  | 12.07 | 5463640 | CH | 1 | 390 | 23.71 | 6706188.6 | 2.2 | 620 | SANDSTONE | NORMAL | CASED HOLE | 3 ZONE | NO | 3-1/2" | 3 | DUAL | L80 | 134.5 |  | NONE | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Missing
2025-07-11 | 2025-08-06 17:28 | ENQUEST | PM | SELIGI | SEC-21ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 73 | 2800 | 1974.5 | N/A | N/A | N/A | N/A | 13028501.41 | 30.17 | SIDETRACK | N/A | DRY TREE | 1970-01-01 | 2025-06-05 22:45 | 2025-06-26 | 2143 | SHALLOW WATER | 2563 | 1891.42 | N/A | N/A | N/A | N/A | 12951846.08 | 32.46 | 2.1 | 1.4 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.3 |  | 546 |  | 1842 |  | 12.49 | 5648193.47 | CH | 1 | 390 | 8.77 | 4778251.21 | 1.1 | 569 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4 | DUAL | L80 |  |  | NONE | L80 |  | SEAWATER/DRILLWATER | NO | NO | Missing
2025-06-30 | 2025-09-25 21:55 | PCSB | SB | SAMARANG | SAMARANG-E45ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 10.5 | 2619 | 2080 | N/A | N/A | N/A | N/A | 11368133.61 | 26.59 | NO | N/A | DRY TREE | 2025-07-24 | 2025-07-15 18:00 | 2025-08-05 22:45 | 1942 | SHALLOW WATER | 2605 | 2068 | N/A | N/A | N/A | N/A | 8766232.29 | 19.43 | 0 | 0 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 1.06 |  | 554 |  | 1376 |  | 3.29 | 1906817.68 | MONOBORE | 0.3 | 159 | 1.89 | 1668832.44 | 0.22 | 195 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 2 | SINGLE | L80 13CR | 535 | False | NONE | L80 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Missing
2025-06-26 | 2025-12-02 17:56 | PCSB | PM | TABU | TABU-A4ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.3 | 1867 | 1714 | N/A | N/A | N/A | N/A | 8583873.16 | 20.3 | NO | N/A | DRY TREE | 2025-06-27 | 2025-06-27 | 2025-10-03 08:30 | 829 | SHALLOW WATER | 1820 | 1689.11 | N/A | N/A | N/A | N/A | 7875280.62 | 15.9 | 1.7 | 0.26 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 2.54 |  | 1429.36 |  | 2994.21 |  | 6.5 |  | CH | 1 | 390 | 3.96 | 2257460.36 | 0.66 | 378.04 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2 | SINGLE | L80 |  | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-06-25 | 2025-06-25 12:07 | HESS | PM | BERGADING | BERGADING A-11 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 57.3634 | 4364.43 | 1165.86 | N/A | N/A | N/A | N/A | 26783985 | 44.71 | NO | N/A | DRY TREE | 2024-07-06 | 2024-07-06 10:30 | 2024-09-21 01:30 | 4264.4568 | SHALLOW WATER | 4365 | 1180 | N/A | N/A | N/A | N/A | 40253798.75 | 75.69 | 2.2 | 2 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 2.2 |  | 1084 |  | 2873 |  | 9.23 | 9788284 | CH | 1 | 390 | 19.43 | 13370462 | 1.3 | 932 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1 | DUAL | L80 13CR | 1160 | True | NONE | L80 13CR | 9.3 | KCL | NO | NO | Missing
2025-06-25 | 2025-10-22 10:10 | PCSB | PM | TABU | TABU-A8ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.3 | 2362 | 1679 | N/A | N/A | N/A | N/A | 7697666.7 | 18.5 | NO | N/A | DRY TREE | 2025-08-18 | 2025-06-20 18:00 | 2025-08-26 07:00 | 661.08 | SHALLOW WATER | 2310 | 1662.85 | N/A | N/A | N/A | N/A | 7649479.36 | 15.25 | 1.43 | 0.41 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 2.41 |  | 1433.86 |  | 3455.98 |  | 5.9 | 2747241.57 | OHSAS/OHPDL | 0.7 | 373 | 3.66 | 2934937.05 | 0.48 | 387.24 | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 2 | SINGLE | L80 | 164.64 | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-06-25 | 2025-09-18 17:01 | HML | PM | N/A | BUNGA ASTER-2 | EXPLORATION/APPRAISAL | JU NAGA IV | JACK UP | 56 | 3033 | 2420 | 19999696.11 | 19999696.11 | 42 | 42 | 0 | 0 |  | N/A | DRY TREE | 2025-06-30 | 2025-09-18 05:00 | 2025-07-24 02:00 | 2977 | SHALLOW WATER | 3064 | 2431 | N/A | 14428740.98 | N/A | 32.5 | 14428740.98 | 32.5 | 0.12 | 0.12 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.07 |  | 474 |  | 1209 |  | 0 | 0 |  | 0 | 0 | [21 empty] | Missing
2025-06-23 | 2025-06-23 15:13 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI-C6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64 | 5544.6168 | 1910.182 | N/A | N/A | N/A | N/A | 19155460.74 | 45.29 | NO | N/A | DRY TREE | 2023-10-10 | 2023-10-09 17:00 | 2024-11-06 06:00 | 5505.88 | SHALLOW WATER | 5612.2824 | 1913.598 | N/A | N/A | N/A | N/A | 22990011.46 | 54.85 | 3.73 | 3.73 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 1.49 |  | 622 |  | 1273 |  | 17.92 | 6759917 | CH | 1 | 390 | 16.69 | 5630422 | 1.25 | 510 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1 | DUAL | L80 13CR | 110 | True | NONE | L80 13CR | 8.8 | KCL | NO | NO | Missing
2025-06-23 | 2025-06-23 09:08 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI-C5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64 | 6049.67 | 1892.2 | N/A | N/A | N/A | N/A | 20680233 | 42.6 | NO | N/A | DRY TREE | 2023-10-12 | 2023-10-12 07:30 | 2024-06-14 06:00 | 5921.94 | SHALLOW WATER | 6028.3344 | 1885.82 | N/A | N/A | N/A | N/A | 22195859.05 | 56.69 | 6.99 | 7.02 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 1.83 |  | 622 |  | 1156 |  | 10.94 | 5287055 | CH | 1 | 390 | 12.71 | 6109969.33 | 0.73 | 332 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1 | DUAL | L80 13CR | 7.8 | True | NONE | L80 13CR | 8.8 | KCL | NO | NO | Missing
2025-06-21 | 2025-07-24 17:26 | PCSB | PM | PM6/12 | LEBAH EMAS-1 ST1 | EXPLORATION/APPRAISAL | PVD 6 | JACK UP | 60 | 2723 | 2705 | 0 | 40704140 | 0 | 59.73 | 0 | 0 | SIDETRACK | N/A | DRY TREE | 2025-05-18 | 2025-05-12 20:30 | 2025-07-01 05:00 | 3611.78 | SHALLOW WATER | 2547.75 | 2532.57 | N/A | 30027221.47 | N/A | 49.35 | 30027221.47 | 49.35 | 25.33 | 25.33 | SW HT |  | 3.5 |  | 2280 |  | 3980 |  | 2.52 |  | 1800 |  | 1992 |  | 0 | 0 |  | 0 | 0 | [21 empty] | Missing
2025-06-19 | 2026-02-23 11:15 | HML |  | BUNGA ORKID | BOC-28 (TE) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 56 | 7121 | 0 | 0 | 0 | 0 | 0 | 44344829.4 | 99.19 | NO | N/A | DRY TREE | 2024-05-25 | 2024-05-25 18:00 | 2024-08-03 12:00 | 6800 | SHALLOW WATER | 6970 | 2000.3 | N/A | N/A | N/A | N/A | 40887362 | 83.52 | 6.32 | 6.32 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 2.69 |  | 1230 |  | 1574 |  | 0 | 0 | CH | 1 | 390 | 9.79 | 7673956 | 0.44 | 344 |  | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1 | SINGLE | L80 1CR | 646.36 | True |  | L80 13CR | 8.9 | SEAWATER/DRILLWATER | NO | NO | Missing
2025-06-14 | 2025-11-21 10:26 | PCSB | PM | TABU | TABU-A16ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.3 | 2881 | 1942 | 0 | 0 | 0 | 0 | 11403926.63 | 26.4 | NO | N/A | DRY TREE | 2025-08-29 | 2025-06-05 22:00 | 2025-09-22 17:00 | 1971 | SHALLOW WATER | 2961 | 1940.89 | N/A | N/A | N/A | N/A | 14572736.25 | 35.83 | 20.54 | 20.26 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.63 |  | 1231.08 |  | 2233.63 |  | 6.7 | 3873000 | OHSAS/OHPDL | 0.7 | 373 | 10.15 | 3006697.7 | 1.04 | 464.94 | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1 | SINGLE | L80 |  | False | NONE | L80 | 8.6 | NACL | NO | NO | Missing
2025-06-13 | 2025-10-07 18:00 | PCSB | PM | BEKOK | BEKOK-BB18ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 72 | 2992 | 1287 | 0 | 0 | 0 | 0 | 15470083.13 | 36.65 |  | N/A | DRY TREE | 2025-08-14 | 2025-07-09 16:30 | 2025-08-28 16:30 | 2413 | SHALLOW WATER | 3005 | 1279.96 | N/A | N/A | N/A | N/A | 9163213.03 | 20.58 | 0.3 | 0.3 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.04 |  | 552.95 |  | 1165.61 |  | 7 | 1882077 | OHSAS/OHPDL | 0.7 | 373 | 5.79 | 2020286 | 0.74 | 402.86 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | 1 ZONE |  | 3-1/2" | 1 | SINGLE | L80 13CR | 493 |  |  | L80 13CR | 11.5 | CABR2 | NO | NO | Missing
2025-06-10 | 2025-09-11 22:04 | PCSB | PM | BEKOK | BEKOK-BB17ST4 | APPRAISAL CUM DEV/DEVELOPMENT | PVD 6 | JACK UP | 72 | 3439.61 | 1291.08 | 0 | 0 | 0 | 0 | 16140319.28 | 36.85 | NO | N/A | DRY TREE | 2025-07-19 | 2025-07-15 20:00 | 2025-08-14 06:00 | 2677 | SHALLOW WATER | 3243 | 1290.28 | N/A | N/A | N/A | N/A | 11766564.77 | 29.42 | 28.58 | 28.58 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.15 |  | 548.68 |  | 1339.66 |  | 7 | 2001214 | OHSAS/OHPDL | 0.7 | 373 | 2 | 16.09 | 1.83 | 686.23 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1 | SINGLE | L80 |  |  |  | L80 |  |  |  |  | Missing
2025-06-09 | 2025-07-30 12:16 | PCSB | SB | SAMARANG | SM-B124 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 47.5 | 2485 | 2063 | 0 | 0 | 0 | 0 | 13.18 | 23.53 | NO | N/A | DRY TREE | 2025-05-04 | 2025-05-04 00:15 | 2025-06-09 02:00 | 2472 | SHALLOW WATER | 2472 | 2047 | N/A | N/A | N/A | N/A | 7650542.91 | 18.09 | 10.42 | 10.42 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.7 |  | 675 |  | 1285 |  | 5.46 | 2.65 | CH | 1 | 390 | 4.75 | 1382819.22 | 0.48 | 171 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4 | SINGLE | L80 13CR | 59 | False | NONE | L80 13CR | 9.6 | KCL | NO | NO | Missing
2025-06-09 | 2025-07-21 10:31 | PCSB | SB | SAMARANG | SM-B125 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 47.5 | 2392 | 2087 | 0 | 0 | 0 | 0 | 13.58 | 24.06 |  | N/A | DRY TREE | 2025-05-03 | 2025-07-03 01:30 | 2025-05-28 15:50 | 2655 | SHALLOW WATER | 2645 | 2343 | N/A | N/A | N/A | N/A | 8975906.91 | 18.99 | 0.49 | 0.49 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.26 |  | 541 |  | 1025.72 |  | 6.6 | 2.89 | CH | 1 | 390 | 6.26 | 2507571.55 | 0.62 | 288 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 5 | SINGLE | L80 13CR | 215 | False | NONE | L80 13CR | 9.6 | KCL | NO | NO | Missing
2025-06-05 | 2025-10-08 17:00 | PCSB |  | SAMARANG | SAMARANG-E48ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 10.73 | 3869.18 | 2203 | N/A | N/A | N/A | N/A | 13627821.48 | 23.16 | SIDETRACK | N/A | DRY TREE | 2025-06-21 | 2025-06-20 12:00 | 2025-08-18 20:00 | 13776 | SHALLOW WATER | 3962.2 | 2413.8 | N/A | N/A | N/A | N/A | 21577601.45 | 34.4 | 56 | 56 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 1.79 |  | 1193 |  | 1566 |  | 3.74 | 2249315.26 | MONOBORE | 0.3 | 159 | 2.48 | 2346235.68 | 0.16 | 263 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 5 | SINGLE | L80 13CR | 1010 | False | NONE | L80 13CR | 8.5 | NACL | NO | NO | Missing
2025-05-30 | 2025-06-03 12:11 | PCSB | SB | KINABALU | KN-B6 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 193.58 | 15382.5 | 14977.8 | N/A | N/A | N/A | N/A | 29288882.27 | 58.42 | NO | N/A | DRY TREE | 2024-12-19 | 2024-12-18 14:00 | 2025-04-12 23:00 | 4569.34 | SHALLOW WATER | 4677.54 | 4555.23 | N/A | N/A | N/A | N/A | 27020441.03 | 58.12 | 19 | 14 | SW DEV C2 |  | 2.5 |  | 1440 |  | 3040 |  | 2.69 |  | 1244 |  | 1745 |  | 12.08 | 3407090.28 | MONOBORE | 0.3 | 159 | 14.39 | 7178045 | 0.94 | 469 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1 | SINGLE | L80 13CR | 436 | True | NONE | L80 13CR | 8.6 | NACL | NO | NO | Missing
2025-05-30 | 2025-06-04 20:06 | PCSB | SB | KINABALU | KN-B5 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 193.58 | 15601 | 14336.29 | N/A | N/A | N/A | N/A | 26343881.81 | 62.46 | NO | N/A | DRY TREE | 2024-11-06 | 2024-11-05 09:00 | 2025-04-20 23:59 | 4689.73 | SHALLOW WATER | 4797.93 | 4396.44 | N/A | N/A | N/A | N/A | 22740550.81 | 51.59 | 7 | 7 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1785 |  | 2.22 |  | 982 |  | 1421 |  | 11.75 | 3183019.76 | MONOBORE | 0.3 | 159 | 9.4 | 5637600 | 0.6 | 360 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1 | SINGLE | L80 13CR | 1404 | False | NONE | L80 13CR | 8.6 | NACL | NO | NO | Missing
2025-05-29 | 2025-10-20 10:55 | SHELL | SK | LAVUNG TEPO | LAVUNG TEPO-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 67 | 2716 | 2365 | 30017527 | 34488514 | 39.63 | 47.94 | N/A | N/A | NO | N/A | N/A | 2025-06-23 | 2025-06-17 05:30 | 2025-08-19 09:15 | 2471.5 | SHALLOW WATER | 2575.43 | 2249.86 | N/A | 38700000 | N/A | 63.16 | 38700000 | 63.16 | 20.6 | 17.3 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.01 |  | 3063 |  | 4773 |  | 0 | 0 |  | 0 | 0 | [21 empty] | Missing
2025-05-22 | 2025-05-23 15:06 | PCSB | SB | KINABALU | KN-B7 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 193.58 | 13718 | 10204 | N/A | N/A | N/A | N/A | 28427933.14 | 65.2 | NO | N/A | DRY TREE | 2025-02-06 | 2025-02-06 18:00 | 2025-04-04 15:30 | 4078 | SHALLOW WATER | 4186.2 | 3105.6 | N/A | N/A | N/A | N/A | 23506373.36 | 56.9 | 5 | 3 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 2.1 |  | 832 |  | 1684 |  | 19.6 | 4431855.3 | CHGP | 2 | 789 | 19.36 | 4.03 | 2 | 591 | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2 | SINGLE | L80 13CR | 477 | True | NONE | L80 13CR | 8.6 | NACL | NO | NO | Missing
2024-04-09 | 2024-08-20 | PCSB | SK | KERDAS | KERDAS-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 62.5 | 1609 | 1430 | 34415879.12 | 38905563.52 | 68.3 | 84 | N/A | N/A | NO | N/A | N/A | 2024-04-13 | 2024-04-13 11:00 | 2024-06-02 17:00 | 1105 | SHALLOW WATER | 1200 | 1092.7 | 24351396.59 | N/A | 50.25 | N/A | N/A | N/A | 2.69 | 2.69 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 5.07 |  | 3225 |  | 5489 | [27 empty] | Exist
2024-03-19 | 2024-06-13 | PCSB | SK | BOKOR | BOKOR-E501 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 1691 | 1528 | N/A | N/A | N/A | N/A | 9845000 | 17.55 | NO | N/A | DRY TREE | 2024-03-20 18:00 | 2024-03-20 18:00 | 2024-05-06 19:00 | 1585 | SHALLOW WATER | 1694 | 1529.33 | N/A | N/A | N/A | N/A | 9844700 | 16.7 | 0.75 | 0.75 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2 |  | 1100.71 |  | 1766.2 | [6 empty] | 6.3 | 3462634 | 1.13 | 623 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | DUAL | L80 13CR | 2323 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
2024-02-22 | 2024-08-12 | PCSB | SK | CECIL | CECIL-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 118 | 2046 | 2046 | 29440000 | 35380000 | 57.65 | 70.25 | N/A | N/A | NO | N/A | N/A | 2024-02-25 | 2024-02-25 07:00 | 2024-05-20 00:30 | 1854 | SHALLOW WATER | 2000 | 2000 | N/A | 40679382.52 | N/A | 84.73 | N/A | N/A | 28.26 | 26.59 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 7.08 |  | 3943 |  | 5897 | [27 empty] | Exist
2024-01-26 | 2024-06-24 | PCSB | SK | GEDOMBAK | GEDOMBAK-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 51 | 2530 | 2530 | 58000000 | 74488120.44 | 118.22 | 161.05 | N/A | N/A | NO | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-04-07 15:00 | 2646.58 | SHALLOW WATER | 2730 | 2724.08 | N/A | 26248129.08 | N/A | 65.63 | N/A | N/A |  |  | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.95 |  | 1215 |  | 2569 | [27 empty] | Exist
2024-01-24 | 2024-05-11 | PCSB | SK | BOKOR | BOKOR-E507 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 1595 | 1536 | N/A | N/A | N/A | N/A | 11450125 | 23.03 | NO | N/A | DRY TREE | 2024-01-28 | 2024-01-28 20:00 | 2024-03-13 04:00 | 1373 | SHALLOW WATER | 1596 | 1540.03 | N/A | N/A | N/A | N/A | 8219237 | 16.33 | 0.13 | 0.13 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2 |  | 922 |  | 1679 | [6 empty] | 4.2 | 1869252 | 0.8 | 357 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1749 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
2024-01-11 | 2024-06-24 | PTTEP | SK | SATONG | SATONG-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 44.9 | 1611 | 1536 | 9540000 | 15060000 | 20.63 | 31.13 | N/A | N/A | NO | N/A | N/A | 2024-02-10 | 2024-02-10 | 2024-03-15 17:00 | 1533.8 | SHALLOW WATER | 1616 | 1538 | N/A | 15420000 | N/A | 40.71 | N/A | N/A | 26.9 | 1.66 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.52 |  | 1091 |  | 3065 | [27 empty] | Exist
2024-01-05 | 2024-06-12 | PCSB | SK | TANGGU | TANGGU-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 52.71 | 2182.5 | 2182.5 | 33458354.56 | 35141308.32 | 76.39 | 82.76 | N/A | N/A | NO | N/A | N/A | 2024-02-02 | 2024-02-02 09:00 | 2024-04-13 11:00 | 2544.79 | SHALLOW WATER | 2630 | 2627.21 | 33458354.56 | N/A | 76.39 | N/A | N/A | N/A | 20.08 | 20.08 | SW EXP C2 |  | 2.7 |  | 1490 |  | 1220 |  | 3.22 |  | 1794 |  | 3113 | [27 empty] | Exist
2024-01-01 | 2024-06-07 | PCSB | SK | BOKOR | BOKOR-E506 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 903 | 794 | N/A | N/A | N/A | N/A | 8088123.48 | 17.36 | NO | N/A | DRY TREE | 2024-01-11 | 2024-01-11 03:30 | 2024-04-27 09:45 | 794 | SHALLOW WATER | 903 | 795.08 | N/A | N/A | N/A | N/A | 6573505.13 | 10.22 | 1.12 | 1.12 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 3.19 |  | 758.42 |  | 2610.55 | [6 empty] | 2.96 | 1719724 | 1 | 580.45 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1066 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
2023-12-28 | 2024-05-17 | VESTIGO | PM | BERANTAI | BRWA-19 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 66.7 | 4336 | 1798 | N/A | N/A | N/A | N/A | 24825000 | 51.36 | NO | N/A | DRY TREE | 2024-02-15 | 2024-02-03 | 2024-03-27 12:00 | 4193.08 | SHALLOW WATER | 4310 | 1826.55 | N/A | N/A | N/A | N/A | 24975626 | 61.85 | 0 | 0 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 2.74 |  | 1074 |  | 1299 | [6 empty] | 4.5 | 2620828 | 0.32 | 185 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 33 | False |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | 2 | Exist
2023-12-21 | 2024-05-24 | SHELL | SB | PEKAKA | PEKAKA-1 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 2896 | 4178.6 | 4152.7 | 65300000 | 89200000 | 48.81 | 67.91 | N/A | N/A | NO | N/A | N/A | 2024-01-15 | 2024-01-15 | 2024-02-22 | 1000.61 | DEEP WATER | 3923 | 3922.54 | 59960000 | N/A | 52.85 | N/A | N/A | N/A | 14.5 | 7.4 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | No |  | No |  | No | [27 empty] | Exist
2023-12-20 | 2024-05-13 | PCSB | PM | BESAR | BESAR-A6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2635 | 1751 | N/A | N/A | N/A | N/A | 27490962 | 55.83 | NO | N/A | DRY TREE | 2024-01-03 | 2024-01-03 04:00 | 2024-04-09 | 2590.2 | SHALLOW WATER | 2708 | 1788.04 | N/A | N/A | N/A | N/A | 22877147 | 52.07 | 6.92 | 2.86 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 2.14 |  | 890 |  | 2521 | [6 empty] | 30.4 | 13149800 | 3.28 | 1480 | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 7.0 | SINGLE | L80 13CR | 5243 | True |  | L80 13CR | 10.3 | CACL2 | NO | NO | Exist
2023-12-10 | 2024-03-20 | PCSB | SK | E11 | E11SC-5ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 70.71 | 1387.69 | 1231.94 | N/A | N/A | N/A | N/A | 20106588 | 38.03 | NO | N/A | DRY TREE | 2023-12-23 | 2023-12-23 08:00 | 2024-01-22 03:30 | 1281.3167 | SHALLOW WATER | 1382.29 | 1230.16 | N/A | N/A | N/A | N/A | 13019952.13 | 28.69 | 0.91 | 0.91 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 7.7 |  | 3234 |  | 7104 | [6 empty] | 5.63 | 2870655 | 1.07 | 633 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 427 | True |  | L80 13CR | 9.8 | NACL | NO | NO | Exist
2023-12-08 | 2024-06-13 | PCSB | SK | BOKOR | BOKOR-E505 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 995 | 799 | N/A | N/A | N/A | N/A | 8222525.16 | 18.03 | NO | N/A | DRY TREE | 2024-01-09 | 2024-01-09 21:30 | 2024-05-19 | 886 | SHALLOW WATER | 995 | 801.55 | N/A | N/A | N/A | N/A | 7677851.67 | 15.21 | 1.51 | 1.51 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.21 |  | 1184.75 |  | 2020.02 | [6 empty] | 4.37 | 2357330 | 1.34 | 722 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1358 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
2023-12-07 | 2024-04-15 | PTTEP | SB | ROTAN | ROTAN-2 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 1407.1 | 2172 | 2154 | 15100000 | 17500000 | 17.2 | 20.5 | N/A | N/A | NO | N/A | N/A | 2023-12-20 | 2023-12-20 15:30 | 2024-01-03 09:30 | 738.9 | DEEP WATER | 2172 | 2154.34 | 18860000 | N/A | 19.4 | N/A | N/A | N/A | 1.95 | 1.93 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 2.44 |  | 2601 |  | 4719 | [27 empty] | Exist
2023-12-01 | 2024-06-25 | HML | PM | BUNGA ORKID | BUNGA ASTER -1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 53.79 | 3310 | 1820 | N/A | N/A | N/A | N/A | 21773000 | 46.1 | NO | N/A | N/A | 2024-04-02 | 2024-03-05 18:00 | 2024-04-29 06:00 | 3136.45 | SHALLOW WATER | 3234 | 1835.83 | N/A | N/A | N/A | N/A | 21445000 | 54.5 | 8.49 | 4.01 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.56 |  | 812 |  | 1343 | [27 empty] | Exist
2023-11-18 | 2024-04-25 | PCSB | PM | BESAR | BESAR-A7 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2380.6 | 1193 | N/A | N/A | N/A | N/A | 22502875 | 40.27 | NO | N/A | DRY TREE | 2024-01-09 21:00 | 2023-12-15 | 2024-03-08 15:15 | 2251.2 | SHALLOW WATER | 2369 | 1188.74 | N/A | N/A | N/A | N/A | 17213704 | 37.42 | 2.46 | 0.27 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.63 |  | 746 |  | 2191 | [6 empty] | 22.9 | 10493550 | 2.95 | 1350 | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 28 | True |  | L80 13CR | 9.3 | NACL | NO | NO | Exist
2023-11-11 | 2024-09-26 | PCSB | SK | BESAH | BESAH-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 120.8 | 2288 | 2149 | 44000000 | 50000000 | 93 | 105 | N/A | N/A | SIDETRACK | N/A | N/A | 2023-11-23 | 2023-11-13 02:00 | 2024-02-25 07:00 | 1973.2 | SHALLOW WATER | 2122 | 2013.73 | N/A | 49538138.18 | N/A | 104.39 | N/A | N/A | 9 | 9 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 6.85 |  | 3254 |  | 4365 | [27 empty] | Exist
2023-11-09 | 2024-06-20 | PCSB | PM | BESAR | BESAR-A9 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2740 | 1456.7 | N/A | N/A | N/A | N/A | 21887802.47 | 43.37 | NO | N/A | DRY TREE | 2023-11-15 | 2023-11-15 | 2024-04-12 | 2664.7 | SHALLOW WATER | 2782.5 | 1467.43 | N/A | N/A | N/A | N/A | 24105040.53 | 59.5 | 5.2 | 1.76 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.9 |  | 873 |  | 2668 | [6 empty] | 34.82 | 13675814.99 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 656 | True | NONE | 13CR | 9.2 | NACL | NO | NO | Exist
2023-10-30 | 2024-07-24 | VESTIGO | SK | KMSE | KMSE-A03 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 85 | 1655.73 | 1198.83 | N/A | N/A | N/A | N/A | 6017000 | 11.07 | NO | N/A | DRY TREE | 2024-04-30 | 2024-04-29 17:00 | 2024-06-02 17:30 | 1517.93 | SHALLOW WATER | 1636 | 1196.79 | N/A | N/A | N/A | N/A | 4069000 | 9.01 | 0 | 0 | SW DEV SLIM HOLEC (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | 1.2 |  | 492 |  | 803 | [6 empty] | 2.74 | 1548767 | 0.55 | 311 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 2-7/8" | 1.0 | SINGLE | L80 | 79 | True | NONE | L80 | 9.4 | NACL | NO | NO | Exist
2023-10-30 | 2024-07-24 | VESTIGO | SK | KMSE | KMSE-A04 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 85 | 1478.21 | 1200.16 | N/A | N/A | N/A | N/A | 5602000 | 9.69 | NO | N/A | DRY TREE | 2024-04-25 | 2024-04-24 09:00 | 2024-06-09 11:30 | 1357.93 | SHALLOW WATER | 1476 | 1194.1 | N/A | N/A | N/A | N/A | 4131000 | 9.44 | 17.78 | 17.78 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | 1.65 |  | 620 |  | 926 | [6 empty] | 2.07 | 1360241 | 0.43 | 281 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 2-7/8" | 1.0 | SINGLE | L80 | 39 | True | NONE | L80 | 9.4 | NACL | NO | NO | Exist
2023-10-30 | 2024-04-23 | HML | SB | SOUTH FURIOUS | SF MERAH-1 | EXPLORATION/APPRAISAL | PVD-3 | JACK UP | 58.82 | 3378.54 | 2124.66 | 16200389.19 | 23114569.43 | 48.11 | 63.94 | N/A | N/A | NO | N/A | N/A | 2024-01-25 | 2024-01-19 18:00 | 2024-03-05 18:00 | 3433.4044 | SHALLOW WATER | 3526 | 2385.86 | N/A | 16200000 | N/A | 47 | N/A | N/A | 0 | 0 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 1.97 |  | 665.94 |  | 961.94 | [27 empty] | Exist
2023-10-16 | 2024-03-27 | PCSB | SK | GARANTUNG | GARANTUNG-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 50 | 2300 | 2300 | 32678598.61 | 39410000 | 70.43 | 91.97 | N/A | N/A | NO | N/A | N/A | 2023-10-26 02:45 | 2023-10-20 | 2024-02-02 | 2220 | SHALLOW WATER | 2300 | 2299.27 | 39969249.33 | N/A | 105.03 | N/A | N/A | N/A | 46.48 | 5.07 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.98 |  | 2415 |  | 2756 | [27 empty] | Exist
2023-09-27 | 2024-03-22 | PCSB | SK | NAHARA | NAHARA-2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 50 | 2630 | 2495 | 51440000 | 71490000 | 107.56 | 158.98 | N/A | N/A | NO | N/A | N/A | 2023-11-01 | 2023-10-27 04:00 | 2024-02-02 | 3280.23 | SHALLOW WATER | 3280.23 | 2630 | N/A | 48118103.68 | N/A | 97.84 | N/A | N/A | 8.25 | 3.42 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.04 |  | 1378 |  | 3882 | [27 empty] | Exist
2023-09-22 | 2024-01-25 | PCSB | PM | BESAR | BESAR-A4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2865 | 2166.87 | N/A | N/A | N/A | N/A | 19377438.93 | 30.01 | NO | N/A | DRY TREE | 2023-10-08 | 2023-10-08 08:00 | 2023-11-28 | 2750.7 | SHALLOW WATER | 2868.5 | 2169.06 | N/A | N/A | N/A | N/A | 21038518.89 | 37.68 | 10.34 | 10.34 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 3.03 |  | 1701 |  | 2278 | [6 empty] | 9.54 | 4188139.08 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 2433.2224 | True | NONE | 13CR | 9 | NACL | NO | NO | Exist
2023-09-21 | 2024-03-13 | SEAH | SB | SOUTH FURIOUS | SF UNGU-1 | EXPLORATION/APPRAISAL | PVD-3 | JACK UP | 41.15 | 3023.16 | 2377.32 | 21376483.31 | 45605624.03 | 66.2 | 126.16 | N/A | N/A | SIDETRACK | N/A | N/A | 2023-10-29 | 2023-10-03 11:00 | 2024-01-19 18:00 | 2957.3301 | SHALLOW WATER | 3032.0024 | 2385.86 | N/A | 36500000 | N/A | 108.3 | N/A | N/A | 21.79 | 1.02 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 1.28 |  | 495.2 |  | 784.1 | [27 empty] | Exist
2023-09-18 | 2024-02-15 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI C-4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 63.61 | 2886.01 | 1738.19 | N/A | N/A | N/A | N/A | 6780000 | 29.42 | NO | N/A | DRY TREE | 2023-10-18 | 2023-10-17 | 2023-11-10 | 2797.45 | SHALLOW WATER | 2903.83 | 1739.88 | N/A | N/A | N/A | N/A | 15765592.83 | 29.42 | 1.3 | 0.9 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 0.95 |  | 224 |  | 849 | [6 empty] | 8.15 | 3455341 |  |  | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 190.08 | True |  | L80 13CR | 9.4 | KCL | NO | NO | Exist
2023-09-18 | 2024-08-05 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI C-3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 63.61 | 4946.66 | 1853.4 | N/A | N/A | N/A | N/A | 18530000 | 44.5 | NO | N/A | DRY TREE | 2023-10-15 | 2023-10-15 | 2024-06-16 | 4684.22 | SHALLOW WATER | 4790.61 | 1844.41 | N/A | N/A | N/A | N/A | 16700000 | 36.5 | 6.1 | 0.6 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 1.35 |  | 640 |  | 1103 | [6 empty] | 13.09 | 5112463 | 0.83 | 325 | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 405 | True |  | L80 13CR | 8.5 | KCL | NO | NO | Exist
2023-09-18 | 2024-08-12 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI C-2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 63.61 | 3113.38 | 1850.66 | N/A | N/A | N/A | N/A | 16010000 | 32 | NO | N/A | DRY TREE | 2023-10-20 | 2023-10-20 08:30 | 2023-12-10 19:00 | 3014 | SHALLOW WATER | 3120.39 | 1852.92 | N/A | N/A | N/A | N/A | 14620000 | 30.02 | 15.68 | 0.9 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1600 |  | 1.33 |  | 846 |  | 1478 | [6 empty] | 7.27 | 4125413 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 405 | True |  | L80 13CR | 8.5 | KCL | NO | NO | Exist
2023-09-14 | 2024-03-05 | PCSB | SK | F13 | F13ESC-A6 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 78.02 | 1114.97 | 1049.68 | N/A | N/A | N/A | N/A | 21295217 | 43.5 | NO | N/A | DRY TREE | 2023-10-07 | 2023-10-07 | 2024-01-06 | 1074.61 | SHALLOW WATER | 1117.65 | 1053.55 | N/A | N/A | N/A | N/A | 15412487 | 35.25 | 4.45 | 3.51 | SW DEV C2 |  | 2 |  | 725 |  | 1380 |  | 4.86 |  | 1858 |  | 2845 | [6 empty] | 5.04 | 2823590 | 1.37 | 770 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 131 | True | NONE | L80 13CR | 8.5 | NACL | NO | NO | Exist
2023-09-14 | 2024-02-12 | PCSB | SK | F13 | F13ESC-A5 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 76.5 | 1247.49 | 1164.89 | N/A | N/A | N/A | N/A | 24171151.23 | 48.14 | NO | N/A | DRY TREE | 2023-10-07 | 2023-10-06 | 2023-12-15 | 1150.26 | SHALLOW WATER | 1259.68 | 1164.58 | N/A | N/A | N/A | N/A | 22224997.19 | 55.75 | 18.72 | 18.68 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 11.58 |  | 4186 |  | 6013 | [6 empty] | 8 | 2798041 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1053 | True | NONE | L80 13CR | 8.5 | NACL | NO | NO | Exist
2023-09-11 | 2024-01-31 | PCSB | SK | NAFIRI | NAFIRI-1 | EXPLORATION/APPRAISAL | BORR IDUN | JACK UP | 54 | 2730 | 2730 | 34685148 | 38536117 | 79.7 | 89.54 | N/A | N/A | NO | N/A | N/A | 2023-09-25 | 2023-09-12 12:00 | 2023-12-12 | 2681 | SHALLOW WATER | 2765 | 2764.87 | N/A | 36426033.19 | N/A | 91.5 | N/A | N/A | 4.11 | 3.12 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 3.66 |  | 1953 |  | 3685 | [27 empty] | Exist
2023-08-23 | 2024-05-02 | PTTEP | SK | LANG LEBAH | LANG LEBAH-3 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 88.2 | 4570 | 4508 | 74790000 | 74790000 | 131.5 | 131.5 | N/A | N/A | NO | N/A | N/A | 2023-09-25 | 2023-09-25 14:30 | 2024-02-03 | 4342.9 | SHALLOW WATER | 4468.3 | 4417.07 | N/A | 73400000 | N/A | 140.4 | N/A | N/A | 15.57 | 7.94 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.19 |  | 1820 |  | 4184 | [27 empty] | Exist
2023-08-11 | 2023-11-15 | HML | SB | KINABALU | KNDW-D08ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.04 | 4703.44 | 2390.73 | N/A | N/A | N/A | N/A | 14330000 | 39.2 | NO | N/A | DRY TREE | 2023-08-28 | 2023-08-24 | 2023-09-25 12:00 | 4473.19 | SHALLOW WATER | 4570.25 | 2390.12 | N/A | N/A | N/A | N/A | 13950000 | 32.5 | 13.01 | 13.01 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.01 |  | 786 |  | 1371 | [6 empty] | 6.6 | 4873375 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 3889 | True | AICV | L80 13CR | 8.9 | KCL | NO | NO | Exist
2023-07-20 | 2024-01-02 | PCSB | SK | BENDAI | BENDAI-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 49.5 | 3600 | 3151 | 24980000 | 28550000 | 68.9 | 82.7 | N/A | N/A | SIDETRACK | N/A | N/A | 2023-08-03 | 2023-07-24 | 2023-10-27 | 3437.5 | SHALLOW WATER | 3517 | 3083.13 | N/A | 30513670 | N/A | 94.46 | N/A | N/A | 20.1 | 20 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.49 |  | 956 |  | 2030.59 | [27 empty] | Exist
2023-07-04 | 2024-04-25 | PTTEP | SK | BABADON | BABADON-1 | EXPLORATION/APPRAISAL | NOBLE TOM PROSSER | JACK UP | 44.7 | 2308 | 2036 | 21380000 | 28710000 | 45.48 | 59.94 | N/A | N/A | NO | N/A | N/A | 2023-08-01 | 2023-07-25 20:15 | 2023-09-16 14:45 | 2452 | SHALLOW WATER | 2533 | 2201.84 | N/A | 23800000 | N/A | 52.77 | N/A | N/A | 7.67 | 7.67 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | No |  | No |  | No | [27 empty] | Exist
2023-06-28 | 2023-10-01 | PCSB | PM | BEKOK | BEKOK-AA19 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.5 | 3151 | 1555 | N/A | N/A | N/A | N/A | 19157862.73 | 31.73 | NO | N/A | DRY TREE | 2023-07-06 | 2023-07-04 12:00 | 2023-08-03 18:00 | 2952.2 | SHALLOW WATER | 3065 | 1524.15 | N/A | N/A | N/A | N/A | 14020566.52 | 28.56 | 0 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.7 |  | 846 |  | 1389 | [6 empty] | 7.76 | 4535375.52 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 180.455 | False | NONE | 13CR | 8.8 | NACL | NO | NO | Exist
2023-06-23 | 2023-10-20 | HML | SB | KINABALU | KNDW-D18 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 4190.8 | 2402.62 | N/A | N/A | N/A | N/A | 14010000 | 30.9 | NO | N/A | DRY TREE | 2023-07-24 09:15 | 2023-07-20 12:00 | 2023-08-24 | 4009.63 | SHALLOW WATER | 4106.67 | 2411.46 | N/A | N/A | N/A | N/A | 14090000 | 34.5 | 9.03 | 9.03 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 1.57 |  | 641.4 |  | 1070.75 | [6 empty] | 10.1 | 5784792.42 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2342 | True | AICV | L80 13CR | 8.9 | KCL | NO | NO | Exist
2023-06-12 | 2024-02-14 | SAPURA OMV | SK | JERUN | JERUN-A5 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 2095 | 1915 | N/A | N/A | N/A | N/A | 19028093 | 28.12 | NO | N/A | DRY TREE | 2023-07-16 | 2023-07-16 15:00 | 2023-12-04 18:00 | 2023.75 | SHALLOW WATER | 2160 | 1981.35 | N/A | N/A | N/A | N/A | 16461048.85 | 23.63 | 3.97 | 3.79 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.34 |  | 1080 |  | 2458 | [10 empty] | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1100 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-06-12 | 2024-01-11 | SAPURA OMV | SK | JERUN | JERUN-A3 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 2265 | 2117 | N/A | N/A | N/A | N/A | 26800426 | 38.88 | NO | N/A | DRY TREE | 2023-07-16 | 2023-07-16 | 2023-10-30 | 2025.4 | SHALLOW WATER | 2308 | 2161.65 | N/A | N/A | N/A | N/A | 21805124.26 | 35.75 | 3.93 | 3.93 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.97 |  | 1639.7 |  | 2814.4 | [10 empty] | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1745 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-06-12 | 2023-12-27 | SAPURA OMV | SK | JERUN | JERUN-A2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 2154 | 2007 | N/A | N/A | N/A | N/A | 19230219 | 28.33 | NO | N/A | DRY TREE | 2023-07-19 | 2023-07-19 | 2023-11-15 | 1904.62 | SHALLOW WATER | 2186 | 2040.87 | N/A | N/A | N/A | N/A | 13980658.64 | 20.26 | 5.96 | 5.55 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.03 |  | 1446 |  | 2548 | [10 empty] | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1276 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-06-12 | 2024-01-11 | SAPURA OMV | SK | JERUN | JERUN-A4 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 1995 | 1828 | N/A | N/A | N/A | N/A | 18740394 | 27.66 | NO | N/A | DRY TREE | 2023-07-19 | 2023-07-19 | 2023-09-29 12:00 | 1884.75 | SHALLOW WATER | 2021 | 1851.22 | N/A | N/A | N/A | N/A | 17916016 | 28.13 | 6.11 | 6.11 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.58 |  | 1409 |  | 2663 | [10 empty] | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 948 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-06-12 | N/A | SAPURA OMV | SK | JERUN | JERUN-A6 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 2267 | 2069 | N/A | N/A | N/A | N/A | 19352890 | 35.06 | NO | N/A | DRY TREE | 2023-07-15 | 2023-07-15 | 2024-01-04 | 2089.75 | SHALLOW WATER | 2226 | 1997.74 | N/A | N/A | N/A | N/A | 19692697 | 35 | 9.91 | 0 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.6 |  | 1521 |  | 2517 | [6 empty] | 10.4 | 8895670 | 1.42 | 1218 | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 735 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-05-25 | N/A | PCSB | SK | PANGKIN | PANGKIN-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 119 | 2500 | 1921 | 24520000 | 48289166.5 | 61.85 | 116.14 | N/A | N/A | SIDETRACK | N/A | N/A | 2023-05-30 07:15 | 2023-05-26 13:15 | 2023-09-15 10:30 | 2393 | SHALLOW WATER | 2540 | 1953 | N/A | 41478839 | N/A | 111.85 | N/A | N/A | 10.65 | 10.59 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 3.93 |  | 1644 |  | 3188 | [27 empty] | Exist
2023-05-22 | 2023-11-15 | HESS | PM | BUNGA DAHLIA | BUNGA DAHLIA A-3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 66.11 | 3106.98 | 1939.96 | N/A | N/A | N/A | N/A | 14140000 | 30.45 | NO | N/A | DRY TREE | 2023-07-10 | 2023-07-10 16:00 | 2023-09-20 03:00 | 3037.03 | SHALLOW WATER | 3145.99 | 1938.6 | N/A | N/A | N/A | N/A | 13230000 | 25.35 | 0.2 | 0 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.45 |  | 681 |  | 1278 | [6 empty] | 7.66 | 4161462 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 228.48 | True |  | L80 13CR | 9.2 | KCL | NO | NO | Exist
2023-05-21 | 2023-11-08 | HESS | PM | BUNGA DAHLIA | BUNGA DAHLIA A-2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 66.11 | 3623.29 | 1873.21 | N/A | N/A | N/A | N/A | 16120000 | 37.04 | NO | N/A | DRY TREE | 2023-07-07 | 2023-07-07 08:00 | 2023-09-19 17:00 | 3559.13 | SHALLOW WATER | 3668.09 | 1885.99 | N/A | N/A | N/A | N/A | 13720000 | 28.94 | 1.37 | 1.22 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.54 |  | 674 |  | 1132 | [6 empty] | 9.23 | 4194726 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 505.22 | True |  | L80 13CR | 9.4 | NACL | NO | NO | Exist
2023-05-21 | N/A | HESS | PM | BUNGA DAHLIA | BUNGA DAHLIA A-1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 66.11 | 2918.93 | 1921.67 | N/A | N/A | N/A | N/A | 13870000 | 31.64 | NO | N/A | DRY TREE | 2023-07-04 | 2023-07-04 | 2023-09-19 08:00 | 2813.93 | SHALLOW WATER | 2922.89 | 1929.6 | N/A | N/A | N/A | N/A | 11350000 | 22.65 | 1.38 | 1.2 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.78 |  | 789 |  | 1175 | [6 empty] | 6.21 | 2907475 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 212.3 | True |  | L80 13CR | 9 | KCL | NO | NO | Exist
2023-05-16 | N/A | SHELL | SK | F14 | F14-109 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 105.15 | 3405.06 | 1371.23 | N/A | N/A | N/A | N/A | 44600000 | 67.19 | NO | N/A | N/A | 2023-07-14 12:45 | 2023-07-14 12:45 | 2023-08-10 16:30 | 3195.06 | SHALLOW WATER | 3334.96 | 1357.82 | N/A | N/A | N/A | N/A | 53800000 | 96.71 | 26.53 | 24.9 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | No |  | No |  | No | [27 empty] | Exist
2023-05-12 | 2023-11-27 | SAPURA OMV | SK | JERUN | JERUN-A1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 87.2 | 1674 | 1666 | N/A | N/A | N/A | N/A | 17852159 | 26.09 | NO | N/A | DRY TREE | 2023-07-14 | 2023-05-28 | 2023-09-06 | 1553.75 | SHALLOW WATER | 1690 | 1682.55 | N/A | N/A | N/A | N/A | 16689024.45 | 34 | 8.15 | 7.97 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.9 |  | 1790 |  | 2738 | [10 empty] | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 915 | True | NONE | SUPER 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2023-04-11 | 2024-03-01 | PTTEP | SK | BANGSAWAN | BANGSAWAN-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 46 | 2701 | 2701 | 10120000 | 19000000 | 24.53 | 43.8 | N/A | N/A | NO | N/A | N/A | 2023-05-31 19:30 | 2023-05-18 05:00 | 2023-07-13 20:00 | 2622.5 | SHALLOW WATER | 2701 | 2632.76 | N/A | 22210000 | N/A | 56.8 | N/A | N/A | 32.54 | 32.54 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.84 |  | 1284.14 |  | 2495.04 | [27 empty] | Exist
2023-04-06 | 2024-01-22 | PTTEP | SB | HIKMAT | HIKMAT-1 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 1159.82 | 2661.4 | 2306 | 17000000 | 22580000 | 16.5 | 21.8 | N/A | N/A | NO | N/A | N/A | 2023-05-02 | 2023-04-23 11:25 | 2023-06-14 12:00 | 1404.18 | DEEP WATER | 2590 | 2264.73 | N/A | 23170000 | N/A | 29 | N/A | N/A | 0.01 | 0 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 2.57 |  | 2588 |  | 5026 | [27 empty] | Exist
2023-04-05 | 2023-11-08 | ENQUEST | PM | KERANJI | KERANJI-1 | EXPLORATION/APPRAISAL | BORR IDUN | JACK UP | 76.8 | 2500 | 2181 | 7440000 | 7440000 | 22.1 | 25.5 | N/A | N/A | NO | N/A | N/A | 2023-08-27 20:30 | 2023-08-23 20:00 | 2023-09-10 14:40 | 2393.2 | SHALLOW WATER | 2500 | 2211 | N/A | 5051413.06 | N/A | 17.78 | N/A | N/A | 5.98 | 5.98 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1 |  | 340 |  | 466 | [27 empty] | Exist
2023-04-05 | 2024-01-22 | PTTEP | SB | DERMAWAN | DERMAWAN-1 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 1407.1 | 2326 | 2326 | 13800000 | 15900000 | 13.4 | 15.1 | N/A | N/A | NO | N/A | N/A | 2023-05-04 | 2023-05-04 00:30 | 2023-05-12 10:00 | 892.9 | DEEP WATER | 2326 | 2325.95 | N/A | 20250000 | N/A | 23 | N/A | N/A | 24.1 | 24.1 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 3.82 |  | 4472 |  | 7617 | [27 empty] | Exist
2023-04-03 | 2023-08-15 | PCSB | SK | KALUNG EMAS | KALUNG EMAS-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 66.6 | 1410 | 1410 | 16350000 | 23570000 | 34.91 | 51.43 | N/A | N/A | NO | N/A | N/A | 2023-04-26 | 2023-04-19 06:15 | 2023-06-17 15:00 | 2333.4 | SHALLOW WATER | 2430 | 2430 | N/A | 28859799.57 | N/A | 59.36 | N/A | N/A | 8.4 | 8.4 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.36 |  | 2113 |  | 3019 | [27 empty] | Exist
2023-03-21 | 2023-09-25 | PCSB | SK | BARAM | BARAM-B43 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 61.99 | 1889.67 | 1408.29 | N/A | N/A | N/A | N/A | 12663747.75 | 32.59 | NO | N/A | DRY TREE | 2023-06-08 | 2023-06-08 19:00 | 2023-08-21 | 1801.31 | SHALLOW WATER | 1890.28 | 1407.25 | N/A | N/A | N/A | N/A | 12425238.07 | 34.43 | 14.19 | 13.98 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 2.07 |  | 726 |  | 1598 | [6 empty] | 17.93 | 6221410.13 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 | 1267 | True |  | 9CR | 9.3 | NACL | NO | NO | Exist
2023-03-21 | 2024-09-25 | PCSB | PM | BEKOK | BEKOK DEEP-1RDR1 | EXPLORATION/APPRAISAL | BORR IDUN | JACK UP | 68.5 | 4072 | 3555 | 20963136.65 | 23832210.87 | 39.22 | 45.58 | N/A | N/A | NO | N/A | N/A | 2024-02-15 15:30 | 2024-02-15 15:30 | 2024-07-30 17:30 | 3083.2 | SHALLOW WATER | 3196 | 3195.6 | N/A | 60572716 | N/A | 112.94 | N/A | N/A | 18.05 | 8.24 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.09 |  | 1912 |  | 4053 | [27 empty] | Exist
2023-03-21 | 2023-09-07 | PCSB | SK | BARAM | BARAM-B42 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 61.99 | 1960.99 | 1067.75 | N/A | N/A | N/A | N/A | 13470000 | 32.39 | NO | N/A | DRY TREE | 2023-06-23 | 2023-06-22 21:00 | 2023-08-04 14:15 | 1849.47 | SHALLOW WATER | 1938.43 | 1091.98 | N/A | N/A | N/A | N/A | 12980342.74 | 32.14 | 4.31 | 3.4 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.74 |  | 667 |  | 1668 | [6 empty] | 16.5 | 6915685.45 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 | 729 | True |  | 9CR | 9.3 | NACL | NO | 4 | Exist
2023-03-20 | N/A | PCSB | SK | TADOM | TADOM-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 113.7 | 1389 | 1330 | 17990000 | 24650000 | 39.67 | 56.78 | N/A | N/A | NO | N/A | N/A | 2023-04-08 | 2023-04-04 22:45 | 2023-05-26 01:15 | 1268.3 | SHALLOW WATER | 1410 | 1330.12 | N/A | 12088893.22 | N/A | 26.68 | N/A | N/A | 2.49 | 2.49 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.85 |  | 1392 |  | 2436 | [27 empty] | Exist
2023-03-10 | 2023-07-25 | PTTEP | PM | SIMPOH BELUDU | SIMPOH BELUDU-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 77.8 | 3421 | 2672 | 9930000 | 12270000 | 27.43 | 34.16 | N/A | N/A | NO | N/A | N/A | 2023-03-31 | 2023-03-23 | 2023-04-22 | 3365.3 | SHALLOW WATER | 3478 | 2709 | N/A | 10340000 | N/A | 30.08 | N/A | N/A | 3.42 | 3.42 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.12 |  | 436 |  | 936 | [27 empty] | Exist
2023-03-03 | N/A | SHELL | SK | MEMALI | MEMALI-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 87.6 | 2390.73 | 2390.73 | 13300000 | 15500000 | 34.12 | 42.68 | N/A | N/A | NO | N/A | N/A | 2023-04-25 | 2023-04-21 21:30 | 2023-05-27 18:30 | 2334.84 | SHALLOW WATER | 2453.83 | 2453.25 | N/A | 13725270 | N/A | 35.88 | N/A | N/A | 2.5 | 2.5 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.79 |  | 1236 |  | 1792 | [27 empty] | Exist
2023-02-16 | 2023-06-30 | HML | PM | BUNGA LAVATERA | BUNGA LAVATERA-1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 6000 | 2388.88 | N/A | N/A | N/A | N/A | 18133000 | 42.1 | NO | N/A | DRY TREE | 2023-03-22 | 2023-03-22 09:00 | 2023-04-29 | 5899.27 | SHALLOW WATER | 6000 | 2389.95 | N/A | N/A | N/A | N/A | 15635000 | 37.63 | 0 | 0 | SW DEV C3 |  | 2.2 |  | 915 |  | 1290 |  | 1.44 |  | 505.2 |  | 799.9 | [6 empty] | 7.09 | 5185292 | 0.36 | 263.4 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 116 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2023-02-09 | 2023-04-21 | SHELL | SK | RUKU RUKU | RUKU RUKU-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 88.39 | 2622.07 | 2622.07 | 12900000 | 15120000 | 34.7 | 42.92 | N/A | N/A | NO | N/A | N/A | 2023-03-15 | 2023-03-12 | 2023-04-18 | 2159.71 | SHALLOW WATER | 2279.49 | 2278.88 | N/A | 14725820 | N/A | 40.11 | N/A | N/A | 4.44 | 4.31 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.67 |  | 1458 |  | 2078 | [27 empty] | Exist
2023-02-02 | 2024-01-17 | PTTEP | SK | CHENDA | CHENDA-1 | EXPLORATION/APPRAISAL | NAGA-3 | JACK UP | 14.66 | 771.87 | 771.87 | 12910000 | 20530000 | 29 | 43.48 | N/A | N/A | NO | N/A | N/A | 2023-03-21 09:15 | 2023-03-13 07:00 | 2023-05-18 05:00 | 747.3 | SHALLOW WATER | 771.87 | 771.53 | N/A | 27860000 | N/A | 65.92 | N/A | N/A | 6.84 | 6.84 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2023-01-26 | 2023-05-30 | PCSB | SK | MACHINCANG | MACHINCANG-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 117.9 | 1668 | 1668 | 15960000 | 21060000 | 30.72 | 45.49 | N/A | N/A | NO | N/A | N/A | 2023-02-10 18:00 | 2023-02-04 | 2023-04-04 22:45 | 1522.1 | SHALLOW WATER | 1668 | 1668 | N/A | 23959210.31 | N/A | 59.2 | N/A | N/A | 6.84 | 0.88 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 3.17 |  | 1533 |  | 2282 | [27 empty] | Exist
2023-01-17 | 2023-06-22 | PCSB | SB | LAYANG-LAYANG | LAYANG-LAYANG-1 | EXPLORATION/APPRAISAL | NOBLE VIKING | DRILLSHIP | 2881 | 4030 | 4030 | 57100000 | 63300000 | 58.53 | 65.56 | N/A | N/A | NO | N/A | N/A | 2023-03-02 | 2023-02-03 12:00 | 2023-04-23 12:00 | 1800 | DEEP WATER | 4707 | 4706.96 | N/A | 63543173.17 | N/A | 79 | N/A | N/A | 21.7 | 21.7 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 3.31 |  | 5540 |  | 8752 | [27 empty] | Exist
2023-01-12 | 2023-08-04 | HESS | PM | BUNGA KANGSAR | BUNGA KANGSAR A-1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64.61 | 5035.05 | 2337.4 | N/A | N/A | N/A | N/A | 23949434 | 51.23 | NO | N/A | DRY TREE | 2023-02-09 | 2023-02-09 06:00 | 2023-05-16 08:00 | 5010.39 | SHALLOW WATER | 5120.39 | 2348.27 | N/A | N/A | N/A | N/A | 21240000 | 56.48 | 18.3 | 18.3 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 1.9 |  | 777 |  | 1280 | [6 empty] | 19.25 | 5139987 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 2.0 | SINGLE | L80 13CR | 136.48 | True |  | L80 13CR | 8.5 | KCL | NO | NO | Exist
2023-01-11 | 2023-06-28 | PTTEP | SK | SIRUNG | SIRUNG-2 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 47.5 | 1386 | 1383.02 | 7870000 | 12620000 | 23.3 | 32.7 | N/A | N/A | NO | N/A | N/A | 2023-02-05 | 2023-02-05 09:30 | 2023-03-22 | 1305.65 | SHALLOW WATER | 1386 | 1383.02 | N/A | 20700000 | N/A | 48.33 | N/A | N/A | 36.64 | 36.64 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 5.4 |  | 2069 |  | 3616 | [27 empty] | Exist
2022-12-28 | 2023-03-07 | HML | PM | BUNGA ORKID | BOC-30 (T1) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 3853 | 2971 | N/A | N/A | N/A | N/A | 16652000 | 37 | NO | N/A | DRY TREE | 2022-12-29 | 2022-12-29 04:00 | 2023-02-06 | 3684.48 | SHALLOW WATER | 3784 | 2951.57 | N/A | N/A | N/A | N/A | 15331000 | 39.83 | 4.73 | 0.58 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.4 |  | 575 |  | 1268 | [6 empty] | 12.95 | 5128910 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 6.0 | DUAL | L80 13CR | 321.5223 | False | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2022-12-22 | 2023-04-19 | PCSB | PM | BEKOK | BEKOK-AA14 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.5 | 2415.29 | 1699.27 | N/A | N/A | N/A | N/A | 16641503.11 | 34.12 | SIDETRACK | N/A | DRY TREE | 2023-01-03 | 2023-01-03 08:15 | 2023-03-20 21:30 | 2222.23 | SHALLOW WATER | 2335 | 1733.3 | N/A | N/A | N/A | N/A | 11111030.41 | 24.84 | 3.73 | 3.73 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.22 |  | 509 |  | 1097 | [6 empty] | 4.11 | 2788653.14 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 | 1893.137 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-12-22 | 2023-06-14 | PCSB | SK | MIRDANGA | MIRDANGA-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 46.8 | 2600 | 2600 | 17560000 | 24710000 | 38.37 | 59.92 | N/A | N/A | NO | N/A | N/A | 2023-02-02 15:00 | 2023-01-17 | 2023-04-19 06:15 | 2523.2 | SHALLOW WATER | 2600 | 2599.97 | N/A | 24710000 | N/A | 59.92 | N/A | N/A | 6 | 6 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.35 |  | 1261 |  | 2437 | [27 empty] | Exist
2022-12-19 | 2023-04-19 | PCSB | PM | BEKOK | BEKOK-AA16ST2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.5 | 2250.83 | 1687.26 | N/A | N/A | N/A | N/A | 16379098.15 | 32.92 | NO | N/A | DRY TREE | 2022-12-31 | 2022-12-31 | 2023-02-20 16:00 | 2021.23 | SHALLOW WATER | 2134 | 1695.38 | N/A | N/A | N/A | N/A | 12801492.74 | 32.32 | 13.06 | 13.06 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.27 |  | 531 |  | 1315 | [6 empty] | 5.71 | 2954697.99 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1150.9748 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-12-16 | N/A | SHELL | SK | TIMI | TIMI-101 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 142.94 | 1879 | 1729.05 | N/A | N/A | N/A | N/A | 42240000 | 57.2 | NO | N/A | N/A | 2023-01-19 | 2022-12-30 | 2023-05-19 | 1749.1 | SHALLOW WATER | 1926.24 | 1770.19 | N/A | N/A | N/A | N/A | 40940000 | 76.71 | 21.88 | 5.38 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 7.54 |  | 2864 |  | 5395 | [27 empty] | Exist
2022-12-16 | N/A | SHELL | SK | TIMI | TIMI-103 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 142.94 | 1967.08 | 1728.74 | N/A | N/A | N/A | N/A | 42900000 | 60.4 | NO | N/A | N/A | 2023-01-21 | 2022-12-30 | 2023-05-11 | 1796.34 | SHALLOW WATER | 1973.48 | 1726.91 | N/A | N/A | N/A | N/A | 34470000 | 65.7 | 27.13 | 25.07 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.85 |  | 2111 |  | 5297 | [27 empty] | Exist
2022-12-03 | 2023-05-10 | PCSB | PM | BEKOK | BEKOK-AA13 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.25 | 3438.04 | 2129.27 | N/A | N/A | N/A | N/A | 24377709.49 | 50.72 | SIDETRACK | N/A | DRY TREE | 2022-12-05 | 2022-12-05 02:30 | 2023-03-08 08:00 | 3206.48 | SHALLOW WATER | 3319 | 2820 | N/A | N/A | N/A | N/A | 18021298.63 | 48.63 | 15.64 | 6.41 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.88 |  | 844 |  | 1522 | [6 empty] | 8.8 | 4237888.07 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1491.2145 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-12-01 | 2023-03-21 | PCSB | SK | SINSING | SINSING-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 117.8 | 2018 | 2018 | 20730000 | 27970000 | 44.79 | 59.81 | N/A | N/A | NO | N/A | N/A | 2022-12-09 | 2022-12-05 13:00 | 2023-02-04 18:00 | 1872.2 | SHALLOW WATER | 2018 | 2018 | N/A | 28331415.82 | N/A | 61.21 | N/A | N/A | 9.48 | 2.59 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.2 |  | 1875 |  | 3063 | [27 empty] | Exist
2022-11-21 | N/A | SHELL | SK | KECUPU | KECUPU-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 84.61 | 2749.16 | 2426.39 | 13300000 | 15530000 | 35.81 | 39.22 | N/A | N/A | NO | N/A | N/A | 2023-01-15 | 2023-01-12 03:45 | 2023-03-02 | 2070.83 | SHALLOW WATER | 2186.83 | 2041.08 | 18154630 | N/A | 59.63 | N/A | N/A | N/A | 47.2 | 33.9 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.86 |  | 1192 |  | 1879 | [27 empty] | Exist
2022-11-14 | 2023-02-20 | PTTEP | SK | MONG MERAH | MONG MERAH-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 25.3 | 1980 | 1980 | 6320000 | 11490000 | 19.33 | 29.11 | N/A | N/A | NO | N/A | N/A | 2022-12-31 | 2022-12-28 12:00 | 2023-02-02 16:00 | 1924.8 | SHALLOW WATER | 1985 | 1985 | N/A | 13590000 | N/A | 36.5 | N/A | N/A | 1.38 | 1.32 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | No |  | No |  | No | [27 empty] | Exist
2022-11-08 | 2023-04-18 | HESS | PM | BUNGA TERATAI | BUNGA KANGSAR A-3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64.61 | 3304.79 | 2347.15 | N/A | N/A | N/A | N/A | 17430000 | 33.55 | NO | N/A | DRY TREE | 2022-12-27 | 2022-12-27 | 2023-01-27 23:30 | 3206.34 | SHALLOW WATER | 3316.34 | 2360.62 | N/A | N/A | N/A | N/A | 15070000 | 34.25 | 7.59 | 7.59 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1600 |  | 2.27 |  | 1044 |  | 1411 | [6 empty] | 7.57 | 3443463 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 137 | True |  | L80 13CR | 12.6 | OTHER | NO | NO | Exist
2022-11-08 | 2023-02-15 | PTTEP | SB | KIKEH | PX12 (150) | APPRAISAL CUM DEV/DEVELOPMENT | NOBLE VIKING | DRILLSHIP | 1345.4 | 4087 | 2817 | N/A | N/A | N/A | N/A | 53070000 | 48.94 | NO | N/A | WET TREE | 2022-12-04 | 2022-12-04 | 2023-02-03 12:00 | 2099.6 | DEEP WATER | 3471 | 2765.79 | N/A | N/A | N/A | N/A | 64550000 | 61.5 | 7.42 | 7.11 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 3.98 |  | 3275 |  | 8301 | [6 empty] | 19.8 | 11988029.76 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1124.694 | True |  | L80 13CR | 10.4 | NACL/NABR | 3 | NO | Exist
2022-11-08 | 2023-07-31 | HESS | PM | BUNGA TERATAI | BUNGA KANGSAR A-2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64.61 | 2622.07 | 2349.89 | N/A | N/A | N/A | N/A | 16480000 | 31.02 | NO | N/A | DRY TREE | 2023-02-03 | 2023-01-30 06:00 | 2023-06-04 21:00 | 2522.74 | SHALLOW WATER | 2632.73 | 2361.96 | N/A | N/A | N/A | N/A | 16100000 | 37.31 | 22.8 | 13.1 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1600 |  | 3.33 |  | 1446 |  | 1910 | [6 empty] | 5.16 | 2937212 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 173 | True |  | L80 13CR | 12.6 | OTHER | NO | NO | Exist
2022-11-04 | 2023-03-15 | PCSB | SK | GEDOMBAK | GEDOMBAK-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 53.81 | 2700 | 2700 | 19310000 | 26240000 | 40.56 | 55.47 | N/A | N/A | NO | N/A | N/A | 2022-12-02 | 2022-11-24 20:30 | 2023-02-02 15:00 | 2713.77 | SHALLOW WATER | 2800 | 2799.98 | N/A | 26994203.61 | N/A | 69.69 | N/A | N/A | 15.93 | 7.13 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.13 |  | 1055 |  | 2377 | [27 empty] | Exist
2022-10-14 | 2023-02-20 | HESS | PM | BUNGA TERATAI | BUNGA KANGSAR A-4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 64.61 | 3049.98 | 1783.3 | N/A | N/A | N/A | N/A | 15500000 | 31.67 | NO | N/A | DRY TREE | 2022-11-14 | 2022-11-14 07:00 | 2022-12-26 14:00 | 2886.04 | SHALLOW WATER | 2996.04 | 1743.81 | N/A | N/A | N/A | N/A | 17395000 | 40.54 | 16.3 | 10.6 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.25 |  | 1129 |  | 1773 | [6 empty] | 15.36 | 4349000 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 280 | True |  | L80 13CR | 8.5 | KCL | NO | NO | Exist
2022-10-07 | 2023-06-12 | PCSB | PM | BEKOK | BEKOK-AA18 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.5 | 3567.8 | 1659.2 | N/A | N/A | N/A | N/A | 16305502.98 | 31.84 | NO | N/A | DRY TREE | 2022-10-10 | 2022-10-10 03:00 | 2022-12-05 02:30 | 3637.23 | SHALLOW WATER | 3750 | 1660.91 | N/A | N/A | N/A | N/A | 13252526.62 | 32.83 | 8.19 | 6.82 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.2 |  | 536 |  | 896 | [6 empty] | 5.29 | 3211278.75 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2014.534 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-10-06 | 2023-02-15 | PCSB | SK | SELUANG | SELUANG-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 99 | 1908 | 1908 | 17180000 | 18220000 | 35.21 | 37.52 | N/A | N/A | NO | N/A | N/A | 2022-11-06 | 2022-11-04 | 2022-12-02 13:45 | 1781 | SHALLOW WATER | 1908 | 1907.83 | N/A | 17308817 | N/A | 27.98 | N/A | N/A | 1.67 | 0.71 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.67 |  | 1533 |  | 2053 | [27 empty] | Exist
2022-10-06 | 2023-02-15 | PCSB | SK | SELUANG | SELUANG-1RDR1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 99 | 1908 | 1908 | 17180000 | 18220000 | 35.21 | 37.52 | N/A | N/A | NO | N/A | N/A | 2022-11-06 | 2022-11-04 | 2022-12-02 13:45 | 1781 | SHALLOW WATER | 1908 | 1907.83 | N/A | 17308816.94 | N/A | 27.98 | N/A | N/A | 3.17 | 3.17 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.67 |  | 1533 |  | 2053 | [27 empty] | Exist
2022-09-30 | 2023-05-05 | PTTEP | SK | PERMAS | PRPA-13 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 48.8 | 3306 | 1872 | N/A | N/A | N/A | N/A | 8825883.78 | 23.57 | NO | N/A | DRY TREE | 2022-11-13 | 2022-11-06 18:00 | 2022-12-28 12:00 | 3289.8 | SHALLOW WATER | 3385 | 1837.33 | N/A | N/A | N/A | N/A | 15177611.76 | 51.75 | 29.93 | 9.28 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.2 |  | 672 |  | 987 | [6 empty] | 4 | 1577052 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 36 | True |  | L80 13CR | 10 | NACL/NABR | NO | NO | Exist
2022-09-07 | 2023-05-05 | PTTEP | PM | KECAPI | KECAPI-1 | EXPLORATION/APPRAISAL | NAGA-5 | JACK UP | 26.4 | 1580 | 1580 | 5640000 | 8010000 | 18.17 | 26.48 | N/A | N/A | RE-SPUD | N/A | N/A | 2022-10-03 | 2022-09-27 19:30 | 2022-10-24 17:15 | 1523.6 | SHALLOW WATER | 1582 | 1581.6 | 8360000 | N/A | 26.91 | N/A | N/A | N/A | 21.4 | 4.43 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.7 |  | 383 |  | 1673 | [27 empty] | Exist
2022-09-02 | N/A | SHELL | SK | CENMUMUR | CENMUMUR-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 84.7 | 2629.69 | 2629.69 | 13390000 | 15560000 | 32.47 | 39.76 | N/A | N/A | NO | N/A | N/A | 2023-11-10 | 2023-11-07 | 2023-12-01 | 2025.33 | SHALLOW WATER | 2141.42 | 2141.23 | N/A | 21361560 | N/A | 67.11 | N/A | N/A | 54.4 | 3.02 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.69 |  | 1226 |  | 3215 | [27 empty] | Exist
2022-09-01 | 2023-01-18 | PCSB | SK | NAHARA | NAHARA-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 53 | 2600 | 2430 | 17810000 | 22621900.59 | 47.68 | 66.25 | N/A | N/A | NO | N/A | N/A | 2022-09-16 | 2022-09-15 10:00 | 2022-11-24 22:30 | 2593.6 | SHALLOW WATER | 2676.6 | 2498.87 | N/A | 32201093.26 | N/A | 84.51 | N/A | N/A | 9.02 | 7.72 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.65 |  | 1457 |  | 2635 | [27 empty] | Exist
2022-08-23 | 2022-12-15 | HML | PM | BUNGA RAYA | BRB-11ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 52.12 | 2925 | 2050 | N/A | N/A | N/A | N/A | 17540000 | 47.2 | SIDETRACK | N/A | DRY TREE | 2022-09-14 | 2022-08-30 03:00 | 2022-10-19 04:00 | 2837.48 | SHALLOW WATER | 2914 | 2043 | N/A | N/A | N/A | N/A | 16284000 | 50.1 | 7 | 7 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.6 |  | 500 |  | 1400 | [6 empty] | 5.1 | 2100939 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1423.8845 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2022-08-18 | 2023-04-12 | ENQUEST | PM | SELIGI | SED-03 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 74 | 3316 | 1605 | N/A | N/A | N/A | N/A | 10880000 | 30.32 | SIDETRACK | N/A | DRY TREE | 2022-09-18 11:30 | 2022-08-25 11:00 | 2022-11-15 12:00 | 2524.7 | SHALLOW WATER | 2634 | 1921 | N/A | N/A | N/A | N/A | 21747476 | 73.67 | 24.66 | 24.55 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.25 |  | 664.28 |  | 969.19 | [6 empty] | 8 | 2931260 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 4593.4 | True | AICD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-08-17 | 2023-04-20 | ENQUEST | PM | SELIGI | SED-22ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 74 | 3331 | 1605 | N/A | N/A | N/A | N/A | 12370000 | 38.04 | SIDETRACK | N/A | DRY TREE | 2022-11-17 04:30 | 2022-09-08 05:00 | 2022-12-10 16:15 | 3290.7 | SHALLOW WATER | 3400 | 1599.95 | N/A | N/A | N/A | N/A | 10672000 | 33.55 | 2.51 | 2.05 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.69 |  | 443.3 |  | 1072.91 | [6 empty] | 8.31 | 3460047 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 3431.926 | True | AICD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-08-05 | 2022-12-05 | HESS | PM | BERGADING DEEP | BERGADING DEEP-4 | EXPLORATION/APPRAISAL | BORR SAGA | JACK UP | 55.9 | 2869.25 | 2812.86 | 25670000 | 25670000 | 55.43 | 55.4 | N/A | N/A | NO | N/A | N/A | 2022-08-27 | 2022-08-23 16:30 | 2022-10-07 20:00 | 2774.37 | SHALLOW WATER | 2862.24 | 2802.8 | N/A | 23280000 | N/A | 45.15 | N/A | N/A | 1.75 | 1.75 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 2.4 |  | 1414 |  | 2439 | [27 empty] | Exist
2022-07-14 | N/A | SHELL | SK | TEMU | TEMU-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 82.51 | 2369.09 | 2337.7 | 12430000 | 23980000 | 30.14 | 65.13 | N/A | N/A | SIDETRACK | N/A | N/A | 2022-08-26 | 2022-08-23 12:00 | 2022-11-06 | 2738.89 | SHALLOW WATER | 2852.79 | 2684.55 | N/A | 23005000 | N/A | 74.32 | N/A | N/A | 24 | 11 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.32 |  | 1139 |  | 1828 | [27 empty] | Exist
2022-07-10 | 2023-02-21 | PCSB | PM | BEKOK | BEKOK-AA17 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 68.5 | 1654.27 | 1609.07 | N/A | N/A | N/A | N/A | 16397789.44 | 33.56 | SIDETRACK | N/A | DRY TREE | 2022-10-14 | 2022-08-10 | 2022-11-30 05:00 | 2944.23 | SHALLOW WATER | 3057 | 2448.7 | N/A | N/A | N/A | N/A | 14275578.1 | 29.75 | 7.28 | 7.28 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.51 |  | 625 |  | 1020 | [6 empty] | 4.04 | 2828464.79 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 3258.033 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-06-23 | 2022-12-02 | PCSB | PM | BEKOK | BEKOK-BB20 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 72 | 2237.43 | 1688.02 | N/A | N/A | N/A | N/A | 14374049.12 | 29.37 | SIDETRACK | N/A | DRY TREE | 2022-07-09 | 2022-07-09 11:00 | 2022-09-24 | 2141.71 | SHALLOW WATER | 2254 | 1692.28 | N/A | N/A | N/A | N/A | 13993294.8 | 28.31 | 6.11 | 6.11 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.81 |  | 967 |  | 1730 | [6 empty] | 3.25 | 3026486.27 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 715.5861 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-06-23 | 2022-11-17 | PCSB | PM | BEKOK | BEKOK-BB18ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 72 | 4284.74 | 2145.3 | N/A | N/A | N/A | N/A | 19142403.97 | 42.31 | NO | N/A | DRY TREE | 2022-07-04 | 2022-07-04 06:30 | 2022-09-28 15:00 | 4227.71 | SHALLOW WATER | 4340 | 2149.82 | N/A | N/A | N/A | N/A | 18911558.48 | 40.42 | 0.41 | 0.41 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.64 |  | 778 |  | 1200 | [6 empty] | 4.17 | 3246689.93 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2109.3549 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-06-19 | 2022-10-14 | HESS | PM | BERGADING | BERGADING-D5 (D_1_10) | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 54.31 | 3853.31 | 1196.27 | N/A | N/A | N/A | N/A | 16900000 | 48.4 | NO | N/A | DRY TREE | 2022-07-05 | 2022-07-05 | 2022-08-23 | 3750.96 | SHALLOW WATER | 3850.96 | 1182.03 | N/A | N/A | N/A | N/A | 22800000 | 54.7 | 2.5 | 2.5 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.4 |  | 922 |  | 1558 | [6 empty] | 8 | 5360000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 785.43 | True |  | L80 13CR | 9 | NACL/NABR | NO | NO | Exist
2022-06-16 | 2023-09-06 | PCSB | SK | BAYAN | BAYAN-C315 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 29.69 | 3307.53 | 1758.76 | N/A | N/A | N/A | N/A | 9293795.11 | 23.64 | NO | N/A | DRY TREE | 2022-06-24 | 2022-06-24 | 2022-10-06 | 3279.85 | SHALLOW WATER | 3346.54 | 1775.59 | N/A | N/A | N/A | N/A | 9067244.4 | 29.73 | 3.33 | 2.94 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.77 |  | 523 |  | 826 | [6 empty] | 9.9 | 2038102.74 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR |  | False | NONE | 13CR | 9.1 | NACL | NO | NO | Exist
2022-05-30 | N/A | PTTEP | SK | WEST PATRICIA | WPPB-14 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.2 | 1198.34 | 1082.48 | N/A | N/A | N/A | N/A | 5866029 | 8.48 | SIDETRACK | N/A | N/A | 2022-06-22 07:15 | 2022-06-21 10:00 | 2022-10-30 | 916.2 | SHALLOW WATER | 1008 | 921.1 | N/A | N/A | N/A | N/A | 9160500.84 | 24.29 | 60.77 | 60.77 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | No |  | No |  | No | [27 empty] | Exist
2022-05-30 | 2023-02-07 | PTTEP | SK | WEST PATRICIA | WPPB-15/15ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.2 | 1758.9 | 1067.9 | N/A | N/A | N/A | N/A | 7999172 | 17.42 | NO | N/A | DRY TREE | 2022-06-17 | 2022-06-17 | 2022-10-10 | 1715 | SHALLOW WATER | 1806 | 1063 | N/A | N/A | N/A | N/A | 15595473.73 | 37.21 | 7.28 | 7.28 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.66 |  | 1057.7 |  | 1240.4 | [6 empty] | 3.8 | 2375925 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 33 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-05-30 | N/A | PTTEP | SK | WEST PATRICIA | WPPB-16 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.2 | 1118.73 | 969.53 | N/A | N/A | N/A | N/A | 5975561 | 11.07 | NO | N/A | DRY TREE | 2022-06-28 04:45 | 2022-06-20 03:00 | 2022-10-02 12:00 | 1026.4 | SHALLOW WATER | 1118.2 | 974 | N/A | N/A | N/A | N/A | 6579229.43 | 12.85 | 0.32 | 0.32 | SW DEV SLIM HOLE (With Offline Capability Rig) |  | 1.1 |  | 420 |  | 680 |  | 2.82 |  | 1302.9 |  | 1793.61 | [6 empty] | 2.7 | 1926225 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 34 | True |  | L80 13CR | 8.6 | NACL/NABR | NO | NO | Exist
2022-05-23 | 2023-09-06 | PCSB | SK | BAYAN | BAYAN-C314 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 29.69 | 2785.74 | 1549.68 | N/A | N/A | N/A | N/A | 9584033.81 | 27.49 | NO | N/A | DRY TREE | 2022-06-19 | 2022-06-19 21:00 | 2022-08-16 | 2575.8 | SHALLOW WATER | 2642.49 | 1560.8 | N/A | N/A | N/A | N/A | 9589563.9 | 28.17 | 7.1 | 7.03 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.97 |  | 556 |  | 1106 | [6 empty] | 6.29 | 2206609 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | 2 ZONES | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 1162 | False | AICD | 13CR | 9.6 | NACL | NO | 3 | Exist
2022-05-23 | 2022-08-12 | PCSB | PM | DULANG | DULANG-B31ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 1735 | 1388 | N/A | N/A | N/A | N/A | 10232618.13 | 35.88 | NO | N/A | DRY TREE | 2022-06-04 | 2022-05-31 | 2022-06-24 16:30 | 1621.22 | SHALLOW WATER | 1735 | 1385.27 | N/A | N/A | N/A | N/A | 8166095.63 | 24.69 | 11.81 | 11.81 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.37 |  | 778 |  | 2067 | [6 empty] | 5.13 | 3032320 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 3.0 | SINGLE | 22CR | 178.9 | False | ICD | 25CR | 8.5 | KCL | NO | NO | Exist
2022-05-23 | 2023-09-06 | PCSB | SK | BAYAN | BAYAN-C313ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 29.69 | 2737.88 | 1554.86 | N/A | N/A | N/A | N/A | 9677784 | 25.85 | NO | N/A | DRY TREE | 2022-07-21 | 2022-07-20 04:00 | 2022-09-26 06:00 | 2671.2 | SHALLOW WATER | 2737.88 | 1554.86 | N/A | N/A | N/A | N/A | 12200559.79 | 36.44 | 1.89 | 1.89 | No DMS category. Having value but not sure refering which version | [7 empty] | 2.34 |  | 695 |  | 1102 | [6 empty] | 8.21 | 3007672.39 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | 2 ZONES | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 384 | False | AICD | 13CR | 9.3 | NACL | NO | 3 | Exist
2022-05-20 | 2023-03-05 | HML | PM | BUNGA ORKID | BOC-29 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 7473 | 1977.2 | N/A | N/A | N/A | N/A | 28840000 | 62.27 | SIDETRACK | N/A | DRY TREE | 2022-06-18 | 2022-06-17 21:00 | 2023-03-03 18:00 | 13275.48 | SHALLOW WATER | 6963 | 1974.3 | N/A | N/A | N/A | N/A | 45390000 | 142.54 | 9.75 | 9.75 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 3.52 |  | 1152.83 |  | 1539.42 | [6 empty] | 36.37 | 10099319.78 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1919 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2022-05-16 | 2022-10-14 | COP | SK | BENUM | BENUM-2 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 89 | 1432 | 1432 | 11283000 | 13230000 | 24.4 | 32.3 | N/A | N/A | SIDETRACK | N/A | N/A | 2022-08-15 | 2022-08-10 21:00 | 2022-09-16 18:30 | 1311.15 | SHALLOW WATER | 1435 | 1435 | N/A | 15590000 | N/A | 36.9 | N/A | N/A | 1.9 | 1.9 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.3 |  | 523 |  | 1663 | [27 empty] | Exist
2022-04-27 | N/A | PCSB | SK | BAYAN | BY-311 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 29.69 | 1774.76 | 1607.13 | N/A | N/A | N/A | N/A | 6445825 | 15.52 | NO | N/A | DRY TREE | 2022-06-01 | 2022-05-31 19:00 | 2022-09-11 06:00 | 1713.26 | SHALLOW WATER | 1779.95 | 1606.89 | N/A | N/A | N/A | N/A | 5939645.1 | 16.82 | 1.5 | 1.5 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.59 |  | 476 |  | 1104 | [6 empty] | 6.24 | 2184927.92 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR |  | False | NONE | 13CR | 9.7 | NACL | NO | NO | Exist
2022-04-27 | N/A | PCSB | SK | BAYAN | BY-312 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 29.69 | 1837.55 | 1642.79 | N/A | N/A | N/A | N/A | 6291239.17 | 15.09 | NO | N/A | DRY TREE | 2022-05-27 | 2022-05-26 20:30 | 2022-09-04 | 1717.83 | SHALLOW WATER | 1784.52 | 1604.33 | N/A | N/A | N/A | N/A | 7338865.03 | 19.08 | 2.51 | 2.18 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.74 |  | 627 |  | 1253 | [6 empty] | 7.34 | 2250810 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR |  | False | NONE | 13CR | 9.6 | NACL | NO | NO | Exist
2022-04-24 | 2022-08-27 | COP | SK | SALAM | SALAM-3 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 92.7 | 1553 | 1553 | 10183000 | 10183000 | 22 | 22 | N/A | N/A | NO | N/A | N/A | 2022-07-23 | 2022-07-17 07:15 | 2022-08-10 21:00 | 1442.45 | SHALLOW WATER | 1570 | 1471 | N/A | 13350000 | N/A | 24.57 | N/A | N/A | 11.57 | 0.34 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.33 |  | 722 |  | 1842 | [27 empty] | Exist
2022-04-19 | 2022-08-15 | HESS | PM | BERGADING DEEP | BERGADING-B4(J2) | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 56.99 | 3469.98 | 2615.67 | N/A | N/A | N/A | N/A | 23730000 | 44.96 | NO | N/A | DRY TREE | 2022-05-13 | 2022-05-13 | 2022-06-22 18:00 | 3375.37 | SHALLOW WATER | 3476.99 | 2619.87 | N/A | N/A | N/A | N/A | 21450000 | 38.92 | 2.78 | 2.78 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.2 |  | 1132 |  | 1803 | [6 empty] | 10.4 | 5966608 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 17CR | 48 | True |  | 718 | 8.4 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-04-14 | N/A | SHELL | SK | BEBOLI | BEBOLI-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 89.7 | 2992.38 | 2960.99 | 13280000 | 15610000 | 31.64 | 39.65 | N/A | N/A | NO | N/A | N/A | 2022-07-07 | 2022-07-02 12:00 | 2022-08-23 | 2334.56 | SHALLOW WATER | 2455.65 | 2447.42 | 17670000 | N/A | 52.22 | N/A | N/A | N/A | 28.53 | 28.21 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.56 |  | 1578 |  | 2307 | [27 empty] | Exist
2022-04-13 | 2023-04-10 | ENQUEST | PM | SELIGI | SEC-33ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SK PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 72 | 3540.3 | 1860.3 | N/A | N/A | N/A | N/A | 10343034 | 32.82 | SIDETRACK | N/A | DRY TREE | 2022-06-14 11:00 | 2022-06-12 06:00 | 2022-07-23 18:00 | 3211.7 | SHALLOW WATER | 3319 | 1600.8 | N/A | N/A | N/A | N/A | 12170165 | 41.65 | 4.78 | 4.23 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.84 |  | 483.01 |  | 674.29 | [6 empty] | 7.4 | 2982698 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 3937.2 | True | AICD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-04-06 | 2022-08-03 | COP | SK | GAGAU | GAGAU-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 90.7 | 1532 | 1532 | 10115000 | 13330000 | 21.1 | 29.8 | N/A | N/A | NO | N/A | N/A | 2022-06-27 | 2022-06-21 06:00 | 2022-07-17 07:15 | 1409.3 | SHALLOW WATER | 1535 | 1535 | 12016000 | N/A | 26.05 | N/A | N/A | N/A | 18.2 | 0.2 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.44 |  | 627 |  | 1551 | [27 empty] | Exist
2022-04-04 | 2022-11-28 | PTTEP | SK | SERAMPANG | SEPA-10ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 47.5 | 2627.9 | 2083.1 | N/A | N/A | N/A | N/A | 4291054.24 | 10.52 | SIDETRACK | N/A | N/A | 2022-04-19 | 2022-04-05 12:30 | 2022-09-03 06:00 | 2535.4 | SHALLOW WATER | 2625 | 2032.61 | N/A | N/A | N/A | N/A | 6604189.38 | 12.85 | 5.59 | 5.59 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1000 |  | 1.6 |  | 722.14 |  | 1272.4 | [27 empty] | Exist
2022-03-26 | 2022-08-01 | PCSB | PM | DULANG | DULANG-B30ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 2101.4 | 1362.3 | N/A | N/A | N/A | N/A | 12917149.59 | 33.69 | NO | N/A | DRY TREE | 2022-04-19 | 2022-04-19 | 2022-05-31 | 1932.22 | SHALLOW WATER | 2046 | 1348.63 | N/A | N/A | N/A | N/A | 12846719.68 | 42 | 11.68 | 11.68 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 2.57 |  | 1069 |  | 2572 | [6 empty] | 16.76 | 5585216 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 708.7 | True | NONE | 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2022-03-18 | 2022-10-06 | PCSB | PM | DULANG | DULANG-B25ST2 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 2120 | 1253.08 | N/A | N/A | N/A | N/A | 7173603.36 | 19.6 | SIDETRACK | N/A | N/A | N/A | 2022-04-10 | 2022-08-11 | 2052.28 | SHALLOW WATER | 2166.08 | 1252.73 | N/A | N/A | N/A | N/A | 15275854.19 | 55.83 | 36.19 | 33.94 | No DMS category. Having value but not sure refering which version | [7 empty] | 4.31 |  | 1070 |  | 1562 | [27 empty] | Exist
2022-03-04 | 2022-10-18 | PCSB | PM | BEKOK | BEKOK-BB17 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 72 | 3279.29 | 2148.29 | N/A | N/A | N/A | N/A | 18764917.13 | 36.7 | SIDETRACK | N/A | DRY TREE | 2022-06-19 | 2022-03-19 | 2022-08-20 03:30 | 3170.71 | SHALLOW WATER | 3283 | 2294 | N/A | N/A | N/A | N/A | 30844898.72 | 69.33 | 13.09 | 13.01 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 2.72 |  | 1123.12 |  | 2275.17 | [6 empty] | 4.89 | 3436569.73 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 3005.396 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-03-04 | 2022-12-02 | PCSB | PM | BEKOK | BEKOK-BB19 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 72 | 3740 | 2148 | N/A | N/A | N/A | N/A | 19076813.59 | 32.15 | SIDETRACK | N/A | DRY TREE | 2022-08-29 | 2022-08-29 19:00 | 2022-10-01 16:30 | 3505.71 | SHALLOW WATER | 3618 | 2189.79 | N/A | N/A | N/A | N/A | 24986818.87 | 58.23 | 28.66 | 28.66 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.67 |  | 1008 |  | 1540 | [6 empty] | 5.57 | 3027017.79 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2980.7885 | False | INNER STRING WITH SSD | 9CR | 8.6 | NACL | NO | NO | Exist
2022-03-03 | 2022-08-17 | HML | PM | BUNGA ORKID | BOC-26 (3B) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 5643.41 | 2014.76 | N/A | N/A | N/A | N/A | 18870000 | 52.61 | NO | N/A | DRY TREE | 2022-03-14 | 2022-03-13 09:00 | 2022-06-17 21:00 | 4389.35 | SHALLOW WATER | 4490 | 2020.38 | N/A | N/A | N/A | N/A | 17030000 | 56 | 11.72 | 11.72 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.19 |  | 687.16 |  | 937.59 | [6 empty] | 14.34 | 4374763.03 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 1CR | 787.4016 | False | NONE | L80 1CR | 8.9 | KCL | NO | NO | Exist
2022-02-25 | 2022-08-26 | MUBADALA | SK | LADA PUTIH | LADA PUTIH-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 104 | 2294 | 2294 | 19451295 | 24056339 | 34.6 | 45 | N/A | N/A | NO | N/A | N/A | 2022-05-27 | 2022-05-19 13:00 | 2022-06-29 12:00 | 2274 | SHALLOW WATER | 2402 | 2402 | 23946501 | N/A | 40.96 | N/A | N/A | N/A | 2.82 | 2.82 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.16 |  | 1897 |  | 3212 | [27 empty] | Exist
2022-02-25 | 2022-09-30 | MUBADALA | SK | CENGKIH | CENGKIH-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 118.4 | 2212 | 2212 | 16393012 | 19938360 | 29.8 | 37.9 | N/A | N/A | NO | N/A | N/A | 2022-07-02 | 2022-06-30 19:30 | 2022-08-11 14:00 | 1539.6 | SHALLOW WATER | 1681 | 1681 | N/A | 23000263 | N/A | 43.08 | N/A | N/A | 10.04 | 10.04 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.06 |  | 1591 |  | 4558 | [27 empty] | Exist
2022-02-23 | 2022-06-24 | HML | PM | BUNGA ORKID | BOC-27 (3C) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 4505 | 2026 | N/A | N/A | N/A | N/A | 16800000 | 43.12 | NO | N/A | DRY TREE | 2022-03-15 | 2022-03-15 | 2022-04-24 12:00 | 4389.35 | SHALLOW WATER | 4490 | 2020.38 | N/A | N/A | N/A | N/A | 13570000 | 40.43 | 18.19 | 18.19 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.44 |  | 406.81 |  | 972.16 | [6 empty] | 10.7 | 4669717.85 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 183.727 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2022-02-11 | N/A | SHELL | SK | INAI | INAI-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 84.49 | 3007.92 | 2976.53 | 13440000 | 15880000 | 33 | 41.6 | N/A | N/A | NO | N/A | N/A | 2022-04-25 | 2022-04-18 | 2022-07-02 | 2497.65 | SHALLOW WATER | 2613.53 | 2612.92 | N/A | 20958000 | N/A | 74.77 | N/A | N/A | 32 | 31 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 6.31 |  | 1786 |  | 2563 | [27 empty] | Exist
2022-01-27 | 2022-08-08 | COP | SK | MERSING | MERSING-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 64.3 | 2830 | 2282 | 21500000 | 21500000 | 42.5 | 42.5 | N/A | N/A | NO | N/A | N/A | 2022-05-21 | 2022-05-10 04:15 | 2022-06-21 06:00 | 2737.88 | SHALLOW WATER | 2837 | 2285.15 | N/A | 20000000 | N/A | 42.1 | N/A | N/A | 6.61 | 6.61 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 2.25 |  | 1544 |  | 862 | [27 empty] | Exist
2022-01-18 | N/A | SHELL | SB | GUMUSUT KAKAP | GK-W526C | APPRAISAL CUM DEV/DEVELOPMENT | MAERSK VIKING | DRILLSHIP | 1200.76 | 4155.44 | 2682.72 | N/A | N/A | N/A | N/A | 35300000 | 38.8 | NO | N/A | N/A | 2022-03-03 | 2022-03-02 | 2022-09-26 | 2866.51 | DEEP WATER | 4093.26 | 2672.05 | N/A | N/A | N/A | N/A | 39289267 | 53.17 | 31.05 | 31.05 | DW DEV C3 (Wet Tree) |  | 3.6 |  | 2590 |  | 4150 |  | No |  | No |  | No | [27 empty] | Exist
2022-01-18 | N/A | SHELL | SB | GUMUSUT KAKAP | GK-W721C | APPRAISAL CUM DEV/DEVELOPMENT | MAERSK VIKING | DRILLSHIP | 1201.07 | 4228.28 | 2431.18 | N/A | N/A | N/A | N/A | 36100000 | 42.7 | NO | N/A | N/A | 2022-03-08 | 2022-03-08 | 2022-08-30 | 3179.82 | DEEP WATER | 4406.89 | 2447.73 | N/A | N/A | N/A | N/A | 36550000 | 51.86 | 14.7 | 14.7 | DW DEV C3 (Wet Tree) |  | 3.6 |  | 2590 |  | 4150 |  | No |  | No |  | No | [27 empty] | Exist
2022-01-18 | N/A | SHELL | SB | GUMUSUT KAKAP | GK-P527BS1 | APPRAISAL CUM DEV/DEVELOPMENT | MAERSK VIKING | DRILLSHIP | 1087.38 | 2932.67 | 2488.17 | N/A | N/A | N/A | N/A | 42100000 | 52.5 | NO | N/A | N/A | 2022-03-16 | 2022-03-13 12:30 | 2022-07-22 21:45 | 1840.6 | DEEP WATER | 2953.98 | 2516.61 | N/A | N/A | N/A | N/A | 40446664.64 | 56.59 | 33.8 | 33.8 | DW DEV C3 (Wet Tree) |  | 3.6 |  | 2590 |  | 4150 |  | No |  | No |  | No | [27 empty] | Exist
2022-01-16 | 2023-02-02 | PTTEP | SK | PAPRIKA | PAPRIKA-1 | EXPLORATION/APPRAISAL | NAGA-5 | JACK UP | 92.3 | 3409 | 3232 | 13190000 | 24070000 | 34.3 | 66.94 | N/A | N/A | NO | N/A | N/A | 2022-07-22 | 2022-07-22 16:00 | 2022-09-27 19:30 | 3223.7 | SHALLOW WATER | 3348 | 3182.19 | N/A | 29660238 | N/A | 87.52 | N/A | N/A | 14.17 | 8.58 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.92 |  | 978 |  | 1960 | [27 empty] | Exist
2021-12-17 | 2022-05-19 | PETROFAC | PM | WEST DESARU | WD-A09-ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 64.8 | 2000 | 1509.5 | N/A | N/A | N/A | N/A | 8805377 | 25.5 | NO | N/A | DRY TREE | 2022-01-18 | 2022-01-01 19:00 | 2022-03-28 14:00 | 1823.22 | SHALLOW WATER | 1937.8 | 1454.8 | N/A | N/A | N/A | N/A | 12100000 | 50.96 | 14.25 | 14.25 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 3.04 |  | 707 |  | 1897.3 | [6 empty] | 6.5 | 1726632 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-12-06 | 2022-05-31 | HESS | PM | BERGADING DEEP | BERGADING-B1(H) | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 56.99 | 3482.78 | 2531.55 | N/A | N/A | N/A | N/A | 26700000 | 48.9 | NO | N/A | DRY TREE | 2021-12-15 | 2021-12-15 05:30 | 2022-03-31 00:30 | 3383.72 | SHALLOW WATER | 3485.34 | 2560.26 | N/A | N/A | N/A | N/A | 21420000 | 43.69 | 9.21 | 9.06 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.2 |  | 1024 |  | 1691 | [6 empty] | 16 | 6832138 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 17CR | 1200 | True |  | 718 | 8.34 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-12-06 | 2022-07-14 | HESS | PM | BERGADING | BERGADING-B2(N) | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 56.99 | 3378.85 | 2557.45 | N/A | N/A | N/A | N/A | 26450000 | 46.68 | NO | N/A | N/A | 2021-12-13 | 2021-12-13 09:00 | 2022-03-28 09:00 | 3183.66 | SHALLOW WATER | 3285.28 | 2556.02 | N/A | N/A | N/A | N/A | 20240000 | 41.71 | 9.89 | 9.89 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.4 |  | 1080 |  | 1673 | [27 empty] | Exist
2021-12-06 | 2022-07-21 | HESS | PM | BERGADING DEEP | BERGADING-B3(O) | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 56.99 | 4373.67 | 2557.45 | N/A | N/A | N/A | N/A | 30420000 | 65.03 | NO | N/A | DRY TREE | 2021-12-11 | 2021-12-11 05:00 | 2022-05-22 | 4317.76 | SHALLOW WATER | 4419.38 | 2552.76 | N/A | N/A | N/A | N/A | 30320000 | 68.29 | 2.41 | 2.35 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.6 |  | 1068 |  | 1712 | [6 empty] | 19.25 | 9151387 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 17CR | 1051 | True |  | 718 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-11-17 | 2022-06-29 | PETROFAC | PM | IRAMA | WD-A13 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 64.8 | 4815 | 1787.8 | N/A | N/A | N/A | N/A | 14950514 | 48.82 | SIDETRACK | N/A | DRY TREE | 2022-02-12 | 2021-12-01 13:00 | 2022-05-02 08:00 | 4763.42 | SHALLOW WATER | 4878 | 1711.5 | N/A | N/A | N/A | N/A | 26900000 | 108.83 | 14.25 | 14.25 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 3.02 |  | 804 |  | 1391 | [6 empty] | 4.48 | 2407711 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | GRE | 0 | True |  | 25CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-11-17 | 2022-05-12 | HML | PM | BUNGA ORKID | BOC-25 (DD) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 4547.7 | 2059 | N/A | N/A | N/A | N/A | 14980000 | 42.4 | NO | N/A | DRY TREE | 2022-01-29 | 2022-01-28 12:00 | 2022-03-13 09:00 | 4584.35 | SHALLOW WATER | 4685 | 2069.54 | N/A | N/A | N/A | N/A | 14810000 | 43.87 | 17.36 | 16.6 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.85 |  | 514.83 |  | 1006.6 | [6 empty] | 10.71 | 4128732.84 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 1CR | 590.5512 | False | NONE | L80 1CR | 8.9 | KCL | NO | NO | Exist
2021-10-25 | 2022-01-14 | PCSB | SK | BOKOR | BO-F605 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 69 | 1070 | 816 | N/A | N/A | N/A | N/A | 6614228.44 | 16 | SIDETRACK | N/A | DRY TREE | 2021-11-06 | 2021-11-06 | 2022-01-01 | 941 | SHALLOW WATER | 1055 | 803.49 | N/A | N/A | N/A | N/A | 6933000.65 | 20.1 |  |  | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.54 |  | 1076 |  | 1603 | [6 empty] | 3.35 | 1823947 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1788.145 | True | INNER STRING WITH SSD | 13CR | 9 | NACL | NO | NO | Exist
2021-10-21 | 2022-02-08 | PCSB | SK | BOKOR | BO-602 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 68 | 1328 | 1148 | N/A | N/A | N/A | N/A | 11966876.16 | 40.37 | NO | N/A | DRY TREE | 2021-11-19 | 2021-11-19 12:00 | 2021-12-25 | 1213.93 | SHALLOW WATER | 1321 | 1142 | N/A | N/A | N/A | N/A | 9290288.9 | 24.13 | 1.12 | 0.04 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.26 |  | 1168 |  | 1856 | [6 empty] | 7.04 | 2778223 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 638.7451 | True | INNER STRING WITH SSD | 13CR | 9 | NACL | NO | NO | Exist
2021-10-18 | 2022-03-28 | HML | PM | BUNGA ORKID | BOC-24 (RR) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 3878 | 2032 | N/A | N/A | N/A | N/A | 15850000 | 41.5 | NO | N/A | DRY TREE | 2021-12-25 | 2021-12-24 19:30 | 2022-01-28 12:00 | 3681.35 | SHALLOW WATER | 3782 | 2026.54 | N/A | N/A | N/A | N/A | 12760000 | 35.69 | 4.64 | 4.64 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.53 |  | 475.1 |  | 1078.5 | [6 empty] | 8.86 | 3643905.83 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 1CR | 954.7244 | False | NONE | L80 1CR | 8.7 | KCL | NO | NO | Exist
2021-10-07 | 2022-04-04 | PCSB | SK | KUMANG | KUMANG-A6 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA PELAUT | TENDER ASSISTED DRILLING RIG (TADR) | 80.2 | 1994.63 | 1142.83 | N/A | N/A | N/A | N/A | 7163495.06 | 14.7 | SIDETRACK | N/A | DRY TREE | N/A | 2021-12-03 15:30 | 2022-02-09 06:15 | 2322.3 | SHALLOW WATER | 2438 | 1145.63 | N/A | N/A | N/A | N/A | 17329127 | 53.68 | 23 | 11.7 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.05 |  | 1633.79 |  | 2032.58 | [6 empty] | 6.86 | 2009260.01 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1453.483 | True | NONE | 13CR | 9.5 | NACL | NO | NO | Exist
2021-09-27 | 2022-02-20 | PCSB | SK | HADRAH | HADRAH-1 | EXPLORATION/APPRAISAL | NAGA-2 | JACK UP | 60 | 1887 | 1887 | 15450000 | 16270000 | 41.75 | 46.46 | N/A | N/A | NO | N/A | N/A | 2021-11-06 | 2021-10-24 18:30 | 2021-12-31 07:00 | 1760 | SHALLOW WATER | 1850 | 1757.4 | N/A | 18993289.39 | N/A | 67.52 | N/A | N/A | 23.39 | 4.95 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.27 |  | 1360 |  | 1934 | [27 empty] | Exist
2021-09-23 | 2021-12-15 | PCSB | SK | BOKOR | BO-F606 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 69 | 825 | 790 | N/A | N/A | N/A | N/A | 5729796 | 13.91 | NO | N/A | DRY TREE | 2021-11-08 02:30 | 2021-11-08 02:30 | 2021-11-19 12:00 | 709 | SHALLOW WATER | 823 | 786.23 | N/A | N/A | N/A | N/A | 5324746.54 | 11.4 | 23.76 | 23.76 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.83 |  | 855 |  | 1972 | [6 empty] | 5.94 | 3023524 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 551.208 | False | INNER STRING WITH SSD | 13CR | 9 | NACL | NO | NO | Exist
2021-09-15 | 2022-03-31 | PCSB | PM | LEDANG | LEDANG-4SS | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 76 | 1740 | 1701 | N/A | N/A | N/A | N/A | 16458913.44 | 42.06 | SIDETRACK | N/A | N/A | 2021-10-16 | 2021-10-16 | 2022-02-08 | 1262 | SHALLOW WATER | 1378 | 1207.25 | N/A | N/A | N/A | N/A | 36834036.89 | 115 | 28.64 | 23.95 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 26.66 |  | 7660 |  | 8337 | [27 empty] | Exist
2021-09-13 | 2022-06-13 | HESS | PM | BUNGA KESUMBA | BUNGA KESUMBA A-4 | APPRAISAL CUM DEV/DEVELOPMENT | BORR SAGA | JACK UP | 55.5 | 3324.74 | 1240.07 | N/A | N/A | N/A | N/A | 12200000 | 32.12 | NO | N/A | DRY TREE | 2021-10-13 | 2021-10-12 15:00 | 2021-11-26 05:00 | 3283.63 | SHALLOW WATER | 3384.94 | 1232.92 | N/A | N/A | N/A | N/A | 16530000 | 37.04 | 0.9 | 0.9 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.5 |  | 1018 |  | 1567 | [6 empty] | 7.77 | 2530000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1877.37 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2021-09-03 | 2023-01-25 | PCSB | SK | KASAWARI | KASAWARI-A5 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 108 | 3085 | 2643 | N/A | N/A | N/A | N/A | 29422230 | 36.04 | NO | N/A | DRY TREE | 2021-10-05 | 2021-10-05 09:00 | 2022-11-02 08:00 | 3057.2 | SHALLOW WATER | 3204 | 2772 | N/A | N/A | N/A | N/A | 42563446.34 | 86.98 | 0 | 0 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 6.24 |  | 2641 |  | 4054 | [6 empty] | 17.42 | 14126784 |  |  | CARBONATE | HPHT | CASED HOLE | NO | NO | 7" | 1.0 | SINGLE | 17CR | 302 | False | NONE | INCONEL 925 | 13.95 | CABR2 | NO | NO | Exist
2021-09-03 | 2023-02-20 | PCSB | SK | KASAWARI | KASAWARI-A1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 108 | 2778 | 2778 | N/A | N/A | N/A | N/A | 33449984.03 | 38.47 | NO | N/A | DRY TREE | 2021-10-13 | 2021-10-12 18:00 | 2022-11-22 15:00 | 2631.2 | SHALLOW WATER | 2778 | 2777.94 | N/A | N/A | N/A | N/A | 67049439.13 | 141.54 | 65.65 | 64.39 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 5.38 |  | 3028.21 |  | 7417.3 | [6 empty] | 92.4 | 40199210.9 |  |  | CARBONATE | HPHT | CASED HOLE | NO | NO | 7" | 1.0 | SINGLE | 17CR | 878.65 | False | NONE | INCONEL 925 | 14.4 | CABR2 | NO | NO | Exist
2021-08-27 | 2022-02-07 | PCSB | SK | F9 | F9-A7 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 94.8 | 4714.37 | 1363.49 | N/A | N/A | N/A | N/A | 20580000 | 52.63 | NO | N/A | DRY TREE | 2021-09-15 | 2021-09-15 | 2021-12-22 | 4609.01 | SHALLOW WATER | 4749 | 1387.84 | N/A | N/A | N/A | N/A | 23906482.81 | 70.43 | 9.13 | 8.99 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.38 |  | 1092.6 |  | 1373.9 | [6 empty] | 8.73 | 4269322.51 |  |  | CARBONATE | NORMAL | OPEN HOLE BAREFOOT | NO | NO | 7" | 1.0 | SINGLE | L80 13CR |  | True | NONE | 13CR | 8.9 | NACL | NO | NO | Exist
2021-08-23 | 2022-02-01 | PCSB | SK | BARONIA | BN-87 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 76.01 | 2240.48 | 2195.67 | N/A | N/A | N/A | N/A | 11983433.79 | 22.3 | NO | N/A | DRY TREE | 2021-09-26 | 2021-09-26 05:00 | 2021-12-16 09:30 | 3444.25 | SHALLOW WATER | 3565.99 | 2243.8 | N/A | N/A | N/A | N/A | 8706881.81 | 22.31 | 1.31 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.03 |  | 249 |  | 770 | [6 empty] | 5.46 | 1870736.75 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 0 | True | AICV | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-08-23 | 2021-12-09 | PCSB | SK | BARONIA | BN-86 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 76.01 | 3250.53 | 2215.06 | N/A | N/A | N/A | N/A | 11133921.19 | 19.82 | NO | N/A | DRY TREE | 2021-09-26 | 2021-09-26 22:45 | 2021-11-03 10:45 | 3270.53 | SHALLOW WATER | 3392.26 | 2224.35 | N/A | N/A | N/A | N/A | 7392904.95 | 15.93 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.12 |  | 374.46 |  | 688.96 | [6 empty] | 3.53 | 1654585.62 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 0 | False |  | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-08-23 | 2022-02-01 | PCSB | SK | BARONIA | BN-85 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 75.89 | 3089.3 | 2218.23 | N/A | N/A | N/A | N/A | 11796515.53 | 23.42 | NO | N/A | DRY TREE | 2021-09-26 | 2021-09-26 | 2021-12-03 18:00 | 3020.12 | SHALLOW WATER | 3141.73 | 2221.43 | N/A | N/A | N/A | N/A | 7463191.76 | 16.91 | 1.4 | 1.31 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.23 |  | 459 |  | 752 | [6 empty] | 4.23 | 1492915.67 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 0 | True |  | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-08-06 | 2021-11-11 | PCSB | SK | TUKAU | TUKAU-E41ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 46.94 | 2300.94 | 2216.32 | N/A | N/A | N/A | N/A | 12210000 | 40.02 | SIDETRACK | N/A | DRY TREE | 2021-08-26 06:15 | 2021-08-16 | 2021-10-05 21:00 | 2226.09 | SHALLOW WATER | 2293.81 | 2218.38 | N/A | N/A | N/A | N/A | 10162815.81 | 39.04 | 13.24 | 12.92 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.44 |  | 433 |  | 937 | [6 empty] | 8.38 | 1821292 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 | 1209 | False | NONE | 9CR | 9.3 | NACL | NO | NO | Exist
2021-08-06 | 2021-11-22 | PCSB | SK | TUKAU | TUKAU-E42ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 46.94 | 2300.94 | 2216.32 | N/A | N/A | N/A | N/A | 8387122 | 23.4 | NO | N/A | DRY TREE | N/A | 2021-08-11 21:00 | 2021-10-16 18:30 | 2228.53 | SHALLOW WATER | 2296.25 | 2259.04 | N/A | N/A | N/A | N/A | 8209895 | 27.81 | 3.14 | 2.84 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.3 |  | 519 |  | 1395 | [6 empty] | 10.31 | 1966374 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 | 4356 | False | NONE | 9CR | 9.3 | NACL | NO | NO | Exist
2021-07-12 | 2021-12-09 | PCSB | SK | F9 | F9-A6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 94.8 | 2290.11 | 1382.05 | N/A | N/A | N/A | N/A | 10695268.62 | 21.74 | NO | N/A | DRY TREE | 2021-09-22 | 2021-09-21 10:00 | 2021-10-15 13:00 | 2150.01 | SHALLOW WATER | 2290 | 1369.19 | N/A | N/A | N/A | N/A | 11566644.79 | 24.13 | 7.21 | 7.08 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.51 |  | 911 |  | 1562 | [6 empty] | 5.85 | 3568907.75 |  |  | CARBONATE | NORMAL | OPEN HOLE BAREFOOT | NO | NO | 7" | 1.0 | SINGLE | L80 13CR |  | True | NONE | 13CR | 8.9 | NACL | NO | NO | Exist
2021-06-22 | 2021-11-25 | PETROFAC | PM | CENDOR | EC-A08 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 2222 | 1682 | N/A | N/A | N/A | N/A | 5085790 | 15.02 | NO | N/A | DRY TREE | 2021-07-02 15:30 | 2021-07-02 | 2021-10-05 | 2116.84 | SHALLOW WATER | 2228 | 1698 | N/A | N/A | N/A | N/A | 4737353 | 14.88 | 6 | 6 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.22 |  | 339 |  | 648 | [6 empty] | 5.97 | 2262769.25 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 | 0 | False |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-06-22 | 2021-11-16 | PETROFAC | PM | CENDOR | EC-A07 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 62.5 | 3035 | 1706 | N/A | N/A | N/A | N/A | 7651560 | 27.25 | NO | N/A | DRY TREE | 2021-06-29 | 2021-06-29 | N/A | 2889.84 | SHALLOW WATER | 3001 | 1702.65 | N/A | N/A | N/A | N/A | 5270000 | 17.95 | 0.52 | 0.52 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.08 |  | 348 |  | 535 | [6 empty] | 5.23 | 1845847.96 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | False |  | 25CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2021-06-12 | 2021-11-25 | PETROFAC | PM | CENDOR | EC-A04 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 2503 | 1629 | N/A | N/A | N/A | N/A | 7272528 | 22.4 | NO | N/A | DRY TREE | 2021-06-21 | 2021-06-20 | 2021-09-23 | 2420.84 | SHALLOW WATER | 2532 | 1657 | N/A | N/A | N/A | N/A | 5598047 | 18.25 | 0.74 | 0.29 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.24 |  | 407 |  | 674 | [6 empty] | 5.56 | 2218251.13 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-06-11 | 2021-10-21 | PETROFAC | PM | CENDOR | EC-A03 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 2152 | 1575 | N/A | N/A | N/A | N/A | 7525297 | 23.2 | NO | N/A | DRY TREE | 2021-06-23 | 2021-06-23 20:00 | 2021-08-24 03:30 | 2265.84 | SHALLOW WATER | 2377 | 1741.79 | N/A | N/A | N/A | N/A | 5570000 | 18.07 | 5.42 | 5.42 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.22 |  | 402 |  | 714 | [6 empty] | 6.15 | 2428549.97 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-06-11 | 2021-10-06 | PETROFAC | PM | CENDOR | EC-A05 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 1937 | 1690 | N/A | N/A | N/A | N/A | 6363952 | 18.8 | NO | N/A | DRY TREE | 2021-08-06 | 2021-06-26 | 2021-08-13 | 1918.84 | SHALLOW WATER | 2030 | 1728.96 | N/A | N/A | N/A | N/A | 5520000 | 18.74 | 13.73 | 13.73 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.7 |  | 553 |  | 829 | [6 empty] | 5.13 | 1832211 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-06-11 | 2021-10-06 | PETROFAC | PM | CENDOR | EC-A06 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 2520 | 1700 | N/A | N/A | N/A | N/A | 7265825 | 23.1 | SUSPEND | N/A | DRY TREE | 2021-07-05 | 2021-07-04 17:00 | 2021-08-19 | 2477.84 | SHALLOW WATER | 2589 | 1734.83 | N/A | N/A | N/A | N/A | 5788312 | 19.29 | 3 | 2.21 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.2 |  | 407 |  | 681 | [6 empty] | 6.13 | 2327087.03 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-06-05 | 2022-01-07 | PTTEP | SK | SOUTH ACIS | SASA-02 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 3123 | 1484.42 | N/A | N/A | N/A | N/A | 8126457.28 | 17.01 | SIDETRACK | N/A | DRY TREE | 2021-07-02 22:00 | 2021-07-02 21:30 | 2021-11-02 12:00 | 3008 | SHALLOW WATER | 3094.85 | 1453.77 | N/A | N/A | N/A | N/A | 17814833.8 | 55.84 | 30.15 | 30.15 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 5.11 |  | 1516 |  | 1754 | [6 empty] | 4.46 | 2967882.2 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 595 | True |  | L80 13CR | 9.3 | CACL2 | NO | NO | Exist
2021-05-24 | 2021-10-06 | PCSB | SK | BAKAU | BAKAU-A09 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 54.25 | 3351.11 | 2996.83 | N/A | N/A | N/A | N/A | 7590000 | 21.2 | NO | N/A | DRY TREE | N/A | 2021-07-18 22:00 | 2021-08-08 17:30 | 3260.01 | SHALLOW WATER | 3357.21 | 3004.5 | N/A | N/A | N/A | N/A | 7624406 | 20.81 | 3.2 | 3.2 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.09 |  | 382 |  | 669 | [6 empty] | 7.3 | 2553639.12 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1480 | False |  | L80 13CR | 10.5 | NACL/NABR | NO | NO | Exist
2021-05-24 | 2021-10-08 | PCSB | SK | BAKAU | BAKAU-A10 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 54.25 | 3129.53 | 3046.39 | N/A | N/A | N/A | N/A | 7760000 | 22.2 | NO | N/A | DRY TREE | N/A | 2021-07-03 | 2021-08-24 21:00 | 3034.78 | SHALLOW WATER | 3131.97 | 3048.43 | N/A | N/A | N/A | N/A | 8003322 | 22.35 | 5.46 | 5.46 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.28 |  | 414 |  | 771 | [6 empty] | 7.33 | 2512100.41 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1625 | False |  | L80 13CR | 11.4 | NACL/NABR | NO | NO | Exist
2021-05-24 | 2021-11-03 | PCSB | SK | BAKAU | BAKAU-A08 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 54.25 | 2964.04 | 2807.65 | N/A | N/A | N/A | N/A | 7710000 | 21 | NO | N/A | DRY TREE | 2021-07-15 | 2021-07-04 13:00 | 2021-09-07 12:00 | 2837.88 | SHALLOW WATER | 2935.08 | 2784.56 | N/A | N/A | N/A | N/A | 7973398 | 23.33 | 2.5 | 2.5 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.64 |  | 464 |  | 824 | [6 empty] | 6.01 | 2129236.6 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 915 | False |  | L80 13CR | 9.8 | NACL/NABR | NO | NO | Exist
2021-05-10 | 2021-08-13 | PTTEP | SK | MAK YONG | MAK YONG-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 36.9 | 2375 | 2335 | 7710000 | 9930000 | 18.35 | 26.78 | N/A | N/A | NO | N/A | N/A | 2021-05-24 | 2021-05-21 14:00 | 2021-06-15 07:45 | 2304.1 | SHALLOW WATER | 2376 | 2335 | N/A | 7660000 | N/A | 24.74 | N/A | N/A | 11.49 | 11.49 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.46 |  | 354 |  | 1013 | [27 empty] | Exist
2021-04-28 | 2021-09-10 | PCSB | PM | PUTERI | PADANG-A02 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 60 | 4969.22 | 2059 | N/A | N/A | N/A | N/A | 17084686.7 | 39.4 | NO | N/A | DRY TREE | 2021-05-25 | 2021-05-25 20:00 | 2021-07-12 18:00 | 4664.8 | SHALLOW WATER | 4768.8 | 2066.73 | N/A | N/A | N/A | N/A | 17528811.51 | 47.92 | 9.15 | 8.85 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.76 |  | 815 |  | 1109 | [6 empty] | 4.81 | 3223165.16 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 | 2829 | False | INNER STRING WITH SSD | 9CR | 8.5 | NACL | NO | NO | Exist
2021-04-19 | 2022-04-05 | PTTEP | SB | SNP | S-SW1-P17 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1395 | 2486 | 2370 | N/A | N/A | N/A | N/A | 39527950 | 36 | NO | N/A | WET TREE | 2021-07-22 | 2021-07-21 | 2021-12-08 | 1045 | DEEP WATER | 2465 | 2379 | N/A | N/A | N/A | N/A | 29078728 | 35 | 0.65 | 0.65 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 6.78 |  | 4449 |  | 8482 | [6 empty] | 14.5 | 16375865 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 860.6063 | True |  | L80 13CR | 10.4 | NACL/NABR | 3 | NO | Exist
2021-04-19 | N/A | PTTEP | SB | SNP | S-CN1-P11 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1314 | 3531 | 2311 | N/A | N/A | N/A | N/A | 51178159 | 42 | NO | N/A | WET TREE | 2021-07-25 | 2021-07-25 | 2022-03-04 12:00 | 1956 | DEEP WATER | 3295 | 2332.88 | N/A | N/A | N/A | N/A | 43334185 | 38.5 | 0.22 | 0.22 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 3.8 |  | 2702 |  | 6752 | [6 empty] | 17.75 | 19978747.63 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 3339.2377 | True |  | L80 13CR | 10.4 | NACL/NABR | 3 | NO | Exist
2021-04-19 | N/A | PTTEP | SB | SNP | S-CN1-P14 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1313 | 2858 | 2279 | N/A | N/A | N/A | N/A | 45361570 | 38.5 | NO | N/A | WET TREE | 2021-07-16 | 2021-07-15 07:00 | 2021-11-21 | 1433 | DEEP WATER | 2771 | 2275 | N/A | N/A | N/A | N/A | 37844216 | 52.71 | 13.4 | 13.4 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 7.17 |  | 4124 |  | 6656 | [6 empty] | 13.54 | 9721318.24 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 1427.5631 | True |  | L80 13CR | 10.4 | NACL/NABR | 3 | NO | Exist
2021-04-19 | N/A | PTTEP | SB | SNP | S-NE1-P10 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1237 | 3935 | 2426 | N/A | N/A | N/A | N/A | 48437133 | 47 | NO | N/A | WET TREE | 2021-07-29 | 2021-07-29 | 2022-02-06 | 2690 | DEEP WATER | 3952 | 2444.68 | N/A | N/A | N/A | N/A | 65897365 | 106 | 8.82 | 8.31 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 4.37 |  | 1901 |  | 5341 | [6 empty] | 70.99 | 44132584.35 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 1807.831 | True |  | L80 13CR | 10.4 | NACL/NABR | 3 | NO | Exist
2021-04-17 | 2021-11-18 | PTTEP | SK | NANGKA | NANGKA-1 | EXPLORATION/APPRAISAL | BORR SAGA | JACK UP | 77 | 5042 | 4632 | 20500000 | 23000000 | 49.4 | 57 | N/A | N/A | NO | N/A | N/A | 2021-06-30 | 2021-06-06 08:30 | 2021-09-19 17:00 | 3649 | SHALLOW WATER | 3758 | 3565.37 | N/A | 33300000 | N/A | 105.4 | N/A | N/A | 26.33 | 26.27 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 3.6 |  | 1266 |  | 2430 | [27 empty] | Exist
2021-04-01 | N/A | PTTEP | SK | PESA | PESA-01 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 31.3 | 1730 | 1633.5 | N/A | N/A | N/A | N/A | 3265225 | 6.98 | NO | N/A | DRY TREE | 2021-04-21 | 2021-04-21 12:30 | 2021-05-04 12:00 | 1643.35 | SHALLOW WATER | 1710 | 1615.63 | N/A | N/A | N/A | N/A | 2933751 | 7.31 | 4.84 | 4.84 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.17 |  | 409.88 |  | 543.41 | [6 empty] | 1.1 | 752000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 82 | False |  | L80 13CR | 6.95 | OTHER | 1 | NO | Exist
2021-04-01 | 2021-06-29 | PTTEP | SK | PEMANIS | PESA-02 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 31.3 | 1987 | 1518.97 | N/A | N/A | N/A | N/A | 3737949.4 | 7.87 | NO | N/A | DRY TREE | 2021-04-22 | 2021-04-18 | 2021-05-18 17:00 | 1958.35 | SHALLOW WATER | 2025 | 1525.53 | N/A | N/A | N/A | N/A | 3260492.06 | 5.53 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.74 |  | 365.74 |  | 507.37 | [6 empty] | 0.75 | 943448 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 70 | False |  | L80 13CR | 6.95 | OTHER | 1 | NO | Exist
2021-04-01 | N/A | PTTEP | SK | PESA | PESA-04 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 31.3 | 2424 | 1544.1 | N/A | N/A | N/A | N/A | 4062754 | 8.48 | NO | N/A | DRY TREE | 2021-04-23 | 2021-04-23 07:15 | 2021-05-10 16:30 | 2317.35 | SHALLOW WATER | 2384 | 1523.85 | N/A | N/A | N/A | N/A | 3533586 | 8.16 | 10.47 | 10.47 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.96 |  | 341.96 |  | 464.28 | [6 empty] | 0.92 | 957000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 76 | False |  | L80 13CR | 6.95 | OTHER | 1 | NO | Exist
2021-03-19 | 2021-08-12 | PETROFAC | PM | CENDOR | ECA-02 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 62.5 | 1954 | 1171 | N/A | N/A | N/A | N/A | 6038531 | 15 | NO | N/A | DRY TREE | 2021-04-28 | 2021-04-27 | N/A | 1849.84 | SHALLOW WATER | 1961 | 1720.69 | N/A | N/A | N/A | N/A | 6360000 | 21.79 | 4 | 4 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.4 |  | 710 |  | 988 | [6 empty] | 4.4 | 1739307 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2021-03-15 | 2021-08-19 | PETROFAC | PM | CENDOR | EC-A01 | APPRAISAL CUM DEV/DEVELOPMENT | ICON CAREN | JACK UP | 62.5 | 2625 | 1619 | N/A | N/A | N/A | N/A | 8264114 | 22 | SIDETRACK | N/A | DRY TREE | 2021-05-04 | 2021-05-04 | 2021-06-20 | 2509.84 | SHALLOW WATER | 2621 | 1616.51 | N/A | N/A | N/A | N/A | 10672398 | 32.46 | 17.65 | 17.65 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.4 |  | 888 |  | 1237 | [6 empty] | 9.77 | 3011401.95 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 0 | True |  | L80 13CR | 9.8 | NACL/NABR | 1 | NO | Exist
2021-03-09 | 2022-09-27 | PCSB | SK | KASAWARI | KASAWARI-A7 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 108 | 2856.5 | 2697.8 | N/A | N/A | N/A | N/A | 27083987 | 38.38 | NO | N/A | DRY TREE | 2021-10-17 | 2021-10-17 | 2022-07-19 | 2718.2 | SHALLOW WATER | 2865 | 2703.6 | N/A | N/A | N/A | N/A | 27438656.05 | 57 | 30.72 | 26.14 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 4.7 |  | 1827.77 |  | 2916.19 | [6 empty] | 13.01 | 10288112 |  |  | CARBONATE | HPHT | CASED HOLE | NO | NO | 7" | 1.0 | SINGLE | 17CR | 1028 | False | NONE | INCONEL 925 | 14.9 | CABR2 | NO | NO | Exist
2021-03-02 | 2021-07-15 | VESTIGO | PM | BERANTAI | BRWA-17 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 67 | 3598 | 1123 | N/A | N/A | N/A | N/A | 7500000 | 21.1 | NO | N/A | DRY TREE | 2021-03-26 | 2021-03-25 18:00 | 2021-05-21 11:15 | 3351.67 | SHALLOW WATER | 3467 | 1102.65 | N/A | N/A | N/A | N/A | 6865167 | 24 | 8.55 | 8.55 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.66 |  | 435 |  | 624 | [6 empty] | 5.79 | 2084874.68 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 144.364 | False |  | L80 | 9.2 | NACL | NO | NO | Exist
2021-03-02 | 2021-07-07 | VESTIGO | PM | BERANTAI | BRWA-16ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 67 | 1660 | 734 | N/A | N/A | N/A | N/A | 5369181.89 | 13.5 | NO | N/A | DRY TREE | 2021-03-30 | 2021-03-28 10:30 | 2021-05-11 16:00 | 1556.24 | SHALLOW WATER | 1671.57 | 735.25 | N/A | N/A | N/A | N/A | 20615401 | 71.9 | 0.16 | 0.16 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 1.96 |  | 548 |  | 927 | [6 empty] | 5.04 | 1933846 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 52.496 | False |  | L80 | 9.4 | NACL | NO | NO | Exist
2021-03-02 | 2021-07-07 | VESTIGO | PM | BERANTAI | BRWA-13ST | APPRAISAL CUM DEV/DEVELOPMENT | BORR IDUN | JACK UP | 67 | 1234 | 736 | N/A | N/A | N/A | N/A | 5500000 | 14.2 | NO | N/A | DRY TREE | 2021-04-04 | 2021-04-01 19:00 | 2021-05-15 16:15 | 1103.67 | SHALLOW WATER | 1219 | 733.31 | N/A | N/A | N/A | N/A | 5147216 | 17.6 | 9.53 | 9.53 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 3.76 |  | 960 |  | 1421 | [6 empty] | 4.01 | 1669839 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 229.67 | False |  | L80 | 8.5 | NACL | NO | NO | Exist
2021-02-26 | 2021-06-02 | PCSB | SB | KACAK | KACAK-1 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 1172 | 2265 | 2265 | 25000000 | 35800000 | 27.77 | 44.2 | N/A | N/A | NO | N/A | N/A | 2021-03-10 | 2021-03-09 10:30 | 2021-04-09 | 1043 | DEEP WATER | 2240 | 2239.76 | N/A | 26040582.17 | N/A | 30.56 | N/A | N/A | 2.97 | 2.97 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 3.5 |  | 3527 |  | 6257 | [27 empty] | Exist
2021-02-01 | 2021-07-05 | PCSB | SB | JANGAS | JANGAS-3 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 1656 | 3462 | 3375 | 30466179.21 | 50135854.48 | 29 | 55 | N/A | N/A | NO | N/A | N/A | 2021-03-04 | 2021-03-03 04:15 | 2021-05-10 04:00 | 1745 | DEEP WATER | 3426 | 3339.25 | N/A | 33439301.76 | N/A | 37.43 | N/A | N/A | 8.15 | 8.15 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 2.32 |  | 2330 |  | 3651 | [27 empty] | Exist
2021-01-13 | 2021-04-27 | ROC OIL | SK | D21 | D21-A14 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 2302.04 | 2051.51 | N/A | N/A | N/A | N/A | 9296708 | 26.22 | NO | N/A | N/A | 2021-01-19 | 2021-01-18 09:00 | 2021-03-07 15:00 | 2349.31 | SHALLOW WATER | 2442.85 | 2189.58 | N/A | N/A | N/A | N/A | 8608954 | 22.79 | 8 | 4 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.42 |  | 624 |  | 1238 | [27 empty] | Exist
2021-01-06 | 2021-07-09 | PTTEP | SK | KULINTANG | KULINTANG-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 35.5 | 2242 | 2000 | 6324000 | 8077000 | 16.58 | 23.73 | N/A | N/A | SIDETRACK | N/A | N/A | 2021-03-03 02:00 | 2021-03-03 02:00 | 2021-04-18 02:30 | 2167.5 | SHALLOW WATER | 2238 | 2035 | N/A | 13500000 | N/A | 46.02 | N/A | N/A | 30.4 | 30.4 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 4.01 |  | 997 |  | 1859 | [27 empty] | Exist
2021-01-03 | 2021-08-09 | JX NIPPON | SK | HELANG | HELANG DEEP-1 | EXPLORATION/APPRAISAL | BORR SAGA | JACK UP | 90.6 | 4532 | 4500 | 44814000 | 44814000 | 109 | 109 | N/A | N/A | SIDETRACK | N/A | N/A | 2021-02-06 | 2021-01-26 15:45 | 2021-06-06 08:30 | 4157.39 | SHALLOW WATER | 4280 | 4279.17 | N/A | 38139000 | N/A | 130.5 | N/A | N/A | 24 | 19 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 6.31 |  | 2215 |  | 2797 | [27 empty] | Exist
2020-11-29 | 2021-07-05 | ROC OIL | SK | D21 | D21-A11 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 3055.17 | 2266.99 | N/A | N/A | N/A | N/A | 10060000 | 29.4 | NO | N/A | N/A | 2021-01-23 | 2020-12-23 03:00 | 2021-03-07 03:00 | 2832.4 | SHALLOW WATER | 2925.94 | 2148.43 | N/A | N/A | N/A | N/A | 8526216 | 21.13 | 3 | 3 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 1.41 |  | 512 |  | 915 | [27 empty] | Exist
2020-11-12 | 2021-04-14 | PTTEP | SK | SIRUNG | SIRUNG-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 46.4 | 2030 | 2030 | 10289458 | 10289458 | 30 | 30 | N/A | N/A | SIDETRACK | N/A | N/A | 2021-01-22 02:00 | 2021-01-16 15:00 | 2021-03-03 02:00 | 2521.47 | SHALLOW WATER | 2600 | 2595.58 | N/A | 10289458 | N/A | 30 | N/A | N/A | 11.81 | 3.19 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.9 |  | 791 |  | 1561 | [27 empty] | Exist
2020-10-12 | 2021-06-01 | ROC OIL | SK | D21 | D21-A12 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 3339.23 | 2076.2 | N/A | N/A | N/A | N/A | 18547699 | 52.93 | SIDETRACK | N/A | N/A | 2020-10-30 | 2020-10-30 09:00 | 2021-03-30 03:00 | 7133.3 | SHALLOW WATER | 3438.59 | 2157.88 | N/A | N/A | N/A | N/A | 14737952 | 44.01 | 31.69 | 31.69 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.69 |  | 522 |  | 2559 | [27 empty] | Exist
2020-10-12 | 2021-04-28 | ROC OIL | SK | D21 | D21-A13 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 3194.76 | 2257.85 | N/A | N/A | N/A | N/A | 9628000 | 27.27 | NO | N/A | N/A | 2020-11-04 | 2020-10-29 12:00 | 2021-03-01 17:00 | 3000.64 | SHALLOW WATER | 3094.18 | 2196.59 | N/A | N/A | N/A | N/A | 10038208.95 | 26.87 | 2.48 | 2.21 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.57 |  | 524 |  | 992 | [27 empty] | Exist
2020-10-06 | 2020-12-31 | PTTEP | PM | BEBARU | BEBARU-2 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 71 | 3425 | 2868 | 6190000 | 7120000 | 18.14 | 21.22 | N/A | N/A | NO | N/A | N/A | 2020-10-23 | 2020-10-19 22:00 | 2020-11-06 13:00 | 2795 | SHALLOW WATER | 2901 | 2473.9 | 6660000 | N/A | 17.62 | N/A | N/A | N/A | 1.7 | 1.7 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1 |  | 306 |  | 481 | [27 empty] | Exist
2020-09-30 | 2021-02-26 | PTTEP | SK | DOKONG | DOKONG-1 | EXPLORATION/APPRAISAL | BORR GUNNLOD | JACK UP | 100.5 | 3821 | 3280 | 11100000 | 15800000 | 29.1 | 41.6 | N/A | N/A | NO | N/A | N/A | 2020-11-13 | 2020-11-06 | 2021-01-15 03:30 | 3675 | SHALLOW WATER | 3810 | 3283.67 | N/A | 17100000 | N/A | 69.6 | N/A | N/A | 23.3 | 14.9 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.53 |  | 643 |  | 1161 | [27 empty] | Exist
2020-09-30 | 2020-12-14 | PCSB | SK | KAMOMIL | KAMOMIL-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 125 | 1433 | 1433 | 15819250 | 16320000 | 32.77 | 34.57 | N/A | N/A | NO | N/A | N/A | 2020-10-22 | 2020-10-20 04:00 | 2020-11-15 16:00 | 1285 | SHALLOW WATER | 1433 | 1432.96 | 12878354.98 | N/A | 26.51 | N/A | N/A | N/A | 5.66 | 1.89 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 3.43 |  | 1761 |  | 2168 | [27 empty] | Exist
2020-09-14 | N/A | SHELL | SB | MALIKAI | MLK-119 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.83 | 2794.57 | 1572.39 | N/A | N/A | N/A | N/A | 20500000 | 41.2 | NO | N/A | N/A | 2020-11-23 | 2020-10-23 | 2021-05-16 | 2214.87 | DEEP WATER | 2746.11 | 1618.1 | N/A | N/A | N/A | N/A | 21988026 | 44.98 | 27.9 | 27.7 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | No |  | No |  | No | [27 empty] | Exist
2020-09-14 | N/A | SHELL | SB | MALIKAI | MLK-121 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 484.16 | 2979.88 | 1502.59 | N/A | N/A | N/A | N/A | 19900000 | 43 | SUSPEND | N/A | N/A | 2020-10-26 | 2020-10-15 | 2021-04-11 | 2241.84 | DEEP WATER | 2771.41 | 1505.64 | N/A | N/A | N/A | N/A | 16400000 | 39.65 | 10.19 | 7.74 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | 3.69 |  | 1478 |  | 2294 | [27 empty] | Exist
2020-09-14 | N/A | SHELL | SB | MALIKAI | MLK-121 S1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 484.16 | 2748.25 | 1506.86 | N/A | N/A | N/A | N/A | 19900000 | 43 | NO | N/A | N/A | 2020-10-26 | 2020-10-15 10:30 | 2021-04-11 | 2241.84 | DEEP WATER | 2771.41 | 1505.64 | N/A | N/A | N/A | N/A | 16396249 | 39.65 | 10.19 | 7.74 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | No |  | No |  | No | [27 empty] | Exist
2020-09-14 | N/A | SHELL | SB | MALIKAI | MLK-106 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 487.2 | 2788.17 | 1350.81 | N/A | N/A | N/A | N/A | 19300000 | 38.9 | NO | N/A | N/A | 2020-11-17 | 2020-11-17 | 2021-04-24 | 2294.88 | DEEP WATER | 2827.49 | 1401.4 | N/A | N/A | N/A | N/A | 15400000 | 27.42 | 1.28 | 1.28 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | No |  | No |  | No | [27 empty] | Exist
2020-09-14 | N/A | SHELL | SB | MALIKAI | MLK-118 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 486.28 | 2678.15 | 1265.77 | N/A | N/A | N/A | N/A | 21200000 | 29.6 | NO | N/A | N/A | 2020-11-14 | 2020-11-13 | 2021-03-11 20:00 | 2100.12 | DEEP WATER | 2631.82 | 1260.87 | N/A | N/A | N/A | N/A | 18443907 | 32.73 | 8.31 | 7.92 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | No |  | No |  | No | [27 empty] | Exist
2020-09-13 | 2021-03-25 | PTTEP | SK | LANG LEBAH | LANG LEBAH-2 | EXPLORATION/APPRAISAL | BORR SAGA | JACK UP | 88.6 | 4200 | 4170 | 47700000 | 50712522.77 | 97.1 | 104.1 | N/A | N/A | NO | N/A | N/A | 2020-09-27 | 2020-09-27 08:00 | 2021-01-26 15:45 | 4199.4 | SHALLOW WATER | 4320 | 4317.31 | N/A | 53963657 | N/A | 121.3 | N/A | N/A | 14.42 | 14.41 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.9 |  | 2012 |  | 3631 | [27 empty] | Exist
2020-09-02 | 2021-02-16 | ROC OIL | SK | D21 | D21-A9 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 2581.53 | 2226.76 | N/A | N/A | N/A | N/A | 9440000 | 27.7 | NO | N/A | N/A | 2020-10-25 | 2020-10-17 16:30 | 2020-12-20 10:30 | 2462.39 | SHALLOW WATER | 2555.93 | 2205.43 | N/A | N/A | N/A | N/A | 9582016 | 28.46 | 7 | 6.88 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.77 |  | 553 |  | 1188 | [27 empty] | Exist
2020-08-09 | 2021-02-17 | ROC OIL | SK | D21 | D21-A10 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 50.59 | 2264.25 | 2206.95 | N/A | N/A | N/A | N/A | 7670000 | 21.4 | NO | N/A | N/A | 2020-10-21 04:30 | 2020-10-20 | 2020-12-15 | 2156.39 | SHALLOW WATER | 2249.92 | 2192.62 | N/A | N/A | N/A | N/A | 7093725 | 18.99 | 2.6 | 2.5 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.79 |  | 628 |  | 1107 | [27 empty] | Exist
2020-08-07 | 2020-12-17 | PCSB | SK | GAHARU | GAHARU-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 93 | 3530 | 3530 | 29605498.51 | 29605498.51 | 43.16 | 64 | N/A | N/A | NO | N/A | N/A | 2020-08-29 | 2020-08-26 04:00 | 2020-10-20 04:00 | 3407 | SHALLOW WATER | 3523 | 3521.85 | N/A | 28267950.69 | N/A | 55 | N/A | N/A | 2.51 | 1.49 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.62 |  | 1466 |  | 2234 | [27 empty] | Exist
2020-07-17 | 2020-12-11 | PCSB | SK | BARAM | BARAM-H14 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 56.69 | 1615.48 | 1032.92 | N/A | N/A | N/A | N/A | 8274511 | 17.98 | NO | N/A | N/A | 2020-09-03 | 2020-09-03 | 2020-10-09 05:00 | 1551.36 | SHALLOW WATER | 1645.84 | 1051.97 | N/A | N/A | N/A | N/A | 7613029 | 20.25 | 5.35 | 3.76 | SW DEV C1 |  | 2.2 |  | 830 |  | 1455 |  | 1.62 |  | 640.63 |  | 1461.39 | [27 empty] | Exist
2020-06-25 | 2020-10-23 | SEAH | SB | ST JOSEPH | SJ-610A | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 34.99 | 2261.96 | 755.07 | N/A | N/A | N/A | N/A | 8447985 | 24.5 | NO | N/A | DRY TREE | 2020-07-13 | 2020-07-13 08:00 | 2020-08-25 20:30 | 2084.52 | SHALLOW WATER | 2158.49 | 743.4 | N/A | N/A | N/A | N/A | 8567452 | 23.8 | 13 | 13 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.3 |  | 729 |  | 996 | [6 empty] | 3.9 | 2294568 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2054 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2020-06-25 | 2020-11-11 | SEAH | SB | ST JOSEPH | SJ-609C | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 34.75 | 1847.91 | 755.07 | N/A | N/A | N/A | N/A | 6780065 | 17.17 | NO | N/A | DRY TREE | 2020-07-26 | 2020-07-25 14:00 | 2020-09-15 12:00 | 1831.18 | SHALLOW WATER | 1904.91 | 739.41 | N/A | N/A | N/A | N/A | 6145976 | 14.4 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 1.7 |  | 657.9 |  | 983.4 | [6 empty] | 3.5 | 2031250 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1702 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2020-06-25 | 2020-10-27 | SEA HIBISCUS | SB | ST JOSEPH | SJ-609A | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 34.99 | 1608.35 | 755.09 | N/A | N/A | N/A | N/A | 8140000 | 26.57 | NO | N/A | DRY TREE | 2020-07-07 | 2020-07-06 12:00 | 2020-09-01 12:00 | 1632.83 | SHALLOW WATER | 1706.8 | 759.31 | N/A | N/A | N/A | N/A | 7577725 | 20.7 | 0.4 | 0.4 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.1 |  | 736.4 |  | 961.6 | [6 empty] | 3.1 | 1775200 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2203 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2020-06-23 | 2020-11-05 | SEAH | SB | SAINT JOSEPH | SJ-609B | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 114.8 | 5125 | 2477.5 | N/A | N/A | N/A | N/A | 6253613 | 14.58 | NO | N/A | DRY TREE | 2020-08-03 13:30 | 2020-08-02 | 2020-08-09 12:00 | 4959.3 | SHALLOW WATER | 5202 | 2482.8 | N/A | N/A | N/A | N/A | 5379411 | 12.1 | 2 | 2 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 1.7 |  | 582.9 |  | 1034 | [6 empty] | 3 | 2346102 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2437 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2020-06-16 | 2020-12-24 | PCSB | SK | BARAM | BARAM-H15 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 56.69 | 1210.85 | 1142.76 | N/A | N/A | N/A | N/A | 8682464 | 21.76 | NO | N/A | DRY TREE | 2020-08-24 | 2020-08-24 09:00 | 2020-11-24 21:00 | 1086.56 | SHALLOW WATER | 1181.04 | 1114.81 | N/A | N/A | N/A | N/A | 8572757 | 24.28 | 2.32 | 2.06 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.2 |  | 409.23 |  | 1662.35 | [6 empty] | 12.63 | 2086366.27 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 | 38 | True |  | 13CR | 9 | NACL | NO | NO | Exist
2020-06-16 | 2020-12-11 | PCSB | SK | BARAM | BARAM-H16 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 56.69 | 2598.82 | 1571.02 | N/A | N/A | N/A | N/A | 13479841 | 34.04 | SIDETRACK | N/A | DRY TREE | 2020-08-23 | 2020-08-23 07:30 | 2020-11-11 16:00 | 2370.62 | SHALLOW WATER | 2465.1 | 1584.4 | N/A | N/A | N/A | N/A | 16344099 | 48.55 | 14.83 | 14.52 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.5 |  | 353.73 |  | 1278.78 | [6 empty] | 23.71 | 4461154.1 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 6.0 | DUAL | L80 | 42 | True |  | 13CR | 9 | NACL | NO | 6 | Exist
2020-06-08 | 2021-08-13 | MUBADALA | SK | PEGAGA | PGA-06 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2356.44 | 2250.8 | N/A | N/A | N/A | N/A | 27227319 | 43.03 | NO | N/A | DRY TREE | 2021-02-08 | 2021-02-08 | 2021-06-20 14:00 | 2207.2 | SHALLOW WATER | 2356 | 2250 | N/A | N/A | N/A | N/A | 16297089 | 28.58 | 12.17 | 6.71 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 2.16 |  | 1107 |  | 2036 | [6 empty] | 8.19 | 6200000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 955 | True | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-06-01 | 2020-10-29 | PCSB | PM | BUNGA TASBIH | BUNGA TASBIH-1 (HARAPAN-1) | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 60 | 2322 | 1948 | 6220000 | 10540000 | 17.52 | 34.74 | N/A | N/A | NO | N/A | N/A | 2020-08-30 | 2020-08-21 01:15 | 2020-09-29 13:15 | 2220 | SHALLOW WATER | 2310 | 1937.17 | N/A | 11142230.14 | N/A | 47.64 | N/A | N/A | 5.21 | 4.27 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.27 |  | 586 |  | 897 | [27 empty] | Exist
2020-05-22 | 2021-01-21 | MUBADALA | SK | PEGAGA | PGA-01ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2565 | 2320 | N/A | N/A | N/A | N/A | 33360848 | 81.97 | NO | N/A | DRY TREE | 2020-07-16 | 2020-06-21 22:30 | 2020-10-28 05:00 | 2466.2 | SHALLOW WATER | 2615 | 2410.64 | N/A | N/A | N/A | N/A | 33266858 | 85.15 | 48 | 47.83 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 6.69 |  | 2861 |  | 3117 | [6 empty] | 15.92 | 7530000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1542 | True | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-05-07 | 2021-09-07 | MUBADALA | SK | PEGAGA | PGA-02ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2580 | 2303 | N/A | N/A | N/A | N/A | 25309526 | 53.07 | SUSPEND | N/A | N/A | 2020-06-25 | 2020-06-24 02:00 | 2021-07-18 19:30 | 2438.2 | SHALLOW WATER | 2587 | 2344.1 | N/A | N/A | N/A | N/A | 29170000 | 85.73 | 34.41 | 34.41 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 6.1 |  | 2801 |  | 2339 | [27 empty] | Exist
2020-04-25 | 2020-11-24 | PCSB | SK | BARONIA | BN-82ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 75.59 | 3676.93 | 3072.51 | N/A | N/A | N/A | N/A | 16541703.02 | 46.68 | NO | N/A | DRY TREE | 2020-05-15 | 2020-05-15 20:00 | 2020-10-02 12:00 | 3554.53 | SHALLOW WATER | 3678.76 | 3089.03 | N/A | N/A | N/A | N/A | 17889065.49 | 62.33 | 10.13 | 10.13 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 4 |  | 1496 |  | 2488 | [6 empty] | 17.85 | 4526250 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 3.0 | SINGLE | L80 13CR | 74 | True |  | 13CR | 12 | KCOOH | NO | NO | Exist
2020-04-17 | 2021-08-11 | MUBADALA | SK | PEGAGA | PGA-04 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2555 | 2478 | N/A | N/A | N/A | N/A | 24104199 | 48.58 | NO | N/A | DRY TREE | 2020-06-23 | 2020-06-23 04:30 | 2021-06-24 04:00 | 2331.2 | SHALLOW WATER | 2480 | 2443 | N/A | N/A | N/A | N/A | 19365111 | 39 | 10.87 | 10.6 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 3.25 |  | 1149 |  | 2394 | [6 empty] | 8.54 | 7770000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1532 | False | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-04-17 | 2021-09-01 | MUBADALA | SK | PEGAGA | PGA-07 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2990 | 2504 | N/A | N/A | N/A | N/A | 26176267 | 46.85 | NO | N/A | DRY TREE | 2020-07-13 | 2020-06-22 08:30 | 2021-07-27 12:00 | 2762.2 | SHALLOW WATER | 2911 | 2485 | N/A | N/A | N/A | N/A | 23442066 | 51.04 | 36 | 30.82 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 3.29 |  | 1587 |  | 2251 | [6 empty] | 8.29 | 6200000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1532 | True | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-04-17 | 2021-02-11 | MUBADALA | SK | PEGAGA | PGA-05 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2790 | 2545 | N/A | N/A | N/A | N/A | 22381932.8 | 45.61 | NO | N/A | DRY TREE | 2020-07-01 | 2020-06-23 14:00 | 2020-11-28 18:00 | 2542.2 | SHALLOW WATER | 2691 | 2451.8 | N/A | N/A | N/A | N/A | 18613117 | 35.29 | 11.22 | 11.22 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 2.92 |  | 1066 |  | 2041 | [6 empty] | 9.81 | 6000000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1171 | True | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-04-17 | 2021-08-09 | MUBADALA | SK | PEGAGA | PGA-03ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 108 | 2825 | 2439 | N/A | N/A | N/A | N/A | 25131785 | 51.38 | NO | N/A | DRY TREE | 2020-07-09 | 2020-06-22 19:00 | 2021-06-16 02:30 | 2608.2 | SHALLOW WATER | 2757 | 2401.12 | N/A | N/A | N/A | N/A | 31737947 | 71.69 | 35.4 | 35.4 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3580 |  | 4.63 |  | 2581 |  | 3013 | [6 empty] | 6.71 | 7010000 |  |  | CARBONATE | HPHT | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 1483 | False | NONE | SUPER 13CR | 8.33 | SEAWATER/DRILLWATER | NO | NO | Exist
2020-04-01 | 2020-07-17 | REPSOL | SB | KINABALU | KNDW-D03 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 4298.99 | 2656.2 | N/A | N/A | N/A | N/A | 15176502 | 40.79 | SIDETRACK | N/A | DRY TREE | 2020-04-10 | 2020-04-09 15:00 | 2020-05-21 06:00 | 4257.91 | SHALLOW WATER | 4354.95 | 2665.59 | N/A | N/A | N/A | N/A | 14580000 | 40.63 | 5.77 | 5.67 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.48 |  | 438.4 |  | 919 | [6 empty] | 16.58 | 7497276 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 3051 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2020-03-17 | 2020-10-14 | PCSB | SK | BAYAN | BY-415 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.69 | 2758 | 1178.2 | N/A | N/A | N/A | N/A | 10090000 | 23.03 | NO | N/A | DRY TREE | 2020-04-28 | 2020-04-27 | 2020-07-13 | 2304.49 | SHALLOW WATER | 2373.97 | 1172.04 | N/A | N/A | N/A | N/A | 6243201 | 26.13 | 4.43 | 4.43 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.95 |  | 698 |  | 802 | [27 empty] | Exist
2020-03-17 | 2020-10-06 | PCSB | SK | BAYAN | BY-417 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.69 | 2289.55 | 1165.19 | N/A | N/A | N/A | N/A | 8332549 | 20.68 | NO | N/A | DRY TREE | 2020-05-03 | 2020-05-03 | 2020-06-13 | 2399.27 | SHALLOW WATER | 2468.76 | 1184.58 | N/A | N/A | N/A | N/A | 8334277 | 29.81 | 1.85 | 1.85 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.63 |  | 808 |  | 1029 | [27 empty] | Exist
2020-03-13 | 2020-08-28 | EMEPMI | PM | TABU | TABU-B19 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 3180 | 1947 | N/A | N/A | N/A | N/A | 13700000 | 33 | NO | N/A | DRY TREE | 2020-03-30 08:00 | 2020-03-30 | 2020-07-03 | 3018.9 | SHALLOW WATER | 3116 | 1929 | N/A | N/A | N/A | N/A | 12303000 | 29.3 | 3.13 | 3.13 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1550 |  | 1.6 |  | 459 |  | 1469 | [6 empty] | 19.3 | 12737000 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 4347.325 | False | INNER STRING WITH SSD | L80 13CR | 9.3 | NACL | NO | NO | Exist
2020-03-06 | 2020-06-23 | PCSB | SK | D18 | D18-301ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2570 | 1751.2 | N/A | N/A | N/A | N/A | 10399884 | 30.7 | NO | N/A | DRY TREE | 2020-03-28 | 2020-03-28 15:00 | 2020-05-17 21:00 | 2533.8 | SHALLOW WATER | 2590 | 1806 | N/A | N/A | N/A | N/A | 11196081 | 50.25 | 3.2 | 0 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.85 |  | 1414 |  | 2687 | [6 empty] | 11.88 | 3644440.8 |  |  | SANDSTONE | NORMAL | CASED HOLE | 4 ZONES | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR |  | True | ICV | 13CR | 9.1 | NACL | NO | NO | Exist
2020-02-28 | 2020-11-24 | PCSB | SK | BARONIA | BN-84 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 75.6 | 4331.91 | 2240.48 | N/A | N/A | N/A | N/A | 16928000 | 42.58 | SUSPEND | N/A | N/A | 2020-04-21 | 2020-04-19 08:30 | 2020-09-21 18:00 | 4079.67 | SHALLOW WATER | 4199.94 | 2235.29 | N/A | N/A | N/A | N/A | 15347138.37 | 48.9 | 14.68 | 14.68 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 2.9 |  | 1090 |  | 1260 | [27 empty] | Exist
2020-02-23 | 2020-11-30 | SHELL | SK | E06 | E06-101 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 70.04 | 4555.32 | 1834.81 | N/A | N/A | N/A | N/A | 26590000 | 51.13 | NO | N/A | N/A | 2020-09-04 | 2020-06-04 16:30 | 2020-10-04 | 4439.56 | SHALLOW WATER | 4555.32 | 1834.9 | N/A | N/A | N/A | N/A | 24837987 | 72.78 | 41.74 | 41.74 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 3.6 |  | 1233 |  | 1655 | [27 empty] | Exist
2020-02-23 | 2020-11-07 | SHELL | SK | E06 | E06-102 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 70.04 | 4099.66 | 1831.76 | N/A | N/A | N/A | N/A | 30700000 | 66.41 | NO | N/A | N/A | 2020-03-26 | 2020-03-26 22:30 | 2020-09-09 21:00 | 3985.43 | SHALLOW WATER | 4101.19 | 1831.24 | N/A | N/A | N/A | N/A | 22690852 | 64.48 | 9.05 | 9.03 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1850 |  | 3 |  | 909 |  | 1357 | [27 empty] | Exist
2020-02-19 | 2020-09-22 | PCSB | SK | BAYAN | BY-416 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 29.87 | 1537.55 | 1342.18 | N/A | N/A | N/A | N/A | 7040000 | 16.31 | NO | N/A | DRY TREE | 2020-03-17 | 2020-03-08 | 2020-09-07 02:00 | 1481.38 | SHALLOW WATER | 1551.05 | 1329.34 | N/A | N/A | N/A | N/A | 8249069.96 | 23.92 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.84 |  | 583 |  | 1586 | [6 empty] | 12.23 | 4230387 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 |  | True | NONE | 9CR | 8.6 | SEAWATER/DRILLWATER | NO | 4 | Exist
2020-02-19 | 2020-09-25 | PCSB | SK | BAYAN | BY-414 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.69 | 1427.31 | 1366.35 | N/A | N/A | N/A | N/A | 6150000 | 14.29 | NO | N/A | DRY TREE | 2020-03-10 | 2020-03-08 12:00 | 2020-04-04 | 1423.96 | SHALLOW WATER | 1493.45 | 1377.11 | N/A | N/A | N/A | N/A | 7410000 | 21.92 | 4.08 | 4.08 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 2.1 |  | 589 |  | 1512 | [6 empty] | 5.31 | 2943798 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | L80 |  | True | NONE | 9CR | 8.6 | SEAWATER/DRILLWATER | NO | 3 | Exist
2020-02-18 | 2020-06-10 | VESTIGO | SK | BENTARA | BENTARA-A2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 64.8 | 3220 | 2665 | N/A | N/A | N/A | N/A | 6000000 | 16.8 | NO | N/A | DRY TREE | 2020-03-27 | 2020-03-27 | 2020-05-06 16:00 | 1690.99 | SHALLOW WATER | 1793.29 | 1769.85 | N/A | N/A | N/A | N/A | 22348372 | 66.31 | 0 | 0 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 1.03 |  | 330 |  | 573 | [6 empty] | 3.5 | 1971756.02 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 108.273 | True |  | L80 13CR | 8.6 | KCL | NO | NO | Exist
2020-02-18 | 2020-06-10 | VESTIGO | SK | BENTARA | BENTARA-A3 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 64.8 | 2720 | 2639 | N/A | N/A | N/A | N/A | 5692000 | 16.8 | NO | N/A | DRY TREE | 2020-03-24 | 2020-03-24 02:30 | 2020-05-01 15:00 | 2658.7 | SHALLOW WATER | 2761 | 2727.63 | N/A | N/A | N/A | N/A | 22348373 | 66.31 | 0.57 | 0.57 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.5 |  | 1320 |  | 2115 | [6 empty] | 4.14 | 1733026 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 27.8885 | True |  | L80 13CR | 8.6 | KCL | NO | NO | Exist
2020-02-18 | 2020-06-10 | VESTIGO | SK | BENTARA | BENTARA-A4 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 64.8 | 2755 | 2697 | N/A | N/A | N/A | N/A | 5812000 | 15.8 | NO | N/A | DRY TREE | 2020-03-29 | 2020-03-29 09:30 | 2020-05-04 19:00 | 2678.7 | SHALLOW WATER | 2781 | 2709.77 | N/A | N/A | N/A | N/A | 5589000 | 14.29 | 0 | 0 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 0.95 |  | 338 |  | 636 | [6 empty] | 4.7 | 2229555 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 32.81 | True |  | L80 13CR | 8.6 | KCL | NO | NO | Exist
2020-02-11 | 2020-07-07 | HESS | PM | BUNGA ANGGERIK | BUNGA ANGGERIK A-5(B)ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.08 | 4262.71 | 1239.73 | N/A | N/A | N/A | N/A | 14600000 | 35.98 | SIDETRACK | N/A | DRY TREE | 2020-02-26 | 2020-02-25 07:00 | 2020-05-04 11:00 | 2008.67 | SHALLOW WATER | 2105.76 | 1250.44 | N/A | N/A | N/A | N/A | 23120000 | 71.75 | 21.05 | 21.05 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 3.54 |  | 1092 |  | 1462 | [6 empty] | 7.07 | 2840000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 113.91 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2020-02-10 | 2021-01-19 | PCSB | SK | SERAWA | SERAWA-1 | EXPLORATION/APPRAISAL | NAGA-7 | JACK UP | 70 | 1576 | 1576 | 7812426 | 7812426 | 21.19 | 21.19 | N/A | N/A | NO | N/A | N/A | 2020-11-25 | 2020-11-23 | 2020-12-18 15:00 | 1446.2 | SHALLOW WATER | 1548.6 | 1548.58 | N/A | 6471964.69 | N/A | 25.63 | N/A | N/A | 12 | 4 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.23 |  | 517 |  | 687 | [27 empty] | Exist
2020-02-10 | 2020-08-04 | PCSB | SB | SAMARANG | SAMARANG-B123 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 47.55 | 4127.7 | 2838.16 | N/A | N/A | N/A | N/A | 15860627 | 51.7 | NO | N/A | DRY TREE | 2020-02-16 | 2020-02-16 03:30 | 2020-05-27 06:00 | 3962.24 | SHALLOW WATER | 4047.55 | 2706.1 | N/A | N/A | N/A | N/A | 20960228 | 73.77 | 11.13 | 11.13 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3830 |  | 3.17 |  | 944 |  | 1499 | [6 empty] | 18.56 | 5600095.54 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR | 3306 | False |  | 13CR | 8.7 | NACL | NO | NO | Exist
2020-02-07 | 2020-07-16 | EMEPMI | PM | TABU | TABU-B11 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 3229 | 2010 | N/A | N/A | N/A | N/A | 10600000 | 30 | NO | N/A | DRY TREE | 2020-04-21 | 2020-03-19 | 2020-05-18 12:00 | 2891.9 | SHALLOW WATER | 2989 | 2009 | N/A | N/A | N/A | N/A | 11275000 | 36.5 | 17.64 | 17.64 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.2 |  | 880 |  | 1455 | [6 empty] | 17.7 | 11580000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 1CR | 3451.612 | False | INNER STRING WITH SSD | 25CR | 9.3 | NACL | NO | NO | Exist
2020-02-01 | 2020-05-28 | REPSOL | SB | KINABALU | KNDW-D13 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 5484 | 3534.11 | N/A | N/A | N/A | N/A | 17370000 | 52.69 | NO | N/A | DRY TREE | 2020-02-25 08:00 | 2020-02-24 09:00 | 2020-03-27 20:15 | 5389.09 | SHALLOW WATER | 5486.13 | 3535.29 | N/A | N/A | N/A | N/A | 10022000 | 32.47 | 7.12 | 7.12 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.18 |  | 337.9 |  | 568 | [6 empty] | 10.53 | 3819057 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 3955 | True | NONE | L80 13CR | 8.9 | KCL | NO | NO | Exist
2020-01-30 | 2020-08-14 | PTTEP | SB | ROTAN | RT-P2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CARINA | DRILLSHIP | 1155.9 | 2009 | 2009 | N/A | N/A | N/A | N/A | 32854719 | 32 | NO | N/A | WET TREE | 2020-03-10 14:45 | 2020-03-10 | 2020-06-22 | 829.1 | DEEP WATER | 2009 | 2009 | N/A | N/A | N/A | N/A | 23492126 | 25.4 | 3.36 | 3.36 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 3.16 |  | 2431 |  | 5739 | [6 empty] | 18.5 | 17110406.73 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 147.645 | True |  | L80 13CR | 10.4 | NABR | 2 | NO | Exist
2020-01-30 | 2020-07-28 | PTTEP | PM | BL | BL-P1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CARINA | DRILLSHIP | 1250 | 2194 | 920 | N/A | N/A | N/A | N/A | 33359310 | 32.5 | NO | N/A | WET TREE | 2020-03-07 12:30 | 2020-03-07 | 2020-06-02 19:00 | 925 | DEEP WATER | 2199 | 2199 | N/A | N/A | N/A | N/A | 30114718 | 32.5 | 11.35 | 11.35 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 2.66 |  | 1927 |  | 8225 | [6 empty] | 22.68 | 21015440.13 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 180.0285 | True |  | L80 13CR | 10.4 | NABR | 2 | NO | Exist
2020-01-29 | 2020-08-13 | PTTEP | SB | ROTAN | RT-P3 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CARINA | DRILLSHIP | 1144 | 2009 | 2009 | N/A | N/A | N/A | N/A | 33093250 | 32 | NO | N/A | WET TREE | 2020-03-13 06:45 | 2020-03-13 | 2020-06-13 | 841 | DEEP WATER | 2009 | 2009 | N/A | N/A | N/A | N/A | 26115617 | 28.5 | 2.05 | 2.05 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 2.72 |  | 2453 |  | 6501 | [6 empty] | 17.3 | 15315260.14 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 187.017 | True |  | L80 13CR | 10.4 | NABR | 2 | NO | Exist
2020-01-21 | 2020-07-29 | PCSB | PM | DULANG | DULANG-A04 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 73 | 3700 | 1499 | N/A | N/A | N/A | N/A | 20873462.95 | 57.61 | NO | N/A | DRY TREE | N/A | 2020-01-24 08:00 | 2020-05-05 21:00 | 3489.9 | SHALLOW WATER | 3593 | 1513.29 | N/A | N/A | N/A | N/A | 25184316.9 | 78.67 | 30.49 | 16.8 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 1.75 |  | 775 |  | 2059 | [6 empty] | 34.02 | 11081315.02 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 147.645 | True | INNER STRING WITH SSD | L80 13CR | 9.1 | NACL | NO | 5 | Exist
2020-01-14 | 2020-05-27 | PCSB | PM | TINGGI | TINGGI M-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 77 | 2789 | 2442 | 6110000 | 9030000 | 28.45 | 36.44 | N/A | N/A | NO | N/A | N/A | 2020-02-26 | 2020-02-06 20:15 | 2020-03-28 12:45 | 2645 | SHALLOW WATER | 2752 | 2442.8 | N/A | 12560000 | N/A | 50.69 | N/A | N/A | 16.75 | 3.39 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.07 |  | 419 |  | 374 | [27 empty] | Exist
2020-01-14 | 2020-05-18 | SAPURA OMV | SK | REMAYONG | REMAYONG-1 | EXPLORATION/APPRAISAL | PVD-6 | JACK UP | 94.4 | 2777 | 2743 | 11555661 | 14217691 | 39.72 | 49.35 | N/A | N/A | NO | N/A | N/A | 2020-03-04 20:45 | 2020-02-29 12:30 | 2020-04-11 10:45 | 1975.8 | SHALLOW WATER | 2104.8 | 2104.15 | 10447449 | N/A | 41.93 | N/A | N/A | N/A | 5.7 | 5.7 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.33 |  | 758 |  | 1611 | [27 empty] | Exist
2020-01-09 | 2020-09-04 | PCSB | SK | BAYAN | BAYAN-221ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.5 | 2585.19 | 1371.53 | N/A | N/A | N/A | N/A | 6160000 | 18.85 | NO | N/A | DRY TREE | 2020-01-22 | 2020-01-15 20:00 | 2020-02-24 | 2544.2 | SHALLOW WATER | 2614.14 | 1384.33 | N/A | N/A | N/A | N/A | 9050000 | 34.17 | 3.93 | 3.93 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.1 |  | 580 |  | 1140 | [6 empty] | 11.64 | 2009760 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 |  | False | NONE | 9CR | 9 | KCL | NO | NO | Exist
2020-01-07 | 2020-07-29 | PCSB | SK | WEST LUTONG | WEST LUTONG-A06ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 30.48 | 2232.74 | 2164.2 | N/A | N/A | N/A | N/A | 9530502 | 28.64 | NO | N/A | DRY TREE | N/A | 2020-01-28 19:00 | 2020-05-13 12:00 | 2180.49 | SHALLOW WATER | 2234.07 | 2153.34 | N/A | N/A | N/A | N/A | 8235223.11 | 38.72 | 0.24 | 0.15 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.7 |  | 640 |  | 1555 | [6 empty] | 10.85 | 2147690 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 2-7/8" | 2.0 | SINGLE | L80 13CR | 470 | False |  | L80 13CR | 8.9 | NACL | NO | NO | Exist
2020-01-07 | N/A | PCSB | SK | WEST LUTONG | WEST LUTONG-A13ST2 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 30.48 | 2795.19 | 2368.71 | N/A | N/A | N/A | N/A | 9926255.82 | 34.07 | NO | N/A | DRY TREE | 2020-02-20 | 2020-02-14 15:30 | 2020-05-14 18:00 | 2751.05 | SHALLOW WATER | 2804.63 | 2376.47 | N/A | N/A | N/A | N/A | 8878166.84 | 38.1 | 5.2 | 0.78 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.48 |  | 465 |  | 1120 | [6 empty] | 18.19 | 2429328 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 2-7/8" | 4.0 | SINGLE | L80 13CR | 1153 | False |  | L80 13CR | 8.9 | NACL | NO | NO | Exist
2020-01-07 | 2020-06-16 | PCSB | SB | SAMARANG | SAMARANG-B122 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 47.55 | 2657.12 | 2211.43 | N/A | N/A | N/A | N/A | 11437527.82 | 34.2 | NO | N/A | DRY TREE | 2020-02-04 | 2020-02-02 18:00 | 2020-03-20 | 2590.55 | SHALLOW WATER | 2676.01 | 1987.2 | N/A | N/A | N/A | N/A | 10921263 | 40.73 | 7.41 | 7.41 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 2.48 |  | 677 |  | 1244 | [6 empty] | 17.55 | 4409038.5 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR | 1679 | False |  | 13CR | 8.7 | NACL | NO | NO | Exist
2020-01-01 | 2020-05-06 | IPC | PM | BERTAM | BERTAM A-15ST1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST TELESTO | JACK UP | 74.7 | 5329 | 1653 | N/A | N/A | N/A | N/A | 14605598 | 34.2 | NO | N/A | DRY TREE | 2020-02-13 | 2020-01-11 09:30 | 2020-03-10 07:00 | 5052.3 | SHALLOW WATER | 5180 | 1656.4 | N/A | N/A | N/A | N/A | 14610000 | 50.2 | 42.25 | 42.25 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 7.1 |  | 2592 |  | 6364 | [6 empty] | 12.9 | 4700000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 2 | 3-1/2" | 1.0 | SINGLE | L80 | 1653.5912 | True | ICD | L80 | 9.2 | BASE OIL/DIESEL | NO | NO | Exist
2019-12-26 | 2020-07-16 | PCSB | PM | SEPAT | SEPAT-A11 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 63 | 2603 | 1759 | N/A | N/A | N/A | N/A | 9951415 | 23.18 | NO | N/A | N/A | 2020-01-23 | 2020-01-23 04:00 | 2020-05-29 08:30 | 2519.4 | SHALLOW WATER | 2625 | 1772.07 | N/A | N/A | N/A | N/A | 7394283.9 | 25.75 | 11.97 | 11.97 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.29 |  | 399 |  | 858.54 | [27 empty] | Exist
2019-12-26 | 2020-07-16 | PCSB | PM | SEPAT | SEPAT-A12 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 63 | 2520 | 1711 | N/A | N/A | N/A | N/A | 9128863 | 20.83 | NO | N/A | DRY TREE | 2020-01-30 | 2020-01-26 17:00 | 2020-06-04 17:45 | 2416 | SHALLOW WATER | 2520 | 1720.83 | N/A | N/A | N/A | N/A | 6697621 | 25.97 | 7.58 | 7.58 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.03 |  | 495 |  | 813.03 | [6 empty] | 5.13 | 1959544.44 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | SINGLE | GRE | 302 | False | NONE | 25CR | 8.6 | NACL | NO | NO | Exist
2019-12-26 | 2020-07-31 | PCSB | PM | DULANG | DULANG-A17ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 23.38 | 666.26 | 414.2 | N/A | N/A | N/A | N/A | 13865103.16 | 35.82 | NO | N/A | DRY TREE | 2020-01-08 | 2020-01-08 | 2020-05-31 12:00 | 664.94 | SHALLOW WATER | 696.43 | 435.55 | N/A | N/A | N/A | N/A | 12904866.08 | 40.88 | 28.49 | 28.49 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.57 |  | 654 |  | 2352 | [6 empty] | 24.54 | 7811962.57 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 269.042 | True | INNER STRING WITH SSD | L80 13CR | 8.5 | NACL | NO | 2 | Exist
2019-12-19 | 2020-09-22 | EMEPMI | PM | TABU | TABU-B08ST2 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 4000 | 1649 | N/A | N/A | N/A | N/A | 14000000 | 38 | NO | N/A | DRY TREE | 2020-03-14 | 2020-03-14 15:30 | 2020-08-01 | 4147.9 | SHALLOW WATER | 4245 | 1647 | N/A | N/A | N/A | N/A | 14388000 | 45.1 | 3.51 | 3.51 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.7 |  | 613 |  | 1085 | [6 empty] | 18.3 | 7621000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 6447.165 | False | AICD | L80 13CR | 9.3 | NACL | NO | NO | Exist
2019-12-19 | 2020-08-05 | EMEPMI | PM | TABU | TABU-B23 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 5700 | 1654.3 | N/A | N/A | N/A | N/A | 8500000 | 23 | NO | N/A | DRY TREE | 2020-05-22 17:00 | 2020-05-18 | 2020-06-08 | 3923.9 | SHALLOW WATER | 4021 | 1479 | N/A | N/A | N/A | N/A | 7405000 | 21 | 7.14 | 6.75 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 2.3 |  | 748 |  | 1478 | [6 empty] | 12.3 | 8557000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2861.032 | False | AICD | L80 13CR | 9.3 | NACL | NO | NO | Exist
2019-12-15 | 2020-04-27 | VESTIGO | PM | TEMBIKAI | TBK-A3ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.7 | 2060 | 1454 | N/A | N/A | N/A | N/A | 4355166 | 11.3 | SIDETRACK | N/A | DRY TREE | 2020-02-16 | 2020-02-02 11:00 | 2020-03-04 01:45 | 2646.8 | SHALLOW WATER | 2760 | 1794.64 | N/A | N/A | N/A | N/A | 8597395 | 17.65 | 39.31 | 39.31 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 2.2 |  | 880 |  | 1235 | [6 empty] | 0.69 | 718082.23 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 39.372 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-12-05 | 2020-04-07 | VESTIGO | PM | TEMBIKAI | TBK-A5 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.7 | 2033 | 1848 | N/A | N/A | N/A | N/A | 3394452 | 7.7 | NO | N/A | DRY TREE | 2020-01-30 | 2020-01-30 09:30 | 2020-02-16 06:00 | 1924.8 | SHALLOW WATER | 2038 | 1849.43 | N/A | N/A | N/A | N/A | 2792625 | 6.77 | 5.08 | 5.08 | SW DEV C1 |  | 2.1 |  | 700 |  | 555 |  | 0.95 |  | 355 |  | 442 | [6 empty] | 0.76 | 552528 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 19.686 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-12-05 | 2020-04-07 | VESTIGO | PM | TEMBIKAI | TBK-A1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.7 | 2433 | 1789 | N/A | N/A | N/A | N/A | 4096851 | 11.1 | SIDETRACK | N/A | DRY TREE | 2020-02-06 | 2020-02-06 11:15 | 2020-02-23 12:45 | 2428.8 | SHALLOW WATER | 2542 | 1812.71 | N/A | N/A | N/A | N/A | 3474337 | 9.26 | 0 | 0 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1000 |  | 2.2 |  | 880 |  | 436 | [6 empty] | 5.61 | 3284901 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 45.934 | True |  | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-12-05 | 2020-04-27 | VESTIGO | PM | TEMBIKAI | TBK-A3 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.7 | 2779 | 1810 | N/A | N/A | N/A | N/A | 4355166 | 11.3 | NO | N/A | DRY TREE | 2020-02-16 | 2020-02-02 11:00 | 2020-04-03 01:45 | 2646.8 | SHALLOW WATER | 2760 | 1794.64 | N/A | N/A | N/A | N/A | 16704367 | 41.48 | 16.75 | 16.75 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 1.22 |  | 677 |  | 865 | [6 empty] | 7.5 | 3892649 |  |  |  | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 120.7408 | True |  | L80 13CR | 9 | KCL | NO | NO | Exist
2019-12-05 | 2020-04-07 | VESTIGO | PM | TEMBIKAI | TBK-A1ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.7 | 2433 | 1789 | N/A | N/A | N/A | N/A | 14609385 | 37.6 | NO | N/A | DRY TREE | 2020-01-30 | 2020-01-25 17:00 | 2020-03-07 04:30 | 2428.8 | SHALLOW WATER | 2542 | 1812.71 | N/A | N/A | N/A | N/A | 16704367 | 41.48 | 0 | 0 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 0.91 |  | 301 |  | 436 | [6 empty] | 0.77 | 605861.1 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 65.62 | False |  | L80 | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-12-03 | 2020-05-22 | HESS | PM | BUNGA ANGGERIK | BUNGA ANGGERIK A-4(C) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.08 | 3476.93 | 1257.39 | N/A | N/A | N/A | N/A | 13900000 | 30.3 | NO | N/A | DRY TREE | 2019-12-20 | 2019-12-20 03:00 | 2020-03-04 | 3395.75 | SHALLOW WATER | 3492.84 | 1252.65 | N/A | N/A | N/A | N/A | 12690000 | 33.81 | 0.6 | 0.6 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 0.83 |  | 766 |  | 1140 | [6 empty] | 11.69 | 5714285.71 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1291.33 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-12-03 | 2020-04-01 | HESS | PM | BUNGA ANGGERIK | BUNGA ANGGERIK A-3(E) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.08 | 3754.04 | 1323.93 | N/A | N/A | N/A | N/A | 15880000 | 39.05 | NO | N/A | DRY TREE | 2019-12-23 | 2019-12-22 18:00 | 2020-02-06 | 3656.95 | SHALLOW WATER | 3754.04 | 1323.93 | N/A | N/A | N/A | N/A | 12750000 | 33.35 | 1.3 | 1.3 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.8 |  | 1560 |  | 1245 | [6 empty] | 9.35 | 3840000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 987.79 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-12-01 | 2020-04-13 | REPSOL | SB | KINABALU | KNDW-D15 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 2429.75 | 2305.09 | N/A | N/A | N/A | N/A | 7370000 | 19.39 | NO | N/A | DRY TREE | 2020-01-06 | 2020-01-06 | 2020-01-19 05:30 | 2293.39 | SHALLOW WATER | 2390.43 | 2265.77 | N/A | N/A | N/A | N/A | 6170000 | 13.23 | 2.83 | 2.83 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 0.9 |  | 293.3 |  | 371 | [6 empty] | 3.96 | 1999965 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 77.5 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-11-25 | 2020-04-29 | SAPURA OMV | SK | KESIDANG | KESIDANG-2 | EXPLORATION/APPRAISAL | PVD-6 | JACK UP | 88.1 | 2410 | 2376 | 10448000 | 12921000 | 29.26 | 38.19 | N/A | N/A | NO | N/A | N/A | 2020-01-15 16:00 | 2020-01-11 14:15 | 2020-02-29 12:30 | 1358.85 | SHALLOW WATER | 1481 | 1480.76 | N/A | 12650811.47 | N/A | 48.93 | N/A | N/A | 50.28 | 28.85 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 6.41 |  | 1926.33 |  | 2837.53 | [27 empty] | Exist
2019-11-25 | 2020-07-14 | PCSB | SK | LALA | LALA-1 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 1575 | 4325 | 4325 | 47500000 | 47500000 | 83.7 | 83.7 | N/A | N/A | RE-SPUD | N/A | N/A | 2019-12-23 | 2019-12-21 11:00 | 2020-05-14 09:30 | 2450 | DEEP WATER | 4050 | 4043.38 | N/A | 35897607 | N/A | 76.75 | N/A | N/A | 8.46 | 8.46 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 7.73 |  | 3607 |  | 4341 | [27 empty] | Exist
2019-11-25 | 2020-03-12 | VESTIGO | PM | IRONG | IRONG-7 | EXPLORATION/APPRAISAL | BORR MIST | JACK UP | 65.5 | 2245 | 2245 | 6471178 | 6471178 | 18.3 | 18.3 | N/A | N/A | SIDETRACK | N/A | N/A | 2020-01-13 | 2019-12-25 21:30 | 2020-01-25 17:00 | 1675.5 | SHALLOW WATER | 1771 | 1240.9 | N/A | 6915062 | N/A | 30.2 | N/A | N/A | 53.5 | 53.5 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 0.53 |  | 200 |  | 605 | [27 empty] | Exist
2019-11-20 | 2020-03-02 | PCSB | SB | SAMARANG | SM-B59ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 47.55 | 1847.3 | 1737.88 | N/A | N/A | N/A | N/A | 9439000 | 33.35 | NO | N/A | DRY TREE | 2019-12-19 | 2019-12-17 | 2020-01-27 15:00 | 1909.57 | SHALLOW WATER | 1987.2 | 1823.96 | N/A | N/A | N/A | N/A | 8860248 | 39.63 | 3.33 | 3.33 | SW DEV C1 |  | 1.7 |  | 720 |  | 1345 |  | 1.51 |  | 816 |  | 3297 | [6 empty] | 13 | 3314764.69 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 | 1046 | False |  | 9CR | 8.7 | NACL | NO | NO | Exist
2019-11-15 | 2020-05-11 | SHELL | SK | GOREK | GRK-101 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 88.76 | 3222.8 | 2283.45 | N/A | N/A | N/A | N/A | 21690000 | 52.6 | NO | N/A | N/A | 2020-02-28 | 2020-01-21 | 2020-03-16 18:00 | 2976.77 | SHALLOW WATER | 3110.03 | 2282.97 | N/A | N/A | N/A | N/A | 17829621 | 40.25 | 12.5 | 12.5 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.65 |  | 606 |  | 1092 | [27 empty] | Exist
2019-11-15 | 2020-05-11 | SHELL | SK | GOREK | GOREK-104 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 88.76 | 3976.23 | 2342.58 | N/A | N/A | N/A | N/A | 20511503 | 48.02 | NO | N/A | N/A | 2020-01-26 | 2020-01-25 03:15 | 2020-03-23 18:00 | 3536.36 | SHALLOW WATER | 3669.61 | 2339.58 | N/A | N/A | N/A | N/A | 14281757 | 39.2 | 9.6 | 9.6 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.48 |  | 478 |  | 1031 | [27 empty] | Exist
2019-11-14 | 2020-03-26 | PCSB | SK | ARAPAIMA | ARAPAIMA-1 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 1582 | 3725 | 3725 | 31500000 | 40400000 | 43 | 65.4 | N/A | N/A | NO | N/A | N/A | 2020-01-10 | 2020-01-09 15:00 | 2020-02-27 21:30 | 2118 | DEEP WATER | 3725 | 3724.96 | N/A | 30040818.88 | N/A | 49.27 | N/A | N/A | 18.94 | 18.94 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 3.14 |  | 2186 |  | 3467 | [27 empty] | Exist
2019-11-12 | 2020-06-02 | ROC OIL | SK | D35 | D35B-214ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 3306.31 | 1968.61 | N/A | N/A | N/A | N/A | 12540000 | 43.7 | NO | N/A | N/A | 2019-12-15 | 2019-12-03 10:00 | 2020-04-09 06:00 | 3306.31 | SHALLOW WATER | 3393.78 | 2013.72 | N/A | N/A | N/A | N/A | 15235528 | 50.8 | 1.21 | 1.21 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.4 |  | 422 |  | 1517 | [27 empty] | Exist
2019-11-12 | 2020-06-05 | PCSB | PM | DULANG | DULANG-A23ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 1689 | 1486 | N/A | N/A | N/A | N/A | 13566845.98 | 39.04 | NO | N/A | N/A | N/A | 2019-11-14 | 2020-03-30 22:00 | 1568.2 | SHALLOW WATER | 1675 | 1476.44 | N/A | N/A | N/A | N/A | 11004029.14 | 36.92 | 7.2 | 7.2 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.72 |  | 463 |  | 2965 | [27 empty] | Exist
2019-11-11 | 2020-09-04 | PCSB | SK | BAYAN | BAYAN-B225 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.5 | 2711.67 | 1375.19 | N/A | N/A | N/A | N/A | 8800000 | 22.46 | NO | N/A | DRY TREE | 2019-11-12 | 2019-11-12 | 2020-02-09 | 2715.79 | SHALLOW WATER | 2785.74 | 1418.77 | N/A | N/A | N/A | N/A | 6670000 | 22.68 | 4.82 | 4.82 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.31 |  | 444 |  | 986 | [6 empty] | 2.13 | 914304.63 |  |  | SANDSTONE | NORMAL | CASED HOLE | 2 ZONES | NO | 3-1/2" | 1.0 | SINGLE | L80 |  | True | NONE | 9CR | 8.6 | KCL | NO | 4 | Exist
2019-11-07 | 2020-06-18 | PCSB | PM | DULANG | DULANG-A33ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 1886.46 | 1419.45 | N/A | N/A | N/A | N/A | 8017304.09 | 22.62 | SIDETRACK | N/A | DRY TREE | N/A | 2019-12-01 21:00 | 2020-04-04 | 1847.3 | SHALLOW WATER | 1954.1 | 1527.07 | N/A | N/A | N/A | N/A | 4061575.47 | 10.83 | 0 | 0 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 0.83 |  | 375 |  | 1215 | [6 empty] | 3.96 | 1333811.48 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | GRE | 32.81 | False | NONE | 25CR | 8.5 | NACL | NO | NO | Exist
2019-11-07 | N/A | PCSB | SK | WEST LUTONG | WEST LUTONG-A08ST3 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 30.48 | 2484.91 | 2252.36 | N/A | N/A | N/A | N/A | 12121930 | 51.34 | NO | N/A | DRY TREE | 2020-02-09 | 2020-01-29 21:45 | 2020-06-24 10:30 | 2450.47 | SHALLOW WATER | 2505.33 | 2265.86 | N/A | N/A | N/A | N/A | 14763796 | 70.82 | 7.5 | 7 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 1.35 |  | 397 |  | 2101 | [6 empty] | 47.19 | 7052760 |  |  | SANDSTONE | NORMAL | CASED HOLE SAND CONSOLIDATION | NO | NO | 2-7/8" | 4.0 | DUAL | L80 13CR | 3258 | False |  | L80 13CR | 9.1 | NACL | NO | NO | Exist
2019-11-07 | 2020-04-06 | PCSB | SK | KELAPA BALI | KELAPA BALI-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 44 | 3692 | 3692 | 25404464 | 27235254 | 63.8 | 75.2 | N/A | N/A | NO | N/A | N/A | 2019-11-21 | 2019-11-12 16:15 | 2020-02-06 20:15 | 3629 | SHALLOW WATER | 3705 | 3703.6 | 31054332.44 | N/A | 86.16 | N/A | N/A | N/A | 8.36 | 6.15 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.7 |  | 1958 |  | 2398 | [27 empty] | Exist
2019-11-01 | N/A | PCSB | PM | SEPAT | SEPAT-9 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 63 | 2029 | 1730 | N/A | N/A | N/A | N/A | 9002914 | 26.1 | NO | N/A | DRY TREE | 2019-11-17 | 2019-11-16 15:00 | 2020-07-01 19:00 | 1913.15 | SHALLOW WATER | 2013 | 1718.66 | N/A | N/A | N/A | N/A | 9206722 | 34.29 | 9.88 | 2.8 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.75 |  | 729 |  | 1235 | [6 empty] | 8.42 | 2268143.8 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 367.5 | True | NONE | 13CR | 9 | NACL | 1 | NO | Exist
2019-11-01 | 2020-04-13 | REPSOL | SB | KINABALU | KNDW-D10 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 4489.48 | 3618.1 | N/A | N/A | N/A | N/A | 13019618 | 38.29 | NO | N/A | DRY TREE | 2019-12-12 | 2019-12-11 03:45 | 2020-01-05 05:00 | 4392.44 | SHALLOW WATER | 4489.48 | 3624.2 | N/A | N/A | N/A | N/A | 11550000 | 37.66 | 0.33 | 0.33 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.1 |  | 313 |  | 784 | [6 empty] | 10.98 | 4181143 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 160 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-11-01 | 2020-02-20 | REPSOL | SB | KINABALU | KNDW-D17 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 3517.22 | 3352.94 | N/A | N/A | N/A | N/A | 9520000 | 27.39 | SIDETRACK | N/A | DRY TREE | 2019-11-15 | 2019-11-14 12:00 | 2019-12-11 03:45 | 3407.99 | SHALLOW WATER | 3505.03 | 3341.05 | N/A | N/A | N/A | N/A | 8980000 | 26.24 | 0.16 | 0.16 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.1 |  | 326 |  | 621 | [6 empty] | 3.91 | 2007228 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 90 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-11-01 | 2020-03-06 | PCSB | PM | SEPAT | SEPAT-10 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 63 | 1797.92 | 1710 | N/A | N/A | N/A | N/A | 9018369 | 25.72 | NO | N/A | DRY TREE | 2019-11-16 04:00 | 2019-11-13 | 2020-01-15 12:00 | 1698.07 | SHALLOW WATER | 1797.92 | 1710 | N/A | N/A | N/A | N/A | 8364619 | 26.04 | 5.18 | 5.18 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 3.07 |  | 802 |  | 1508 | [6 empty] | 7.24 | 2166027.12 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 193.6 | True | NONE | 13CR | 9 | NACL | 1 | NO | Exist
2019-10-31 | 2020-04-09 | PCSB | SK | D18 | D18-403 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2034.13 | 1348 | N/A | N/A | N/A | N/A | 9918798 | 26.64 | NO | N/A | DRY TREE | N/A | 2019-11-09 06:00 | 2020-03-14 | 2157.8 | SHALLOW WATER | 2214 | 1678 | N/A | N/A | N/A | N/A | 12336152 | 32.21 | 2.94 | 2.94 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 3.33 |  | 979 |  | 1698 | [6 empty] | 8.46 | 5221378 |  |  | SANDSTONE | NORMAL | CASED HOLE | 4 ZONES | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR |  | True | ICV | 13CR | 9.3 | NACL | 1 | NO | Exist
2019-10-31 | 2020-09-04 | PCSB | SK | BAYAN | BAYAN-B224 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 29.5 | 2514.48 | 1239.26 | N/A | N/A | N/A | N/A | 8890000 | 23.04 | NO | N/A | DRY TREE | 2019-12-09 | 2019-12-09 17:15 | 2020-01-04 15:00 | 2395.77 | SHALLOW WATER | 2465.71 | 1418.77 | N/A | N/A | N/A | N/A | 6105013 | 19 | 0.27 | 0.27 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.73 |  | 454 |  | 755 | [6 empty] | 1.65 | 1804070 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 |  | False | NONE | 9CR | 8.6 | KCL | NO | 3 | Exist
2019-10-31 | 2020-04-09 | PCSB | SK | D18 | D18-404 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 1998 | 1828 | N/A | N/A | N/A | N/A | 8776585 | 26 | NO | N/A | DRY TREE | 2019-11-06 | 2019-11-04 09:00 | 2020-01-14 18:00 | 1794.8 | SHALLOW WATER | 1851 | 1058 | N/A | N/A | N/A | N/A | 9713206 | 26.33 | 19 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 3.05 |  | 727 |  | 1599 | [6 empty] | 7.79 | 5300244.9 |  |  | SANDSTONE | NORMAL | CASED HOLE | 4 ZONES | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR |  | True | ICV | 13CR | 9.4 | NACL | 1 | NO | Exist
2019-10-31 | 2020-04-09 | PCSB | SK | D18 | D18-402 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2151 | 1858 | N/A | N/A | N/A | N/A | 10890564 | 24.71 | NO | N/A | DRY TREE | 2019-11-16 | 2019-11-15 18:00 | 2020-02-20 | 2193.8 | SHALLOW WATER | 2250 | 2250 | N/A | N/A | N/A | N/A | 10899280 | 31.67 | 1 | 1 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.19 |  | 700 |  | 1260 | [6 empty] | 8.67 | 4132800 |  |  | SANDSTONE | NORMAL | CASED HOLE | 5 ZONES | NO | 3-1/2" | 5.0 | SINGLE | L80 13CR |  | True | ICV | 13CR | 9.4 | NACL | 1 | NO | Exist
2019-10-31 | 2020-04-09 | PCSB | SK | D18 | D18 401 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2150 | 1346 | N/A | N/A | N/A | N/A | 9944992 | 25 | NO | N/A | N/A | N/A | 2019-11-12 18:00 | 2019-12-27 06:00 | 2193.8 | SHALLOW WATER | 2250 | 1343 | N/A | N/A | N/A | N/A | 9777597 | 31.67 | 19 | 19 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.84 |  | 695 |  | 1324 | [27 empty] | Exist
2019-10-17 | 2020-04-13 | REPSOL | SB | KINABALU | KNDW-D09 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 2711.37 | 1959.71 | N/A | N/A | N/A | N/A | 8640000 | 23.43 | NO | N/A | DRY TREE | 2019-10-28 | 2019-10-28 | 2019-11-14 | 2614.63 | SHALLOW WATER | 2711.67 | 1959.46 | N/A | N/A | N/A | N/A | 8190000 | 18.42 | 5.15 | 5.15 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.45 |  | 631.4 |  | 920 | [6 empty] | 5.5 | 2570056 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 76 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-10-16 | 2020-01-21 | HESS | PM | BUNGA ANGGERIK | BUNGA ANGGERIK A-1(D) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.08 | 2211.76 | 1348.67 | N/A | N/A | N/A | N/A | 8310000 | 19.41 | NO | N/A | DRY TREE | 2019-11-01 | 2019-10-29 18:00 | 2020-01-04 | 2109.56 | SHALLOW WATER | 2206.64 | 1344.09 | N/A | N/A | N/A | N/A | 10670000 | 26.69 | 0.08 | 0.08 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.52 |  | 918 |  | 1596 | [6 empty] | 13.48 | 4360000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 267.26 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-10-16 | 2020-01-23 | HESS | PM | BUNGA ANGGERIK | BUNGA ANGGERIK A-2(A) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.08 | 2416.89 | 1257.39 | N/A | N/A | N/A | N/A | 8520000 | 19.6 | NO | N/A | DRY TREE | 2019-10-30 | 2019-10-29 03:00 | 2020-01-07 | 2177.52 | SHALLOW WATER | 2274.61 | 1248.82 | N/A | N/A | N/A | N/A | 10390000 | 24.67 | 1.1 | 1.1 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.68 |  | 1098 |  | 1505 | [6 empty] | 7.65 | 3180000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 417.68 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-10-11 | 2020-01-06 | SEAH | SB | SOUTH FURIOUS | SF30-13 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 17.68 | 2288.94 | 985.68 | N/A | N/A | N/A | N/A | 8770664 | 25.65 | NO | N/A | DRY TREE | 2019-10-22 | 2019-10-21 06:00 | 2019-12-11 13:00 | 2231.79 | SHALLOW WATER | 2288.94 | 985.68 | N/A | N/A | N/A | N/A | 6936881 | 22.29 | 5 | 5 | SW DEV C1 |  | 1.7 |  | 720 |  | 1345 |  | 1.64 |  | 435.95 |  | 923.69 | [6 empty] | 8.29 | 3662866.57 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | DUAL | L80 | 2287 | True | NONE | L80 | 9.4 | KCL | NO | NO | Exist
2019-10-04 | 2020-03-05 | PCSB | SB | SAMARANG | SAMARANG-C110 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 10.06 | 1663.82 | 1393.17 | N/A | N/A | N/A | N/A | 9513699.73 | 26.93 | NO | N/A | DRY TREE | 2019-10-10 | 2019-10-09 15:00 | 2019-11-07 19:00 | 1610.48 | SHALLOW WATER | 1661.38 | 1404.88 | N/A | N/A | N/A | N/A | 9041177 | 29.17 | 2.57 | 2.14 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 2.15 |  | 671 |  | 1757 | [6 empty] | 11.44 | 4320613.12 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 2385 | False |  | 13CR | 8.7 | NACL | NO | NO | Exist
2019-10-01 | 2020-05-21 | ROC OIL | SK | D35 | D35-215ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 3035.05 | 1688.2 | N/A | N/A | N/A | N/A | 11054198 | 29.2 | NO | N/A | N/A | 2020-02-23 | 2020-02-23 06:00 | 2020-03-25 03:00 | 3134.41 | SHALLOW WATER | 3221.58 | 1710.76 | N/A | N/A | N/A | N/A | 11219956 | 30.9 | 0.43 | 0.43 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.5 |  | 512 |  | 834 | [27 empty] | Exist
2019-10-01 | 2020-04-21 | ROC OIL | SK | D35 | D35B-221 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 2999.7 | 1962.51 | N/A | N/A | N/A | N/A | 10064243 | 28.4 | NO | N/A | N/A | 2019-11-09 | 2019-11-09 | 2020-02-23 06:00 | 2811.34 | SHALLOW WATER | 2898.51 | 1965.56 | N/A | N/A | N/A | N/A | 9921888.18 | 34.2 | 9.45 | 9.45 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.9 |  | 556 |  | 1023 | [27 empty] | Exist
2019-09-30 | 2020-04-06 | ROC OIL | SK | D35 | D35B-219ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 3884.79 | 2200.24 | N/A | N/A | N/A | N/A | 13191510 | 40.9 | NO | N/A | N/A | 2020-01-15 | 2020-01-04 08:00 | 2020-02-09 18:00 | 3963.12 | SHALLOW WATER | 4050.59 | 2287.41 | N/A | N/A | N/A | N/A | 12118044 | 36.42 | 0.2 | 0.2 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.48 |  | 553 |  | 1427 | [27 empty] | Exist
2019-09-27 | 2020-03-06 | PCSB | SK | WEST LUTONG | WEST LUTONG-A15ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 30.48 | 3236.3 | 2743.07 | N/A | N/A | N/A | N/A | 17531147.27 | 55.24 | NO | N/A | DRY TREE | 2019-11-22 | 2019-11-22 | 2020-01-28 19:00 | 3209.11 | SHALLOW WATER | 3262.72 | 2766.14 | N/A | N/A | N/A | N/A | 17235514.83 | 64.78 | 7 | 3 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 2.48 |  | 702 |  | 1676 | [6 empty] | 25.17 | 6455115 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 2-7/8" | 6.0 | DUAL | L80 13CR | 3750 | False |  | L80 13CR | 9.3 | NACL | NO | NO | Exist
2019-09-24 | 2020-02-20 | PCSB | PM | DULANG | DULANG-A11ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 2185 | 1301 | N/A | N/A | N/A | N/A | 10500380.18 | 27.73 | NO | N/A | DRY TREE | 2019-10-31 | 2019-10-21 | 2019-12-01 21:00 | 2078.2 | SHALLOW WATER | 2185 | 1302 | N/A | N/A | N/A | N/A | 11213319.67 | 35.13 | 32.47 | 29.69 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.91 |  | 985 |  | 2984 | [6 empty] | 10.63 | 4036138.56 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 164.05 | False | NONE | L80 13CR | 8.5 | NACL | NO | NO | Exist
2019-09-20 | 2020-07-16 | PCSB | PM | SEPAT | SEPAT-A08ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 63 | 4040 | 1668.86 | N/A | N/A | N/A | N/A | 14080421 | 44.75 | NO | N/A | DRY TREE | 2020-02-02 | 2019-12-28 | 2020-04-24 10:00 | 3981.4 | SHALLOW WATER | 4087 | 1680.09 | N/A | N/A | N/A | N/A | 21643512 | 108.02 | 39.94 | 39.94 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.86 |  | 526 |  | 1609.4 | [6 empty] | 13.54 | 3553503.46 |  |  | SANDSTONE | NPNT | CASED HOLE | NO | NO | 2-7/8" | 2.0 | SINGLE | L80 13CR | 193.579 | True | NONE | L80 13CR | 9 | NACL | 1 | NO | Exist
2019-09-19 | 2020-01-22 | VESTIGO | PM | JITANG | JTG-A2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 2201.26 | 1481.15 | N/A | N/A | N/A | N/A | 28190000 | 69.55 | NO | N/A | DRY TREE | 2019-11-01 | 2019-10-24 15:15 | 2019-11-29 07:00 | 2096.03 | SHALLOW WATER | 2209 | 1484 | N/A | N/A | N/A | N/A | 21548749 | 62.26 | 0.55 | 0.52 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 0.8 |  | 351 |  | 566 | [6 empty] | 4.08 | 1479948.55 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 729.5599 | False |  | L80 | 8.6 | KCL | NO | NO | Exist
2019-09-19 | 2020-01-22 | VESTIGO | PM | JITANG | JTG-A1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 2481 | 1483 | N/A | N/A | N/A | N/A | 5940000 | 12.7 | NO | N/A | DRY TREE | 2019-10-27 | 2019-10-27 16:30 | 2019-11-23 11:15 | 2103.03 | SHALLOW WATER | 2216 | 1483.29 | N/A | N/A | N/A | N/A | 5071547 | 14.03 | 13.29 | 13.29 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.4 |  | 491 |  | 735 | [6 empty] | 4.68 | 1682372.22 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 686.4607 | False |  | L80 | 8.6 | KCL | NO | NO | Exist
2019-09-19 | 2020-01-22 | VESTIGO | PM | JITANG | JTG-A3 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 2197.4 | 1482 | N/A | N/A | N/A | N/A | 5950000 | 9.38 | NO | N/A | DRY TREE | 2019-10-30 | 2019-10-27 19:10 | 2019-12-10 08:00 | 2284.03 | SHALLOW WATER | 2397 | 1483 | N/A | N/A | N/A | N/A | 3885038 | 9.38 | 0 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 0.8 |  | 343 |  | 518 | [6 empty] | 3.64 | 1318008.36 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 513.2698 | False |  | L80 | 8.6 | KCL | NO | NO | Exist
2019-09-19 | 2020-01-22 | VESTIGO | PM | JITANG | JTG-A4 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 2981 | 1487 | N/A | N/A | N/A | N/A | 6400000 | 15.08 | NO | N/A | DRY TREE | 2019-11-01 | 2019-11-01 | 2019-12-05 08:15 | 2791.03 | SHALLOW WATER | 2904 | 1487 | N/A | N/A | N/A | N/A | 4233250 | 10.91 | 2.86 | 2.86 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 0.8 |  | 311 |  | 462 | [6 empty] | 3.96 | 1387402.7 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 1373.2593 | False |  | L80 | 8.6 | KCL | NO | NO | Exist
2019-09-01 | 2020-01-06 | SEAH | SB | SOUTH FURIOUS | SF30-6 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 17.68 | 935.08 | 901.86 | N/A | N/A | N/A | N/A | 1536657 | 25.04 | NO | N/A | DRY TREE | 2019-09-15 | 2019-09-15 02:00 | 2019-11-23 13:00 | 882.51 | SHALLOW WATER | 939.65 | 905.52 | N/A | N/A | N/A | N/A | 6750000 | 23.81 | 4 | 4 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.22 |  | 735.4 |  | 1074.6 | [6 empty] | 3.96 | 1766025.87 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 500 | True | NONE | L80 | 9.4 | KCL | NO | NO | Exist
2019-08-29 | 2019-11-20 | PCSB | SK | TEMANA | TE-82 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 29 | 2348 | 1096 | N/A | N/A | N/A | N/A | 13878912 | 42.34 | NO | N/A | DRY TREE | 2019-09-23 | 2019-09-20 18:30 | 2019-10-26 | 2434 | SHALLOW WATER | 2500 | 1246.16 | N/A | N/A | N/A | N/A | 10790469.64 | 35.23 | 2.37 | 1.85 | SW DEV C2 |  | 2 |  | 725 |  | 1725 |  | 1.72 |  | 529 |  | 1352 | [6 empty] | 17.53 | 4298110 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | DUAL | L80 | 228 | False |  | 9CR | 9.7 | NACL | NO | NO | Exist
2019-08-29 | 2020-02-17 | PCSB | SB | NURI | NURI-1 | EXPLORATION/APPRAISAL | WEST CAPELLA | DRILLSHIP | 2677 | 5336 | 5060 | 38832218 | 39332591 | 64.54 | 66.17 | N/A | N/A | NO | N/A | N/A | 2019-09-19 | 2019-09-17 10:00 | 2019-12-21 11:00 | 2734 | DEEP WATER | 5436 | 5150 | N/A | 54003472.18 | N/A | 95.4 | N/A | N/A | 10.9 | 10.9 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 8.24 |  | 4374 |  | 5775 | [27 empty] | Exist
2019-08-28 | 2020-05-05 | PCSB | SK | TUKAU TIMUR | TT-A7 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 4373.97 | 4046.02 | N/A | N/A | N/A | N/A | 22267510 | 58.6 | NO | N/A | DRY TREE | 2019-09-23 | 2019-09-22 23:00 | 2020-03-13 22:00 | 4271.11 | SHALLOW WATER | 4358.43 | 4030.63 | N/A | N/A | N/A | N/A | 17294104 | 54.08 | 3.81 | 3.76 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 1.84 |  | 621 |  | 1234 | [6 empty] | 17.15 | 5834400 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 5.0 | SINGLE | L80 13CR | 2332 | True |  | L80 13CR | 9.9 | NACOOH | NO | NO | Exist
2019-08-28 | 2020-05-05 | PCSB | SK | TUKAU TIMUR | TUKAU TIMUR-A4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 5533.37 | 4122.83 | N/A | N/A | N/A | N/A | 25437820.51 | 70.8 | NO | N/A | DRY TREE | 2019-09-28 | 2019-09-27 15:00 | 2020-03-11 | 5430.05 | SHALLOW WATER | 5517.22 | 4112.47 | N/A | N/A | N/A | N/A | 21513213 | 64.64 | 13.51 | 13.51 | SW DEV C1 |  | 2.2 |  | 830 |  | 1455 |  | 1.49 |  | 558 |  | 1208 | [6 empty] | 17.05 | 7204596 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 5.0 | SINGLE | L80 13CR | 3968 | True |  | L80 13CR | 9.2 | NACOOH | NO | NO | Exist
2019-08-26 | 2019-12-24 | PCSB | SK | TUKAU TIMUR | TT-A1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 5029.87 | 3805.85 | N/A | N/A | N/A | N/A | 24508007 | 63.09 | NO | N/A | DRY TREE | 2019-10-01 | 2019-10-01 | 2019-11-24 | 4981.87 | SHALLOW WATER | 5069.19 | 3836.6 | N/A | N/A | N/A | N/A | 18253395 | 53.98 | 8.22 | 8.14 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.07 |  | 645 |  | 1097 | [6 empty] | 13.02 | 5106024 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 5.0 | SINGLE | L80 13CR | 2919 | False |  | L80 13CR | 10.2 | NACOOH | NO | NO | Exist
2019-08-16 | 2020-03-05 | PCSB | SB | SAMARANG | SAMARANG-C23S2 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 10.06 | 1606.22 | 1308.44 | N/A | N/A | N/A | N/A | 6935672 | 25.8 | NO | N/A | N/A | 2019-09-24 | 2019-09-24 12:00 | 2019-10-09 15:00 | 1564.46 | SHALLOW WATER | 1615.36 | 1483.85 | N/A | N/A | N/A | N/A | 4051079 | 15.13 | 9.71 | 9.43 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.66 |  | 359.4 |  | 843.56 | [27 empty] | Exist
2019-08-07 | 2019-12-10 | IPC | PM | BERTAM | BERTAM A-18 | APPRAISAL CUM DEV/DEVELOPMENT | WEST TELESTO | JACK UP | 74.7 | 2664 | 1663.8 | N/A | N/A | N/A | N/A | 11710000 | 31 | NO | N/A | DRY TREE | 2019-08-23 | 2019-08-16 18:30 | 2019-10-14 22:30 | 2437.28 | SHALLOW WATER | 2565 | 1666.3 | N/A | N/A | N/A | N/A | 12630000 | 35.3 | 4.8 | 4.8 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.9 |  | 849.6 |  | 1501.4 | [6 empty] | 9.5 | 3600000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 2 | 3-1/2" | 1.0 | SINGLE | L80 | 1352.2806 | True | ICD | L80 | 9.1 | BASE OIL/DIESEL | NO | NO | Exist
2019-08-06 | 2019-12-20 | PCSB | PM | SEPAT | SEPAT-11 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 63 | 2089 | 1717 | N/A | N/A | N/A | N/A | 8660208 | 22.77 | NO | N/A | N/A | 2019-09-09 | 2019-09-08 18:00 | 2019-10-05 22:30 | 1976.6 | SHALLOW WATER | 2080 | 1709.76 | N/A | N/A | N/A | N/A | 7891557.11 | 27.19 | 11.37 | 11.37 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.08 |  | 573 |  | 1173 | [27 empty] | Exist
2019-08-02 | 2019-12-13 | COP | SK | BENUM | BENUM-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 90 | 1532 | 1500 | 13700000 | 19800000 | 23.4 | 38.3 | N/A | N/A | NO | N/A | N/A | 2019-10-02 | 2019-09-27 14:30 | 2019-11-02 20:30 | 1462.62 | SHALLOW WATER | 1584 | 1533 | 14400000 | N/A | 36.4 | N/A | N/A | N/A | 1.8 | 1.8 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 2.4 |  | 1036 |  | 1686 | [27 empty] | Exist
2019-07-29 | 2019-12-31 | IPC | PM | BERTAM | BERTAM A-19 | APPRAISAL CUM DEV/DEVELOPMENT | WEST TELESTO | JACK UP | 74.7 | 3307 | 1663.85 | N/A | N/A | N/A | N/A | 13014993 | 36.1 | NO | N/A | DRY TREE | 2019-08-21 | 2019-08-20 | 2019-11-09 12:00 | 2779.28 | SHALLOW WATER | 2907 | 1663.54 | N/A | N/A | N/A | N/A | 12733904 | 37 | 16.5 | 16.5 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.7 |  | 1397 |  | 787 | [6 empty] | 11 | 3600000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 2 | 3-1/2" | 1.0 | SINGLE | L80 | 410.7714 | True | ICD | L80 | 9.1 | BASE OIL/DIESEL | NO | NO | Exist
2019-07-29 | 2019-11-05 | REPSOL | PM | BUNGA ORKID | BOD-26 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 4738.1 | 1958.43 | N/A | N/A | N/A | N/A | 12610523 | 40.4 | NO | N/A | DRY TREE | 2019-08-21 14:45 | 2019-08-21 08:30 | 2019-10-07 14:15 | 4700.52 | SHALLOW WATER | 4800 | 1974 | N/A | N/A | N/A | N/A | 12850000 | 46.9 | 3 | 3 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 2.47 |  | 601 |  | 816 | [6 empty] | 8 | 3401574.8 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 164.042 | False | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-07-25 | 2019-11-28 | SEAH | SB | SOUTH FURIOUS | SF30-4 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 17.68 | 1802.13 | 920.15 | N/A | N/A | N/A | N/A | 6958104 | 16.4 | NO | N/A | DRY TREE | 2019-09-09 | 2019-09-09 07:00 | 2019-10-21 06:00 | 1756.32 | SHALLOW WATER | 1813.47 | 915.27 | N/A | N/A | N/A | N/A | 5500000 | 14.6 | 6 | 6 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.46 |  | 635.77 |  | 927.59 | [6 empty] | 3.58 | 1736331.4 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 115 | True | NONE | L80 | 9.4 | KCL | NO | NO | Exist
2019-07-25 | 2019-11-07 | PCSB | SK | D18 | D18 107ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2238 | 1363.4 | N/A | N/A | N/A | N/A | 9217147 | 27.97 | NO | N/A | DRY TREE | 2019-09-04 | 2019-08-20 18:00 | 2019-09-22 18:00 | 2233.8 | SHALLOW WATER | 2290 | 1753.29 | N/A | N/A | N/A | N/A | 9660400.22 | 33 | 22 | 22 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.78 |  | 517 |  | 1975 | [6 empty] | 8.5 | 3763011 |  |  | SANDSTONE | NORMAL | CASED HOLE | 3 ZONES | NO | 3-1/2" | 4.0 | SINGLE | 15CR |  | True | ICV | 25CR | 9.1 | NACL | NO | NO | Exist
2019-07-23 | 2019-12-23 | ENQUEST | PM | SELIGI | SEE-32 | APPRAISAL CUM DEV/DEVELOPMENT | EDRILL-2 | TENDER ASSISTED DRILLING RIG (TADR) | 73.2 | 2464 | 1917 | N/A | N/A | N/A | N/A | 8363533 | 29.07 | SIDETRACK | N/A | N/A | 2019-08-08 02:15 | 2019-08-03 15:00 | 2019-10-10 03:15 | 2468.4 | SHALLOW WATER | 2575 | 2028.71 | N/A | N/A | N/A | N/A | 7025145 | 34.44 | 12.34 | 7.32 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.63 |  | 339 |  | 505 | [27 empty] | Exist
2019-07-22 | 2019-11-20 | SEAH | SB | SOUTH FURIOUS | SF30-2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 17.59 | 2350.96 | 1142.94 | N/A | N/A | N/A | N/A | 8160000 | 20.3 | NO | N/A | DRY TREE | 2019-08-26 | 2019-08-26 | 2019-10-06 | 2305.64 | SHALLOW WATER | 2362.69 | 1149.34 | N/A | N/A | N/A | N/A | 8400000 | 28.46 | 20 | 20 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.7 |  | 798.76 |  | 1082.98 | [6 empty] | 4.75 | 2203287.6 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 312 | True | NONE | L80 | 9.4 | KCL | NO | NO | Exist
2019-07-22 | 2019-12-23 | ENQUEST | PM | SELIGI | SEE-33 | APPRAISAL CUM DEV/DEVELOPMENT | EDRILL-2 | TENDER ASSISTED DRILLING RIG (TADR) | 73.2 | 3245 | 2047 | N/A | N/A | N/A | N/A | 8865963 | 30.75 | NO | N/A | N/A | 2019-08-17 10:30 | 2019-08-03 10:00 | 2019-09-23 21:00 | 3110.4 | SHALLOW WATER | 3217 | 2041.29 | N/A | N/A | N/A | N/A | 8970024 | 39.15 | 7.88 | 7.42 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.71 |  | 356 |  | 889 | [27 empty] | Exist
2019-07-19 | 2019-11-19 | COP | SK | PATAWALI | PATAWALI-2 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 90 | 1532 | 1532 | 13704000 | 21130000 | 22.9 | 37.8 | N/A | N/A | NO | N/A | N/A | 2019-08-21 | 2019-08-15 08:00 | 2019-09-27 14:30 | 495 | SHALLOW WATER | 615 | 615 | 4500000 | N/A | 16.3 | N/A | N/A | N/A | 3.96 | 3.07 | SW EXP C1 | SW EXP C1 | 2.4 | 2.4 | 1375 | 1375 | 3025 | 3025 | Yes | 2.3 | Yes | 958 | Yes | 1512 | [26 empty] | Exist
2019-07-17 | 2019-11-14 | PCSB | SB | ERB WEST | EW-102ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.97 | 3999.09 | 2113.99 | N/A | N/A | N/A | N/A | 9850000 | 28.61 | SUSPEND | N/A | N/A | 2019-07-28 | 2019-07-26 | 2019-09-19 04:00 | 3797.07 | SHALLOW WATER | 3891.19 | 2099.6 | N/A | N/A | N/A | N/A | 9670065.23 | 40.82 | 31.31 | 30.16 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.75 |  | 698 |  | 1528.4 | [27 empty] | Exist
2019-07-17 | 2019-09-23 | IPC | PM | KERUING | KERUING-1 | EXPLORATION/APPRAISAL | WEST TELESTO | JACK UP | 74.7 | 1417 | 1389 | 7500000 | 13650000 | 21.4 | 41.2 | N/A | N/A | NO | N/A | N/A | 2019-07-29 | 2019-07-29 | 2019-08-10 | 1257.28 | SHALLOW WATER | 1374 | 1348.55 | 7461001 | N/A | 19.23 | N/A | N/A | N/A | 5.96 | 5.96 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.89 |  | 601.94 |  | 1797.84 | [27 empty] | Exist
2019-07-15 | N/A | VESTIGO | PM | TEMBIKAI | TBK-B1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 2599 | 2457 | N/A | N/A | N/A | N/A | 23299745 | 59.7 | NO | N/A | DRY TREE | 2019-09-15 | 2019-09-15 | 2019-12-17 | 2608.15 | SHALLOW WATER | 2722 | 2501.94 | N/A | N/A | N/A | N/A | 18914990 | 54.6 | 0 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 0.61 |  | 231 |  | 305 | [6 empty] | 1.01 | 164037.62 | 0.11 | 18.37 | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 42.653 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-07-15 | 2019-12-10 | VESTIGO | PM | TNAG | TBK-B4 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 3001 | 2146 | N/A | N/A | N/A | N/A | 3803182 | 9.5 | NO | N/A | DRY TREE | 2019-09-14 | 2019-08-31 00:30 | 2019-10-24 15:15 | 2660.15 | SHALLOW WATER | 2774 | 2172.04 | N/A | N/A | N/A | N/A | 2825460 | 6.71 | 1.24 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 0.69 |  | 256 |  | 324 | [6 empty] | 0.7 | 589298 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 37.7315 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-07-15 | 2019-12-10 | VESTIGO | PM | TEMBIKAI | TBK-B3 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 3136 | 2702 | N/A | N/A | N/A | N/A | 4212662 | 10.1 | NO | N/A | DRY TREE | 2019-09-16 | 2019-09-01 | 2019-10-19 02:30 | 2973 | SHALLOW WATER | 3087 | 2715.46 | N/A | N/A | N/A | N/A | 3364749 | 9.02 | 23.79 | 23.79 | SW DEV C1 |  | 2.1 |  | 700 |  | 555 |  | 0.63 |  | 238 |  | 346 | [6 empty] | 2.87 | 1047814 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 106.6325 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-07-15 | 2019-12-10 | VESTIGO | PM | TEMBIKAI | TBK-B2 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 71.5 | 3118 | 2781 | N/A | N/A | N/A | N/A | 23299745 | 59.7 | NO | N/A | DRY TREE | 2019-09-15 18:00 | 2019-09-01 | 2019-10-10 | 3006.15 | SHALLOW WATER | 3120 | 2811.7 | N/A | N/A | N/A | N/A | 18914990 | 54.6 | 0 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 0.56 |  | 204 |  | 288 | [6 empty] | 0.78 | 831311 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 111.554 | False |  | L80 13CR | 6.8 | BASE OIL/DIESEL | NO | NO | Exist
2019-07-03 | 2019-11-20 | EMEPMI | PM | TABU | TABU-A05 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 64 | 2490 | 2002 | N/A | N/A | N/A | N/A | 6600000 | 16.1 | SIDETRACK | N/A | DRY TREE | 2019-09-06 | 2019-08-31 | 2019-09-19 12:00 | 2382.7 | SHALLOW WATER | 2480 | 1992 | N/A | N/A | N/A | N/A | 5720000 | 13.5 | 0.5 | 0.5 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.7 |  | 652 |  | 1988 | [6 empty] | 15.9 | 14132200 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2860 | False | INNER STRING WITH SSD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-07-03 | 2019-08-16 | IPC | PM | BERTAM | BERTAM-4 | EXPLORATION/APPRAISAL | WEST TELESTO | JACK UP | 77 | 1705 | 1705 | 6104264 | 6556875 | 19.6 | 21.2 | N/A | N/A | NO | N/A | N/A | 2019-07-14 | 2019-07-13 05:00 | 2019-07-27 | 1585.9 | SHALLOW WATER | 1705 | 1705 | N/A | 4920000 | N/A | 14.4 | N/A | N/A | 0.14 | 0.14 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.25 |  | 344 |  | 716 | [27 empty] | Exist
2019-07-03 | 2019-12-05 | EMEPMI | PM | TABU | TABU-A17ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 2648 | 2003 | N/A | N/A | N/A | N/A | 6100000 | 14.5 | NO | N/A | DRY TREE | 2019-09-19 | 2019-08-25 09:00 | 2019-10-10 | 2632.7 | SHALLOW WATER | 2730 | 1994 | N/A | N/A | N/A | N/A | 6763900 | 26.4 | 31.72 | 31.64 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.6 |  | 550 |  | 2348 | [6 empty] | 16.7 | 14821000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2861.032 | False | INNER STRING WITH SSD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-07-03 | 2020-01-08 | EMEPMI | PM | TABU | TABU-A09 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 3242 | 1617 | N/A | N/A | N/A | N/A | 9200000 | 18.5 | NO | N/A | DRY TREE | 2019-10-24 12:00 | 2019-08-01 12:00 | 2019-11-13 | 1794.7 | SHALLOW WATER | 1892 | 1395 | N/A | N/A | N/A | N/A | 9779000 | 19.5 | 16.77 | 3.74 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1580 |  | 1.4 |  | 521 |  | 1583 | [6 empty] | 16.7 | 8897000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | DUAL | L80 13CR | 5338.187 | False | AICD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-07-03 | 2019-12-13 | EMEPMI | PM | TABU | TABU-A11ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 2823.5 | 1978 | N/A | N/A | N/A | N/A | 6100000 | 14.5 | NO | N/A | DRY TREE | 2019-10-11 | 2019-10-10 | 2019-10-24 12:00 | 2737.7 | SHALLOW WATER | 2835 | 1980 | N/A | N/A | N/A | N/A | 5083000 | 13.4 | 14.15 | 14.15 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 2.6 |  | 889 |  | 2365 | [6 empty] | 21.5 | 14858000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2063.749 | False | INNER STRING WITH SSD | L80 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-07-01 | 2019-12-23 | SAPURA OMV | SK | LARAK | LARAK-A1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 81.2 | 2237 | 2237 | N/A | N/A | N/A | N/A | 15142859 | 28.1 | NO | N/A | N/A | 2019-07-24 | 2019-07-23 22:00 | 2019-10-20 18:00 | 2113.3 | SHALLOW WATER | 2237 | 2237 | N/A | N/A | N/A | N/A | 11160314.91 | 32.82 | 29.36 | 29.36 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.03 |  | 672.05 |  | 1154.48 | [27 empty] | Exist
2019-07-01 | 2019-12-11 | SAPURA OMV | SK | LARAK | LARAK-A2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 81.2 | 2187 | 2083.19 | N/A | N/A | N/A | N/A | 15168816 | 28.28 | NO | N/A | N/A | 2019-07-23 | 2019-07-22 | 2019-08-10 | 2114.39 | SHALLOW WATER | 2238 | 2130.08 | N/A | N/A | N/A | N/A | 8857339 | 27.06 | 0 | 0 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.76 |  | 486 |  | 1028 | [27 empty] | Exist
2019-06-28 | 2019-10-16 | PCSB | SK | TEMANA | TE-83 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 30.6 | 2697 | 1120 | N/A | N/A | N/A | N/A | 14036109 | 47.18 | NO | N/A | DRY TREE | 2019-07-30 | 2019-07-28 16:30 | 2019-09-20 18:30 | 2928.5 | SHALLOW WATER | 2984 | 1256.71 | N/A | N/A | N/A | N/A | 13753785 | 54.04 | 1.85 | 1.85 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.64 |  | 447 |  | 1232 | [6 empty] | 31.1 | 6275713.06 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | DUAL | L80 | 1515.8 | False |  | 9CR | 9.7 | NACL | NO | NO | Exist
2019-06-25 | 2019-12-26 | HESS | PM | BUNGA ZETUNG | BUNGA ZETUNG A-2 (B) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.02 | 3273.7 | 1300.52 | N/A | N/A | N/A | N/A | 13160000 | 27 | NO | N/A | DRY TREE | 2019-07-29 | 2019-07-28 19:00 | 2019-10-18 19:00 | 3208.9 | SHALLOW WATER | 3308.14 | 1313.34 | N/A | N/A | N/A | N/A | 17815000 | 43.56 | 22.14 | 22.14 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 3.26 |  | 1238 |  | 1730 | [6 empty] | 11.3 | 6730000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 379.99 | True |  | L80 13CR | 9.4 | NACL/NABR | NO | NO | Exist
2019-06-25 | 2020-08-11 | HESS | PM | BUNGA ZETUNG | BUNGA ZETUNG A-3 (F) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.02 | 2791.83 | 1219.14 | N/A | N/A | N/A | N/A | 11420000 | 20.8 | NO | N/A | DRY TREE | 2019-08-01 | 2019-08-01 09:00 | 2020-05-07 01:30 | 2529.93 | SHALLOW WATER | 2629.38 | 1229.81 | N/A | N/A | N/A | N/A | 9430000 | 23.92 | 1.3 | 1.3 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.83 |  | 680 |  | 1169 | [6 empty] | 8.32 | 3930000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 2225.77 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-06-25 | 2020-07-27 | HESS | PM | BUNGA ZETUNG | BUNGA ZETUNG A-4 (C) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 55.93 | 3383.72 | 1231.94 | N/A | N/A | N/A | N/A | 14300000 | 26.7 | NO | N/A | DRY TREE | 2019-08-05 03:30 | 2019-08-04 14:30 | 2020-06-17 19:30 | 3375.95 | SHALLOW WATER | 3462.36 | 1343.19 | N/A | N/A | N/A | N/A | 11110000 | 28.94 | 8.35 | 8.35 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.81 |  | 617 |  | 1028 | [6 empty] | 10.94 | 4310000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1265.14 | True |  | L80 13CR | 9.3 | NACL/NABR | NO | NO | Exist
2019-06-25 | 2019-12-18 | HESS | PM | BUNGA ZETUNG | BUNGA ZETUNG A-1(A) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 56.02 | 2875.34 | 1225.24 | N/A | N/A | N/A | N/A | 11160000 | 23.4 | NO | N/A | DRY TREE | 2019-08-08 | 2019-08-07 19:00 | 2019-10-16 18:00 | 2788.6 | SHALLOW WATER | 2887.84 | 1237 | N/A | N/A | N/A | N/A | 11450000 | 32.06 | 6.82 | 6.82 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.4 |  | 891 |  | 1284 | [6 empty] | 10.75 | 4460000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1025.37 | True |  | L80 13CR | 9.4 | NACL/NABR | NO | NO | Exist
2019-06-10 | 2019-10-04 | SHELL | SK | BOLAI | BOLAI-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 121.4 | 1969 | 1946 | 13597000 | 18021000 | 31.38 | 44.49 | N/A | N/A | NO | N/A | N/A | 2019-06-22 | 2019-06-20 07:00 | 2019-08-07 19:00 | 2650.74 | SHALLOW WATER | 2795 | 2795 | N/A | 18340000 | N/A | 50.6 | N/A | N/A | 2.9 | 2.9 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.5 |  | 1060 |  | 2685 | [27 empty] | Exist
2019-05-23 | 2019-11-06 | PCSB | SK | BOKOR | BO-404 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 68.88 | 2199.94 | 1190.49 | N/A | N/A | N/A | N/A | 9993869 | 23 | NO | N/A | DRY TREE | 2019-06-21 | 2019-06-20 17:30 | 2019-09-09 21:00 | 2179.52 | SHALLOW WATER | 2288.02 | 1203.87 | N/A | N/A | N/A | N/A | 9431177.67 | 27.34 | 1.52 | 1.52 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.61 |  | 602 |  | 1237 | [6 empty] | 13.1 | 2838014 |  |  | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | 3 ZONES | NO | 3-1/2" | 3.0 | SINGLE | 25CR | 1233 | True | ICV | 25CR | 8.5 | NACL | NO | NO | Exist
2019-05-23 | 2019-11-28 | PCSB | SK | BOKOR | BO-401ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 68.88 | 1300.77 | 1146.6 | N/A | N/A | N/A | N/A | 9290745 | 20.76 | NO | N/A | DRY TREE | 2019-06-14 | 2019-06-09 12:00 | 2019-09-25 08:00 | 1296.56 | SHALLOW WATER | 1405.06 | 1208.05 | N/A | N/A | N/A | N/A | 9097196 | 26.23 | 21.92 | 21.72 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.03 |  | 727 |  | 1218 | [6 empty] | 9.33 | 1919319 |  |  | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | 3 ZONES | NO | 3-1/2" | 3.0 | SINGLE | 25CR | 647 | True | ICV | 25CR | 8.5 | NACL | NO | NO | Exist
2019-05-23 | 2019-11-28 | PCSB | SK | BOKOR | BOKOR-D403 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 70.1 | 2605.91 | 1160.22 | N/A | N/A | N/A | N/A | 13807202.15 | 27.5 | NO | N/A | DRY TREE | 2019-06-20 | 2019-06-20 | 2019-10-11 | 2585.19 | SHALLOW WATER | 2694.91 | 1194.18 | N/A | N/A | N/A | N/A | 15721194.6 | 48.97 | 22.97 | 22.51 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.44 |  | 845 |  | 1815 | [6 empty] | 24.25 | 5444007.18 |  |  | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | 3 ZONES | NO | 3-1/2" | 3.0 | SINGLE | 25CR | 1047 | True | ICV | 25CR | 8.5 | NACL | NO | NO | Exist
2019-05-23 | 2019-10-25 | PCSB | SK | BOKOR | BO-402 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 70.1 | 1260.69 | 1139.59 | N/A | N/A | N/A | N/A | 8512030.77 | 19.51 | NO | N/A | DRY TREE | 2019-06-22 | 2019-06-21 11:00 | 2019-08-27 12:00 | 1275.53 | SHALLOW WATER | 1385.25 | 1208.02 | N/A | N/A | N/A | N/A | 7829880.89 | 23.9 | 4.99 | 4.99 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.19 |  | 803 |  | 1628 | [6 empty] | 12.85 | 2296683.18 |  |  | SANDSTONE | NORMAL | CASED HOLE STAND ALONE SCREEN | 3 ZONES | NO | 3-1/2" | 3.0 | SINGLE | 25CR | 618 | True | ICV | 25CR | 8.5 | NACL | NO | NO | Exist
2019-05-21 | 2019-12-09 | SEA HIBISCUS | SB | ST JOSEPH | SJ-105C | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 39.38 | 1934.47 | 759.83 | N/A | N/A | N/A | N/A | 7240734 | 18.2 | NO | N/A | N/A | 2019-06-14 13:00 | 2019-06-13 06:00 | 2019-07-23 21:00 | 1805.36 | SHALLOW WATER | 1883.57 | 763.05 | N/A | N/A | N/A | N/A | 6304229 | 18.25 | 18.84 | 18.84 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.42 |  | 857 |  | 1020 | [27 empty] | Exist
2019-05-21 | 2019-07-31 | IPC | PM | BERTAM | BERTAM-5 | APPRAISAL CUM DEV/DEVELOPMENT | WEST TELESTO | JACK UP | 76.8 | 1700 | 1700 | N/A | N/A | N/A | N/A | 6553308 | 21.2 | NO | N/A | N/A | 2019-06-25 16:00 | 2019-06-22 09:30 | 2019-07-13 03:00 | 1588.1 | SHALLOW WATER | 1707 | 1664.9 | N/A | N/A | N/A | N/A | 6560041 | 21.6 | 4.2 | 4.2 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.9 |  | 597.5 |  | 1259.1 | [27 empty] | Exist
2019-05-16 | 2019-09-23 | ROC OIL | SK | D35 | D35A-107ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 47.24 | 2505.03 | 1778.73 | N/A | N/A | N/A | N/A | 11773145 | 43.36 | NO | N/A | N/A | 2019-07-06 | 2019-06-21 | 2019-08-12 | 2421.21 | SHALLOW WATER | 2508.38 | 1780.86 | N/A | N/A | N/A | N/A | 8211766 | 30.96 | 10 | 10 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.72 |  | 518.15 |  | 848.5 | [27 empty] | Exist
2019-05-15 | 2019-08-07 | SAPURA OMV | PM | WEST BELUMUT | WB A-03ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 3588 | 1162 | N/A | N/A | N/A | N/A | 6827044 | 20.77 | NO | N/A | N/A | 2019-05-25 | 2019-05-22 22:00 | 2019-06-10 12:00 | 2854.3 | SHALLOW WATER | 2967 | 1163.48 | N/A | N/A | N/A | N/A | 5956372 | 18.58 | 5.66 | 5.66 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.35 |  | 361.63 |  | 597.57 | [27 empty] | Exist
2019-05-15 | 2019-09-12 | PCSB | SB | ERB WEST | ERB WEST 120 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 61.87 | 2767.5 | 2150.25 | N/A | N/A | N/A | N/A | 5969846.58 | 18.11 | SIDETRACK | N/A | N/A | N/A | 2019-06-16 10:30 | 2019-07-13 13:30 | 2679.46 | SHALLOW WATER | 2771.41 | 1968.24 | N/A | N/A | N/A | N/A | 5626209.04 | 21.64 | 7.85 | 7.51 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 2.16 |  | 604 |  | 1344 | [27 empty] | Exist
2019-05-15 | 2019-09-12 | PCSB | SB | ERB WEST | EW-119 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 61.87 | 2767.5 | 2150.25 | N/A | N/A | N/A | N/A | 5969847 | 18.11 | SIDETRACK | N/A | DRY TREE | 2019-06-16 | 2019-06-16 10:30 | 2019-07-13 13:30 | 2679.46 | SHALLOW WATER | 2771.41 | 1968.24 | N/A | N/A | N/A | N/A | 5626209 | 21.64 | 7.85 | 7.51 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 2.16 |  | 604 |  | 1344 | [27 empty] | Exist
2019-05-15 | 2019-08-15 | PCSB | SB | ERB WEST | EW-119 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.97 | 3102.8 | 2138.05 | N/A | N/A | N/A | N/A | 5875000 | 18.1 | NO | N/A | DRY TREE | 2019-06-04 | 2019-06-02 13:30 | 2019-06-16 10:30 | 2948.58 | SHALLOW WATER | 3042.67 | 2128.47 | N/A | N/A | N/A | N/A | 4687081.49 | 13.88 | 8.13 | 8.03 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.8 |  | 781 |  | 1456 | [6 empty] | 4.83 | 1327739 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 39 | False | NONE | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-05-15 | 2019-08-26 | SAPURA OMV | PM | WEST BELUMUT | WB A-02ST3 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 3234 | 1162.8 | N/A | N/A | N/A | N/A | 6691555 | 20.08 | NO | N/A | N/A | 2019-06-12 | 2019-06-10 12:00 | 2019-06-27 12:00 | 2517.3 | SHALLOW WATER | 2630 | 1159.18 | N/A | N/A | N/A | N/A | 5745054 | 17 | 3.55 | 3.55 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.31 |  | 336.61 |  | 708.62 | [27 empty] | Exist
2019-05-15 | 2019-12-09 | SEA HIBISCUS | SB | ST JOSEPH | SJ-105B | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 39.13 | 2061.57 | 759.22 | N/A | N/A | N/A | N/A | 7509244 | 18.9 | NO | N/A | DRY TREE | 2019-06-25 | 2019-06-24 14:00 | 2019-07-30 21:00 | 1845.66 | SHALLOW WATER | 1920.15 | 760.74 | N/A | N/A | N/A | N/A | 6572066 | 14.4 | 0 | 0 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.49 |  | 774 |  | 1015 | [6 empty] | 3.73 | 2051832.9 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2329 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2019-05-14 | 2019-10-07 | ROC OIL | SK | D35 | D35A-111ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 47.24 | 1986.59 | 1811.34 | N/A | N/A | N/A | N/A | 7040000 | 20.44 | NO | N/A | N/A | 2019-07-23 | 2019-06-23 20:00 | 2019-08-09 21:00 | 1890.89 | SHALLOW WATER | 1978.06 | 1803.41 | N/A | N/A | N/A | N/A | 5619079 | 20.55 | 3.69 | 3.69 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.53 |  | 801.37 |  | 1616.07 | [27 empty] | Exist
2019-05-14 | 2019-10-25 | VESTIGO | SK | PUDING EMAS | PE-1 | EXPLORATION/APPRAISAL | BORR MIST | JACK UP | 70.5 | 3343 | 1954 | 6200000 | 6200000 | 23.5 | 23.5 | N/A | N/A | NO | N/A | N/A | 2019-07-20 | 2019-05-30 18:00 | 2019-08-27 02:30 | 3109.35 | SHALLOW WATER | 3215 | 1960.83 | N/A | 6454588 | N/A | 21.89 | N/A | N/A | 25.45 | 25.45 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 1.55 |  | 474 |  | 719 | [27 empty] | Exist
2019-05-14 | 2019-10-22 | VESTIGO | SK | ANJUNG KECIL | AJK-A1ST1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.5 | 2595 | 1710 | N/A | N/A | N/A | N/A | 8373993 | 22.2 | SIDETRACK | N/A | DRY TREE | 2019-06-29 | 2019-06-19 | 2019-08-23 22:30 | 2474.35 | SHALLOW WATER | 2580 | 1708 | N/A | N/A | N/A | N/A | 8990865 | 29.45 | 24.08 | 24.08 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 1.37 |  | 377 |  | 559 | [6 empty] | 7.3 | 2805797 |  |  | CARBONATE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 93.5905 | False | ICD | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-05-10 | 2019-09-12 | SEAH | SB | SAINT JOSEPH | SJ-105A | APPRAISAL CUM DEV/DEVELOPMENT | PVD-1 | JACK UP | 39.38 | 2042.06 | 751.6 | N/A | N/A | N/A | N/A | 7984465 | 22.17 | NO | N/A | DRY TREE | 2019-06-07 | 2019-06-03 14:30 | 2019-07-16 23:00 | 1952.87 | SHALLOW WATER | 2031.09 | 749.47 | N/A | N/A | N/A | N/A | 7389743 | 24.65 | 14.96 | 14.96 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.03 |  | 849 |  | 1087 | [6 empty] | 4.38 | 2231582.79 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2471 | True | AICD | L80 | 8.6 | KCL | NO | NO | Exist
2019-05-07 | 2019-10-10 | PCSB | SK | ANJUNG | ANJUNG-A2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 76 | 2125.07 | 1999.24 | N/A | N/A | N/A | N/A | 13396131.83 | 33.63 | NO | N/A | DRY TREE | 2019-06-16 | 2019-06-16 21:00 | 2019-07-02 | 1980.22 | SHALLOW WATER | 2100 | 1950.36 | N/A | N/A | N/A | N/A | 12528040.54 | 36.65 | 5.32 | 3.96 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.77 |  | 881 |  | 1564 | [6 empty] | 7.51 | 2452841.1 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | L80 13CR | 0 | True |  | SUPER 13CR | 10.7 | NACOOH | NO | NO | Exist
2019-05-06 | 2019-10-22 | PCSB | SK | D18 | D18 201ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 2089 | 1636 | N/A | N/A | N/A | N/A | 9616611 | 31.8 | NO | N/A | N/A | 2019-06-24 13:00 | 2019-06-19 16:00 | 2019-08-02 12:00 | 2168.8 | SHALLOW WATER | 2225 | 1753.29 | N/A | N/A | N/A | N/A | 6103257 | 21.33 | 2 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.48 |  | 393 |  | 832 | [27 empty] | Missing
2019-05-01 | 2019-11-05 | REPSOL | PM | BUNGA ORKID | BOD-25 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 56 | 5100 | 1945 | N/A | N/A | N/A | N/A | 13101906 | 41.1 | SIDETRACK | N/A | DRY TREE | 2019-06-25 | 2019-06-22 12:00 | 2019-08-21 07:30 | 4760.16 | SHALLOW WATER | 4860 | 1948.1 | N/A | N/A | N/A | N/A | 18055910 | 59.87 | 19 | 19 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 2.28 |  | 744 |  | 1132 | [6 empty] | 9.58 | 4129724.41 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2414.6982 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-04-26 | 2019-10-22 | PCSB | SK | D18 | D18 208B | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34.6 | 1692 | 1683 | N/A | N/A | N/A | N/A | 7397722 | 23.6 | NO | N/A | DRY TREE | 2019-06-13 | 2019-06-13 06:00 | 2019-08-01 12:00 | 1848.8 | SHALLOW WATER | 1905 | 1845 | N/A | N/A | N/A | N/A | 9439394.58 | 28.83 | 3 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1455 |  | 1.09 |  | 476 |  | 1362 | [6 empty] | 11.39 | 4111447.2 |  |  | SANDSTONE | NORMAL | CASED HOLE | 4 ZONES | NO | 3-1/2" | 7.0 | SINGLE | L80 13CR |  | True | ICV | 13CR | 9.1 | NACL | NO | NO | Exist
2019-04-22 | N/A | SHELL | SK | F14 | F14-108 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 105.03 | 3200.24 | 1333.13 | N/A | N/A | N/A | N/A | 19147500 | 56.45 | NO | N/A | N/A | 2019-05-14 | 2019-05-13 19:45 | 2019-07-18 12:00 | 2989.76 | SHALLOW WATER | 3129.53 | 1362.97 | N/A | N/A | N/A | N/A | 14516148 | 36.7 | 5.67 | 5.67 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.39 |  | 869 |  | 1268 | [27 empty] | Exist
2019-04-22 | N/A | SHELL | SK | F14 | F14-106 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 105.03 | 2969.83 | 1340.75 | N/A | N/A | N/A | N/A | 22680000 | 63.53 | NO | N/A | N/A | 2019-05-12 | 2019-05-04 07:15 | 2019-07-30 14:30 | 2730.39 | SHALLOW WATER | 2870.16 | 1374.28 | N/A | N/A | N/A | N/A | 23284607 | 50.6 | 0.84 | 0.76 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.28 |  | 873 |  | 1275 | [27 empty] | Exist
2019-04-12 | 2019-11-14 | PCSB | SB | ERB WEST | EW-123ST2 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 63.97 | 3483.69 | 2163.97 | N/A | N/A | N/A | N/A | 6137000 | 20.97 | NO | N/A | DRY TREE | 2019-07-16 | 2019-05-29 14:30 | 2019-09-07 05:00 | 3360.29 | SHALLOW WATER | 3454.37 | 2151.48 | N/A | N/A | N/A | N/A | 6081191.77 | 21.06 | 1.91 | 0.91 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.2 |  | 860 |  | 1415 | [6 empty] | 6.16 | 1303387 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 57 | False | NONE | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-04-10 | 2019-07-31 | SHELL | SK | GANDARUSA | GANDARUSA-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 137 | 1266 | 1266 | 11167000 | 14593000 | 25.19 | 35.89 | N/A | N/A | NO | N/A | N/A | 2019-05-15 | 2019-05-09 | 2019-06-02 13:00 | 773 | SHALLOW WATER | 933 | 933 | 11170000 | N/A | 21.32 | N/A | N/A | N/A | 15.1 | 15.1 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 5.97 |  | 2453 |  | 3627 | [27 empty] | Exist
2019-04-06 | 2019-08-15 | SHELL | SK | JERANGAU | JERANGAU-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 139 | 1052 | 973 | 10690000 | 14470000 | 23.44 | 35.35 | N/A | N/A | NO | N/A | N/A | 2019-05-06 | 2019-05-06 | 2019-06-19 04:30 | 944 | SHALLOW WATER | 1106 | 1026 | 7810000 | N/A | 17.75 | N/A | N/A | N/A | 8.22 | 8.22 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.63 |  | 1594 |  | 2520 | [27 empty] | Exist
2019-04-01 | 2019-07-03 | PTTEP | SK | MONG | MONG-01 | EXPLORATION/APPRAISAL | NAGA-7 | JACK UP | 24.1 | 1803 | 1620 | 6173717 | 6173717 | 18.29 | 18.29 | N/A | N/A | NO | N/A | N/A | 2019-04-29 | 2019-04-27 14:00 | 2019-05-11 03:00 | 1747.51 | SHALLOW WATER | 1802 | 1621 | 4683343 | N/A | 11.88 | N/A | N/A | N/A | 1.75 | 1.75 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.02 |  | 348 |  | 712 | [27 empty] | Exist
2019-04-01 | 2019-08-13 | REPSOL | PM | BUNGA SAFRON | BUNGA SAFFRON-1 | EXPLORATION/APPRAISAL | PVD-3 | JACK UP | 56 | 3258 | 2346 | 9100000 | 17800000 | 26.4 | 49.9 | N/A | N/A | SIDETRACK | N/A | N/A | 2019-04-24 19:00 | 2019-04-19 19:45 | 2019-05-24 | 3226 | SHALLOW WATER | 3312 | 2388 | N/A | 26050000 | N/A | 60.62 | N/A | N/A | 9.87 | 9.87 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 0.88 |  | 299 |  | 513 | [27 empty] | Missing
2019-03-15 | 2019-07-16 | PCSB | SB | TAWAKAL | TAWAKAL-1 | EXPLORATION/APPRAISAL | WEST CARINA | DRILLSHIP | 478 | 2400 | 2324 | 26700000 | 28200000 | 41.7 | 46.2 | N/A | N/A | NO | N/A | N/A | 2019-04-17 | 2019-04-11 19:15 | 2019-05-22 08:00 | 1888 | DEEP WATER | 2390 | 2311.7 | N/A | 19259122.36 | N/A | 40.53 | N/A | N/A | 28.99 | 28.99 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 3.84 |  | 2057 |  | 2958 | [27 empty] | Exist
2019-03-14 | 2019-08-21 | ROC OIL | SK | D35 | D35A-106ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 47.24 | 3734.23 | 1704.05 | N/A | N/A | N/A | N/A | 14259467 | 54.66 | NO | N/A | N/A | 2019-05-25 | 2019-05-10 12:00 | 2019-06-21 18:00 | 3673.88 | SHALLOW WATER | 3761.05 | 1712.28 | N/A | N/A | N/A | N/A | 11100598 | 42.25 | 5 | 5 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.65 |  | 586.29 |  | 815.79 | [27 empty] | Exist
2019-03-11 | 2019-06-27 | PTTEP | SK | SERDAM | SERDAM-01 | EXPLORATION/APPRAISAL | NAGA-7 | JACK UP | 27.3 | 1164 | 1164 | 5491577 | 5821577.43 | 16.63 | 21.02 | N/A | N/A | NO | N/A | N/A | 2019-04-06 | 2019-04-06 09:30 | 2019-04-27 10:00 | 1109.4 | SHALLOW WATER | 1164 | 1164 | N/A | 5328045 | N/A | 21.02 | N/A | N/A | 27.65 | 27.65 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 2.91 |  | 738 |  | 1468 | [27 empty] | Exist
2019-03-07 | 2019-05-13 | PETROFAC | PM | CENDOR | CD-C12 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 62.5 | 1914 | 1248 | N/A | N/A | N/A | N/A | 8050000 | 22.17 | NO | N/A | DRY TREE | 2019-03-20 | 2019-03-20 12:00 | 2019-04-19 19:30 | 1808.05 | SHALLOW WATER | 1917 | 1200.41 | N/A | N/A | N/A | N/A | 7960000 | 28.27 | 10 | 10 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 3.29 |  | 817.9 |  | 1267 | [6 empty] | 6.56 | 2238233 | 1.04 | 355.88 | SANDSTONE | HPHT | CASED HOLE COMPLIANT SCREEN | 1 ZONE | 1 | 2-7/8" | 3.0 | DUAL | 15CR | 5 | False | AICV | L80 13CR | 5 | CACL2 | 4 | 3 | Exist
2019-03-01 | N/A | SHELL | SB | GUMUSUT KAKAP | GK-P718AR2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1044.5 | 4694.3 | 2377.93 | N/A | N/A | N/A | N/A | 63400000 | 71.36 | NO | N/A | N/A | 2019-05-03 | 2019-05-03 09:30 | 2019-05-06 | 3532.76 | DEEP WATER | 4602.26 | 2366.45 | N/A | N/A | N/A | N/A | 40420000 | 57.82 | 16.4 | 16.4 | DW DEV C3 (Wet Tree) |  | 3.6 |  | 2590 |  | 4150 |  | 4 |  | 2345 |  | 3488 | [27 empty] | Exist
2019-02-22 | N/A | SAPURA OMV | PM | EAST BELUMUT | EB A-18ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 3352 | 1165 | N/A | N/A | N/A | N/A | 5241870 | 14.41 | NO | N/A | N/A | 2019-05-05 | 2019-04-29 12:00 | 2019-05-17 | 3141.3 | SHALLOW WATER | 3260 | 1167.18 | N/A | N/A | N/A | N/A | 4907501.75 | 17.5 | 8.87 | 8.87 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.3 |  | 391.93 |  | 733.92 | [27 empty] | Exist
2019-02-20 | 2019-06-10 | SAPURA OMV | PM | EAST BELUMUT | EB A-22ST2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 3195 | 1164 | N/A | N/A | N/A | N/A | 4612720 | 13.08 | NO | N/A | N/A | 2019-03-31 | 2019-03-27 06:00 | 2019-04-13 12:00 | 3024.3 | SHALLOW WATER | 3143 | 1168.5 | N/A | N/A | N/A | N/A | 5069330 | 17.25 | 3.5 | 3.5 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.63 |  | 439.59 |  | 838.34 | [27 empty] | Exist
2019-02-20 | 2019-07-04 | SAPURA OMV | PM | EAST BELUMUT | EB A-29ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 2791 | 1165 | N/A | N/A | N/A | N/A | 5244999 | 14.46 | NO | N/A | N/A | 2019-04-17 | 2019-04-13 12:00 | 2019-04-29 12:00 | 2667.3 | SHALLOW WATER | 2786 | 1164.66 | N/A | N/A | N/A | N/A | 5056125 | 16 | 7.68 | 7.68 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.06 |  | 289.47 |  | 722.09 | [27 empty] | Exist
2019-02-20 | 2019-05-24 | SAPURA OMV | PM | EAST BELUMUT | EB A-19ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-2 | JACK UP | 72.8 | 3362 | 1164.6 | N/A | N/A | N/A | N/A | 5141654 | 13.55 | NO | N/A | N/A | 2019-03-13 | 2019-03-09 22:30 | 2019-03-27 06:00 | 3175.3 | SHALLOW WATER | 3294 | 1163.79 | N/A | N/A | N/A | N/A | 5625477 | 17.35 | 2.76 | 2.76 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.67 |  | 525.92 |  | 911.86 | [27 empty] | Exist
2019-02-20 | 2019-09-20 | PTTEP | SK | LANG LEBAH | LANG LEBAH-1RDL2 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 90 | 4080 | 4080 | 27860000 | 27860000 | 57 | 57 | N/A | N/A | NO | N/A | N/A | 2019-03-14 | 2019-03-09 08:00 | 2019-07-21 06:15 | 3676 | SHALLOW WATER | 3796 | 3729 | N/A | 48400000 | N/A | 133.4 | N/A | N/A | 32.3 | 32.3 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 5.8 |  | 1818 |  | 2595 | [27 empty] | Exist
2019-02-04 | 2019-03-15 | PCSB | PM | ANGSI | ANGSI-E16 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 69 | 1940.09 | 1681.72 | N/A | N/A | N/A | N/A | 8473824.9 | 24.1 | NO | N/A | DRY TREE | 2019-02-10 | 2019-02-09 13:00 | 2019-02-28 03:00 | 1857 | SHALLOW WATER | 1963 | 1693.75 | N/A | N/A | N/A | N/A | 6283904.03 | 18.58 | 0 | 0 | SW DEV C1 |  | 2.1 |  | 700 |  | 1280 |  | 1.36 |  | 590 |  | 904 | [6 empty] | 4.98 | 1407766.05 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 426.53 | False | INNER STRING WITH SSD | 9CR | 9.7 | CACL2 | NO | NO | Exist
2019-01-31 | 2019-05-30 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B16ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 43 | 2592 | 1490.4 | N/A | N/A | N/A | N/A | 9179077 | 37.56 | SIDETRACK | N/A | DRY TREE | 2019-03-12 | 2019-02-08 20:00 | 2019-04-06 14:00 | 2559.01 | SHALLOW WATER | 2636 | 1491.8 | N/A | N/A | N/A | N/A | 8904626 | 32.92 | 2.92 | 2.92 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.87 |  | 762 |  | 1244 | [6 empty] | 3.75 | 1729743.2 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1227.094 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-01-31 | 2019-04-01 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B11ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 43 | 2688 | 1511 | N/A | N/A | N/A | N/A | 8188000 | 25.22 | NO | N/A | DRY TREE | N/A | 2019-02-15 14:45 | 2019-03-11 10:45 | 1418.99 | SHALLOW WATER | 1496.39 | 1496.39 | N/A | N/A | N/A | N/A | 6290783.1 | 23.83 | 1.97 | 1.97 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.85 |  | 777 |  | 1306 | [6 empty] | 4.68 | 1327453.23 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 656.2 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2019-01-16 | N/A | PCSB | SK | BARONIA | BN-83 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.6 | 3242.3 | 3055.47 | N/A | N/A | N/A | N/A | 14883903 | 36.15 | SUSPEND | N/A | DRY TREE | 2019-02-01 | 2019-02-01 | 2019-05-05 18:00 | 2045.83 | SHALLOW WATER | 2170.07 | 1989 | N/A | N/A | N/A | N/A | 7592305 | 29.88 | 18.65 | 18.55 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | No |  | No |  | No | [6 empty] | 16 | 3544100 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 3.0 | SINGLE | L80 13CR | 75.1 | False |  | 13CR | 12 | KCOOH | NO | NO | Exist
2019-01-01 | 2020-04-21 | REPSOL | SB | KINABALU | KNDW-D04 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54.25 | 4099.51 | 2695.95 | N/A | N/A | N/A | N/A | 14574743 | 45.05 | NO | N/A | DRY TREE | 2020-01-31 | 2020-01-30 05:00 | 2020-02-24 09:00 | 4002.32 | SHALLOW WATER | 4099.36 | 2703.51 | N/A | N/A | N/A | N/A | 9553842 | 25.17 | 2.94 | 2.94 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 0.99 |  | 352 |  | 710 | [6 empty] | 10.86 | 4586073 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 1789 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2019-01-01 | 2019-09-13 | REPSOL | PM | BUNGA KEKWA | BKC-03 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54 | 4007 | 2451.46 | N/A | N/A | N/A | N/A | 16289140 | 35.75 | SIDETRACK | N/A | DRY TREE | 2019-02-18 | 2019-02-18 02:00 | 2019-03-16 06:00 | 3756.4 | SHALLOW WATER | 3854 | 2317.89 | N/A | N/A | N/A | N/A | 10158724 | 26.17 | 0.84 | 0.84 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.55 |  | 513 |  | 698 | [6 empty] | 5.85 | 2155692 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 52.4934 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2018-12-27 | 2019-03-21 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B12ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 43 | 2151.01 | 1456.51 | N/A | N/A | N/A | N/A | 8600867 | 27.5 | SIDETRACK | N/A | DRY TREE | 2019-01-21 | 2019-01-09 15:30 | 2019-02-08 20:00 | 2210.6 | SHALLOW WATER | 2288 | 1494.79 | N/A | N/A | N/A | N/A | 7549919 | 30.19 | 12.75 | 12.75 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 3.1 |  | 823 |  | 1523 | [6 empty] | 4.66 | 1516399.46 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 974.457 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-12-14 | 2019-03-05 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B02ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 42.8 | 2130.9 | 1490 | N/A | N/A | N/A | N/A | 9368410 | 31.23 | NO | N/A | DRY TREE | 2018-12-18 | 2018-12-18 | 2019-01-09 15:30 | 2154.2 | SHALLOW WATER | 2231.4 | 1485.92 | N/A | N/A | N/A | N/A | 6016456.77 | 22.59 | 6.87 | 6.87 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.8 |  | 523 |  | 1012 | [6 empty] | 6.79 | 1566741.81 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1371.458 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-12-14 | 2019-05-31 | PCSB | SB | TAMPAN | TAMPAN-1 | EXPLORATION/APPRAISAL | WEST CARINA | DRILLSHIP | 378.85 | 1379.15 | 1379.15 | 35900000 | 40000000 | 56.6 | 64.6 | N/A | N/A | NO | N/A | N/A | 2019-01-20 | 2019-01-19 11:30 | 2019-04-11 19:45 | 937.21 | DEEP WATER | 1323.38 | 1323.32 | N/A | 44381711.58 | N/A | 82.32 | N/A | N/A | 15.88 | 15.88 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 5.93 |  | 3407.65 |  | 4386.13 | [27 empty] | Exist
2018-12-14 | 2019-04-01 | PETROFAC | PM | CENDOR | CD-B17 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 62.5 | 3435 | 1519 | N/A | N/A | N/A | N/A | 12900000 | 34 | NO | N/A | DRY TREE | 2018-12-20 | 2018-12-19 | 2019-02-10 | 3340.35 | SHALLOW WATER | 3450 | 1520 | N/A | N/A | N/A | N/A | 12250803 | 53 | 22 | 22 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.62 |  | 590 |  | 1085 | [6 empty] | 21.1 | 4499460 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 2-7/8" | 2.0 | DUAL | L80 13CR | 0 | False |  | L80 13CR | 10.5 | KCOOH | NO | NO | Exist
2018-12-11 | 2019-07-23 | REPSOL | PM | BUNGA KEKWA | BKC-17 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54 | 4885 | 3155 | N/A | N/A | N/A | N/A | 21170000 | 50.8 | SIDETRACK | N/A | N/A | 2018-12-19 | 2018-12-17 | 2019-02-08 | 4357.4 | SHALLOW WATER | 4455 | 2915.94 | N/A | N/A | N/A | N/A | 17930000 | 52.42 | 17.81 | 17.81 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | No |  | No |  | No | [27 empty] | Exist
2018-11-30 | N/A | SHELL | SB | GUMUSUT | GK-W515B | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1062.18 | 2771.72 | 2746.72 | N/A | N/A | N/A | N/A | 49800000 | 56.12 | NO | N/A | N/A | 2018-12-28 | 2018-12-27 20:00 | 2019-04-19 21:00 | 2687.6 | DEEP WATER | 3774.76 | 2733.52 | N/A | N/A | N/A | N/A | 27970000 | 39.66 | 10.27 | 10.27 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | 3.6 |  | 2234 |  | 3172 | [27 empty] | Exist
2018-11-29 | N/A | SHELL | SB | GUMUSUT KAKAP | GK-W614B | APPRAISAL CUM DEV/DEVELOPMENT | WEST CAPELLA | DRILLSHIP | 1114.6 | 3302.65 | 2622.68 | N/A | N/A | N/A | N/A | 40200000 | 45.26 | NO | N/A | N/A | 2019-01-01 | 2018-12-31 19:00 | 2019-05-17 | 1978.36 | DEEP WATER | 3117.95 | 2611.7 | N/A | N/A | N/A | N/A | 23320000 | 34.31 | 5.4 | 5.4 | No DMS category. Having value but not sure refering which version | [7 empty] | 4.3 |  | 2626 |  | 3592 | [27 empty] | Exist
2018-11-02 | 2019-02-13 | PCSB | SK | SHALLOW CLASTIC | SCDR-A6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 72 | 2591 | 1247 | N/A | N/A | N/A | N/A | 11923696 | 33.5 | NO | N/A | DRY TREE | 2018-12-19 | 2018-12-17 15:00 | 2019-01-23 | 2410 | SHALLOW WATER | 2515 | 1271.13 | N/A | N/A | N/A | N/A | 11644925.61 | 37.33 | 0.7 | 0.7 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.94 |  | 502 |  | 994 | [6 empty] | 6.74 | 3086141.41 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 1703 | True | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
2018-11-02 | 2019-01-31 | PETROFAC | PM | CENDOR | CD-B16 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 62.5 | 2591 | 1476.15 | N/A | N/A | N/A | N/A | 10500000 | 37 | NO | N/A | DRY TREE | 2018-11-08 | 2018-11-07 | 2018-12-18 | 2486.35 | SHALLOW WATER | 2596 | 1479 | N/A | N/A | N/A | N/A | 9050003 | 38.9 | 10.6 | 10.6 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.81 |  | 631 |  | 1150 | [6 empty] | 12.3 | 3106052 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.9 | KCOOH | 1 | NO | Exist
2018-10-30 | 2019-04-26 | PCSB | SK | BARONIA | BN-80 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.59 | 4014.01 | 2411.45 | N/A | N/A | N/A | N/A | 14890697.26 | 34.52 | NO | N/A | DRY TREE | 2018-11-14 | 2018-11-14 04:00 | 2018-12-18 21:30 | 3856.26 | SHALLOW WATER | 3980.49 | 2386.71 | N/A | N/A | N/A | N/A | 11066922.72 | 32.3 | 6.06 | 4.9 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.22 |  | 379 |  | 838 | [6 empty] | 11.64 | 3170765.98 |  |  | SANDSTONE | NORMAL | CASED HOLE | 3 ZONES | NO | 4-1/2" | 3.0 | SINGLE | 15CR | 372 | True | ICV | 25CR | 8.5 | KCL | NO | NO | Exist
2018-10-24 | 2019-05-27 | ROC OIL | SK | D35 | D35C-301ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 50.29 | 3162.76 | 1642.49 | N/A | N/A | N/A | N/A | 10946921 | 37.24 | NO | N/A | N/A | 2019-01-26 | 2018-12-02 18:00 | 2019-03-29 | 3067.66 | SHALLOW WATER | 3154.53 | 1642.54 | N/A | N/A | N/A | N/A | 11368695 | 38.8 | 10.5 | 10.5 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.93 |  | 776 |  | 2278 | [27 empty] | Exist
2018-10-24 | 2019-04-13 | ROC OIL | SK | D35 | D35C-303ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 50.29 | 2547.04 | 1508.69 | N/A | N/A | N/A | N/A | 13452755 | 46.5 | NO | N/A | N/A | 2019-01-17 | 2018-11-27 | 2019-03-14 | 2549.53 | SHALLOW WATER | 2636.39 | 1592.43 | N/A | N/A | N/A | N/A | 14051450 | 49.7 | 6.87 | 6.45 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.15 |  | 599 |  | 1568 | [27 empty] | Exist
2018-10-24 | 2019-05-15 | ROC OIL | SK | D35 | D35C-305ST3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 50.29 | 2392.56 | 1723.26 | N/A | N/A | N/A | N/A | 12232581.86 | 41.7 | NO | N/A | N/A | 2019-01-11 | 2018-12-03 | 2019-03-19 | 2200.55 | SHALLOW WATER | 2287.41 | 1665.65 | N/A | N/A | N/A | N/A | 9573451.65 | 33.4 | 1.55 | 1.25 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 2.3 |  | 636 |  | 1466 | [27 empty] | Exist
2018-10-24 | 2019-01-17 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B20 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 42.8 | 1971.1 | 1487.4 | N/A | N/A | N/A | N/A | 9123537.25 | 24.41 | NO | N/A | DRY TREE | 2018-11-12 | 2018-11-12 04:30 | 2018-12-08 | 1980.8 | SHALLOW WATER | 2058 | 1511.4 | N/A | N/A | N/A | N/A | 6929796.72 | 25.81 | 10.4 | 10.1 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 2.26 |  | 569 |  | 815 | [6 empty] | 3.31 | 1296441.22 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1046.639 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-10-15 | 2019-02-16 | PCSB | PM | ANGSI | ANGSI-E14 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 69 | 2004 | 1695.6 | N/A | N/A | N/A | N/A | 7880044.34 | 23.1 | NO | N/A | DRY TREE | 2018-12-15 | 2018-12-14 11:30 | 2019-01-05 05:00 | 1898 | SHALLOW WATER | 2004 | 1656.12 | N/A | N/A | N/A | N/A | 6513802.82 | 21.73 | 11.56 | 3.31 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.87 |  | 616 |  | 972 | [6 empty] | 9.58 | 1992829.11 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 442.935 | False | INNER STRING WITH SSD | 9CR | 8.5 | KCL | NO | NO | Exist
2018-10-08 | 2019-09-05 | REPSOL | PM | BUNGA KEKWA | BKC-8 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54 | 4518 | 2095 | N/A | N/A | N/A | N/A | 16887482 | 36.35 | SIDETRACK | N/A | N/A | 2018-11-23 | 2018-11-21 18:30 | 2019-02-18 02:00 | 3931.4 | SHALLOW WATER | 4029 | 2095 | N/A | N/A | N/A | N/A | 14973061 | 35.9 | 16.34 | 16.34 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.1 |  | 643 |  | 1209 | [27 empty] | Exist
2018-10-03 | 2018-12-05 | PCSB | SK | BARONIA | BN-81 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.59 | 2745.2 | 2518.13 | N/A | N/A | N/A | N/A | 8457309.94 | 15.38 | NO | N/A | N/A | N/A | 2018-10-12 01:00 | 2018-11-08 19:00 | 2630.42 | SHALLOW WATER | 2754.65 | 2517.98 | N/A | N/A | N/A | N/A | 6458303.64 | 27.15 | 7.64 | 7.37 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.19 |  | 345.97 |  | 639.88 | [27 empty] | Exist
2018-09-27 | 2019-10-09 | REPSOL | PM | BUNGA KEKWA | BKC-10ST1 (B) | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 54 | 3966 | 2860 | N/A | N/A | N/A | N/A | 18767604 | 49.1 | NO | N/A | DRY TREE | 2018-11-15 03:30 | 2018-11-15 03:30 | 2019-04-18 | 3828.4 | SHALLOW WATER | 3926 | 2816.46 | N/A | N/A | N/A | N/A | 13087997 | 39.38 | 12.57 | 12.57 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.25 |  | 453 |  | 1019 | [6 empty] | 14.46 | 3159436 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 164.042 | True | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2018-09-14 | 2019-04-01 | PCSB | SK | BARAM | BARAM D2-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 55.4 | 3990 | 3990 | 20550000 | 34707153.55 | 58.97 | 91.97 | N/A | N/A | NO | N/A | N/A | 2018-11-24 | 2018-11-19 08:00 | 2019-02-02 09:30 | 3630.5 | SHALLOW WATER | 3716.5 | 3715.78 | N/A | 27029847.69 | N/A | 75.06 | N/A | N/A | 14.24 | 8.91 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 3.77 |  | 1474 |  | 1861 | [27 empty] | Exist
2018-09-06 | 2018-12-19 | VESTIGO | PM | BERANTAI | BERANTAI WEST-1 | EXPLORATION/APPRAISAL | NAGA-2 | JACK UP | 66.7 | 2536 | 1968 | 6908238.68 | 6908238.68 | 22 | 22 | N/A | N/A | NO | N/A | N/A | 2018-11-07 | 2018-10-28 20:00 | 2018-11-22 20:30 | 2403.5 | SHALLOW WATER | 2501 | 1948 | N/A | 4724355 | N/A | 19.1 | N/A | N/A | 26.01 | 1.53 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 0.57 |  | 191 |  | 446 | [27 empty] | Exist
2018-09-06 | N/A | SHELL | SK | E06 | E06-108 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 70.04 | 4348.98 | 1831.76 | N/A | N/A | N/A | N/A | 39442928 | 69.4 | NO | N/A | N/A | 2018-10-16 | 2018-10-16 | 2019-03-21 | 4221.33 | SHALLOW WATER | 4337.09 | 1831.28 | N/A | N/A | N/A | N/A | 23187970 | 62.3 | 6.98 | 6.43 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.3 |  | 1036 |  | 1792 | [27 empty] | Exist
2018-09-06 | 2018-12-19 | VESTIGO | PM | BERANTAI | BERANTAI EAST-2 | EXPLORATION/APPRAISAL | NAGA-2 | JACK UP | 66.4 | 2224 | 1985 | 7250731 | 7250731 | 23 | 23 | N/A | N/A | NO | N/A | N/A | 2018-10-18 | 2018-10-04 21:30 | 2018-10-28 16:00 | 2090.8 | SHALLOW WATER | 2188 | 1958 | N/A | 4942641 | N/A | 23.8 | N/A | N/A | 0 | 0 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 0.71 |  | 219 |  | 475 | [27 empty] | Exist
2018-08-28 | 2018-11-15 | PCSB | SK | D28 | D28-OP2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34 | 1285 | 1089 | N/A | N/A | N/A | N/A | 6370795 | 14.48 | NO | N/A | N/A | 2018-09-15 | 2018-09-15 03:00 | 2018-10-14 21:00 | 1199.69 | SHALLOW WATER | 1266.5 | 1075.06 | N/A | N/A | N/A | N/A | 5403058 | 15.96 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.67 |  | 519 |  | 1220 | [27 empty] | Missing
2018-08-24 | 2018-11-02 | PCSB | SK | D28 | D28-OP1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 34 | 1069 | 1047 | N/A | N/A | N/A | N/A | 6633543.23 | 14.28 | NO | N/A | DRY TREE | 2018-09-12 | 2018-09-12 | 2018-10-06 14:30 | 1047.19 | SHALLOW WATER | 1114 | 1082.02 | N/A | N/A | N/A | N/A | 5505344.92 | 16.92 | 0.76 | 0.76 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.76 |  | 526 |  | 1133 | [6 empty] | 5.77 | 1418268.46 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR |  | True | NONE | 13CR | 9.9 | NACL | NO | NO | Exist
2018-08-24 | 2019-01-29 | PCSB | SK | BARONIA | BN-79 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.59 | 2352.64 | 2142.94 | N/A | N/A | N/A | N/A | 8586030.4 | 26.23 | NO | N/A | DRY TREE | 2018-10-09 | 2018-09-09 14:30 | 2018-12-09 15:00 | 2481.68 | SHALLOW WATER | 2605.91 | 2318.35 | N/A | N/A | N/A | N/A | 8997581.05 | 34.61 | 9.26 | 9.23 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.62 |  | 491 |  | 1049 | [6 empty] | 12.57 | 3103657.16 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 307 | False | INNER STRING WITH SSD | 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-08-15 | 2019-03-11 | PCSB | PM | ANGSI | ANGSI-E15 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 69 | 2393 | 1706 | N/A | N/A | N/A | N/A | 8993906.2 | 27 | NO | N/A | DRY TREE | 2018-11-12 | 2018-11-12 | 2019-01-24 20:00 | 2185 | SHALLOW WATER | 2291 | 1707 | N/A | N/A | N/A | N/A | 7583625.47 | 24.48 | 1.48 | 1.29 | SW DEV C3 |  | 2.2 |  | 915 |  | 1580 |  | 1.33 |  | 533 |  | 892 | [6 empty] | 7.06 | 2088913.43 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 424.8895 | True | INNER STRING WITH SSD | 9CR | 9.7 | CACL2 | NO | NO | Exist
2018-07-31 | 2018-11-20 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN B04 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 43 | 2083 | 1506.4 | N/A | N/A | N/A | N/A | 11297905.16 | 29.6 | NO | N/A | DRY TREE | N/A | 2018-09-14 17:00 | 2018-10-18 20:00 | 2097.6 | SHALLOW WATER | 2175 | 1490.7 | N/A | N/A | N/A | N/A | 10823812.77 | 34.12 | 10.47 | 10.47 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.52 |  | 785 |  | 1503 | [6 empty] | 4.54 | 1796175.25 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1076.168 | False | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-07-31 | 2019-02-18 | PCSB | SB | SUMANDAK SELATAN | SUMANDAK SELATAN-B01ST1 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA BERANI | TENDER ASSISTED DRILLING RIG (TADR) | 43 | 2488.18 | 1504.4 | N/A | N/A | N/A | N/A | 14959583.45 | 43.34 | SIDETRACK | N/A | DRY TREE | 2018-09-05 | 2018-09-05 14:00 | 2018-12-18 | 2268.6 | SHALLOW WATER | 2346 | 1495.53 | N/A | N/A | N/A | N/A | 12974317.17 | 43.48 | 13.03 | 13.03 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.73 |  | 779 |  | 1251 | [6 empty] | 3.3 | 1539907.03 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 1469.888 | True | AICD | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-07-27 | 2018-12-14 | PETROFAC | PM | CENDOR | CD-B02ST2 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 62.5 | 3247 | 1468 | N/A | N/A | N/A | N/A | 15800000 | 66 | NO | N/A | DRY TREE | 2018-08-25 | 2018-08-22 | 2018-11-07 | 3137.35 | SHALLOW WATER | 3247 | 1465 | N/A | N/A | N/A | N/A | 16980000 | 85.4 | 27.14 | 27.14 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 3.7 |  | 721 |  | 1072 | [6 empty] | 15.1 | 3634124 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 11.7 | NABR | 1 | NO | Exist
2018-07-27 | 2018-11-19 | PCSB | SK | TEMANA | TE-81 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 22.4 | 1700 | 1240 | N/A | N/A | N/A | N/A | 9271338.83 | 27.83 | SIDETRACK | N/A | DRY TREE | 2018-08-19 | 2018-08-14 19:00 | 2018-10-20 02:00 | 1836.24 | SHALLOW WATER | 1893 | 1666.31 | N/A | N/A | N/A | N/A | 15550515.07 | 66.21 | 17.98 | 17.5 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 2.54 |  | 536 |  | 1310 | [6 empty] | 19.35 | 6223230.65 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | DUAL | L80 | 1801 | False |  | 9CR | 9.9 | NACL | NO | NO | Exist
2018-07-24 | 2018-12-24 | PCSB | SK | GINSENG | GINSENG-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 94 | 3660 | 3660 | 12900000 | 18700000 | 33.3 | 50.7 | N/A | N/A | NO | N/A | N/A | 2018-08-16 | 2018-08-10 12:00 | 2018-10-27 08:00 | 3463.6 | SHALLOW WATER | 3590 | 3589.34 | N/A | 20941969.79 | N/A | 77.83 | N/A | N/A | 7.9 | 7.71 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.76 |  | 875 |  | 1591 | [27 empty] | Exist
2018-07-19 | 2018-12-19 | SHELL | SK | F14 | F14-102 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 105.03 | 3758.91 | 1367.88 | N/A | N/A | N/A | N/A | 35680000 | 89.13 | NO | N/A | N/A | 2018-08-18 | 2018-08-18 16:00 | 2018-10-17 22:00 | 3689.85 | SHALLOW WATER | 3829.63 | 1372.78 | N/A | N/A | N/A | N/A | 23385023 | 79.42 | 13.61 | 5.25 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.7 |  | 836 |  | 1380 | [27 empty] | Exist
2018-07-17 | 2019-01-15 | ROC OIL | SK | D35 | D35B-216 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 2239.56 | 1913.75 | N/A | N/A | N/A | N/A | 11190000 | 35.4 | NO | N/A | N/A | 2018-08-20 | 2018-08-20 09:00 | 2018-11-11 22:45 | 2179.82 | SHALLOW WATER | 2267.3 | 1943.61 | N/A | N/A | N/A | N/A | 10114164.54 | 28.61 | 1.64 | 1.64 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.74 |  | 638 |  | 1143 | [27 empty] | Exist
2018-07-17 | 2018-12-14 | ROC OIL | SK | D35B | D35B-217 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 2056.69 | 1831.45 | N/A | N/A | N/A | N/A | 8858652.53 | 37.32 | NO | N/A | N/A | 2018-08-23 | 2018-08-23 | 2018-11-16 | 1981.71 | SHALLOW WATER | 2069.19 | 1842.43 | N/A | N/A | N/A | N/A | 9675173.04 | 37.41 | 6.23 | 6.23 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.62 |  | 806 |  | 2000 | [27 empty] | Exist
2018-07-17 | 2019-07-10 | ROC OIL | SK | D35 | D35A-108ST5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 47.24 | 2398.35 | 1888.14 | N/A | N/A | N/A | N/A | 12096264 | 45.32 | NO | N/A | N/A | 2019-04-22 | 2019-04-05 18:00 | 2019-05-10 12:00 | 2272.48 | SHALLOW WATER | 2359.65 | 1860.41 | N/A | N/A | N/A | N/A | 8770307.8 | 34.75 | 2.43 | 2.43 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.45 |  | 523 |  | 922 | [27 empty] | Exist
2018-07-16 | 2019-01-11 | ROC OIL | SK | D35 | D35-218ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 45.11 | 3378.24 | 2014.63 | N/A | N/A | N/A | N/A | 5522916 | 17.62 | NO | N/A | N/A | 2018-10-23 | 2018-10-17 | 2018-11-12 18:00 | 3290.46 | SHALLOW WATER | 3377.93 | 2010.67 | N/A | N/A | N/A | N/A | 5347169 | 18.73 | 5.12 | 5.12 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 2.06 |  | 881 |  | 1528 | [27 empty] | Exist
2018-07-12 | 2019-01-29 | PCSB | SK | BARONIA | BN-77 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.6 | 2625.91 | 2517.1 | N/A | N/A | N/A | N/A | 9877406.44 | 35.11 | NO | N/A | DRY TREE | 2018-07-20 | 2018-07-18 05:00 | 2018-11-13 15:00 | 2501.79 | SHALLOW WATER | 2626.03 | 2518.13 | N/A | N/A | N/A | N/A | 8493653.84 | 34.08 | 0.88 | 0.82 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.3 |  | 404 |  | 998 | [6 empty] | 5.26 | 1740435.98 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 2.0 | SINGLE | L80 | 73 | True |  | 9CR | 8.5 | KCL | NO | NO | Exist
2018-07-12 | 2018-10-30 | PCSB | SK | BARONIA | BN-78 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.6 | 2481.87 | 1732.4 | N/A | N/A | N/A | N/A | 9884575.55 | 29.99 | NO | N/A | DRY TREE | 2018-07-25 | 2018-07-24 12:00 | 2018-09-09 14:30 | 2496.91 | SHALLOW WATER | 2621.15 | 1736.24 | N/A | N/A | N/A | N/A | 6453919.87 | 24.15 | 0.82 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.99 |  | 508.96 |  | 757.61 | [6 empty] | 5.07 | 1449533.32 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2161.1 | False | AICD | 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-07-11 | N/A | REPSOL | PM | BUNGA PAKMA | BPA-5 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 4445 | 3310 | N/A | N/A | N/A | N/A | 9420000 | 22 | NO | N/A | DRY TREE | 2018-07-20 16:15 | 2018-07-19 02:30 | 2018-11-08 17:30 | 4557.13 | SHALLOW WATER | 4658 | 3483 | N/A | N/A | N/A | N/A | 8250000 | 23.63 | 14.6 | 13.8 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.56 |  | 490 |  | 600 | [6 empty] | 4.43 | 2716248 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 63.9764 | True | NONE | L80 13CR | 6.84 | BASE OIL/DIESEL | NO | NO | Exist
2018-07-06 | 2019-04-12 | PETROFAC | PM | CENDOR | CD-C11 | APPRAISAL CUM DEV/DEVELOPMENT | ABAN-8 | JACK UP | 62.5 | 1839 | 1600 | N/A | N/A | N/A | N/A | 6500000 | 23.7 | NO | N/A | DRY TREE | 2019-02-22 | 2019-02-20 15:00 | 2019-04-01 15:00 | 1611.05 | SHALLOW WATER | 1720 | 1533.45 | N/A | N/A | N/A | N/A | 6659223 | 29.9 | 3.76 | 3.76 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 3.28 |  | 723 |  | 1111 | [6 empty] | 8.5 | 1654065 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.5 | NACL | NO | NO | Exist
2018-07-04 | N/A | HESS | PM | BERGADING | BERGADING-A8(K) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 55.78 | 4236.51 | 3194.15 | N/A | N/A | N/A | N/A | 43800000 | 89.8 | NO | N/A | DRY TREE | 2018-08-18 | 2018-08-17 17:00 | 2019-10-07 03:30 | 4184.12 | SHALLOW WATER | 4283.15 | 3155.51 | N/A | N/A | N/A | N/A | 47370000 | 121.94 | 5.1 | 5.1 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3040 |  | 5.8 |  | 2160 |  | 3451 | [6 empty] | 15.44 | 9260000 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 22CR | 0 | True |  | 718 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-07-04 | 2019-01-07 | HESS | PM | BERGADING | BERGADING-A9(M) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 55.81 | 3748.86 | 2754.57 | N/A | N/A | N/A | N/A | 30800000 | 54.6 | NO | N/A | DRY TREE | 2018-09-08 | 2018-08-09 16:00 | 2018-11-07 02:30 | 3580.92 | SHALLOW WATER | 3679.98 | 2710.2 | N/A | N/A | N/A | N/A | 31110000 | 79.48 | 15.78 | 15.78 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.4 |  | 1413 |  | 2648 | [6 empty] | 12.79 | 4640000 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 17CR | 0 | True |  | 718 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-07-04 | 2019-07-17 | HESS | PM | BERGADING | BERGADING-A10(P) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 55.81 | 4532.15 | 2706.24 | N/A | N/A | N/A | N/A | 34470000 | 69.48 | SIDETRACK | N/A | DRY TREE | 2018-08-13 | 2018-08-12 20:00 | 2019-05-18 12:15 | 4321.85 | SHALLOW WATER | 4420.91 | 2646.08 | N/A | N/A | N/A | N/A | 32620000 | 85.83 | 19.1 | 19.1 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 4 |  | 2301 |  | 1562 | [6 empty] | 7.18 | 4510000 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 17CR | 0 | True |  | 718 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2018-06-26 | 2018-09-13 | PCSB | SB | SUMANDAK UTARA | SUMANDAK UTARA-1 | EXPLORATION/APPRAISAL | NAGA-6 | JACK UP | 38 | 1466 | 1466 | 9150000 | 13380000 | 17.63 | 35.19 | N/A | N/A | NO | N/A | N/A | 2018-07-22 | 2018-07-18 09:00 | 2018-08-10 12:00 | 1423 | SHALLOW WATER | 1496 | 1495.29 | 7622612.96 | N/A | 23.13 | N/A | N/A | N/A | 24 | 15 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2 |  | 629 |  | 1064 | [27 empty] | Exist
2018-06-08 | 2018-12-05 | JX NIPPON | SK | BERYL | BU-3 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 92 | 3768 | 1361 | N/A | N/A | N/A | N/A | 16072778 | 36.66 | NO | N/A | N/A | 2018-06-27 | 2018-06-27 16:00 | 2018-10-03 12:00 | 3622.82 | SHALLOW WATER | 3749 | 1331 | N/A | N/A | N/A | N/A | 10878190 | 34.67 | 4.99 | 4.99 | SW DEV C3 |  | 2.2 |  | 915 |  | 1580 |  | 1.95 |  | 556 |  | 910 | [27 empty] | Exist
2018-06-01 | 2018-08-16 | REPSOL | SB | AXINIT | AXINIT-1 | EXPLORATION/APPRAISAL | NAGA-5 | JACK UP | 52.4 | 1530 | 1530 | 10730000 | 10730000 | 27 | 27 | N/A | N/A | NO | N/A | N/A | 2018-06-17 | 2018-06-14 09:25 | 2018-07-16 01:00 | 1448.66 | SHALLOW WATER | 1531 | 1530.92 | 7941530.77 | N/A | 31.78 | N/A | N/A | N/A | 28.84 | 3.05 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2.77 |  | 756.6 |  | 1426.66 | [27 empty] | Exist
2018-05-23 | 2018-11-28 | PTTEP | SK | SOUTH ACIS | SAPA-01ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 34.8 | 2466 | 1482 | N/A | N/A | N/A | N/A | 10144453 | 27.72 | NO | N/A | N/A | 2018-08-26 | 2018-06-17 05:00 | 2018-09-16 12:00 | 2399 | SHALLOW WATER | 2484 | 1504.2 | N/A | N/A | N/A | N/A | 9245456 | 39.65 | 8.56 | 2.84 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 1.67 |  | 473 |  | 1415 | [27 empty] | Exist
2018-05-23 | 2018-11-28 | PTTEP | SK | SOUTH ACIS | SAPA-17ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 34.8 | 2295 | 1386 | N/A | N/A | N/A | N/A | 9395998 | 25.61 | NO | N/A | N/A | 2018-08-18 | 2018-06-28 | 2018-10-04 21:30 | 2194 | SHALLOW WATER | 2279 | 1385 | N/A | N/A | N/A | N/A | 9003088 | 32.35 | 6.05 | 6.05 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.22 |  | 676 |  | 1347 | [27 empty] | Exist
2018-05-23 | 2018-11-29 | PTTEP | SK | SOUTH ACIS | SAPA-03 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 34.8 | 1790 | 1362 | N/A | N/A | N/A | N/A | 8088331 | 18.92 | SIDETRACK | N/A | N/A | 2018-08-08 | 2018-06-28 | 2018-09-23 | 1686 | SHALLOW WATER | 1771 | 1364 | N/A | N/A | N/A | N/A | 8743457 | 37.69 | 6.19 | 6.19 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.99 |  | 656 |  | 1942 | [27 empty] | Exist
2018-05-22 | 2018-09-25 | HESS | PM | BUNGA ANDONG | BUNGA ANDONG-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 62.39 | 2310.88 | 2276.74 | 12903519 | 12903519 | 33.29 | 33.29 | N/A | N/A | SIDETRACK | N/A | N/A | 2018-06-21 | 2018-06-20 | 2018-07-31 05:00 | 2952.68 | SHALLOW WATER | 3044.8 | 2188.49 | N/A | 12556499.99 | N/A | 41.21 | N/A | N/A | 7.53 | 6.27 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.36 |  | 466.51 |  | 833.88 | [27 empty] | Exist
2018-05-21 | 2019-04-26 | PCSB | SK | BARONIA | BN-76 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 75.59 | 4218.23 | 2416.61 | N/A | N/A | N/A | N/A | 15931129.95 | 44.7 | NO | N/A | DRY TREE | 2018-10-06 | 2018-08-06 | 2019-02-26 12:00 | 4094 | SHALLOW WATER | 4218.23 | 2416.61 | N/A | N/A | N/A | N/A | 14836205.21 | 54.31 | 13.7 | 12.47 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.51 |  | 581.37 |  | 1096.66 | [6 empty] | 11.35 | 5398568.69 |  |  | SANDSTONE | NORMAL | CASED HOLE | 2 ZONES | NO | 4-1/2" | 2.0 | SINGLE | 15CR | 574 | True | ICV | 25CR | 8.5 | KCL | NO | NO | Exist
2018-05-18 | 2018-07-16 | REPSOL | PM | BUNGA PAKMA | BPA-3 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 3700 | 2899 | N/A | N/A | N/A | N/A | 11997055 | 29.5 | NO | N/A | DRY TREE | 2018-05-28 | 2018-05-27 05:30 | 2018-06-18 09:30 | 3941.13 | SHALLOW WATER | 4042 | 3189 | N/A | N/A | N/A | N/A | 7540000 | 22.17 | 0.52 | 0.29 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1600 |  | 1.83 |  | 587 |  | 661 | [6 empty] | 3.69 | 2304306 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 63.9764 | True | NONE | L80 13CR | 6.84 | BASE OIL/DIESEL | NO | NO | Exist
2018-05-03 | 2018-06-12 | REPSOL | PM | BUNGA PAKMA | BPA-2 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-3 | JACK UP | 58 | 4338 | 2938 | N/A | N/A | N/A | N/A | 11238287 | 30.5 | NO | N/A | DRY TREE | 2018-05-07 | 2018-05-06 | 2018-05-27 05:00 | 4227.13 | SHALLOW WATER | 4328 | 2937 | N/A | N/A | N/A | N/A | 7940000 | 21.23 | 14 | 14 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | No |  | No |  | No | [6 empty] | 6.44 | 2678892 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 63.9764 | True | NONE | L80 13CR | 6.84 | BASE OIL/DIESEL | NO | NO | Exist
2018-05-03 | 2019-01-02 | ENQUEST | PM | SELIGI | SEC-40 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 72.1 | 2170 | 1921.5 | N/A | N/A | N/A | N/A | 11113236 | 36.34 | NO | N/A | DRY TREE | 2018-05-26 06:00 | 2018-05-25 12:00 | 2018-07-20 06:00 | 2068.4 | SHALLOW WATER | 2174 | 1923.49 | N/A | N/A | N/A | N/A | 8094991 | 31.44 | 1 | 1 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.1 |  | 440 |  | 1208 | [6 empty] | 8.17 | 2245062 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR | 223.108 | False | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
2018-05-01 | 2018-07-27 | REPSOL | SB | REALGAR | REALGAR-2 | EXPLORATION/APPRAISAL | NAGA-5 | JACK UP | 61.3 | 1730 | 1730 | 10766130 | 10766130 | 27.93 | 27.93 | N/A | N/A | NO | N/A | N/A | 2018-05-23 | 2018-05-20 20:25 | 2018-06-11 05:00 | 1648.96 | SHALLOW WATER | 1740 | 1737.69 | 7506525.94 | N/A | 22.51 | N/A | N/A | N/A | 9.4 | 9.4 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2.58 |  | 791.96 |  | 1244.7 | [27 empty] | Exist
2018-04-24 | 2018-08-10 | HESS | PM | BUNGA TERUNTUM | BUNGA TERUNTUM-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 64.89 | 2243.52 | 2192.01 | 12838483 | 12838483 | 33.04 | 33.04 | N/A | N/A | NO | N/A | N/A | 2018-06-01 | 2018-05-30 10:00 | 2018-06-20 | 2066.31 | SHALLOW WATER | 2160.93 | 2113.96 | N/A | 6667760.8 | N/A | 20.58 | N/A | N/A | 3.74 | 3.74 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.55 |  | 498.88 |  | 983.45 | [27 empty] | Exist
2018-04-18 | 2018-12-09 | COP | SK | PATAWALI | PATAWALI-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 90.1 | 1651 | 1632 | 13726000 | 18447000 | 26.4 | 43.2 | N/A | N/A | NO | N/A | N/A | 2018-07-01 | 2018-06-28 02:30 | 2018-07-20 13:30 | 1529.5 | SHALLOW WATER | 1651 | 1629.14 | 12200000 | N/A | 27.2 | N/A | N/A | N/A | 3.9 | 2.76 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.85 |  | 831 |  | 2009 | [27 empty] | Exist
2018-03-28 | 2018-08-21 | COP | SK | SALAM | SALAM-2 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 92.2 | 1652 | 1652 | 16978000 | 20430000 | 32.5 | 46.9 | N/A | N/A | NO | N/A | N/A | 2018-05-12 | 2018-05-10 06:30 | 2018-06-27 23:00 | 1422.6 | SHALLOW WATER | 1607 | 1607 | N/A | 19400000 | N/A | 56.6 | N/A | N/A | 17.8 | 17.8 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 2.42 |  | 1148 |  | 2045 | [27 empty] | Exist
2018-03-22 | 2019-01-09 | JX NIPPON | SK | BERYL | BU-1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 92 | 2979 | 1638 | N/A | N/A | N/A | N/A | 17777537 | 44.3 | SIDETRACK | N/A | N/A | 2018-05-21 | 2018-05-20 | 2018-07-11 01:00 | 2911.82 | SHALLOW WATER | 3038 | 1617 | N/A | N/A | N/A | N/A | 19857346 | 75.08 | 33.69 | 33.69 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 2160 |  | 2.74 |  | 686 |  | 1159 | [27 empty] | Exist
2018-03-12 | 2018-07-31 | HESS | PM | PROSPECT | BUNGA KANGSAR-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 62.71 | 2523.32 | 2465.71 | 16321322 | 16321322 | 36.48 | 36.48 | N/A | N/A | NO | N/A | N/A | 2018-04-14 | 2018-04-12 16:00 | 2018-05-30 10:00 | 2352.54 | SHALLOW WATER | 2444.99 | 2389.31 | N/A | 15500000 | N/A | 47.75 | N/A | N/A | 1.4 | 1.4 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.1 |  | 1138 |  | 1648 | [27 empty] | Exist
2018-03-08 | 2018-11-15 | JX NIPPON | SK | BERYL | BU-2 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 92 | 2861 | 1360 | N/A | N/A | N/A | N/A | 14393635 | 29.9 | NO | N/A | N/A | 2018-07-04 | 2018-04-07 09:00 | 2018-11-09 09:00 | 2731.82 | SHALLOW WATER | 2858 | 1360.54 | N/A | N/A | N/A | N/A | 8554231 | 25.05 | 3.87 | 3.74 | SW DEV C3 |  | 2.2 |  | 915 |  | 1580 |  | 1.8 |  | 529 |  | 956 | [27 empty] | Exist
2018-02-20 | 2018-06-12 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI 5 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 70.1 | 2374.28 | 2132.89 | 24992000 | 24992000 | 66.2 | 66.2 | N/A | N/A | NO | N/A | N/A | 2018-03-15 19:00 | 2018-03-13 18:00 | 2018-04-12 16:00 | 2274.75 | SHALLOW WATER | 2374.58 | 2134.72 | N/A | 9470000 | N/A | 29.92 | N/A | N/A | 7.87 | 7.87 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.97 |  | 691.3 |  | 1196.9 | [27 empty] | Exist
2018-01-26 | 2018-06-08 | PCSB | SB | SAMARANG | SM-47ST | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 46.94 | 3563.85 | 2297.78 | N/A | N/A | N/A | N/A | 8450000 | 29.67 | NO | N/A | N/A | N/A | 2018-04-05 13:30 | 2018-05-10 11:30 | 3285.28 | SHALLOW WATER | 3376.1 | 2140.51 | N/A | N/A | N/A | N/A | 6736553 | 27.94 | 9.4 | 9.4 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.27 |  | 317.52 |  | 807.11 | [27 empty] | Exist
2018-01-26 | 2018-05-22 | PCSB | SB | SAMARANG | SM-50ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 46.94 | 2672.66 | 2149.65 | N/A | N/A | N/A | N/A | 9665069.23 | 25.29 | NO | N/A | N/A | 2018-02-18 | 2018-02-18 | 2018-03-27 | 2731.07 | SHALLOW WATER | 2812.56 | 2161.05 | N/A | N/A | N/A | N/A | 10107084.35 | 36.58 | 9.85 | 9.85 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.84 |  | 486 |  | 1595 | [27 empty] | Exist
2018-01-25 | 2018-05-03 | REPSOL | SB | KINABALU | KNDW-D11 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3892.11 | 3323.68 | N/A | N/A | N/A | N/A | 15980000 | 35 | NO | N/A | N/A | 2018-02-08 | 2018-02-07 13:00 | 2018-03-07 14:00 | 3817.43 | SHALLOW WATER | 3911.92 | 3343.45 | N/A | N/A | N/A | N/A | 13339603 | 29.04 | 1.65 | 1.65 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.04 |  | 385.97 |  | 1064.61 | [27 empty] | Exist
2018-01-18 | 2018-05-14 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI-4 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 65.22 | 1911 | 1900.94 | 16100000 | 16100000 | 41.7 | 41.7 | N/A | N/A | NO | N/A | N/A | 2018-02-18 | 2018-02-15 19:00 | 2018-03-13 18:00 | 1838.29 | SHALLOW WATER | 1933.25 | 1923.29 | N/A | 8200000 | N/A | 25.42 | N/A | N/A | 16.8 | 3.77 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.7 |  | 667.1 |  | 1215.9 | [27 empty] | Exist
2017-12-01 | 2018-04-03 | REPSOL | SB | KINABALU | KNDW-D01 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3647.36 | 2832 | N/A | N/A | N/A | N/A | 13934424 | 31.19 | NO | N/A | N/A | 2018-01-14 | 2018-01-12 14:00 | 2018-02-07 13:00 | 3470.28 | SHALLOW WATER | 3564.77 | 2764.34 | N/A | N/A | N/A | N/A | 11415200.41 | 25.96 | 5.22 | 1.68 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | No |  | No |  | No | [27 empty] | Exist
2017-11-29 | 2018-03-09 | REPSOL | SB | KINABALU | KNDW-D12 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 2933.56 | 2682.11 | N/A | N/A | N/A | N/A | 14200000 | 29.4 | NO | N/A | N/A | 2017-12-22 | 2017-12-21 08:30 | 2018-01-12 14:00 | 2731.73 | SHALLOW WATER | 2826.21 | 2601.66 | N/A | N/A | N/A | N/A | 10970000 | 22.23 | 7.97 | 7.87 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | No |  | No |  | No | [27 empty] | Exist
2017-11-19 | 2018-05-31 | PCSB | PM | DULANG | DULANG-D02ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 74.2 | 1602.3 | 1532.6 | N/A | N/A | N/A | N/A | 12225873.42 | 30.35 | NO | N/A | DRY TREE | 2018-04-10 | 2018-04-10 | 2018-04-20 06:00 | 1512.25 | SHALLOW WATER | 1619 | 1559.4 | N/A | N/A | N/A | N/A | 9008949.64 | 26.33 | 9.5 | 9.5 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 1.61 |  | 479.71 |  | 2139.24 | [6 empty] | 5.46 | 2552758.53 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 138 | True | NONE | L80 13CR | 8.6 | KCL | NO | 4 | Exist
2017-11-17 | 2018-06-13 | SHELL | SK | TIMI | TIMI-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 142 | 2735.45 | 2735.45 | 14649000 | 21100000 | 30 | 43.2 | N/A | N/A | SIDETRACK | N/A | N/A | 2018-01-27 | 2018-01-24 07:45 | 2018-04-08 12:00 | 2214.14 | SHALLOW WATER | 2379 | 2093 | N/A | 31070000 | N/A | 75.98 | N/A | N/A | 13.7 | 13.7 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.83 |  | 1197 |  | 2016 | [27 empty] | Exist
2017-11-17 | 2018-04-04 | PCSB | PM | DULANG | DULANG-D12ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2020 | 1517 | N/A | N/A | N/A | N/A | 14079812 | 31.98 | NO | N/A | DRY TREE | 2018-02-02 | 2018-02-02 12:00 | 2018-02-24 06:00 | 1959.23 | SHALLOW WATER | 2066 | 1546.5 | N/A | N/A | N/A | N/A | 10776573 | 32.73 | 7.1 | 1.6 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.18 |  | 370.76 |  | 1654.84 | [6 empty] | 8.2 | 3416387.18 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 72 | False | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2017-11-17 | 2018-03-02 | PCSB | SK | KAYU SUGI | KAYU SUGI-1 | EXPLORATION/APPRAISAL | WEST TELESTO | JACK UP | 75.5 | 1996 | 1680 | 8040000 | 11750000 | 30.92 | 50.32 | N/A | N/A | NO | N/A | N/A | 2017-12-03 | 2017-11-24 09:00 | 2017-12-28 12:00 | 1462.38 | SHALLOW WATER | 1575 | 1370.63 | N/A | 9737037.79 | N/A | 34.13 | N/A | N/A | 9.58 | 0.97 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.66 |  | 1104 |  | 1598 | [27 empty] | Exist
2017-11-16 | 2018-06-20 | TOTAL ENERGIES | SB | TEPAT | TEPAT-1 | EXPLORATION/APPRAISAL | MAERSK DELIVERER | TENDER ASSISTED DRILLING RIG (TADR) | 2821 | 4816 | 4816 | 50968840 | 50968840 | 58.5 | 58.5 | N/A | N/A | SIDETRACK | N/A | N/A | 2017-12-03 | 2017-12-01 | 2018-03-20 10:00 | 1464.5 | DEEP WATER | 4318 | 4294 | N/A | 59300000 | N/A | 109.4 | N/A | N/A | 34.07 | 34.07 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 9.4 |  | 4163 |  | 7177 | [27 empty] | Exist
2017-11-14 | 2018-02-23 | IPC | PM | BERTAM | BERTAM A-17 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 74.7 | 2903 | 1652 | N/A | N/A | N/A | N/A | 11500000 | 33.8 | NO | N/A | DRY TREE | 2018-01-09 | 2018-01-08 20:00 | 2018-02-06 06:00 | 3072.4 | SHALLOW WATER | 3197 | 1659 | N/A | N/A | N/A | N/A | 11200000 | 35.5 | 24.9 | 18.7 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.6 |  | 527 |  | 961 | [6 empty] | 5.5 | 3900000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 2 | 3-1/2" | 1.0 | SINGLE | L80 | 1855.9305 | True | ICD | L80 | 9.3 | BASE OIL/DIESEL | NO | NO | Exist
2017-11-13 | 2018-03-09 | PCSB | PM | UMBAI | UMBAI-1 | EXPLORATION/APPRAISAL | PVD-3 | JACK UP | 71.5 | 1984 | 1843 | 10440000 | 14990000 | 38.62 | 56.7 | N/A | N/A | NO | N/A | N/A | 2018-01-05 | 2018-01-05 04:30 | 2018-01-28 09:00 | 1532.5 | SHALLOW WATER | 1636 | 1591 | 6468581.01 | N/A | 23.19 | N/A | N/A | N/A | 7.19 | 1.08 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.24 |  | 614 |  | 1170 | [27 empty] | Exist
2017-11-09 | 2018-04-23 | MUBADALA | SK | BUAH KERAS | BUAH KERAS-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 118 | 1454 | 1444 | 12398000 | 12398000 | 25.6 | 25.6 | N/A | N/A | NO | N/A | N/A | 2018-01-31 | 2018-01-28 13:30 | 2018-02-24 22:00 | 1308 | SHALLOW WATER | 1454 | 1443.8 | 8833838 | N/A | 27.65 | N/A | N/A | N/A | 4.1 | 4.1 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.65 |  | 830 |  | 1407 | [27 empty] | Exist
2017-11-03 | 2018-03-23 | MUBADALA | SK | LOKIO | LOKIO-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 109 | 1531 | 1531 | 12887000 | 12887000 | 26.7 | 26.7 | N/A | N/A | NO | N/A | N/A | 2018-01-01 | 2017-12-27 14:45 | 2018-01-28 13:30 | 1388 | SHALLOW WATER | 1525 | 1524.95 | 10864330 | N/A | 31.95 | N/A | N/A | N/A | 7.43 | 3.72 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.64 |  | 1243 |  | 2382 | [27 empty] | Exist
2017-10-31 | 2018-02-14 | REPSOL | SB | KINABALU | KNDW-D06 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3505.64 | 2730.27 | N/A | N/A | N/A | N/A | 14893671.72 | 33.3 | NO | N/A | N/A | 2017-11-21 | 2017-11-21 02:30 | 2017-12-21 08:30 | 3468.45 | SHALLOW WATER | 3562.94 | 2759.83 | N/A | N/A | N/A | N/A | 11550561 | 30.25 | 5.7 | 5.7 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | No |  | No |  | No | [27 empty] | Exist
2017-10-27 | 2018-03-12 | PCSB | PM | BESAR | BESAR-A3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 3350 | 2147 | N/A | N/A | N/A | N/A | 14782747 | 38 | NO | N/A | DRY TREE | 2017-11-09 | 2017-11-09 08:00 | 2017-12-20 13:00 | 3432 | SHALLOW WATER | 3550 | 2193.5 | N/A | N/A | N/A | N/A | 14320347.01 | 38.71 | 6.73 | 6.62 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.98 |  | 705 |  | 1142 | [6 empty] | 9.99 | 4188699.65 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 2.0 | SINGLE | L80 13CR | 55.777 | False | NONE | L80 13CR | 11.4 | CACL2 | NO | NO | Exist
2017-10-27 | 2018-04-13 | PCSB | PM | BESAR | BESAR-A5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2373 | 1783 | N/A | N/A | N/A | N/A | 14774704 | 33 | NO | N/A | DRY TREE | 2017-12-11 | 2017-12-11 08:00 | 2018-02-17 21:00 | 2252 | SHALLOW WATER | 2370 | 1732.9 | N/A | N/A | N/A | N/A | 20876925 | 61.75 | 30.79 | 23.77 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | 1.66 |  | 659 |  | 2518 | [6 empty] | 26.23 | 10236121.4 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 4-1/2" | 2.0 | SINGLE | L80 13CR | 2050.625 | False | INNER STRING WITH SSD | L80 13CR | 9.9 | NACL | NO | NO | Exist
2017-10-25 | 2018-03-22 | SHELL | SK | JARAK | JARAK-1 | EXPLORATION/APPRAISAL | DEEP WATER NAUTILUS | SEMI-SUB | 104 | 2208 | 2208 | 15488502 | 24760000 | 25 | 32 | N/A | N/A | NO | N/A | N/A | 2017-11-29 | 2017-11-23 | 2018-01-19 | 1802 | SHALLOW WATER | 1929 | 1929 | N/A | 25835388 | N/A | 62.34 | N/A | N/A | 35 | 35 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 6.79 |  | 2421 |  | 4369 | [27 empty] | Missing
2017-10-18 | 2018-12-13 | PCSB | SK | TEMANA | TE-80 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 30 | 1980 | 1259 | N/A | N/A | N/A | N/A | 10928045.53 | 32.28 | NO | N/A | DRY TREE | 2018-11-05 | 2018-11-03 21:30 | 2018-12-01 18:00 | 1893.2 | SHALLOW WATER | 1960 | 1251.69 | N/A | N/A | N/A | N/A | 8260521.06 | 27.85 | 1.76 | 1.61 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.76 |  | 465 |  | 1069 | [6 empty] | 12.08 | 4913100.64 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | DUAL | L80 | 1519 | False |  | 9CR | 9.9 | NACL | NO | NO | Exist
2017-10-17 | N/A | PCSB | PM | GANSAR | GANSAR-2 | EXPLORATION/APPRAISAL | PVD-3 | JACK UP | 80.8 | 2942 | 2942 | 18522218.49 | 18522218.49 | 47.4 | 47.4 | N/A | N/A | NO | N/A | N/A | 2017-10-25 | 2017-10-25 | 2018-01-05 04:30 | 2822.2 | SHALLOW WATER | 2935 | 2934.81 | 16166952.72 | N/A | 72.19 | N/A | N/A | N/A | 32.08 | 1.83 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.57 |  | 590 |  | 1031 | [27 empty] | Exist
2017-10-13 | 2018-01-15 | PCSB | SB | SAMARANG ASAM PAYA | SUMAZAU-1 | EXPLORATION/APPRAISAL | WEST TELESTO | JACK UP | 26.1 | 2267 | 2065 | 9286952.7 | 17869285.73 | 26 | 53.8 | N/A | N/A | NO | N/A | N/A | 2017-11-04 | 2017-10-26 08:30 | 2017-11-24 09:00 | 2167.75 | SHALLOW WATER | 2231.8 | 2032.6 | 7107679.28 | N/A | 29.02 | N/A | N/A | N/A | 17.7 | 6.14 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 0.95 |  | 338 |  | 574 | [27 empty] | Exist
2017-10-13 | 2018-07-02 | ROC OIL | SK | J4 | J4-A06ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 53.34 | 1796.71 | 1676.62 | N/A | N/A | N/A | N/A | 13190000 | 31.14 | NO | N/A | N/A | 2018-02-17 | 2017-11-22 14:30 | 2018-05-01 | 1740.02 | SHALLOW WATER | 1836.33 | 1707.41 | N/A | N/A | N/A | N/A | 13037497.49 | 51.23 | 2.85 | 2.36 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 5.61 |  | 1677 |  | 2533 | [27 empty] | Exist
2017-10-13 | 2018-06-11 | ROC OIL | SK | J4 | J4-A02ST1 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 53.34 | 3051.51 | 1934.17 | N/A | N/A | N/A | N/A | 13889593.17 | 46.68 | SIDETRACK | N/A | N/A | 2017-12-22 | 2017-12-05 12:00 | 2018-04-07 04:30 | 2646.75 | SHALLOW WATER | 2743.07 | 2039.93 | N/A | N/A | N/A | N/A | 16493471.31 | 71.6 | 12.03 | 12.03 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 4.41 |  | 1398 |  | 2035 | [27 empty] | Exist
2017-10-05 | 2017-12-27 | SAPURA OMV | PM | EAST BELUMUT | EB A-04ST1 | APPRAISAL CUM DEV/DEVELOPMENT | HAKURYU-11 | JACK UP | 71.8 | 2525 | 1166 | N/A | N/A | N/A | N/A | 5028104 | 11.12 | NO | N/A | N/A | 2017-10-23 09:30 | 2017-10-23 | 2017-11-02 | 2430.9 | SHALLOW WATER | 2548 | 1170 | N/A | N/A | N/A | N/A | 4197764 | 13.42 | 10.64 | 10.64 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.38 |  | 273.81 |  | 715.66 | [27 empty] | Exist
2017-09-29 | 2018-01-26 | PCSB | SK | TUKAU TIMUR | TT-A6 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 4178.3 | 4110.94 | N/A | N/A | N/A | N/A | 24438636.31 | 71.29 | NO | N/A | DRY TREE | 2017-10-13 | 2017-10-12 13:00 | 2017-12-08 20:30 | 4089.76 | SHALLOW WATER | 4177.08 | 4108.53 | N/A | N/A | N/A | N/A | 16411124.39 | 56.29 | 2.1 | 1.81 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.53 |  | 760.75 |  | 1170.1 | [6 empty] | 13.38 | 4377377 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 3.0 | SINGLE | L80 13CR | 1045 | False |  | L80 13CR | 10.2 | CACL2 | NO | NO | Exist
2017-09-28 | 2018-01-18 | REPSOL | SB | KINABALU | KNDW-D07 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3170.37 | 2849.74 | N/A | N/A | N/A | N/A | 15300000 | 33.82 | NO | N/A | N/A | 2017-10-22 | 2017-10-20 08:00 | 2017-11-21 02:30 | 3101.19 | SHALLOW WATER | 3195.67 | 2908.13 | N/A | N/A | N/A | N/A | 12712938.32 | 31.77 | 8.16 | 5.93 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | No |  | No |  | No | [27 empty] | Exist
2017-09-18 | 2018-05-23 | PCSB | PM | DULANG | DULANG-D13ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2373 | 1381 | N/A | N/A | N/A | N/A | 14764740 | 34.84 | NO | N/A | DRY TREE | 2018-01-19 | 2017-09-26 17:00 | 2018-03-30 | 2423.23 | SHALLOW WATER | 2530 | 1434.6 | N/A | N/A | N/A | N/A | 17469053 | 56.7 | 44 | 34.7 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 1.61 |  | 472.65 |  | 2042.1 | [6 empty] | 21.91 | 7280662.69 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 115 | False | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2017-09-13 | 2018-01-26 | PCSB | PM | BESAR | BESAR-A1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 2273 | 2178 | N/A | N/A | N/A | N/A | 11671474 | 22.9 | NO | N/A | DRY TREE | 2017-09-18 | 2017-09-18 03:00 | 2017-11-09 08:00 | 2156 | SHALLOW WATER | 2274 | 2194.8 | N/A | N/A | N/A | N/A | 7302918 | 16.92 | 0.25 | 0.25 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.74 |  | 610 |  | 935 | [6 empty] | 3.94 | 2335645.07 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 13CR | 95.149 | False | NONE | L80 13CR | 8.3 | SEAWATER/DRILLWATER | NO | NO | Exist
2017-09-12 | 2018-01-26 | VESTIGO | SK | BENTARA | BENTARA-A1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 64.7 | 3900 | 2616 | N/A | N/A | N/A | N/A | 11421943 | 48.1 | NO | N/A | DRY TREE | 2017-10-30 19:00 | 2017-10-18 15:30 | 2017-12-03 12:45 | 3192.9 | SHALLOW WATER | 3295 | 2639.5 | N/A | N/A | N/A | N/A | 11009574 | 45.89 | 3.63 | 2.77 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.95 |  | 498 |  | 754 | [6 empty] | 9.01 | 2572805.25 |  |  | SANDSTONE | NORMAL | OPEN HOLE PREDRILLED LINER & CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 742 | True |  | L80 13CR | 9.1 | NACL | NO | NO | Exist
2017-09-07 | 2018-03-15 | PCSB | PM | DULANG | DULANG-D10ST1 (WI) | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2392 | 1431 | N/A | N/A | N/A | N/A | 13695700 | 29.92 | NO | N/A | DRY TREE | 2017-09-15 | 2017-09-15 | 2018-01-08 | 2319.23 | SHALLOW WATER | 2426 | 1448 | N/A | N/A | N/A | N/A | 13915234 | 46.34 | 33.7 | 1.9 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.58 |  | 535 |  | 1874 | [6 empty] | 7.16 | 2624537.52 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 4.0 | SINGLE | L80 13CR | 157.488 | False | NONE | L80 13CR | 8.6 | KCL | NO | NO | Exist
2017-09-05 | 2018-03-12 | SAPURA OMV | SK | PEPULUT | PEPULUT-01 | EXPLORATION/APPRAISAL | HAKURYU-11 | JACK UP | 83.6 | 2759 | 2759 | 11141554 | 11142000 | 33.3 | 41.9 | N/A | N/A | NO | N/A | N/A | 2017-12-17 | 2017-12-14 18:30 | 2018-01-27 14:00 | 2521.8 | SHALLOW WATER | 2640 | 2637.72 | N/A | 10249000 | N/A | 43.8 | N/A | N/A | 2.7 | 2.7 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.2 |  | 649 |  | 1216 | [27 empty] | Exist
2017-09-05 | 2018-12-09 | SAPURA OMV | SK | SK408 | REMUJUNG-01 | EXPLORATION/APPRAISAL | HAKURYU-11 | JACK UP | 84.8 | 2344 | 2344 | 10559111 | 10559111 | 32 | 32 | N/A | N/A | NO | N/A | N/A | 2017-11-20 21:00 | 2017-11-13 02:30 | 2017-12-14 18:30 | 2168.6 | SHALLOW WATER | 2288 | 2288 | N/A | 7340000 | N/A | 31.67 | N/A | N/A | 5.99 | 5.79 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.5 |  | 668 |  | 945 | [27 empty] | Exist
2017-09-05 | 2018-01-21 | PCSB | PM | BESAR | BESAR-A2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 69.8 | 3515 | 2127 | N/A | N/A | N/A | N/A | 17474595 | 38 | NO | N/A | DRY TREE | 2017-09-15 | 2017-09-15 | 2017-11-30 05:00 | 3432 | SHALLOW WATER | 3550 | 2147.5 | N/A | N/A | N/A | N/A | 15171175 | 38.42 | 3.15 | 1.95 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.77 |  | 691 |  | 1293 | [6 empty] | 15.78 | 5956622.19 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 2.0 | SINGLE | L80 13CR | 157.488 | False | NONE | L80 13CR | 11.8 | CACL2 | NO | NO | Exist
2017-09-04 | 2018-01-24 | JX NIPPON | SB | BESTARI | BESTARI-3 | EXPLORATION/APPRAISAL | MAERSK DELIVERER | TENDER ASSISTED DRILLING RIG (TADR) | 1096.3 | 2267 | 2246 | 16147000 | 16147000 | 24.4 | 24.4 | N/A | N/A | NO | N/A | N/A | 2017-11-04 | 2017-11-02 05:30 | 2017-11-27 | 1104.2 | DEEP WATER | 2233 | 2215.3 | N/A | 14300000 | N/A | 25.5 | N/A | N/A | 3.3 | 3.3 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 3.92 |  | 2482 |  | 3957 | [27 empty] | Exist
2017-09-01 | 2017-12-19 | REPSOL | SB | KINABALU | KNDW-D14 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 54.25 | 3670.53 | 2501.07 | N/A | N/A | N/A | N/A | 15800000 | 36.6 | NO | N/A | N/A | 2017-09-20 | 2017-09-20 00:30 | 2017-10-20 08:00 | 3575.13 | SHALLOW WATER | 3669.61 | 2488.3 | N/A | N/A | N/A | N/A | 11141603.49 | 30.3 | 21 | 21 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | No |  | No |  | No | [27 empty] | Exist
2017-08-17 | N/A | SHELL | SB | MALIKAI | MLK-124 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 3050.9 | 1593.72 | N/A | N/A | N/A | N/A | 26511449 | 39.05 | NO | N/A | N/A | 2017-09-17 | 2017-09-17 | 2017-12-15 | 2404.3 | DEEP WATER | 2935.69 | 1548.61 | N/A | N/A | N/A | N/A | 19924119 | 48.52 | 15.52 | 15.37 | No DMS category | [7 empty] | 3.42 |  | 1126 |  | 2069 | [27 empty] | Exist
2017-08-15 | 2017-12-25 | SAPURA OMV | PM | EAST BELUMUT | EAST BELUMUT A-13 ST2 | APPRAISAL CUM DEV/DEVELOPMENT | HAKURYU-11 | JACK UP | 72.7 | 1465 | 1135 | N/A | N/A | N/A | N/A | 6586175 | 17.15 | NO | N/A | N/A | 2017-09-20 09:30 | 2017-09-15 | 2017-10-04 09:30 | 2655.5 | SHALLOW WATER | 2774 | 1128.24 | N/A | N/A | N/A | N/A | 5741906 | 19.4 | 2.58 | 2.58 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 1.36 |  | 312.42 |  | 812.09 | [27 empty] | Exist
2017-08-15 | 2017-12-12 | SAPURA OMV | PM | EAST BELUMUT | EAST BELUMUT A-10 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | HAKURYU-11 | JACK UP | 72.8 | 1462 | 1118 | N/A | N/A | N/A | N/A | 6855463 | 16.52 | NO | N/A | N/A | 2017-10-07 15:30 | 2017-10-04 | 2017-10-20 02:00 | 3073.4 | SHALLOW WATER | 3192 | 1169.77 | N/A | N/A | N/A | N/A | 5632404 | 15.69 | 3.65 | 3.65 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.01 |  | 280.6 |  | 690.82 | [27 empty] | Exist
2017-08-03 | 2018-04-02 | HESS | PM | BERGADING | BERGADING-A7(O) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.39 | 3103.63 | 2647.36 | N/A | N/A | N/A | N/A | 34700000 | 64.6 | NO | N/A | DRY TREE | 2017-12-11 | 2017-12-11 | 2018-02-07 03:30 | 3001.49 | SHALLOW WATER | 3102.1 | 2648.95 | N/A | N/A | N/A | N/A | 25700000 | 57.25 | 13.06 | 11.97 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.8 |  | 2065 |  | 3491 | [6 empty] | 9.33 | 7970000 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 22CR | 0 | True |  | 718 | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2017-07-31 | 2017-12-04 | PCSB | SB | ZUHAL SOUTH | ZUHAL SOUTH-1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST TELESTO | JACK UP | 41.9 | 3938 | 2286 | N/A | N/A | N/A | N/A | 15623000 | 58.5 | NO | N/A | N/A | 2017-09-07 08:00 | 2017-09-06 15:00 | 2017-10-17 07:00 | 3867.7 | SHALLOW WATER | 3951 | 2290 | N/A | N/A | N/A | N/A | 9558440.08 | 40.67 | 2.84 | 2.48 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2415 |  | 2.52 |  | 578 |  | 752 | [27 empty] | Exist
2017-07-11 | 2018-03-09 | PCSB | SB | SAMARANG | SM-121 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 3735.75 | 2284.41 | N/A | N/A | N/A | N/A | 10246181.68 | 31.59 | NO | N/A | DRY TREE | 2017-08-13 | 2017-08-13 13:30 | 2018-01-08 08:30 | 3394.39 | SHALLOW WATER | 3438.89 | 2110.03 | N/A | N/A | N/A | N/A | 9872556.08 | 35.06 | 9.69 | 4.93 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2015 |  | 1.86 |  | 460 |  | 879 | [6 empty] | 9.7 | 2798184 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 | 773 | False | NONE | L80 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2017-07-10 | 2017-10-20 | PCSB | SK | PELAJO | PELAJO-1 | EXPLORATION/APPRAISAL | WEST TELESTO | JACK UP | 70 | 1430 | 1430 | 4590000 | 6499756 | 16.35 | 27.78 | N/A | N/A | NO | N/A | N/A | 2017-07-28 | 2017-07-21 | 2017-08-24 | 1146 | SHALLOW WATER | 1253 | 1218 | N/A | 5965569.35 | N/A | 33.7 | N/A | N/A | 31.33 | 31.23 | No DMS category | [7 empty] | 2.77 |  | 627 |  | 836 | [27 empty] | Exist
2017-07-07 | 2017-12-15 | VESTIGO | PM | SEWOK | SEROK-7 | EXPLORATION/APPRAISAL | NAGA-2 | JACK UP | 95.4 | 3667 | 2509 | 14420000 | 14420000 | 50.57 | 50.57 | N/A | N/A | SIDETRACK | N/A | N/A | 2017-08-20 | 2017-08-12 | 2017-10-18 15:30 | 3513.6 | SHALLOW WATER | 3643 | 2521.5 | N/A | 13654805.41 | N/A | 67.65 | N/A | N/A | 15.63 | 14.26 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.21 |  | 479 |  | 770 | [27 empty] | Exist
2017-07-03 | 2018-03-02 | PCSB | SB | SAMARANG | SM-118 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 33 | 7345 | 6530 | N/A | N/A | N/A | N/A | 11970000 | 26.46 | NO | N/A | DRY TREE | 2017-08-19 | 2017-08-18 11:00 | 2018-01-01 08:30 | 7237 | SHALLOW WATER | 7345 | 6634 | N/A | N/A | N/A | N/A | 9284967.95 | 29.24 | 11.32 | 11.04 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 1.87 |  | 475 |  | 1263 | [6 empty] | 12.26 | 3988335 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 1215 | True | NONE | L80 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2017-07-03 | 2018-02-21 | PCSB | SB | SAMARANG | SM-120 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 2727.83 | 2071.93 | N/A | N/A | N/A | N/A | 9200000 | 23.85 | NO | N/A | DRY TREE | 2017-08-29 | 2017-08-29 07:30 | 2017-12-22 02:30 | 2733.01 | SHALLOW WATER | 2773.54 | 2110.25 | N/A | N/A | N/A | N/A | 6685909.29 | 25.45 | 10.06 | 9.24 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 1.16 |  | 305 |  | 747 | [6 empty] | 11.88 | 3186638 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 116 | False | NONE | L80 13CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2017-07-03 | 2018-12-12 | PCSB | SB | SAMARANG | SM-119ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 3937.82 | 2027.82 | N/A | N/A | N/A | N/A | 13592462.65 | 34.23 | NO | N/A | DRY TREE | 2017-08-15 | 2017-08-12 09:30 | 2017-12-07 01:30 | 3745.81 | SHALLOW WATER | 3790.31 | 2028.04 | N/A | N/A | N/A | N/A | 17726681.59 | 59.1 | 37.36 | 37.29 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2080 |  | 2.34 |  | 643 |  | 886 | [6 empty] | 12.17 | 4656253.78 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 2311 | True | ICD | L80 13CR | 10.5 | CACL2 | NO | NO | Exist
2017-06-22 | 2017-10-09 | OPHIR | PM | OPHIR | OPHIR-A3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 72.9 | 3082 | 1479 | N/A | N/A | N/A | N/A | 8068810 | 23.18 | NO | N/A | N/A | 2017-07-10 | 2017-07-10 14:45 | 2017-07-26 23:15 | 3215.46 | SHALLOW WATER | 3332 | 1486.35 | N/A | N/A | N/A | N/A | 5456381 | 16.16 | 4.7 | 4.7 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.1 |  | 372 |  | 517 | [27 empty] | Exist
2017-06-15 | 2017-10-17 | PCSB | PM | PUTERI | PUTERI BASEMENT-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 60 | 2832 | 2568 | 16085269.32 | 22685065.88 | 36.64 | 58.58 | N/A | N/A | NO | N/A | N/A | 2017-07-15 | 2017-07-10 06:00 | 2017-09-04 10:00 | 2798.4 | SHALLOW WATER | 2888.4 | 2596.4 | N/A | 15600000 | N/A | 56.17 | N/A | N/A | 2.53 | 2.47 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.48 |  | 838 |  | 1106 | [27 empty] | Exist
2017-05-20 | 2017-10-27 | SAPURA OMV | SK | B15 | B15-A1 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 78 | 3181 | 3163.32 | N/A | N/A | N/A | N/A | 61000000 | 106.25 | SIDETRACK | N/A | N/A | 2017-06-06 | 2017-05-28 22:00 | 2017-08-12 03:30 | 3041.2 | SHALLOW WATER | 3162 | 3145 | N/A | N/A | N/A | N/A | 31875000 | 75.23 | 13.03 | 13.03 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 4.78 |  | 1672 |  | 3194 | [27 empty] | Exist
2017-04-07 | 2017-08-25 | OPHIR | PM | OPHIR | OPHIR-A2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 72.9 | 3071 | 1474 | N/A | N/A | N/A | N/A | 8101276 | 23.61 | NO | N/A | N/A | 2017-05-06 | 2017-05-06 19:15 | 2017-06-26 06:30 | 2953.46 | SHALLOW WATER | 3070 | 1484.34 | N/A | N/A | N/A | N/A | 4972381 | 14.55 | 1.65 | 0.93 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1 |  | 337 |  | 513 | [27 empty] | Exist
2017-04-07 | 2017-09-21 | OPHIR | PM | OPHIR | OPHIR-A1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 72.9 | 2950 | 1478 | N/A | N/A | N/A | N/A | 8192583 | 23.8 | SIDETRACK | N/A | N/A | 2017-06-01 | 2017-06-01 22:30 | 2017-07-10 14:15 | 3158.46 | SHALLOW WATER | 3275 | 1485.2 | N/A | N/A | N/A | N/A | 7740985 | 23.82 | 12.9 | 10.32 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.5 |  | 436 |  | 589 | [27 empty] | Exist
2017-04-03 | 2017-11-13 | ROC OIL | SK | D21 | D21-A8 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 50.59 | 3009.45 | 2187.14 | N/A | N/A | N/A | N/A | 13420561.58 | 26.15 | NO | N/A | N/A | 2017-06-28 | 2017-06-28 | 2017-09-13 | 2901.86 | SHALLOW WATER | 2998.17 | 2175.56 | N/A | N/A | N/A | N/A | 10113672.66 | 28.23 | 2 | 2 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | No |  | No |  | No | [27 empty] | Exist
2017-03-31 | 2017-09-21 | PCSB | SK | F12 | F12-A2 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 101.2 | 2935.3 | 1446.7 | N/A | N/A | N/A | N/A | 21850567.6 | 32.12 | NO | N/A | DRY TREE | 2017-05-13 | 2017-05-13 03:00 | 2017-08-02 | 2759.6 | SHALLOW WATER | 2896 | 1446.8 | N/A | N/A | N/A | N/A | 12399424.88 | 30.5 | 6 | 3 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.7 |  | 633 |  | 1100 | [6 empty] | 7.13 | 4415879.43 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | L80 13CR |  | False | NONE | 13CR | 11.2 | CACL2 | NO | NO | Exist
2017-03-31 | 2017-09-21 | PCSB | SK | F12 | F12-A1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 101.2 | 2538.32 | 1429.78 | N/A | N/A | N/A | N/A | 23089240 | 34.89 | NO | N/A | DRY TREE | 2017-05-09 | 2017-05-08 05:00 | 2017-08-03 | 2181.6 | SHALLOW WATER | 2318 | 1419.3 | N/A | N/A | N/A | N/A | 13320172.86 | 31.21 | 6.3 | 0.83 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 1.75 |  | 671.1 |  | 1162.1 | [6 empty] | 7.2 | 4351645.6 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | L80 13CR |  | True | NONE | 13CR | 11.2 | CACL2 | NO | NO | Exist
2017-03-31 | 2017-09-06 | PCSB | SK | F12 | F12-A3 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 100.89 | 2760.16 | 1456.98 | N/A | N/A | N/A | N/A | 24074312.59 | 33.46 | NO | N/A | DRY TREE | 2017-05-16 | 2017-05-15 15:00 | 2017-05-30 14:45 | 2388.91 | SHALLOW WATER | 2525 | 1446.79 | N/A | N/A | N/A | N/A | 12411318.26 | 26.09 | 0.8 | 0 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1635 |  | 1.91 |  | 767.9 |  | 1394.4 | [6 empty] | 7.22 | 4862831.05 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | L80 13CR |  | True | NONE | 13CR | 11.2 | CACL2 | NO | NO | Exist
2017-03-16 | 2017-05-29 | PTTEP | SK | SOUTH ACIS | SASA-19 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 40.85 | 2532.49 | 1561.5 | N/A | N/A | N/A | N/A | 8309198 | 20.29 | SIDETRACK | N/A | DRY TREE | 2017-04-15 | 2017-04-10 | 2017-05-07 | 3952.69 | SHALLOW WATER | 2310 | 1573.14 | N/A | N/A | N/A | N/A | 7214455 | 27.13 | 1.03 | 0.92 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 1.22 |  | 323.59 |  | 600.48 | [6 empty] | 1.42 | 384000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 80 | True |  | L80 | 9.6 | CACL2 | NO | NO | Exist
2017-03-08 | 2017-07-10 | VESTIGO | PM | TEMBIKAI | TBK-A4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-2 | JACK UP | 70.7 | 4172 | 2149 | N/A | N/A | N/A | N/A | 8269000 | 30.8 | NO | N/A | N/A | N/A | 2017-04-01 16:30 | 2017-05-26 22:00 | 4046.5 | SHALLOW WATER | 4160 | 2191 | N/A | N/A | N/A | N/A | 9693904 | 55.18 | 15.68 | 15.68 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.9 |  | 426 |  | 631 | [27 empty] | Exist
2017-02-27 | 2017-11-10 | ROC OIL | SK | D21 | D21-A6 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 50.59 | 2573.91 | 2181.96 | N/A | N/A | N/A | N/A | 10258901.57 | 26.15 | NO | N/A | N/A | 2017-05-10 | 2017-05-03 | 2017-09-11 | 2552.27 | SHALLOW WATER | 2648.58 | 2177.99 | N/A | N/A | N/A | N/A | 10672156 | 26.15 | 1.68 | 1.68 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | No |  | No |  | No | [27 empty] | Exist
2017-02-15 | 2017-07-21 | PCSB | SK | TUKAU TIMUR | TT-A8 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 5117.34 | 4153.92 | N/A | N/A | N/A | N/A | 28502856.36 | 75.48 | NO | N/A | DRY TREE | 2017-03-08 | 2017-03-07 21:00 | 2017-06-02 10:00 | 5012.34 | SHALLOW WATER | 5099.66 | 4139.53 | N/A | N/A | N/A | N/A | 24885275.12 | 86.54 | 10.11 | 9.75 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.49 |  | 728.22 |  | 1513.06 | [6 empty] | 17.98 | 7345348 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 3.0 | SINGLE | L80 13CR | 1347 | True |  | L80 13CR | 9.5 | NACL | NO | NO | Exist
2017-01-26 | 2017-08-09 | PETROFAC | PM | WEST DESARU | WD-A18 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-5 | JACK UP | 65.8 | 4466 | 1636 | N/A | N/A | N/A | N/A | 12000000 | 37.8 | NO | N/A | DRY TREE | 2017-05-27 | 2017-05-26 03:45 | 2017-07-15 03:30 | 4344.74 | SHALLOW WATER | 4454 | 1627 | N/A | N/A | N/A | N/A | 14697381 | 49.9 | 9.5 | 9.5 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1680 |  | No |  | No |  | No | [6 empty] | 6.9 | 2701787.61 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 2-7/8" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.3 | NACL | 1 | NO | Exist
2017-01-09 | 2017-12-29 | HESS | PM | BERGADING | BERGADING-A4(E) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 2825.36 | 2744.29 | N/A | N/A | N/A | N/A | 41648190.93 | 82.6 | NO | N/A | N/A | 2017-02-07 10:30 | 2017-02-07 07:00 | 2017-10-30 23:00 | 2710.45 | SHALLOW WATER | 2811.03 | 2728.13 | N/A | N/A | N/A | N/A | 32400000 | 69.6 | 10.14 | 10.14 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 3.5 |  | 1900 |  | 2590 | [27 empty] | Exist
2017-01-09 | 2017-07-06 | SAPURA OMV | PM | WEST BELUMUT | WEST BELUMUT A-06 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 4110 | 1163 | N/A | N/A | N/A | N/A | 10062751 | 20.02 | NO | N/A | N/A | 2017-04-20 19:15 | 2017-04-20 | 2017-05-12 13:00 | 3056.13 | SHALLOW WATER | 3167 | 1167.14 | N/A | N/A | N/A | N/A | 7772706 | 22.54 | 4.31 | 4.31 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.73 |  | 484.99 |  | 775.17 | [27 empty] | Exist
2017-01-09 | 2017-06-14 | SAPURA OMV | PM | WEST BELUMUT | WEST BELUMUT A-05 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 3131 | 1163 | N/A | N/A | N/A | N/A | 8640870 | 17.09 | NO | N/A | N/A | 2017-03-31 | 2017-03-30 | 2017-04-19 | 3082.13 | SHALLOW WATER | 3193 | 1164.46 | N/A | N/A | N/A | N/A | 7548819 | 20.65 | 1.92 | 1.92 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.43 |  | 394.65 |  | 707.41 | [27 empty] | Exist
2017-01-09 | 2017-07-25 | SAPURA OMV | PM | WEST BELUMUT | WEST BELUMUT A-04 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 2846 | 1163 | N/A | N/A | N/A | N/A | 8597790 | 17.43 | NO | N/A | N/A | 2017-03-26 03:15 | 2017-03-25 09:30 | 2017-05-26 15:00 | 2793.7 | SHALLOW WATER | 2904.6 | 1174.8 | N/A | N/A | N/A | N/A | 6611474 | 19.04 | 0.82 | 0.82 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.45 |  | 412.76 |  | 721.24 | [27 empty] | Exist
2016-12-19 | 2017-06-02 | COP | SK | LANGSAT | LANGSAT-1 | EXPLORATION/APPRAISAL | NOBLE BULLY-2 | HYDRAULIC WORKOVER UNIT (HWU) | 1587.1 | 4725 | 4725 | 57340000 | 70340000 | 59.1 | 83.1 | N/A | N/A | NO | N/A | N/A | 2017-02-08 | 2017-02-04 09:30 | 2017-03-04 07:30 | 1080.8 | DEEP WATER | 4280 | 4273.15 | 40270000 | N/A | 57.9 | N/A | N/A | N/A | 17.67 | 15.29 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 5.4 |  | 3890 |  | 4601 | [27 empty] | Exist
2016-12-15 | 2017-09-02 | SHELL | SB | MALIKAI | MLK-113 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 1883.88 | 1554.71 | N/A | N/A | N/A | N/A | 24904623 | 42.78 | NO | N/A | N/A | 2017-02-17 | 2017-02-09 | 2017-05-13 | 1358.27 | DEEP WATER | 1889.67 | 1509.44 | N/A | N/A | N/A | N/A | 15827000 | 42.22 | 20 | 20 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | No |  | No |  | No | [27 empty] | Exist
2016-11-20 | 2017-04-12 | PCSB | SK | TUKAU TIMUR | TT-A5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 5558.06 | 3751.9 | N/A | N/A | N/A | N/A | 30055455.78 | 78.09 | NO | N/A | DRY TREE | 2016-12-12 | 2016-12-12 17:00 | 2017-03-08 | 5375.04 | SHALLOW WATER | 5462.36 | 3682.66 | N/A | N/A | N/A | N/A | 21567273.69 | 65.76 | 3.56 | 3.47 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.1 |  | 599.43 |  | 1276.55 | [6 empty] | 19.54 | 8396277.78 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 3.0 | SINGLE | L80 13CR | 1977.8 | True |  | L80 13CR | 9.1 | NACL | NO | NO | Exist
2016-10-27 | 2017-02-17 | PCSB | SK | SADOK | SADOK-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 94 | 1960 | 1960 | 14404370 | 15620940 | 39.5 | 44.4 | N/A | N/A | NO | N/A | N/A | 2016-11-26 | 2016-11-23 04:00 | 2017-01-08 09:00 | 1866 | SHALLOW WATER | 1994 | 1993.94 | N/A | 12758456.72 | N/A | 46.21 | N/A | N/A | 25 | 21.9 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 3.52 |  | 1163 |  | 1703 | [27 empty] | Exist
2016-10-25 | 2017-03-22 | PCSB | SB | UNGGUL | UNGGUL-1 | EXPLORATION/APPRAISAL | NOBLE BULLY-2 | HYDRAULIC WORKOVER UNIT (HWU) | 1453.5 | 2938 | 2938 | 60813704 | 60813704 | 79 | 79 | N/A | N/A | NO | N/A | N/A | 2016-11-20 | 2016-11-18 | 2017-01-27 03:00 | 1610.5 | DEEP WATER | 3089 | 3089 | N/A | 42400000 | N/A | 70.1 | N/A | N/A | 9.54 | 9.54 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 7.01 |  | 5407 |  | 7374 | [27 empty] | Exist
2016-10-24 | 2017-05-24 | HESS | PM | BERGADING | BERGADING-A1(A) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 2970.44 | 1211.22 | N/A | N/A | N/A | N/A | 12540000 | 19.77 | SUSPEND | N/A | DRY TREE | 2016-11-14 | 2016-11-14 09:30 | 2017-02-04 07:00 | 2858.27 | SHALLOW WATER | 2958.85 | 1205.43 | N/A | N/A | N/A | N/A | 12306000 | 37.13 | 10.72 | 10.49 | No DMS category | [7 empty] | 1.84 |  | 666.51 |  | 1310.05 | [6 empty] | 12.88 | 4970717 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 1247.5 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-10-20 | N/A | SHELL | SB | MALIKAI | MLK-122 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 2028.65 | 1554.1 | N/A | N/A | N/A | N/A | 28640253 | 46.77 | NO | N/A | N/A | 2016-11-25 | 2016-11-19 | 2017-01-02 | 1521.33 | DEEP WATER | 2052.73 | 1554.55 | N/A | N/A | N/A | N/A | 29861018.69 | 73.94 | 32.04 | 32.03 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | No |  | No |  | No | [27 empty] | Exist
2016-10-12 | 2017-05-24 | HESS | PM | BERGADING | BERGADING-A2(C) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 3265.16 | 1211.22 | N/A | N/A | N/A | N/A | 24662821 | 36.2 | NO | N/A | DRY TREE | 2016-11-17 | 2016-11-17 05:30 | 2017-01-23 | 3145.38 | SHALLOW WATER | 3245.96 | 1199.46 | N/A | N/A | N/A | N/A | 8689400.2 | 23.44 | 4.98 | 4.27 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 1.18 |  | 495.98 |  | 840.46 | [6 empty] | 8.19 | 3196307 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 178 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-10-12 | 2017-05-24 | HESS | PM | BERGADING | BERGADING-A3(B) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 2963.43 | 1194.76 | N/A | N/A | N/A | N/A | 18750000 | 30.36 | SUSPEND | N/A | DRY TREE | 2016-11-16 | 2016-11-16 03:30 | 2017-01-18 06:30 | 2660.77 | SHALLOW WATER | 2761.35 | 1207.75 | N/A | N/A | N/A | N/A | 7868000 | 21.58 | 2.99 | 2.99 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.33 |  | 541.84 |  | 888.82 | [6 empty] | 5.46 | 2553487 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 145 | False |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-10-12 | 2017-02-17 | PCSB | SK | TUKAU TIMUR | TT-A2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 4427.31 | 3547.09 | N/A | N/A | N/A | N/A | 29082946.67 | 76.7 | NO | N/A | DRY TREE | 2016-10-30 | 2016-10-22 21:00 | 2017-01-06 | 4345.63 | SHALLOW WATER | 4432.95 | 3548.86 | N/A | N/A | N/A | N/A | 20846289.56 | 67.74 | 5.6 | 5.6 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.54 |  | 671.09 |  | 1340.68 | [6 empty] | 17.53 | 8936706.24 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 3.0 | SINGLE | L80 13CR | 1357.9 | True |  | L80 13CR | 9.4 | NACL | NO | NO | Exist
2016-08-04 | 2017-02-03 | PCSB | SK | NC3 | NC3-A5 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 104 | 3842 | 2973 | N/A | N/A | N/A | N/A | 41815415.67 | 53.47 | NO | N/A | N/A | 2016-08-06 | 2016-08-05 | 2016-12-21 | 3687.1 | SHALLOW WATER | 3824 | 2996 | N/A | N/A | N/A | N/A | 52995750.59 | 76.54 | 11.89 | 1.39 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1635 |  | 3.2 |  | 1896 |  | 3341 | [27 empty] | Exist
2016-06-14 | 2016-10-11 | PCSB | SB | LAKUM | LAKUM-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 120.6 | 3225 | 3225 | 20000000 | 25300000 | 41.8 | 56.5 | N/A | N/A | NO | N/A | N/A | 2016-07-11 | 2016-07-02 | 2016-08-15 16:00 | 2873.4 | SHALLOW WATER | 3022 | 3021.8 | 18610321.18 | N/A | 44.7 | N/A | N/A | N/A | 1.76 | 1.32 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.32 |  | 1066 |  | 1517 | [27 empty] | Exist
2016-06-14 | 2016-10-26 | PCSB | SB | LIMBAYONG | LIMBAYONG-4 | APPRAISAL CUM DEV/DEVELOPMENT | DSM-1 | DRILLSHIP | 932 | 2406 | 2406 | N/A | N/A | N/A | N/A | 52000000 | 52 | NO | N/A | N/A | 2016-07-17 | 2016-07-16 08:30 | 2016-07-22 15:00 | 850 | DEEP WATER | 1807 | 1807 | N/A | N/A | N/A | N/A | 6292637.21 | 6.25 | 49.54 | 49.54 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | No |  | No |  | No | [27 empty] | Exist
2016-06-14 | 2016-10-26 | PCSB | SB | LIMBAYONG | LIMBAYONG-4 RDR | APPRAISAL CUM DEV/DEVELOPMENT | DSM-1 | DRILLSHIP | 932 | 2406 | 2406 | N/A | N/A | N/A | N/A | 52000000 | 52 | NO | N/A | N/A | 2016-07-17 | 2016-07-16 08:30 | 2016-07-22 15:00 | 850 | DEEP WATER | 1807 | 1807 | N/A | N/A | N/A | N/A | 6292637.21 | 6.25 | 49.54 | 49.54 | DW EXP C1 | DW EXP C1 | 2.3 | 2.3 | 3280 | 3280 | 5760 | 5760 | yes | 2.35 | yes | 1380 | yes | 1994 | [26 empty] | Missing
2016-05-16 | 2017-08-22 | HESS | PM | BUNGA KESUMBA | BUNGA KESUMBA-A2(B) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.11 | 2502.29 | 1238.04 | N/A | N/A | N/A | N/A | 18104544 | 26.36 | NO | N/A | DRY TREE | 2016-06-21 | 2016-06-21 08:30 | 2017-05-14 06:00 | 2406.89 | SHALLOW WATER | 2508.99 | 1245.42 | N/A | N/A | N/A | N/A | 6263720.92 | 12.04 | 1.38 | 1.38 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 0.97 |  | 473 |  | 1057 | [6 empty] | 3.21 | 1934750 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-05-16 | 2017-08-22 | HESS | PM | BUNGA KESUMBA | BUNGA KESUMBA A-3(C) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.11 | 2696.43 | 1238.04 | N/A | N/A | N/A | N/A | 15070000 | 25.1 | NO | N/A | DRY TREE | 2016-06-18 | 2016-06-18 14:00 | 2017-03-26 15:45 | 2615.06 | SHALLOW WATER | 2717.16 | 1246.89 | N/A | N/A | N/A | N/A | 9092198.15 | 21.13 | 25.74 | 25.74 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.2 |  | 615.8 |  | 1057 | [6 empty] | 3.99 | 2103693 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-05-16 | 2017-08-22 | HESS | PM | BUNGA KESUMBA | BUNGA KESUMBA A-1(A) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.11 | 1779.03 | 1238.04 | N/A | N/A | N/A | N/A | 13080000 | 21.4 | NO | N/A | DRY TREE | 2016-06-20 | 2016-06-20 05:00 | 2017-05-31 11:45 | 1679.98 | SHALLOW WATER | 1775.37 | 1238.65 | N/A | N/A | N/A | N/A | 5080572 | 10.52 | 0.96 | 0.96 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.1 |  | 515 |  | 820 | [6 empty] | 3.23 | 1438616 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | False |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-05-14 | 2017-01-05 | VESTIGO | SK | ANJUNG KECIL | PUDING EMAS -1 | APPRAISAL CUM DEV/DEVELOPMENT | BORR MIST | JACK UP | 70.5 | 3343 | 1954 | N/A | N/A | N/A | N/A | 8900000 | 23.5 | NO | N/A | N/A | N/A | 2016-10-11 11:00 | 2016-11-23 04:00 | 2378.82 | SHALLOW WATER | 2488 | 1738.8 | N/A | N/A | N/A | N/A | 10065708 | 36.26 | 7.07 | 2.33 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.6 |  | 477 |  | 736 | [27 empty] | Exist
2016-04-21 | 2016-09-29 | PCSB | SK | BARONIA | BN-72 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 77.72 | 1708.32 | 1443.77 | N/A | N/A | N/A | N/A | 11138553.95 | 29.76 | NO | N/A | N/A | 2016-06-05 | 2016-05-09 12:00 | 2016-08-02 10:00 | 1595.07 | SHALLOW WATER | 1702.53 | 1439.16 | N/A | N/A | N/A | N/A | 11679308.85 | 37.91 | 14.6 | 13.2 | SW DEV C2 |  | 2 |  | 725 |  | 1390 |  | 2.73 |  | 783.2 |  | 1223.2 | [27 empty] | Exist
2016-04-21 | 2016-10-17 | PCSB | SK | BARONIA | BN-73 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 77.72 | 2790.92 | 2387.08 | N/A | N/A | N/A | N/A | 19950620.13 | 34.64 | NO | N/A | N/A | 2016-06-16 09:00 | 2016-05-07 | 2016-08-18 12:00 | 2695.04 | SHALLOW WATER | 2802.5 | 2395.61 | N/A | N/A | N/A | N/A | 17244914.47 | 42.68 | 1.5 | 0.4 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.65 |  | 612.2 |  | 1813.6 | [27 empty] | Exist
2016-04-09 | 2016-12-22 | PCSB | SK | BARONIA | BN-74 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 77.72 | 3217.62 | 1878.09 | N/A | N/A | N/A | N/A | 20244087.53 | 43.2 | NO | N/A | N/A | 2016-09-16 | 2016-05-11 14:30 | 2016-11-20 07:00 | 3171.73 | SHALLOW WATER | 3279.18 | 1896.4 | N/A | N/A | N/A | N/A | 16614139.57 | 42.76 | 8.48 | 1.51 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.58 |  | 563.9 |  | 1509.1 | [27 empty] | Exist
2016-04-04 | 2016-08-26 | PCSB | SK | EMPURAU | EMPURAU-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 190.8 | 4528 | 4528 | 40733134 | 44958859 | 77 | 87 | N/A | N/A | NO | N/A | N/A | 2016-04-18 | 2016-04-09 14:30 | 2016-07-01 | 3527.2 | SHALLOW WATER | 3746 | 3745.3 | 34931876 | N/A | 83.7 | N/A | N/A | N/A | 3.33 | 3.21 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 3.69 |  | 1948 |  | 2467 | [27 empty] | Exist
2016-03-25 | 2016-07-01 | PCSB | PM | JITANG | JITANG-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 71.4 | 2830 | 2830 | 22400000 | 22400000 | 48 | 48 | N/A | N/A | NO | N/A | N/A | 2016-04-11 | 2016-04-01 | 2016-05-15 06:00 | 2728.6 | SHALLOW WATER | 2830 | 2830 | N/A | 15968114.69 | N/A | 44.25 | N/A | N/A | 4.9 | 4.9 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.58 |  | 641 |  | 1111 | [27 empty] | Exist
2016-03-16 | 2016-05-17 | PTTEP | SK | BEDUK | BEDUK-1 | EXPLORATION/APPRAISAL | ENSCO-52 | JACK UP | 31.8 | 1413 | 1330 | 7542847 | 7542847 | 18.25 | 18.25 | N/A | N/A | NO | N/A | N/A | 2016-04-02 | 2016-04-02 06:00 | 2016-04-20 | 1353.2 | SHALLOW WATER | 1415 | 1332.22 | 6412604 | N/A | 18.75 | N/A | N/A | N/A |  |  | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.05 |  | 360 |  | 1445 | [27 empty] | Exist
2016-03-15 | 2016-07-25 | PCSB | SB | SAMARANG | SM-117 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 47.55 | 2623.59 | 2275.83 | N/A | N/A | N/A | N/A | 14164216 | 29.15 | SIDETRACK | N/A | N/A | 2016-03-28 | 2016-03-28 20:00 | 2016-07-06 03:30 | 2593.11 | SHALLOW WATER | 2676.01 | 2308.44 | N/A | N/A | N/A | N/A | 13988236 | 32.73 | 7.89 | 7.89 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 1.83 |  | 597.68 |  | 1679.26 | [27 empty] | Exist
2016-03-15 | 2016-07-25 | PCSB | SB | SAMARANG | SM-49ST | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 47.55 | 2282.23 | 2153.61 | N/A | N/A | N/A | N/A | 12126601 | 27.71 | NO | N/A | N/A | 2016-03-21 | 2016-03-21 10:00 | 2016-06-14 06:00 | 2207.56 | SHALLOW WATER | 2290.46 | 2167.94 | N/A | N/A | N/A | N/A | 10747524 | 25.63 | 1.38 | 1.38 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1670 |  | 1.5 |  | 497.9 |  | 2076.41 | [27 empty] | Exist
2016-03-15 | 2016-07-25 | PCSB | SB | SAMARANG | SM-116 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 47.55 | 2464.19 | 2097.84 | N/A | N/A | N/A | N/A | 12877554 | 27.34 | NO | N/A | N/A | 2016-04-02 | 2016-03-19 | 2016-05-25 12:00 | 2309.66 | SHALLOW WATER | 2392.56 | 2076.5 | N/A | N/A | N/A | N/A | 11194767 | 28.7 | 5.44 | 5.44 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2015 |  | 2.02 |  | 631.95 |  | 1510.76 | [27 empty] | Exist
2016-02-03 | 2017-08-25 | HESS | PM | BERGADING | BERGADING-D2 (B) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 54.01 | 3633.34 | 1202.07 | N/A | N/A | N/A | N/A | 17080000 | 29.1 | NO | N/A | N/A | 2016-03-15 16:00 | 2016-03-15 11:30 | 2017-05-01 13:00 | 3447.58 | SHALLOW WATER | 3540.99 | 1200.61 | N/A | N/A | N/A | N/A | 9670000 | 27.42 | 5.93 | 5.93 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.13 |  | 548 |  | 1057 | [27 empty] | Exist
2016-02-03 | 2017-08-25 | HESS | PM | BERGADING | BERGADING-D1 (C) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 54.01 | 2402.62 | 1217.01 | N/A | N/A | N/A | N/A | 20370000 | 33.6 | NO | N/A | DRY TREE | 2016-03-13 01:30 | 2016-03-12 21:30 | 2016-03-29 06:00 | 2334.2 | SHALLOW WATER | 2427.61 | 1174.95 | N/A | N/A | N/A | N/A | 6430000 | 13.63 | 3.11 | 3.11 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.1 |  | 515 |  | 820 | [6 empty] | 3.2 | 1596999 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | False |  | L80 13CR | 9.9 | CACL2 | NO | NO | Exist
2016-02-03 | 2017-08-25 | HESS | PM | BERGADING | BERGADING-D3 (D) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 54.01 | 3777.51 | 1205.12 | N/A | N/A | N/A | N/A | 18326603 | 31.7 | SIDETRACK | N/A | DRY TREE | 2016-03-14 | 2016-03-14 05:00 | 2017-04-27 21:30 | 3806.92 | SHALLOW WATER | 3900.34 | 1203.6 | N/A | N/A | N/A | N/A | 15488831.77 | 38.58 | 47.63 | 47.63 | No DMS category | [7 empty] | 2.53 |  | 1042 |  | 1240 | [6 empty] | 4.8 | 1410040 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-02-03 | 2017-08-25 | HESS | PM | BERGADING | BERGADING-D4 (A) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 54.01 | 3499.24 | 1205.12 | N/A | N/A | N/A | N/A | 17690000 | 30.1 | NO | N/A | DRY TREE | 2016-03-11 | 2016-03-10 19:00 | 2016-04-15 | 3343.04 | SHALLOW WATER | 3436.45 | 1200.63 | N/A | N/A | N/A | N/A | 8528628.91 | 19.48 | 1.93 | 1.93 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.09 |  | 468 |  | 778 | [6 empty] | 4.91 | 2032416 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | CACL2 | NO | NO | Exist
2016-01-12 | 2016-05-19 | SAPURA OMV | PM | EAST BELUMUT | EB A-14ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 72.8 | 3533 | 1185 | N/A | N/A | N/A | N/A | 12930770 | 25.47 | NO | N/A | N/A | 2016-03-14 | 2016-03-08 | 2016-03-31 20:00 | 3487 | SHALLOW WATER | 3605 | 1164.81 | N/A | N/A | N/A | N/A | 11304747 | 23.83 | 2.84 | 2.84 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 1.17 |  | 429.8 |  | 1116.8 | [27 empty] | Exist
2016-01-06 | 2016-03-25 | ROC OIL | SK | D35 | D35-211 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 45.11 | 1881.13 | 1760.13 | N/A | N/A | N/A | N/A | 10800000 | 16.44 | NO | N/A | N/A | 2016-01-11 | 2016-01-09 | 2016-01-26 20:00 | 1744.84 | SHALLOW WATER | 1837.24 | 1770.26 | N/A | N/A | N/A | N/A | 8157732 | 17.92 | 12.85 | 11.1 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1550 |  | 3.02 |  | 991 |  | 3800 | [27 empty] | Exist
2016-01-05 | N/A | IPC | SB | MALIGAN | MALIGAN-1 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 18.5 | 1818 | 1650 | 16215404 | 19617160 | 34.9 | 41.1 | N/A | N/A | NO | N/A | N/A | 2016-01-19 | 2016-01-18 | 2016-02-24 | 1328.5 | SHALLOW WATER | 1381 | 1257.75 | N/A | 14696625 | N/A | 36.8 | N/A | N/A | 1.3 | 1.3 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2015-12-23 | 2016-05-10 | PCSB | SB | SAMARANG | SM-115 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 10.06 | 2263.94 | 2160.32 | N/A | N/A | N/A | N/A | 14396396.85 | 31.54 | NO | N/A | N/A | 2015-12-31 | 2015-12-31 22:00 | 2016-03-11 09:00 | 2360.56 | SHALLOW WATER | 2404.75 | 2295.43 | N/A | N/A | N/A | N/A | 10884080 | 25.48 | 4.17 | 4.17 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.41 |  | 584.7 |  | 1443.51 | [27 empty] | Exist
2015-12-23 | 2016-04-29 | PCSB | SB | SAMARANG | SM-114 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 10.06 | 2213.35 | 2080.77 | N/A | N/A | N/A | N/A | 14140240.03 | 32.25 | NO | N/A | N/A | 2015-12-31 | 2015-12-31 15:00 | 2016-03-01 07:30 | 2177.69 | SHALLOW WATER | 2221.88 | 2089.3 | N/A | N/A | N/A | N/A | 12436960 | 23.73 | 15.63 | 15.63 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.52 |  | 925.99 |  | 1792.07 | [27 empty] | Exist
2015-12-23 | 2016-03-22 | EMEPMI | PM | GUNTONG | GUNTONG-C11ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 63.7 | 2555 | 2022 | N/A | N/A | N/A | N/A | 11300000 | 17.26 | NO | N/A | N/A | 2016-01-16 | 2016-01-15 19:30 | 2016-02-09 05:00 | 2458 | SHALLOW WATER | 2555 | 2033 | N/A | N/A | N/A | N/A | 10800000 | 24.4 | 2.09 | 1.48 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | No |  | No |  | No | [27 empty] | Exist
2015-12-14 | 2016-04-13 | PTTEP | SK | SOUTH ACIS | SASA-15 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 40.85 | 3493.3 | 1590.38 | N/A | N/A | N/A | N/A | 23843781 | 49.8 | NO | N/A | DRY TREE | 2016-01-04 | 2016-01-04 15:00 | 2016-01-20 | 3247.65 | SHALLOW WATER | 3318.5 | 1550.49 | N/A | N/A | N/A | N/A | 6113744 | 12.17 | 0.51 | 0.51 | No DMS category. Having value but not sure refering which version | [7 empty] | 1 |  | 501 |  | 573 | [6 empty] | 1.23 | 789000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 60 | False |  | L80 | 9.5 | OTHER | NO | NO | Exist
2015-12-14 | 2016-04-13 | PTTEP | SK | SOUTH ACIS | SASA-13 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 40.85 | 2923.31 | 1422.98 | N/A | N/A | N/A | N/A | 7531809 | 15.8 | NO | N/A | DRY TREE | 2016-01-10 | 2016-01-10 | 2016-02-07 | 2631.15 | SHALLOW WATER | 2702 | 1496.27 | N/A | N/A | N/A | N/A | 8272740 | 14.48 | 0 | 0 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | 1.36 |  | 775 |  | 984 | [6 empty] | 2.98 | 3099000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 233 | True |  | L80 13CR | 9.5 | CACL2 | NO | NO | Exist
2015-12-14 | 2016-04-13 | PTTEP | SK | SOUTH ACIS | SASA-14 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 40.85 | 1853.77 | 1445 | N/A | N/A | N/A | N/A | 8896964 | 20 | NO | N/A | N/A | 2016-01-08 09:00 | 2016-01-08 09:00 | 2016-02-11 | 2549.15 | SHALLOW WATER | 2620 | 1713.87 | N/A | N/A | N/A | N/A | 8235939 | 17.23 | 3.02 | 3.02 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.34 |  | 639 |  | 835 | [27 empty] | Exist
2015-12-11 | 2016-04-26 | ROC OIL | SK | D35 | D35-209-ST2 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 45.11 | 3118.87 | 1722.95 | N/A | N/A | N/A | N/A | 14661000 | 18.51 | NO | N/A | N/A | 2016-01-28 | 2016-01-26 20:00 | 2016-03-01 16:00 | 3071.26 | SHALLOW WATER | 3163.67 | 1743.55 | N/A | N/A | N/A | N/A | 10086695 | 18.51 | 16.49 | 16.49 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 2.78 |  | 887 |  | 1720 | [27 empty] | Exist
2015-12-03 | 2016-02-24 | IPC | SB | BAMBAZON | BAMBAZON SH1-1 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 39.5 | 1234 | 1234 | 12636057 | 15166862 | 28 | 31.9 | N/A | N/A | NO | N/A | N/A | 2016-01-05 | 2016-01-03 17:00 | 2016-01-18 04:30 | 1310.5 | SHALLOW WATER | 1384 | 1384 | N/A | 8000000 | N/A | 15.4 | N/A | N/A | 0 | 0 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2.43 |  | 1139 |  | 1856 | [27 empty] | Exist
2015-12-01 | 2016-06-06 | SAPURA OMV | PM | EAST BELUMUT | EBA-06ST2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 72.8 | 3636 | 1164 | N/A | N/A | N/A | N/A | 13125806 | 25.4 | NO | N/A | N/A | 2016-04-04 | 2016-03-31 20:00 | 2016-04-18 18:00 | 3519 | SHALLOW WATER | 3637 | 1161.98 | N/A | N/A | N/A | N/A | 9263844 | 17.92 | 2.09 | 2.09 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 0.91 |  | 367.86 |  | 931.58 | [27 empty] | Exist
2015-12-01 | 2016-06-14 | SAPURA OMV | PM | EAST BELUMUT | EB A-11ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 72.8 | 3090 | 1164.7 | N/A | N/A | N/A | N/A | 11067899 | 20.92 | NO | N/A | N/A | 2016-04-22 | 2016-04-18 18:00 | 2016-05-03 18:00 | 3086 | SHALLOW WATER | 3204 | 1164.74 | N/A | N/A | N/A | N/A | 8053568 | 15 | 7.78 | 7.78 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | 0.9 |  | 382 |  | 978 | [27 empty] | Exist
2015-10-27 | 2016-04-22 | PCSB | SB | SAMARANG | SM-113 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 10.06 | 2737.58 | 2169.77 | N/A | N/A | N/A | N/A | 13295958.62 | 31.11 | NO | N/A | N/A | 2015-11-13 | 2015-11-13 05:00 | 2016-02-22 16:30 | 2683.63 | SHALLOW WATER | 2727.83 | 2158.18 | N/A | N/A | N/A | N/A | 13476010 | 30.88 | 3 | 3 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 1.78 |  | 824.34 |  | 1566.98 | [27 empty] | Exist
2015-10-27 | 2016-05-23 | ROC OIL | SK | D35 | D35-213 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 45.11 | 3200.24 | 1604.08 | N/A | N/A | N/A | N/A | 16370279 | 21.85 | NO | N/A | N/A | 2016-02-18 | 2016-02-17 | 2016-03-22 12:30 | 3260.23 | SHALLOW WATER | 3352.64 | 1657.2 | N/A | N/A | N/A | N/A | 7800000 | 45.25 | 22 | 22 | No DMS category | [7 empty] | 2.79 |  | 976 |  | 1295 | [27 empty] | Exist
2015-10-27 | 2016-04-08 | PCSB | SB | SAMARANG | SM112 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-7 | JACK UP | 10.06 | 2554.71 | 2357.51 | N/A | N/A | N/A | N/A | 14580673 | 33.85 | NO | N/A | N/A | 2015-11-14 | 2015-11-14 05:00 | 2016-02-13 03:00 | 2424.57 | SHALLOW WATER | 2468.76 | 2295.95 | N/A | N/A | N/A | N/A | 15675130 | 41.08 | 14.61 | 14.61 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 2.21 |  | 914.75 |  | 2022.6 | [27 empty] | Exist
2015-10-21 | 2017-09-21 | HESS | PM | BERGADING | BERGADING-C1 (A) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.99 | 3063.4 | 1202.22 | N/A | N/A | N/A | N/A | 16710000 | 28 | NO | N/A | DRY TREE | 2015-12-08 | 2015-12-07 12:00 | 2017-04-05 21:30 | 2962.07 | SHALLOW WATER | 3057.91 | 1204.21 | N/A | N/A | N/A | N/A | 9259836.88 | 22.69 | 1.29 | 1.29 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.6 |  | 649.32 |  | 1094.69 | [6 empty] | 4.81 | 1975586 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.9 | CACL2 | NO | NO | Exist
2015-10-21 | 2017-09-21 | HESS | PM | BERGADING | BERGADING-C3 (C) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.99 | 3257.85 | 1202.38 | N/A | N/A | N/A | N/A | 18340000 | 30.6 | NO | N/A | DRY TREE | 2015-12-10 | 2015-12-09 17:00 | 2017-04-30 18:00 | 3158.04 | SHALLOW WATER | 3253.89 | 1204.18 | N/A | N/A | N/A | N/A | 9200192 | 25.95 | 6.15 | 6.15 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.3 |  | 542 |  | 819 | [6 empty] | 4.43 | 1583558 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.9 | CACL2 | NO | NO | Exist
2015-10-21 | 2017-09-21 | HESS | PM | BERGADING | BERGADING-C4 (D) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.99 | 2914.96 | 1202.38 | N/A | N/A | N/A | N/A | 17480000 | 31.8 | NO | N/A | DRY TREE | 2015-12-13 15:00 | 2015-12-06 10:30 | 2017-04-17 19:30 | 2858.44 | SHALLOW WATER | 2954.28 | 1203.9 | N/A | N/A | N/A | N/A | 11780512.52 | 43.45 | 4.19 | 4.19 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.3 |  | 535 |  | 1267 | [6 empty] | 4.1 | 2196238 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.9 | CACL2 | NO | NO | Exist
2015-10-21 | 2017-09-21 | HESS | PM | BERGADING | BERGADING-C2(B) | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 55.99 | 2463.88 | 1202.22 | N/A | N/A | N/A | N/A | 21508035.53 | 34.1 | NO | N/A | DRY TREE | 2015-12-11 | 2015-12-11 13:00 | 2016-02-27 10:00 | 2349.75 | SHALLOW WATER | 2445.6 | 1204.51 | N/A | N/A | N/A | N/A | 7724125.03 | 19.48 | 12.83 | 12.83 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.6 |  | 675 |  | 1102 | [6 empty] | 5.75 | 2044620 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 9.9 | CACL2 | NO | NO | Exist
2015-10-20 | 2016-06-09 | SHELL | SK | MARJORAM | MARJORAM-2 | EXPLORATION/APPRAISAL | NOBLE BULLY-2 | HYDRAULIC WORKOVER UNIT (HWU) | 866.35 | 2298.08 | 2298.08 | 63080000 | 63080000 | 42.57 | 42.57 | N/A | N/A | NO | N/A | N/A | 2016-01-06 | 2016-01-04 17:45 | 2016-02-27 22:00 | 1378.39 | DEEP WATER | 2270.04 | 2270.04 | N/A | 49650000 | N/A | 54.18 | N/A | N/A | 23.18 | 22.46 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | No |  | No |  | No | [27 empty] | Exist
2015-10-16 | N/A | SAPURA OMV | SB | ZOISIT | ZOISIT-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 38.3 | 950 | 950 | 8298261 | 8298261 | 17.34 | 17.34 | N/A | N/A | NO | N/A | N/A | 2016-01-11 | 2016-01-04 14:00 | 2016-01-29 09:00 | 877.7 | SHALLOW WATER | 946 | 946 | 8264266.94 | N/A | 24.79 | N/A | N/A | N/A | 20.68 | 1.82 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 1.6 |  | 837.9 |  | 2869.8 | [27 empty] | Exist
2015-10-12 | 2016-03-26 | SHELL | SK | TUNTONG | TUNTONG-1 | EXPLORATION/APPRAISAL | NOBLE BULLY-2 | HYDRAULIC WORKOVER UNIT (HWU) | 1089.3 | 3144.77 | 3144.77 | 27760000 | 35600000 | 24.3 | 30.3 | N/A | N/A | NO | N/A | N/A | 2015-11-21 | 2015-11-19 | 2016-01-04 | 1576.65 | DEEP WATER | 2691.25 | 2665.96 | 37000000 | N/A | 46.74 | N/A | N/A | N/A | 30.3 | 30.3 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 2.94 |  | 3530.9 |  | 5284.4 | [27 empty] | Exist
2015-10-02 | 2016-03-02 | PTTEP | SK | SOUTH ACIS | SASA-05 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 40.85 | 1476.83 | 1365 | N/A | N/A | N/A | N/A | 6193839 | 10.5 | NO | N/A | DRY TREE | 2015-11-04 | 2015-11-04 04:30 | 2016-01-04 15:00 | 1395.65 | SHALLOW WATER | 1466.5 | 1371.43 | N/A | N/A | N/A | N/A | 4920222 | 7.88 | 0 | 0 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 1.26 |  | 791 |  | 1127 | [6 empty] | 2.19 | 1665000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 56 | True |  | L80 13CR | 9.7 | CACL2 | NO | NO | Exist
2015-09-22 | 2016-02-23 | HESS | PM | BUNGA TERATAI | BUNGA TERATAI-3 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 68.3 | 2071.32 | 2015.85 | 23377791 | 23377791 | 47 | 47 | N/A | N/A | SIDETRACK | N/A | N/A | 2015-11-02 | 2015-09-29 22:30 | 2015-11-21 | 2483.39 | SHALLOW WATER | 2585.8 | 1990.23 | N/A | 24834845.48 | N/A | 62.9 | N/A | N/A |  |  | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | No |  | No |  | No | [27 empty] | Exist
2015-09-22 | 2015-11-25 | IPC | PM | BERTAM | BERTAM-3 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 76.9 | 1689 | 1689 | 8000000 | 8600000 | 17.2 | 18.3 | N/A | N/A | NO | N/A | N/A | 2015-10-20 | 2015-10-17 07:30 | 2015-11-01 | 1605.1 | SHALLOW WATER | 1716 | 1682 | N/A | 7900000 | N/A | 16.4 | N/A | N/A | 1.52 | 1.52 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 2.03 |  | 675 |  | 1504 | [27 empty] | Exist
2015-09-15 | N/A | SAPURA OMV | SB | BAIDURI | BAIDURI-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 42 | 1450 | 1230 | 7759000 | 7759000 | 17.64 | 17.64 | N/A | N/A | NO | N/A | N/A | 2016-02-01 | 2016-01-29 09:00 | 2016-02-22 09:00 | 1312.26 | SHALLOW WATER | 1384 | 1179 | 7789000 | N/A | 24 | N/A | N/A | N/A | 17.53 | 7.34 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2.69 |  | 907.68 |  | 1812 | [27 empty] | Exist
2015-09-10 | 2016-01-11 | PCSB | SK | F9 NORTH | F9-A5 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 94.8 | 2461.4 | 1344.85 | N/A | N/A | N/A | N/A | 26072070 | 38 | NO | N/A | N/A | 2015-10-27 15:00 | 2015-10-26 12:00 | 2015-11-30 | 2395.61 | SHALLOW WATER | 2536.4 | 1346.4 | N/A | N/A | N/A | N/A | 20430907 | 34.49 | 14.5 | 14.5 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.53 |  | 1252 |  | 2155 | [27 empty] | Exist
2015-09-10 | 2016-02-02 | JX NIPPON | SB | BESTARI | BESTARI-2 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 1106.21 | 2348 | 2348 | 74800000 | 74800000 | 58.7 | 58.7 | N/A | N/A | SIDETRACK | N/A | N/A | 2015-10-09 | 2015-10-08 07:00 | 2015-11-26 06:00 | 1487.59 | DEEP WATER | 2620 | 2619.1 | N/A | 58700000 | N/A | 51.9 | N/A | N/A | 7.3 | 7.3 | No DMS category | [7 empty] | 3.97 |  | 4490 |  | 7840 | [27 empty] | Exist
2015-09-07 | 2016-02-02 | SAPURA OMV | SK | JEREMIN | JEREMIN-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 96 | 1981 | 1981 | 11748955 | 14244880 | 21.64 | 21.64 | N/A | N/A | NO | N/A | N/A | 2015-11-12 | 2015-11-08 02:00 | 2015-12-05 10:00 | 2139 | SHALLOW WATER | 2269 | 2268.64 | N/A | 14069370 | N/A | 27.33 | N/A | N/A | 2.97 | 2.97 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.12 |  | 1010.5 |  | 2004.2 | [27 empty] | Exist
2015-09-07 | 2016-03-02 | SAPURA OMV | SK | PUTAT | PUTAT-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 99.2 | 3171 | 3171 | 13036386 | 13036386 | 25.26 | 25.26 | N/A | N/A | NO | N/A | N/A | 2015-11-12 | 2015-11-12 22:00 | 2016-01-04 14:00 | 2466.8 | SHALLOW WATER | 2600 | 2600 | 14100015.02 | N/A | 30.17 | N/A | N/A | N/A | 13.43 | 0.76 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.18 |  | 893.53 |  | 1742.1 | [27 empty] | Exist
2015-09-02 | 2016-01-03 | SAPURA OMV | SK | JERUN | JERUN-1 | EXPLORATION/APPRAISAL | NAGA-8 | JACK UP | 87.7 | 2370 | 2336 | 11282545 | 17260802 | 20.39 | 40.01 | N/A | N/A | NO | N/A | N/A | 2015-10-07 01:00 | 2015-09-28 18:30 | 2015-11-08 02:00 | 2279.3 | SHALLOW WATER | 2401 | 2399.5 | N/A | 17305899 | N/A | 41.23 | N/A | N/A | 8.41 | 5.76 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 3.32 |  | 1154 |  | 2149 | [27 empty] | Exist
2015-08-25 | 2016-08-24 | PCSB | SK | NC3 | NC3-A4 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 104 | 3770.7 | 2933 | N/A | N/A | N/A | N/A | 43400000 | 56.34 | NO | N/A | DRY TREE | 2016-05-18 | 2016-05-18 17:00 | 2016-06-27 18:00 | 3560.1 | SHALLOW WATER | 3697 | 2907 | N/A | N/A | N/A | N/A | 36480000 | 40.04 | 5.52 | 4.84 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 2.34 |  | 1715 |  | 3195 | [6 empty] | 13.42 | 14934628.02 |  |  | CARBONATE | HPHT | CASED HOLE | NO | NO | 7" | 1.0 | SINGLE | 17CR | 704.7588 | False | NONE | 25CR | 14.8 | CABR2 | NO | NO | Exist
2015-08-17 | 2016-02-02 | PCSB | SK | D18 | D18-309 | APPRAISAL CUM DEV/DEVELOPMENT | MAERSK CONVINCER | JACK UP | 35.8 | 1886.32 | 1324.6 | N/A | N/A | N/A | N/A | 15760000 | 29.1 | NO | N/A | N/A | 2015-09-06 17:15 | 2015-09-05 12:00 | 2015-09-27 07:00 | 1814.42 | SHALLOW WATER | 1896.37 | 1331.61 | N/A | N/A | N/A | N/A | 14904630.51 | 33.75 | 13.6 | 13.6 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.57 |  | 1007 |  | 2503 | [27 empty] | Exist
2015-08-06 | 2015-10-05 | PTTEP | SB | ROTAN | ROTAN RP-1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CARINA | DRILLSHIP | 1189 | 2120 | 2100 | N/A | N/A | N/A | N/A | 22889618.39 | 17.4 | NO | N/A | N/A | 2015-09-01 21:00 | 2015-08-31 17:00 | 2015-09-17 12:00 | 796 | DEEP WATER | 2009 | 2009 | N/A | N/A | N/A | N/A | 20445809 | 16.8 | 0.25 | 0.25 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 2.28 |  | 2773 |  | 5891 | [27 empty] | Exist
2015-07-20 | 2015-10-02 | PTTEP | SK | MERAPUH | MERAPUH-05 | EXPLORATION/APPRAISAL | ENSCO-52 | JACK UP | 34 | 2557 | 1963 | 11489758 | 11489758 | 24 | 24 | N/A | N/A | NO | N/A | N/A | 2015-08-21 07:00 | 2015-08-15 15:00 | 2015-09-11 02:30 | 2096.89 | SHALLOW WATER | 2194 | 1978.09 | N/A | 11195516.87 | N/A | 26.48 | N/A | N/A | 1.5736 | 1.5736 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.08 |  | 674.88 |  | 899.08 | [27 empty] | Exist
2015-07-09 | 2015-09-02 | PTTEP | SK | PERMAS | PRPA-06 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 3404 | 1901 | N/A | N/A | N/A | N/A | 8980844 | 14.92 | NO | N/A | DRY TREE | 2015-07-21 | 2015-07-21 20:00 | 2015-08-11 06:00 | 3191.24 | SHALLOW WATER | 3285 | 1946.64 | N/A | N/A | N/A | N/A | 9809134 | 20.42 | 19.38 | 19.38 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.67 |  | 805 |  | 955 | [6 empty] | 3.23 | 2293000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 390 | True | NONE | L80 13CR | 11.8 | CACL2 | NO | NO | Exist
2015-07-08 | 2015-10-26 | VESTIGO | PM | CHENANG | CHENANG-2 | EXPLORATION/APPRAISAL | ROWAN GORILLA-2 | JACK UP | 63.4 | 1500 | 1500 | 13381276 | 13381276 | 36.43 | 36.43 | N/A | N/A | NO | N/A | N/A | 2015-08-09 18:45 | 2015-08-05 07:00 | 2015-08-30 18:30 | 2707.25 | SHALLOW WATER | 2799 | 2714.27 | N/A | 8478401 | N/A | 21.45 | N/A | N/A | 2.82 | 2.82 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | No |  | No |  | No | [27 empty] | Exist
2015-06-08 | 2016-02-02 | PCSB | SK | D18 | D18-108 | APPRAISAL CUM DEV/DEVELOPMENT | PERISAI PACIFIC-101 | JACK UP | 36.5 | 1590.98 | 1349.59 | N/A | N/A | N/A | N/A | 15260736 | 30 | NO | N/A | N/A | 2015-07-29 14:30 | 2015-07-29 12:00 | 2015-08-24 12:00 | 1521.18 | SHALLOW WATER | 1603.17 | 1351.05 | N/A | N/A | N/A | N/A | 11203639.77 | 26 | 4.48 | 4.48 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.3 |  | 900 |  | 2130 | [27 empty] | Exist
2015-06-04 | 2015-08-06 | PTTEP | SB | PERMAI | PERMAI-1 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 1483.3 | 2450 | 2450 | 24748595 | 24748595 | 19.3 | 19.3 | N/A | N/A | NO | N/A | N/A | 2015-07-06 21:30 | 2015-07-01 15:00 | 2015-07-21 03:00 | 940.5 | DEEP WATER | 2450 | 2450 | N/A | 23654446 | N/A | 19.5 | N/A | N/A | 21.79 | 4.38 | DW EXP C1 |  | 2.3 |  | 3280 |  | 5760 |  | 1.96 |  | 2383 |  | 7666 | [27 empty] | Exist
2015-06-02 | 2016-05-31 | PCSB | SK | NC3 | NC3-A1 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 104 | 3807 | 2910 | N/A | N/A | N/A | N/A | 63100000 | 71.9 | NO | N/A | DRY TREE | 2015-07-25 | 2015-07-25 04:30 | 2016-02-04 16:00 | 3546.1 | SHALLOW WATER | 3683 | 2842 | N/A | N/A | N/A | N/A | 46480000 | 70.11 | 2.45 | 2.45 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.66 |  | 2160 |  | 3847 | [6 empty] | 25.58 | 18551230.33 |  |  | CARBONATE | HPHT | CASED HOLE | NO | NO | 7" | 1.0 | SINGLE | 17CR | 509.8674 | True | NONE | 25CR | 15 | CABR2 | NO | NO | Exist
2015-06-01 | 2015-10-20 | COP | SB | AZURIT | AZURIT-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 95 | 2793 | 2793 | 41410000 | 43860000 | 44.4 | 47.4 | N/A | N/A | NO | N/A | N/A | 2015-07-27 11:15 | 2015-07-25 17:00 | 2015-09-23 22:45 | 2532 | SHALLOW WATER | 2655 | 2653.59 | N/A | 42490000 | N/A | 63.73 | N/A | N/A | 24.45 | 18.49 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | No |  | No |  | No | [27 empty] | Exist
2015-06-01 | 2015-11-03 | JX NIPPON | SK | TOMAN | TOMAN-1 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 499 | 2403.2 | 2403.2 | 61307000 | 75455000 | 35.7 | 48.3 | N/A | N/A | NO | N/A | N/A | 2015-07-26 | 2015-07-25 12:00 | 2015-08-24 15:00 | 1794.8 | DEEP WATER | 2320 | 2319.94 | N/A | 39307030 | N/A | 30 | N/A | N/A | 3.65 | 3.65 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 4.4 |  | 5725 |  | 6675 | [27 empty] | Exist
2015-05-28 | 2015-07-29 | PTTEP | SK | PERMAS | PRPA-01 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 1626 | 1610 | N/A | N/A | N/A | N/A | 6374841 | 8 | NO | N/A | DRY TREE | 2015-06-10 | 2015-06-10 | 2015-06-29 | 1872.24 | SHALLOW WATER | 1966 | 1597.06 | N/A | N/A | N/A | N/A | 5169929 | 8.02 | 2.86 | 2.86 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 555 |  | 1.13 |  | 730 |  | 842 | [6 empty] | 0.75 | 837000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 16.405 | False | NONE | L80 |  | SEAWATER/DRILLWATER | NO | NO | Exist
2015-05-28 | N/A | PTTEP | SK | PERMAS | PRPA-02 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 1900 | 1552 | N/A | N/A | N/A | N/A | 8487834 | 15.67 | NO | N/A | N/A | 2015-06-14 | 2015-06-14 13:00 | 2015-07-19 09:00 | 1715.74 | SHALLOW WATER | 1809.5 | 1500.85 | N/A | N/A | N/A | N/A | 5409461 | 8.69 | 2.4 | 2.4 | No DMS category. Having value but not sure refering which version | [7 empty] | 1.2 |  | 747 |  | 984 | [27 empty] | Exist
2015-05-28 | 2015-07-29 | MURPHY | SK | PERMAS | PRPA-03 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 1562.22 | 1240.26 | N/A | N/A | N/A | N/A | 6211556 | 7.67 | NO | N/A | N/A | 2015-06-16 | 2015-06-16 | 2015-06-24 | 1616.25 | SHALLOW WATER | 1710 | 1651.21 | N/A | N/A | N/A | N/A | 3796184 | 5.04 | 0 | 0 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 0.81 |  | 601 |  | 727 | [27 empty] | Exist
2015-05-28 | 2015-08-10 | MURPHY | SK | PERMAS | PRPA-04 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 2106.18 | 1590.26 | N/A | N/A | N/A | N/A | 7905129 | 13.77 | NO | N/A | N/A | 2015-06-11 | 2015-06-11 | 2015-07-21 | 1499.74 | SHALLOW WATER | 1593.5 | 1255.38 | N/A | N/A | N/A | N/A | 4725162 | 8.21 | 0 | 0 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 0.9 |  | 643 |  | 643 | [27 empty] | Exist
2015-05-27 | 2015-12-18 | PCSB | SK | SALAM | SALAM-1 | EXPLORATION/APPRAISAL | DEEP DRILLER-3 | JACK UP | 92.1 | 3530 | 3530 | 100000000 | 100000000 | 172 | 172 | N/A | N/A | NO | N/A | N/A | 2015-06-13 17:00 | 2015-06-04 15:00 | 2015-11-10 11:30 | 2807.9 | SHALLOW WATER | 2930 | 2930 | 70053058.33 | N/A | 158.61 | N/A | N/A | N/A | 9.93 | 9.81 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 10.87 |  | 5063.28 |  | 6964.06 | [27 empty] | Exist
2015-05-22 | 2015-10-02 | VESTIGO | PM | TEMBIKAI | TBK-A2 | APPRAISAL CUM DEV/DEVELOPMENT | ROWAN GORILLA-2 | JACK UP | 70.7 | 3431.4 | 2381.6 | N/A | N/A | N/A | N/A | 11946960 | 26.86 | NO | N/A | DRY TREE | 2015-06-11 12:15 | 2015-06-10 05:30 | 2015-07-30 13:15 | 3235.68 | SHALLOW WATER | 3346 | 2284.94 | N/A | N/A | N/A | N/A | 9821019 | 25.06 | 1.5 | 1.5 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [6 empty] | 6.82 | 3741428 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 219.1708 | True |  | L80 13CR | 8.9 | KCL | NO | NO | Exist
2015-04-24 | 2015-10-08 | COP | SB | DELIMA | DELIMA-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 139 | 2736 | 2736 | 36690000 | 40150000 | 35.2 | 41.1 | N/A | N/A | NO | N/A | N/A | 2015-06-05 | 2015-06-02 17:30 | 2015-07-22 05:15 | 2569 | SHALLOW WATER | 2736 | 2735.87 | 36730000 | N/A | 50.78 | N/A | N/A | N/A | 11.32 | 11.32 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | No |  | No |  | No | [27 empty] | Exist
2015-04-16 | 2015-07-28 | PTTEP | SK | PERMAS | PRPA-10ST2 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 1292.36 | 1277.62 | N/A | N/A | N/A | N/A | 6789384 | 10.75 | NO | N/A | DRY TREE | 2015-05-01 | 2015-05-01 22:00 | 2015-06-06 | 1329.64 | SHALLOW WATER | 1423.4 | 1259.69 | N/A | N/A | N/A | N/A | 7378739 | 15.35 | 2.44 | 2.44 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.29 |  | 1100 |  | 1278 | [6 empty] | 2.07 | 1287000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 62.6 | True |  | L80 13CR | 10.3 | CACL2 | NO | NO | Exist
2015-04-16 | 2015-07-23 | PTTEP | SK | PERMAS | PRPA-12 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 1990 | 1498.38 | N/A | N/A | N/A | N/A | 8236373 | 13.42 | NO | N/A | DRY TREE | 2015-05-06 | 2015-05-03 | 2015-05-26 | 2767.24 | SHALLOW WATER | 2861 | 1522.74 | N/A | N/A | N/A | N/A | 5972266 | 9.38 | 3.33 | 3.33 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 0.87 |  | 497 |  | 606 | [6 empty] | 1.1 | 1182000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 118.12 | False |  | L80 | 8.3 | SEAWATER/DRILLWATER | NO | NO | Exist
2015-04-16 | 2015-07-28 | PTTEP | SK | PERMAS | PRPA-11 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 2050 | 1481 | N/A | N/A | N/A | N/A | 6583309.7 | 12.25 | SIDETRACK | N/A | DRY TREE | 2015-05-09 | 2015-05-02 21:00 | 2015-06-10 07:00 | 3431.64 | SHALLOW WATER | 1538 | 1340.29 | N/A | N/A | N/A | N/A | 6743172 | 14.65 | 1.99 | 1.99 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 1.41 |  | 652 |  | 788 | [6 empty] | 2.52 | 1691000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 19.36 | True |  | L80 13CR | 10.3 | CACL2 | NO | NO | Exist
2015-04-15 | 2015-08-27 | PCSB | SK | TEMANA | TEMANA-T76 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 29.26 | 1965.86 | 1423.35 | N/A | N/A | N/A | N/A | 20474767 | 34.1 | NO | N/A | DRY TREE | 2015-05-21 | 2015-05-07 13:00 | 2015-06-30 06:00 | 1815 | SHALLOW WATER | 1883.27 | 1368.49 | N/A | N/A | N/A | N/A | 12391846 | 20.5 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.86 |  | 765 |  | 1683 | [6 empty] | 7.7 | 4079341 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 18 | True |  | 9CR | 9.4 | NACL | NO | NO | Exist
2015-04-06 | 2015-08-28 | JX NIPPON | SB | MENAWAN | MENAWAN-1ST1 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 397.83 | 3969 | 3526 | 92817000 | 92817000 | 70.1 | 70.1 | N/A | N/A | NO | N/A | N/A | 2015-05-11 | 2015-05-10 06:00 | 2015-06-30 | 3067.97 | DEEP WATER | 3492 | 3197.8 | N/A | 59291250 | N/A | 50.6 | N/A | N/A | 0.8 | 0.8 | No DMS category. Having value but not sure refering which version | [7 empty] | 3.46 |  | 4254 |  | 5886 | [27 empty] | Exist
2015-03-25 | 2015-08-12 | PTTEP | SK | PERMAS | PRPA-05 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 48.5 | 2196 | 1620 | N/A | N/A | N/A | N/A | 38489455 | 13.19 | NO | N/A | DRY TREE | 2015-06-20 | 2015-06-20 03:30 | 2015-07-16 07:00 | 2093.64 | SHALLOW WATER | 2187.4 | 1614.41 | N/A | N/A | N/A | N/A | 6935993 | 11.58 | 5.22 | 4.86 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 1.25 |  | 750 |  | 1040 | [6 empty] | 2.95 | 2251000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 82.025 | True | NONE | L80 13CR | 11.8 | CACL2 | NO | NO | Exist
2015-03-20 | 2015-09-07 | PCSB | SK | WEST LUTONG | WEST LUTONG DEEP-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 31.3 | 3971.35 | 3690.64 | 23500000 | 24900000 | 57.4 | 60.9 | N/A | N/A | NO | N/A | N/A | 2015-04-17 20:30 | 2015-04-12 22:00 | 2015-07-20 16:00 | 3414.78 | SHALLOW WATER | 3479.73 | 3307.22 | N/A | 32430132.05 | N/A | 98.75 | N/A | N/A | 4.57 | 4.57 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 3.63 |  | 1320 |  | 2321 | [27 empty] | Exist
2015-03-20 | 2015-07-02 | PCSB | SK | BOKOR | BOKOR DEEP WESTERN FLANK - 1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 70 | 2330 | 2330 | 16223982 | 19086064 | 23.15 | 29.65 | N/A | N/A | NO | N/A | N/A | 2015-03-27 | 2015-03-23 06:00 | 2015-05-07 19:00 | 2255 | SHALLOW WATER | 2355 | 2355 | 20820313.35 | N/A | 30.16 | N/A | N/A | N/A | 5.67 | 5.67 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 3.95 |  | 1507 |  | 2027 | [27 empty] | Exist
2015-03-10 | 2015-07-13 | PETROFAC | PM | CENDOR | CD-C10 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 62.3 | 3346 | 1448.47 | N/A | N/A | N/A | N/A | 11623528.44 | 21.33 | NO | N/A | DRY TREE | 2015-04-09 18:00 | 2015-04-08 | 2015-05-15 19:00 | 3136.4 | SHALLOW WATER | 3240 | 1398.53 | N/A | N/A | N/A | N/A | 9319001 | 23.08 | 15.16 | 15.16 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | No |  | No |  | No | [6 empty] | 5.48 | 1863311 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 0 | True |  | L80 13CR | 8.6 | SEAWATER/DRILLWATER | 1 | NO | Exist
2015-02-27 | 2015-08-13 | PCSB | SK | BAYAN | BAYAN-222 | APPRAISAL CUM DEV/DEVELOPMENT | TASHA | JACK UP | 29.26 | 2263.33 | 1326.73 | N/A | N/A | N/A | N/A | 20740000 | 28 | NO | N/A | DRY TREE | 2015-05-07 | 2015-05-06 | 2015-07-07 | 2174.34 | SHALLOW WATER | 2282.84 | 1428.22 | N/A | N/A | N/A | N/A | 6529000 | 28.86 | 8.63 | 8.63 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | No |  | No |  | No | [27 empty] | Exist
2015-02-12 | 2015-12-11 | PCSB | SK | D18 | D18-208A | APPRAISAL CUM DEV/DEVELOPMENT | COSL BOSS | JACK UP | 36.57 | 1658.03 | 1330.69 | N/A | N/A | N/A | N/A | 14890407 | 25.7 | NO | N/A | N/A | 2015-03-06 | 2015-03-05 13:00 | 2015-05-07 02:30 | 1642.18 | SHALLOW WATER | 1716.55 | 1338.01 | N/A | N/A | N/A | N/A | 12443037 | 28.9 | 1.5 | 1.5 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.6 |  | 1019 |  | 2305 | [27 empty] | Exist
2015-02-12 | 2015-12-11 | PCSB | SK | D18 | D18-207A | APPRAISAL CUM DEV/DEVELOPMENT | COSL BOSS | JACK UP | 36.57 | 2573 | 1301.74 | N/A | N/A | N/A | N/A | 16373510.15 | 32 | NO | N/A | N/A | 2015-02-21 | 2015-02-20 | 2015-06-27 | 2509.6 | SHALLOW WATER | 2583.97 | 1299.91 | N/A | N/A | N/A | N/A | 17001419.58 | 39.37 | 2 | 1.8 | SW DEV C1 |  | 2.2 |  | 830 |  | 1220 |  | 2.39 |  | 844 |  | 2062 | [27 empty] | Exist
2015-02-12 | 2015-06-26 | PCSB | PM | ANDING UTARA | ANDING UTARA-3 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 74.5 | 3838 | 3227 | 58930000 | 88960000 | 77.4 | 132.6 | N/A | N/A | NO | N/A | N/A | 2015-02-22 | 2015-02-17 08:00 | 2015-05-03 03:30 | 3490.17 | SHALLOW WATER | 3601 | 3080 | 50890000 | N/A | 74.81 | N/A | N/A | N/A | 4.72 | 4.72 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 4.61 |  | 3433.3 |  | 4068.2 | [27 empty] | Exist
2015-02-09 | 2015-06-04 | PTTEP | SK | BELUM | BESA-12 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 27 | 2043 | 1920 | N/A | N/A | N/A | N/A | 6116494.01 | 6.8 | NO | N/A | DRY TREE | 2015-04-01 22:30 | 2015-03-27 05:00 | 2015-04-22 01:00 | 1977.8 | SHALLOW WATER | 2037 | 1936.84 | N/A | N/A | N/A | N/A | 3600220 | 6.13 | 6.46 | 6.46 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | 0.84 |  | 489 |  | 572 | [6 empty] | 0.87 | 1050000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 31.719 | False | NONE | L80 13CR | 6.68 | BASE OIL/DIESEL | NO | NO | Exist
2015-02-09 | 2015-06-04 | PTTEP | SK | BELUM | BESA-01 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 27 | 1930.36 | 1003.34 | N/A | N/A | N/A | N/A | 4934852.78 | 7.6 | NO | N/A | DRY TREE | N/A | 2015-03-26 19:30 | 2015-04-09 07:00 | 1790.8 | SHALLOW WATER | 1850 | 1040.93 | N/A | N/A | N/A | N/A | 4079821 | 6.19 | 6.73 | 6.73 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 0.86 |  | 564 |  | 725 | [6 empty] | 0.98 | 1407000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 311.695 | False | NONE | L80 13CR | 6.68 | BASE OIL/DIESEL | NO | NO | Exist
2015-02-09 | 2015-06-04 | PTTEP | SK | BELUM | BESA-03 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 27 | 1444.65 | 1008.22 | N/A | N/A | N/A | N/A | 5056009.95 | 6.8 | NO | N/A | DRY TREE | 2015-03-25 | 2015-03-25 | 2015-04-12 | 1460.8 | SHALLOW WATER | 1520 | 1069.09 | N/A | N/A | N/A | N/A | 3571037.08 | 6.4 | 0.65 | 0.65 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 1.16 |  | 645 |  | 745 | [6 empty] | 0.83 | 1100000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 154.207 | False | NONE | L80 13CR | 6.68 | BASE OIL/DIESEL | NO | NO | Exist
2015-01-22 | 2015-11-18 | PCSB | SK | BARAM | BA-33 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 61.57 | 3097.23 | 2978.06 | N/A | N/A | N/A | N/A | 31610000 | 62.81 | SIDETRACK | N/A | N/A | N/A | 2015-03-03 | 2015-05-19 02:30 | 3011.73 | SHALLOW WATER | 3100.27 | 2891.68 | N/A | N/A | N/A | N/A | 29320000 | 87.31 | 7.33 | 7.33 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | No |  | No |  | No | [27 empty] | Exist
2014-12-31 | 2015-05-22 | PCSB | SK | NUANG | NUANG-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 38.2 | 1230 | 1230 | 27337484.27 | 35404480.47 | 43.8 | 61.6 | N/A | N/A | NO | N/A | N/A | 2015-01-28 04:45 | 2015-01-07 | 2015-03-16 15:00 | 1162.3 | SHALLOW WATER | 1234 | 1234 | N/A | 35400000 | N/A | 68.63 | N/A | N/A | 50.33 | 24.81 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 5.77 |  | 2369.5 |  | 5391 | [27 empty] | Exist
2014-12-16 | 2015-10-08 | PCSB | SK | K5 | K5-4 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 79 | 2500 | 2500 | 70955994.97 | 75472844.41 | 122 | 139 | N/A | N/A | NO | N/A | N/A | 2015-03-21 | 2015-03-18 13:30 | 2015-07-27 02:00 | 2267 | SHALLOW WATER | 2373 | 2372.9 | N/A | 72104129 | N/A | 130.52 | N/A | N/A | 8.72 | 8.64 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 3.38 |  | 1650 |  | 5403.58 | [27 empty] | Exist
2014-12-16 | 2015-04-14 | IPC | PM | BERTAM | BERTAM A-3 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3430 | 1652 | N/A | N/A | N/A | N/A | 20374278 | 36 | NO | N/A | DRY TREE | 2015-01-06 | 2015-01-06 | 2015-02-03 18:00 | 3311.26 | SHALLOW WATER | 3430 | 1652.15 | N/A | N/A | N/A | N/A | 21388852 | 39.1 | 8.53 | 8.53 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.68 |  | 1338.31 |  | 1900.68 | [6 empty] | 7.7 | 5400000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 2744.5106 | True | ICD | L80 | 10.4 | BASE OIL/DIESEL | 1 | NO | Exist
2014-12-15 | 2015-07-15 | JX NIPPON | SB | LAWA | LAWA-1 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 666.4 | 3626 | 3626 | 85620000 | 85620000 | 61.25 | 61.25 | N/A | N/A | NO | N/A | N/A | 2015-03-31 04:30 | 2015-03-29 19:00 | 2015-05-10 01:15 | 2890.4 | DEEP WATER | 3583 | 3583 | N/A | 47000000 | N/A | 41.3 | N/A | N/A | 13.2 | 13.2 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 3.11 |  | 3668 |  | 4952 | [27 empty] | Exist
2014-12-11 | 2015-03-18 | PTTEP | SK | SOUTH ACIS | SAPA-07 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 3873.36 | 1554.24 | N/A | N/A | N/A | N/A | 10770220 | 12.66 | NO | N/A | DRY TREE | N/A | 2014-12-17 | 2015-02-19 15:30 | 3945.16 | SHALLOW WATER | 4023 | 1608.05 | N/A | N/A | N/A | N/A | 11424978 | 25.34 | 5.59 | 5.59 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 2.1 |  | 700 |  | 1140 | [6 empty] | 11.02 | 3586000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 250 | False |  | L80 | 6.6 | OTHER | NO | NO | Exist
2014-12-11 | 2015-04-03 | PTTEP | SK | SOUTH ACIS | SAPA-15 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2632.82 | 1566.21 | N/A | N/A | N/A | N/A | 7287154 | 10.92 | NO | N/A | N/A | 2014-12-18 20:30 | 2014-12-18 08:30 | 2015-03-08 | 2192.16 | SHALLOW WATER | 2270 | 1524.24 | N/A | N/A | N/A | N/A | 6829823 | 12.96 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.15 |  | 604 |  | 772 | [27 empty] | Exist
2014-12-10 | 2015-06-02 | PCSB | SK | KUANG NORTH | KUANG NORTH-3 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 196.6 | 3411 | 3411 | 34200000 | 43500000 | 60.5 | 78.5 | N/A | N/A | NO | N/A | N/A | 2015-01-16 | 2015-01-10 19:00 | 2015-04-07 04:00 | 3193 | SHALLOW WATER | 3417.6 | 3411 | N/A | 34277408.45 | N/A | 86.38 | N/A | N/A | 15.59 | 13.17 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.53 |  | 2135 |  | 3496 | [27 empty] | Exist
2014-12-10 | 2015-02-13 | PTTEP | SK | SOUTH ACIS | SAPA-04 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 3124.56 | 1464.4 | N/A | N/A | N/A | N/A | 11580639 | 13.65 | NO | N/A | N/A | 2014-12-22 03:00 | 2014-12-21 18:00 | 2015-01-21 22:30 | 2036.16 | SHALLOW WATER | 2149 | 1364 | N/A | N/A | N/A | N/A | 18676712 | 29.6 | 25.76 | 25.76 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 770 |  | 1.02 |  | 603.09 |  | 1038.12 | [27 empty] | Exist
2014-11-26 | 2015-04-21 | EMEPMI | PM | TELOK | TELOK-B7 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 63.6 | 4279 | 2160 | N/A | N/A | N/A | N/A | 30000000 | 50.68 | NO | N/A | DRY TREE | 2014-12-13 | 2014-12-13 05:00 | 2015-03-10 12:00 | 4122.53 | SHALLOW WATER | 4231 | 2137.08 | N/A | N/A | N/A | N/A | 26068600 | 42.29 | 9.17 | 9.17 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [6 empty] | 7.16 | 6389747.5 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 13CR | 292 | True | NONE | L80 13CR | 9.3 | NACL | NO | NO | Exist
2014-11-24 | 2015-05-27 | PCSB | SB | WAKID | WAKID-3 | EXPLORATION/APPRAISAL | MG HULME | SEMI-SUB | 208 | 3327 | 3327 | 44671060.38 | 44671060.38 | 57 | 57 | N/A | N/A | NO | N/A | N/A | 2014-12-31 | 2014-12-28 16:00 | 2015-03-15 05:30 | 2811.1 | SHALLOW WATER | 3045 | 3045 | N/A | 62650430.58 | N/A | 115.6 | N/A | N/A | 23.1 | 15.7 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 8.57 |  | 4201 |  | 5446 | [27 empty] | Exist
2014-11-13 | 2015-03-04 | PCSB | SB | DANUM | DANUM-2 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 70.4 | 1555 | 1555 | 17540000 | 25416338.95 | 25.28 | 38.03 | N/A | N/A | NO | N/A | N/A | 2014-12-06 | 2014-12-04 22:00 | 2015-01-06 16:00 | 1461.6 | SHALLOW WATER | 1560 | 1558 | 15323425 | N/A | 32.75 | N/A | N/A | N/A | 32.86 | 11.45 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.94 |  | 813 |  | 1385 | [27 empty] | Exist
2014-11-11 | 2015-10-12 | PCSB | SK | D18 | D18-209A | APPRAISAL CUM DEV/DEVELOPMENT | COSL BOSS | JACK UP | 36.57 | 1684.55 | 1325.51 | N/A | N/A | N/A | N/A | 15740000 | 25 | NO | N/A | N/A | 2015-01-16 | 2015-01-05 | 2015-02-20 06:00 | 1605.3 | SHALLOW WATER | 1679.67 | 1324.6 | N/A | N/A | N/A | N/A | 17073609.33 | 36.31 | 11.3 | 5.9 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 3.18 |  | 1389 |  | 3235 | [27 empty] | Exist
2014-11-11 | 2015-11-02 | PCSB | SK | D18 | D18-209B | APPRAISAL CUM DEV/DEVELOPMENT | COSL BOSS | JACK UP | 36.57 | 2026.82 | 1320.33 | N/A | N/A | N/A | N/A | 14890401.62 | 30 | NO | N/A | N/A | 2015-01-08 | 2015-01-06 | 2015-04-17 | 1951.54 | SHALLOW WATER | 2025.91 | 1338.62 | N/A | N/A | N/A | N/A | 17232400.11 | 41.8 | 16.3 | 16.3 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 2.69 |  | 968 |  | 2687 | [27 empty] | Exist
2014-11-05 | 2015-01-15 | PCSB | SB | NILAM | NILAM-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 40 | 3179 | 2632 | 21570316.29 | 21570316.29 | 35.25 | 35.25 | N/A | N/A | NO | N/A | N/A | 2014-11-17 | 2014-11-07 18:30 | 2014-12-21 22:00 | 2988.1 | SHALLOW WATER | 3063 | 2545 | 23105898.83 | N/A | 44.23 | N/A | N/A | N/A | 7.35 | 3.44 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 2.45 |  | 1261 |  | 1923 | [27 empty] | Exist
2014-10-23 | 2014-12-31 | PCSB | SK | AMRA | AMRA-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 66 | 3252 | 2800 | 15308845 | 23550709 | 31 | 44 | N/A | N/A | NO | N/A | N/A | 2014-10-30 | 2014-10-26 02:15 | 2014-11-26 05:00 | 3198 | SHALLOW WATER | 3300 | 2836 | 13518523.11 | N/A | 30.1 | N/A | N/A | N/A | 5.8 | 5.8 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.34 |  | 593 |  | 879 | [27 empty] | Exist
2014-10-21 | 2015-11-17 | IPC | PM | MENGKUANG | MENGKUANG-1 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 69.3 | 1299 | 1299 | 13600000 | 16700000 | 21.7 | 27 | N/A | N/A | NO | N/A | N/A | 2015-10-01 | 2015-09-22 09:00 | 2015-10-16 14:00 | 1189.7 | SHALLOW WATER | 1293 | 1292.9 | N/A | 10700000 | N/A | 20.9 | N/A | N/A | 14.08 | 14.08 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 2.52 |  | 1158.12 |  | 2739.18 | [27 empty] | Exist
2014-10-17 | 2015-05-12 | PETROFAC | PM | WEST DESARU | WD-A12 | APPRAISAL CUM DEV/DEVELOPMENT | TRIDENT-9 | JACK UP | 64.8 | 3402.5 | 1482.96 | N/A | N/A | N/A | N/A | 15563430.55 | 37.5 | NO | N/A | DRY TREE | 2014-11-03 | 2014-10-29 21:00 | 2015-02-21 16:00 | 3279.4 | SHALLOW WATER | 3387 | 1559.22 | N/A | N/A | N/A | N/A | 14660252.57 | 27.62 | 6 | 6 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | No |  | No |  | No | [6 empty] | 4.29 | 2853762 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | GRE | 0 | False |  | 25CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2014-10-03 | 2015-01-05 | PCSB | SB | ZUHAL NORTH | ZUHAL NORTH - 1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 13 | 1710 | 1710 | 16363942.79 | 26436778.72 | 30.41 | 54.05 | N/A | N/A | NO | N/A | N/A | 2014-10-19 12:00 | 2014-10-13 | 2014-11-07 18:30 | 1817.1 | SHALLOW WATER | 1865 | 1865 | 12583111.25 | N/A | 25.77 | N/A | N/A | N/A | 3.36 | 3.36 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 2.02 |  | 961 |  | 1869 | [27 empty] | Exist
2014-09-29 | 2014-12-04 | PCSB | SK | CEKUR MANIS | CEKUR MANIS-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 66.4 | 1305 | 1305 | 16770000 | 22860000 | 27 | 38 | N/A | N/A | NO | N/A | N/A | 2014-10-09 07:30 | 2014-10-02 17:15 | 2014-10-26 02:15 | 1250.75 | SHALLOW WATER | 1353 | 1353 | 11140000 | N/A | 23.36 | N/A | N/A | N/A | 0.89 | 0.89 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 1.54 |  | 789 |  | 1157 | [27 empty] | Exist
2014-09-29 | 2014-12-22 | SAPURA OMV | PM | CHERMINGAT | CHRA-03 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-104 | JACK UP | 66.77 | 1827 | 1328 | N/A | N/A | N/A | N/A | 20935590 | 49.13 | NO | N/A | N/A | 2014-10-13 17:00 | 2014-10-12 22:00 | 2014-11-26 | 1700.16 | SHALLOW WATER | 1806.4 | 1798.52 | N/A | N/A | N/A | N/A | 21574000 | 44.08 | 45.09 | 45.09 | SW DEV C1 | SW DEV C1 | 2.1 | 2.1 | 700 | 700 | 1620 | 1620 | Yes | 2.29 | Yes | 839 | Yes | 3858 | [26 empty] | Exist
2014-09-25 | 2015-05-27 | JX NIPPON | SB | BESTARI | BESTARI-1 | EXPLORATION/APPRAISAL | OCEAN ROVER | SEMI-SUB | 1156.2 | 3250.63 | 3226.2 | 76485000 | 76485000 | 57 | 57 | N/A | N/A | NO | N/A | N/A | 2015-01-28 | 2015-01-26 18:30 | 2015-03-29 12:00 | 1662.6 | DEEP WATER | 2845 | 2819.9 | N/A | 73100000 | N/A | 61.7 | N/A | N/A | 2.58 | 2.48 | No DMS category | [7 empty] | 6.2 |  | 9073 |  | 13402 | [27 empty] | Exist
2014-09-24 | 2015-03-02 | PTTEP | SB | KIKEH | KIKEH_PX03(136) | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1306.5 | 4370 | 3056 | N/A | N/A | N/A | N/A | 66937239 | 52.8 | SIDETRACK | N/A | N/A | 2014-12-16 | 2014-11-28 | 2015-01-26 08:00 | 2462.3 | DEEP WATER | 3795 | 2885 | N/A | N/A | N/A | N/A | 64898942 | 59.33 | 1.09 | 0.46 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | 11.86 |  | 12975 |  | 29676 | [27 empty] | Exist
2014-09-17 | 2015-03-31 | PTTEP | SK | SOUTH ACIS | SAPA-13 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 1783 | 1198 | N/A | N/A | N/A | N/A | 7400000 | 13.5 | NO | N/A | N/A | 2014-12-20 11:30 | 2014-12-20 04:30 | 2015-03-03 05:00 | 2317.16 | SHALLOW WATER | 2395 | 1428.04 | N/A | N/A | N/A | N/A | 6695903 | 13.1 | 3.98 | 3.98 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.02 |  | 487 |  | 503 | [27 empty] | Exist
2014-09-17 | 2015-02-05 | PTTEP | SK | SOUTH ACIS | SAPA-06 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 42.8 | 2211 | 1557 | N/A | N/A | N/A | N/A | 7828912 | 12.67 | NO | N/A | N/A | 2014-12-01 23:00 | 2014-12-01 09:00 | 2014-12-13 17:00 | 2025.36 | SHALLOW WATER | 2111 | 1552.82 | N/A | N/A | N/A | N/A | 5972274 | 10.6 | 33.81 | 33.81 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | 1.39 |  | 783 |  | 929 | [27 empty] | Exist
2014-09-11 | 2014-10-24 | SAPURA OMV | PM | EAST BELUMUT | EB A-09ST2 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-106 | JACK UP | 72 | 4186.6 | 1167.7 | N/A | N/A | N/A | N/A | 17642691 | 30.8 | NO | N/A | N/A | 2014-09-16 | 2014-09-16 | 2014-10-07 07:30 | 3504.3 | SHALLOW WATER | 3621 | 1166.2 | N/A | N/A | N/A | N/A | 10991294.66 | 20.81 | 2.4 | 2.4 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 1160 |  | No |  | No |  | No | [27 empty] | Exist
2014-09-10 | 2015-03-10 | PCSB | SK | SRI AMAN | SRI AMAN-1 RDR-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 77 | 2620 | 2515 | 25205030 | 38713944 | 45.03 | 59.03 | N/A | N/A | NO | N/A | N/A | 2014-11-01 | 2014-10-28 | 2015-01-10 | 2545 | SHALLOW WATER | 2650 | 2521.6 | N/A | 38464353 | N/A | 74.29 | N/A | N/A | 6.76 | 4.95 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.04 |  | 2896 |  | 4623 | [27 empty] | Exist
2014-09-10 | 2014-12-11 | PCSB | SK | KMSE | LIMAU MANIS-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 85 | 1530 | 1530 | 12970000 | 21150000 | 19.5 | 32.95 | N/A | N/A | NO | N/A | N/A | 2014-09-25 01:00 | 2014-09-14 17:00 | 2014-10-13 | 1465 | SHALLOW WATER | 1580 | 1580 | 10076225.92 | N/A | 28.29 | N/A | N/A | N/A | 14.46 | 2.71 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.36 |  | 656 |  | 1678 | [27 empty] | Exist
2014-09-04 | 2015-06-23 | PCSB | SK | BARAM | BA-41 SR | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 61.57 | 2938.43 | 2642.79 | N/A | N/A | N/A | N/A | 26361638 | 71 | NO | N/A | N/A | 2014-09-22 23:30 | 2014-09-22 16:30 | 2014-12-18 13:30 | 2852.64 | SHALLOW WATER | 2941.18 | 2643.71 | N/A | N/A | N/A | N/A | 25204674.88 | 87.13 | 31 | 23.77 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.33 |  | 1107.74 |  | 2863 | [27 empty] | Exist
2014-09-02 | 2015-01-05 | PTTEP | SK | SOUTH ACIS | SAPA-12 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 3117 | 1525 | N/A | N/A | N/A | N/A | 6107953 | 7.5 | NO | N/A | N/A | 2014-09-21 | 2014-09-21 | 2014-11-06 | 2995.2 | SHALLOW WATER | 3073 | 1587.07 | N/A | N/A | N/A | N/A | 6489631.67 | 9.25 | 0.45 | 0.45 | SW DEV C1 | SW DEV C1 | 2.2 | 2.2 | 830 | 830 | 1395 | 1395 | Yes | 0.74 | Yes | 544 | Yes | 644 | [26 empty] | Exist
2014-09-02 | 2015-07-20 | PCSB | SB | KINABALU | KN-B4 | APPRAISAL CUM DEV/DEVELOPMENT | DEEP DRILLER-3 | JACK UP | 59.1 | 4724.78 | 4629.69 | N/A | N/A | N/A | N/A | 118730920.68 | 137.98 | NO | N/A | N/A | 2014-12-06 | 2014-12-05 | 2015-05-31 03:30 | 4658.37 | SHALLOW WATER | 4774.15 | 4673.88 | N/A | N/A | N/A | N/A | 108956298 | 180.4 | 25.3 | 25 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 9.78 |  | 4674 |  | 5895 | [27 empty] | Exist
2014-09-02 | 2015-01-15 | MURPHY | SK | SOUTH ACIS | SAPA-14 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2689 | 1383 | N/A | N/A | N/A | N/A | 8729998 | 18.8 | SIDETRACK | N/A | N/A | 2014-09-22 | 2014-09-22 | 2014-11-23 | 3075.2 | SHALLOW WATER | 3153 | 1447.96 | N/A | N/A | N/A | N/A | 10359462 | 21.35 | 1.17 | 1.17 | SW DEV C1 | SW DEV C1 | 2.2 | 2.2 | 830 | 830 | 1380 | 1380 | Yes | 1.5 | Yes | 752 | Yes | 897 | [26 empty] | Exist
2014-09-02 | 2015-01-14 | PTTEP | SK | SAPA | SAPA-10 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2612 | 1490 | N/A | N/A | N/A | N/A | 7296729.12 | 14.4 | SIDETRACK | N/A | DRY TREE | 2014-09-17 | 2014-09-17 | 2014-11-17 | 2156.16 | SHALLOW WATER | 2234 | 1460.37 | N/A | N/A | N/A | N/A | 9799111.91 | 20.15 | 3.83 | 3.83 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.93 |  | 499.23 |  | 690.66 | [6 empty] | 3.35 | 2329588.95 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 106.6325 | True | NONE | L80 13CR | 9.6 | CACL2 | NO | NO | Exist
2014-08-28 | 2015-01-06 | PCSB | PM | ANGSI | ANGSI-B31 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 69 | 4370 | 1706 | N/A | N/A | N/A | N/A | 28663200 | 47.02 | NO | N/A | DRY TREE | 2014-09-28 | 2014-09-25 | 2014-12-05 06:00 | 4208.82 | SHALLOW WATER | 4312 | 1712 | N/A | N/A | N/A | N/A | 27968113.95 | 52.77 | 10.22 | 10.07 | No DMS category. Having value but not sure refering which version | [7 empty] | 2.17 |  | 1785.23 |  | 1999.11 | [6 empty] | 6.86 | 3732483.86 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 318.257 | True | NONE | 9CR | 9.8 | NACL | NO | NO | Exist
2014-08-27 | 2014-12-19 | IPC | SB | KITABU | KITABU-1 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 48.9 | 2270 | 2270 | 19987000 | 32506000 | 41 | 64 | N/A | N/A | NO | N/A | N/A | 2014-10-24 14:00 | 2014-10-13 16:30 | 2014-11-14 14:30 | 2187.1 | SHALLOW WATER | 2270 | 2268 | 17200000 | N/A | 39 | N/A | N/A | N/A | 0.21 | 0.21 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-08-22 | 2014-12-02 | SAPURA OMV | PM | PUTERI | PUTERI A-05 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-104 | JACK UP | 59 | 2970 | 2084 | N/A | N/A | N/A | N/A | 24960000 | 55.5 | NO | N/A | N/A | 2014-09-06 08:45 | 2014-08-29 | 2014-09-30 16:00 | 2956 | SHALLOW WATER | 3060 | 2079 | N/A | N/A | N/A | N/A | 17877461 | 39.77 | 7.2 | 7.02 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.04 |  | 444 |  | 1287 | [27 empty] | Exist
2014-08-12 | 2015-06-26 | PCSB | PM | GANSAR | GANSAR-1 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 75 | 4243.89 | 3812 | 77470000 | 119700000 | 77 | 146.2 | N/A | N/A | NO | N/A | N/A | 2014-08-18 | 2014-08-13 | 2015-02-17 | 3163 | SHALLOW WATER | 3270 | 3101 | N/A | 121661953.81 | N/A | 188.3 | N/A | N/A | 28.22 | 28.22 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 11.4 |  | 8102.78 |  | 9605.88 | [27 empty] | Exist
2014-08-08 | 2015-01-22 | PCSB | PM | BUJANG | BUJANG D2-1 | EXPLORATION/APPRAISAL | TOPAZ DRILLER | JACK UP | 68.1 | 2685 | 2685 | 55400000 | 66900000 | 77.73 | 94.83 | N/A | N/A | NO | N/A | N/A | 2014-08-20 | 2014-08-09 12:00 | 2014-11-25 09:00 | 2375.95 | SHALLOW WATER | 2477 | 2476.82 | N/A | 62080000 | N/A | 107.88 | N/A | N/A | 14.31 | 12.45 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 5.31 |  | 3758.14 |  | 5771.78 | [27 empty] | Exist
2014-08-05 | 2015-09-10 | PETROFAC | PM | CENDOR | CD-C08 | APPRAISAL CUM DEV/DEVELOPMENT | TRIDENT-9 | JACK UP | 62.3 | 3661.16 | 1488.9 | N/A | N/A | N/A | N/A | 15576883 | 30.16 | NO | N/A | N/A | 2014-10-12 | 2014-10-11 16:00 | 2015-05-27 18:15 | 3281.4 | SHALLOW WATER | 3385 | 1417.94 | N/A | N/A | N/A | N/A | 13876431 | 38.74 | 32.2 | 32.2 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | No |  | No |  | No | [27 empty] | Exist
2014-07-27 | 2015-02-27 | IPC | PM | BERTAM | BERTAM A-1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3455 | 1643 | N/A | N/A | N/A | N/A | 24200000 | 46.7 | NO | N/A | N/A | 2014-08-09 | 2014-08-08 | 2015-01-01 21:00 | 3117.96 | SHALLOW WATER | 3230 | 1654.53 | N/A | N/A | N/A | N/A | 18900000 | 34.2 | 4.15 | 4.15 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.28 |  | 1184.12 |  | 1626.68 | [27 empty] | Exist
2014-07-25 | 2014-10-02 | PCSB | PM | GAYONG DEEP | GAYONG DEEP-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 75 | 2232 | 2232 | 20900000 | 27470000 | 35.55 | 48.52 | N/A | N/A | NO | N/A | N/A | 2014-08-08 21:00 | N/A | 2014-09-14 17:00 | 2179.1 | SHALLOW WATER | 2289 | 2289 | N/A | 19570000 | N/A | 38.71 | N/A | N/A | 7.87 | 7.87 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-07-24 | 2015-07-13 | IPC | PM | BERTAM | BERTAM A-6 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 2580 | 1654.37 | N/A | N/A | N/A | N/A | 18587403 | 30.7 | NO | N/A | DRY TREE | 2014-08-11 | 2014-08-08 | 2015-06-09 11:00 | 2401.78 | SHALLOW WATER | 2520.52 | 1654.76 | N/A | N/A | N/A | N/A | 16251899 | 25.7 | 2.51 | 2.51 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1890 |  | 2.19 |  | 1249.6 |  | 1958.72 | [6 empty] | 5 | 4700000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 1362.2745 | True | ICD | L80 | 10 | BASE OIL/DIESEL | 1 | NO | Exist
2014-07-20 | 2015-02-13 | IPC | PM | BERTAM | BERTAM A-2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3466.34 | 1647.34 | N/A | N/A | N/A | N/A | 22710000 | 41.8 | SIDETRACK | N/A | DRY TREE | 2014-08-11 | 2014-08-08 | 2014-12-20 17:00 | 3354.26 | SHALLOW WATER | 3473 | 1653.6 | N/A | N/A | N/A | N/A | 23500000 | 45.7 | 3.3 | 3.3 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.34 |  | 1149.61 |  | 1519.73 | [6 empty] | 8 | 5030000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 2966.024 | True | ICD | L80 | 9.9 | BASE OIL/DIESEL | 1 | NO | Exist
2014-07-03 | 2014-11-20 | PTTEP | SB | KIKEH | KIKEH_WX16(119) | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1285.12 | 4682 | 3116 | N/A | N/A | N/A | N/A | 76732380 | 54.4 | SIDETRACK | N/A | N/A | 2014-07-29 | 2014-07-27 12:00 | 2014-09-28 12:00 | 3398.68 | DEEP WATER | 4710 | 3118 | N/A | N/A | N/A | N/A | 77687329 | 63 | 2.51 | 2.51 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | 1.7 |  | 2107 |  | 4062 | [27 empty] | Exist
2014-06-27 | 2014-12-18 | EMEPMI | PM | TELOK | TELOK-B2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 63.6 | 2100 | 898 | N/A | N/A | N/A | N/A | 20900000 | 31.8 | NO | N/A | DRY TREE | 2014-09-18 21:30 | 2014-09-18 05:00 | 2014-10-28 | 2014.53 | SHALLOW WATER | 2123 | 897 | N/A | N/A | N/A | N/A | 18833000 | 25.77 | 2.02 | 1.05 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [6 empty] | 13.3 | 4037000 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 7" | 1.0 | SINGLE | L80 13CR | 138 | True | NONE | L80 13CR | 9 | NACL | NO | NO | Exist
2014-06-04 | 2014-09-11 | PTTEP | SB | SIAKAP NORTH PETAI | S-CN1-W4 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1308.3 | 2851 | 2730.5 | N/A | N/A | N/A | N/A | 55912449 | 40.2 | NO | N/A | WET TREE | 2014-06-11 | 2014-06-10 | 2014-07-27 12:00 | 1481.5 | DEEP WATER | 2816 | 2732 | N/A | N/A | N/A | N/A | 47160788 | 35.5 | 0.7 | 0.7 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | 1.83 |  | 2425 |  | 8302 | [6 empty] | 21.25 | 28230049.15 |  |  | SANDSTONE | NORMAL | CASED HOLE COMPLIANT SCREEN | 2 ZONES | NO | 5-1/2" | 2.0 | SINGLE | L80 1CR | 626.0148 | True | ICV | L80 1CR | 10.4 | CACL2 | 1 | NO | Exist
2014-05-30 | 2014-12-28 | SAPURA OMV | SK | BAKONG | BAKONG-1 | EXPLORATION/APPRAISAL | ENSCO-106 | JACK UP | 85 | 2303 | 2159 | 12650000 | 12650000 | 29.5 | 29.5 | N/A | N/A | NO | N/A | N/A | 2014-06-12 10:00 | 2014-06-09 10:00 | 2014-07-09 13:00 | 2263.7 | SHALLOW WATER | 2383 | 2338.6 | N/A | 15650000 | N/A | 30.4 | N/A | N/A | 8.96 | 7.88 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-05-25 | 2014-10-08 | EMEPMI | PM | DAMAR | DAMAR-A05 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 55.7 | 3735 | 1886 | N/A | N/A | N/A | N/A | 38200000 | 65 | NO | N/A | DRY TREE | 2014-06-18 | 2014-06-17 | 2014-08-26 | 3640.51 | SHALLOW WATER | 3740 | 1888 | N/A | N/A | N/A | N/A | 36613000 | 70 | 50.1 | 50.04 | SW DEV C1 |  | 2.1 |  | 700 |  | 1620 |  | No |  | No |  | No | [6 empty] | 7 | 7805000 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR | 1148 | True | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
2014-05-22 | N/A | SHELL | SK | F14 | F14-105 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 105.15 | 1983.54 | 1325.82 | N/A | N/A | N/A | N/A | 99087000 | 33.86 | NO | N/A | N/A | 2014-06-27 12:45 | 2014-06-16 21:30 | 2014-09-04 | 1843.34 | SHALLOW WATER | 1982.32 | 1358.43 | N/A | N/A | N/A | N/A | 99635241.64 | 47.27 | 15.73 | 15.73 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.78 |  | 1647 |  | 2497 | [27 empty] | Exist
2014-05-22 | 2014-11-06 | PCSB | SB | TEMBUNGO | TBG-A01 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 83.4 | 1846.3 | 1681 | N/A | N/A | N/A | N/A | 15434347.91 | 29.6 | NO | N/A | N/A | 2014-07-07 | 2014-06-30 11:00 | 2014-10-06 09:00 | 1791.4 | SHALLOW WATER | 1916.7 | 1735.38 | N/A | N/A | N/A | N/A | 8452057.35 | 24.2 | 2.18 | 2.18 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 3.37 |  | 1643.6 |  | 2768.44 | [27 empty] | Exist
2014-05-19 | 2014-09-05 | IPC | PM | TEMBAKAU | TEMBAKAU-2 | EXPLORATION/APPRAISAL | WEST PROSPERO | JACK UP | 67.9 | 1406 | 1406 | 18400000 | 33400000 | 34 | 66.4 | N/A | N/A | NO | N/A | N/A | 2014-06-18 15:30 | 2014-06-14 17:00 | 2014-08-02 15:30 | 1348.1 | SHALLOW WATER | 1450 | 1416.9 | N/A | 28600000 | N/A | 52.4 | N/A | N/A | 3.78 | 3.78 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | No |  | No |  | No | [27 empty] | Exist
2014-05-05 | 2014-10-29 | PCSB | SB | KUKUSAN | KUKUSAN-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 47 | 3271 | 2663 | 29359877.37 | 37631676.77 | 42 | 54 | N/A | N/A | SIDETRACK | N/A | N/A | 2014-05-13 12:30 | 2014-05-09 13:00 | 2014-07-31 | 2613 | SHALLOW WATER | 2688 | 2227 | N/A | 42994331 | N/A | 90.46 | N/A | N/A | 7.5 | 7.5 | SW EXP C1 |  | 2.6 |  | 1010 |  | 2090 |  | 5.28 |  | 2736 |  | 4031 | [27 empty] | Missing
2014-05-01 | 2014-11-25 | PCSB | SB | TEMBUNGO | TBG-B5ST1 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 86 | 3655.2 | 2762.6 | N/A | N/A | N/A | N/A | 24003385.9 | 43.9 | NO | N/A | DRY TREE | 2014-08-04 09:45 | 2014-06-04 13:45 | 2014-09-30 17:15 | 3076.5 | SHALLOW WATER | 3200 | 2667.4 | N/A | N/A | N/A | N/A | 30949938.92 | 77.2 | 11.9 | 11.8 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 4.1 |  | 1842.69 |  | 3512.17 | [6 empty] | 17.65 | 6285628.41 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 82.025 | True | NONE | 9CR | 8.5 | NACL | NO | 1 | Exist
2014-04-15 | 2014-10-07 | PCSB | SB | TEMBUNGO | TBG-B3ST2 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 86 | 3868 | 2838 | N/A | N/A | N/A | N/A | 25792581.8 | 49.4 | NO | N/A | DRY TREE | 2014-05-13 22:00 | 2014-04-27 11:00 | 2014-07-21 12:00 | 3593.5 | SHALLOW WATER | 3717 | 2773 | N/A | N/A | N/A | N/A | 26259136.77 | 79.1 | 45.8 | 45.7 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 5.1 |  | 1510.34 |  | 3446.77 | [6 empty] | 23.13 | 6715716.7 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 501.993 | True | NONE | 9CR | 9.5 | NACL | NO | 1 | Exist
2014-04-10 | 2014-10-29 | PTTEP | SK | SOUTH ACIS | SAPA-22 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 3390 | 1643 | N/A | N/A | N/A | N/A | 48606488 | 13.8 | SIDETRACK | N/A | N/A | N/A | 2014-05-15 09:30 | 2014-10-22 07:30 | 3546.16 | SHALLOW WATER | 3625 | 1674.45 | N/A | N/A | N/A | N/A | 15959989 | 32.8 | 3.24 | 3.24 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.03 |  | 611.83 |  | 689.79 | [27 empty] | Exist
2014-04-10 | 2014-10-02 | PTTEP | SK | SAPA | SAPA-20 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2341 | 1421 | N/A | N/A | N/A | N/A | 6948002 | 11.5 | NO | N/A | DRY TREE | 2014-05-25 | 2014-05-16 | 2014-07-04 | 2332.16 | SHALLOW WATER | 2410 | 1423.7 | N/A | N/A | N/A | N/A | 6739862.54 | 11.5 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.21 |  | 715.19 |  | 1007.44 | [6 empty] | 3.23 | 1807351.5 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 167.331 | True | NONE | L80 13CR | 9.5 | CACL2 | NO | NO | Exist
2014-04-10 | 2014-11-25 | PTTEP | SK | SAPA | SAPA-21 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2497 | 1440 | N/A | N/A | N/A | N/A | 6781658 | 10.9 | SIDETRACK | N/A | DRY TREE | 2014-05-27 | 2014-05-16 05:00 | 2014-07-08 | 2322.16 | SHALLOW WATER | 2400 | 1414.8 | N/A | N/A | N/A | N/A | 9948753.18 | 17.7 | 3.53 | 3.53 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 0.32 |  | 708.54 |  | 998.53 | [6 empty] | 2.61 | 1817000 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 52.1679 | True | NONE | L80 13CR | 9.5 | CACL2 | NO | NO | Exist
2014-04-10 | 2014-10-14 | MURPHY | SK | SOUTH ACIS | SAPA-24 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 1380 | 1354 | N/A | N/A | N/A | N/A | 6037553 | 9.4 | NO | N/A | N/A | 2014-05-18 | 2014-05-18 | 2014-07-11 | 1372.2 | SHALLOW WATER | 1450 | 1420.01 | N/A | N/A | N/A | N/A | 5640681 | 9.5 | 0.66 | 0.66 | SW DEV C2 | SW DEV C2 | 2 | 2 | 725 | 725 | 1295 | 1295 | Yes | 1.24 | Yes | 737 | Yes | 1186 | [26 empty] | Exist
2014-04-10 | 2014-11-27 | MURPHY | SK | SOUTH ACIS | SAPA-19ST1 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 3024 | 1565 | N/A | N/A | N/A | N/A | 8364259 | 15 | SIDETRACK | N/A | N/A | 2014-05-13 | 2014-05-13 14:00 | 2014-09-17 18:00 | 2942.2 | SHALLOW WATER | 3020 | 1584.9 | N/A | N/A | N/A | N/A | 15172666.05 | 29.4 | 3.68 | 3.68 | SW DEV C1 | SW DEV C1 | 2.2 | 2.2 | 830 | 830 | 1380 | 1380 | Yes | 1.09 | Yes | 565 | Yes | 757 | [26 empty] | Exist
2014-04-04 | 2014-08-12 | HESS | PM | BUNGA KAMANJU | BUNGA KAMANJU-1 | EXPLORATION/APPRAISAL | TRIDENT-9 | JACK UP | 63.4 | 2983.85 | 2983.85 | 24497776 | 24497776 | 39.3 | 39.3 | N/A | N/A | NO | N/A | N/A | 2014-05-18 | 2014-05-10 06:00 | 2014-06-21 09:30 | 2455.65 | SHALLOW WATER | 2553.19 | 2543.37 | N/A | 18720360 | N/A | 42.15 | N/A | N/A | 13.5 | 13.25 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.32 |  | 1255.25 |  | 1952.18 | [27 empty] | Exist
2014-03-26 | 2014-11-10 | SAPURA OMV | SK | LARAK | LARAK-1 | EXPLORATION/APPRAISAL | ENSCO-106 | JACK UP | 81.2 | 2453 | 2453 | 12350000 | 12350000 | 20.9 | 20.9 | N/A | N/A | SUSPEND | N/A | N/A | 2014-05-20 | 2014-05-17 13:00 | 2014-06-09 10:00 | 2363.5 | SHALLOW WATER | 2479 | 2479 | N/A | 12311666 | N/A | 22.9 | N/A | N/A | 3 | 3 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-03-20 | 2014-06-12 | PTTEP | SK | SERENDAH | SNPA-24 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1158.01 | 1158.01 | N/A | N/A | N/A | N/A | 6983629 | 11 | NO | N/A | N/A | 2014-04-03 08:30 | 2014-03-31 12:30 | 2014-04-15 02:00 | 1598.6 | SHALLOW WATER | 1674 | 1674 | N/A | N/A | N/A | N/A | 4980273 | 8.4 | 4.71 | 4.71 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | No |  | No |  | No | [27 empty] | Exist
2014-03-14 | N/A | SHELL | SK | LAILA | LA-104 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-105 | JACK UP | 76.81 | 4959.77 | 3201.77 | N/A | N/A | N/A | N/A | 34632717 | 61.4 | NO | N/A | N/A | 2014-04-16 | 2014-03-19 06:00 | 2014-10-04 | 4841.51 | SHALLOW WATER | 4961.29 | 3202.99 | N/A | N/A | N/A | N/A | 49288525.94 | 92.74 | 12.07 | 11.95 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.6 |  | 1485 |  | 2219 | [27 empty] | Exist
2014-03-14 | N/A | SHELL | SK | LAILA | LA-102 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-105 | JACK UP | 76.99 | 3805.85 | 3142.64 | N/A | N/A | N/A | N/A | 23639776 | 36.79 | NO | N/A | N/A | 2014-04-05 17:15 | 2014-04-04 17:15 | 2014-10-05 14:30 | 3689.28 | SHALLOW WATER | 3809.23 | 3192.22 | N/A | N/A | N/A | N/A | 28319363 | 39.94 | 7.71 | 7.71 | No DMS category | [7 empty] | 2 |  | 1269 |  | 2080 | [27 empty] | Exist
2014-03-14 | N/A | SHELL | SK | LAILA | LA-103 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-105 | JACK UP | 76.81 | 6283.15 | 3260.29 | N/A | N/A | N/A | N/A | 30160000 | 47.52 | NO | N/A | N/A | 2014-04-16 | 2014-03-31 21:30 | 2014-08-27 | 6283.75 | SHALLOW WATER | 6403.54 | 3268.82 | N/A | N/A | N/A | N/A | 39168499.62 | 78.82 | 36.21 | 36.21 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 3.6 |  | 1945 |  | 2217 | [27 empty] | Exist
2014-03-13 | 2014-07-17 | PCSB | SB | LIMBAYONG | LIMBAYONG-3 | EXPLORATION/APPRAISAL | TUNGSTEN EXPLORER | DRILLSHIP | 1007.5 | 2937 | 2800 | 74370000 | 92900000 | 54.7 | 75 | N/A | N/A | NO | N/A | N/A | 2014-04-07 02:15 | 2014-04-04 19:45 | 2014-05-22 21:00 | 1776 | DEEP WATER | 2815 | 2693 | N/A | 51900000 | N/A | 47.05 | N/A | N/A | 5.18 | 5.18 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 3.4 |  | 3752 |  | 5470 | [27 empty] | Exist
2014-03-06 | 2014-05-16 | PCSB | SB | SAMARANG | SM-111 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 2610.79 | 2190.49 | N/A | N/A | N/A | N/A | 19020000 | 37.29 | NO | N/A | DRY TREE | 2014-03-11 | 2014-03-11 05:00 | 2014-04-16 21:30 | 2576.65 | SHALLOW WATER | 2621.15 | 2540.99 | N/A | N/A | N/A | N/A | 19022546.79 | 34.21 | 0.17 | 0.17 | SW DEV C1 |  | 1.7 |  | 720 |  | 1685 |  | 1.96 |  | 829.58 |  | 1998.66 | [6 empty] | 14.27 | 8574088.26 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | 3 ZONES | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 778 | True |  | 13CR | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2014-03-03 | 2014-10-24 | SAPURA OMV | SK | LEGUNDI | LEGUNDI-1 | EXPLORATION/APPRAISAL | ENSCO-106 | JACK UP | 83.7 | 2714 | 2714 | 12150000 | 12150000 | 21.35 | 21.35 | N/A | N/A | NO | N/A | N/A | 2014-04-27 | 2014-04-19 | 2014-05-17 | 2057 | SHALLOW WATER | 2175 | 2174.9 | 14634047 | N/A | 28.56 | N/A | N/A | N/A | 1.3 | 1.3 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-02-20 | 2014-07-04 | SAPURA OMV | SK | GOREK | GOREK-1 | EXPLORATION/APPRAISAL | ENSCO-106 | JACK UP | 88.9 | 2623 | 2623 | 12500000 | 12500000 | 23.44 | 23.44 | N/A | N/A | NO | N/A | N/A | 2014-03-27 | 2014-03-24 21:30 | 2014-04-18 | 2341.8 | SHALLOW WATER | 2465 | 2464.2 | N/A | 12681621 | N/A | 25.1 | N/A | N/A | 5.4 | 4.4 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-02-11 | 2014-06-24 | EMEPMI | PM | DAMAR | DAMAR-A12 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 55.7 | 3272 | 2047 | N/A | N/A | N/A | N/A | 28100000 | 41.31 | NO | N/A | DRY TREE | 2014-02-15 | 2014-02-13 20:00 | 2014-05-11 | 3181.51 | SHALLOW WATER | 3281 | 2055 | N/A | N/A | N/A | N/A | 17159800 | 28 | 5.5 | 5.5 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [6 empty] | 6.86 | 3236279.97 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 2589 | True | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
2014-02-04 | 2014-07-17 | SHELL | SK | KEKEK | KEKEK-1 | EXPLORATION/APPRAISAL | ENSCO-8504 | SEMI-SUB | 1314.66 | 3840.29 | 3729.66 | 46384499 | 46384499 | 34.88 | 34.88 | N/A | N/A | NO | N/A | N/A | 2014-03-21 06:30 | 2014-03-18 | 2014-04-19 | 1891.19 | DEEP WATER | 3232.25 | 3113.81 | N/A | 132300000 | N/A | 31.56 | N/A | N/A | 15.31 | 15.31 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-27 | 2014-06-10 | PTTEP | SK | SERENDAH | SNPA-14 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 2618 | 1700 | N/A | N/A | N/A | N/A | 4778514.12 | 7.1 | NO | N/A | DRY TREE | 2014-02-20 | 2014-02-20 | 2014-03-24 | 2701.6 | SHALLOW WATER | 2777 | 1859.81 | N/A | N/A | N/A | N/A | 4829008.71 | 8.1 | 0 | 0 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | No |  | No |  | No | [6 empty] | 1.44 | 945000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 180.455 | False | NONE | L80 13CR | 9.4 | CACL2 | NO | NO | Exist
2014-01-27 | 2014-05-21 | MURPHY | SK | SERENDAH | SNPA-11 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1520 | 1161 | N/A | N/A | N/A | N/A | 6205321 | 8.64 | NO | N/A | N/A | 2014-02-15 | 2014-02-15 | 2014-03-14 | 1468.6 | SHALLOW WATER | 1544 | 1172.04 | N/A | N/A | N/A | N/A | 5033156 | 9.27 | 5.84 | 5.84 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-27 | 2014-05-21 | MURPHY | SK | SERENDAH | SNPA-12 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1351 | 1329 | N/A | N/A | N/A | N/A | 6365614.77 | 10.38 | SIDETRACK | N/A | N/A | 2014-02-17 02:00 | 2014-02-17 02:00 | 2014-03-17 10:30 | 1247.1 | SHALLOW WATER | 1322.5 | 1298.8 | N/A | N/A | N/A | N/A | 6821844.49 | 10.42 | 5 | 5 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-27 | 2014-05-21 | MURPHY | SK | SERENDAH | SNPA-10 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1642 | 1293 | N/A | N/A | N/A | N/A | 6175127 | 9.63 | NO | N/A | N/A | 2014-02-14 05:00 | 2014-02-13 09:30 | 2014-03-11 | 1556.94 | SHALLOW WATER | 1632.34 | 1299.74 | N/A | N/A | N/A | N/A | 5485640 | 9.31 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-27 | 2014-06-10 | PTTEP | SK | SERENDAH | SNPA-13 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1463.2 | 1090.4 | N/A | N/A | N/A | N/A | 4773800.67 | 6.28 | NO | N/A | DRY TREE | 2014-02-18 | 2014-02-18 11:30 | 2014-03-30 | 1487.6 | SHALLOW WATER | 1563 | 1141.54 | N/A | N/A | N/A | N/A | 4594824.81 | 7.67 | 6.25 | 6.25 | SW DEV C2 |  | 2 |  | 725 |  | 1095 |  | No |  | No |  | No | [6 empty] | 0.98 | 808000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 72.182 | False | NONE | L80 13CR | 9.4 | CACL2 | NO | NO | Exist
2014-01-23 | 2014-05-23 | SAPURA OMV | SK | TEJA | TEJA-1 | EXPLORATION/APPRAISAL | ENSCO-106 | JACK UP | 82 | 2633 | 2633 | 13100000 | 17400000 | 23.52 | 33.3 | N/A | N/A | NO | N/A | N/A | 2014-02-22 08:30 | 2014-02-18 08:00 | 2014-03-24 21:30 | 2677.7 | SHALLOW WATER | 2794 | 2793.69 | N/A | 17085000 | N/A | 34.6 | N/A | N/A | 14.74 | 1.26 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-22 | 2014-07-23 | MUBADALA | SK | PEGAGA | PEGAGA-2 | EXPLORATION/APPRAISAL | SONGA VENUS | SEMI-SUB | 107 | 2664.7 | 2640 | 40928100 | 40928100 | 50.06 | 50.06 | N/A | N/A | NO | N/A | N/A | N/A | N/A | 2014-05-06 18:00 | 2553.3 | SHALLOW WATER | 2685 | 2660.3 | N/A | 45805610 | N/A | 71.08 | N/A | N/A | 11.61 | 10.27 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.41 |  | 1558 |  | 5255 | [27 empty] | Exist
2014-01-20 | 2014-07-17 | PTTEP | SB | SIAKAP NORTH PETAI | S-SW1-P2 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1394.4 | 2569 | 2396 | N/A | N/A | N/A | N/A | 54331710 | 36.7 | SIDETRACK | N/A | WET TREE | 2014-02-13 21:00 | 2014-02-12 | 2014-07-03 | 974.4 | DEEP WATER | 2395 | 2361.5 | N/A | N/A | N/A | N/A | 43184040 | 32 | 2.73 | 2.73 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | 3.69 |  | 4978 |  | 9209 | [6 empty] | 16.53 | 22307255.66 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 569.5816 | True |  | L80 13CR | 10.4 | NABR | 3 | NO | Exist
2014-01-16 | 2014-05-13 | PCSB | PM | KEBAYA | KEBAYA-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 99 | 1380 | 1380 | 34743593.02 | 48082117.35 | 42.38 | 62 | N/A | N/A | NO | N/A | N/A | 2014-01-23 | 2014-01-20 12:00 | 2014-02-28 04:45 | 1252 | SHALLOW WATER | 1380 | 1380 | 30248619.98 | N/A | 38.7 | N/A | N/A | N/A | 10.21 | 10.21 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 5.98 |  | 2063 |  | 6160 | [27 empty] | Exist
2014-01-06 | N/A | PCSB | SB | SAMARANG | SM-102 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 2378.3 | 2058.26 | N/A | N/A | N/A | N/A | 16550000 | 34.48 | NO | N/A | DRY TREE | 2014-01-08 13:30 | 2014-01-08 05:30 | 2014-03-12 07:00 | 2378.54 | SHALLOW WATER | 2423.04 | 2092.96 | N/A | N/A | N/A | N/A | 15390000 | 28.06 | 2.52 | 2.52 | SW DEV C2 | SW DEV C2 | 2.5 | 2.5 | 1440 | 1440 | 2015 | 2015 | Yes | 2.28 | Yes | 809 | Yes | 1917 | [5 empty] | 8.25 | 5484522.08 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 1538 | True | NONE | 13CR | 8.6 | KCL | NO | NO | Exist
2014-01-03 | 2014-06-02 | PTTEP | SB | SIAKAP NORTH PETAI | S-CN2-W2 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1355.7 | 3495 | 2685 | N/A | N/A | N/A | N/A | 54974507 | 43.6 | NO | N/A | WET TREE | 2014-04-01 | 2014-03-30 | 2014-05-11 | 2142.1 | DEEP WATER | 3524 | 2699 | N/A | N/A | N/A | N/A | 53624183 | 42 | 13.99 | 13.99 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | No |  | No |  | No | [6 empty] | 26.17 | 33412973.07 |  |  | SANDSTONE | NORMAL | CASED HOLE COMPLIANT SCREEN | 2 ZONES | NO | 5-1/2" | 2.0 | SINGLE | L80 1CR | 810.407 | True | ICV | L80 1CR | 10.4 | CACL2 | 1 | NO | Exist
2014-01-03 | 2014-07-05 | EMEPMI | PM | DAMAR | DAMAR-A07 | APPRAISAL CUM DEV/DEVELOPMENT | SEADRILL WEST LEDA | JACK UP | 55.7 | 3531 | 2034 | N/A | N/A | N/A | N/A | 30000000 | 52.7 | NO | N/A | N/A | N/A | 2014-02-25 | 2014-05-28 | 3437.51 | SHALLOW WATER | 3537 | 2042.1 | N/A | N/A | N/A | N/A | 22192000 | 36.58 | 0.11 | 0.11 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-03 | 2014-07-31 | EMEPMI | PM | DAMAR | DAMAR-A14 | APPRAISAL CUM DEV/DEVELOPMENT | SEADRILL WEST LEDA | JACK UP | 55.7 | 3354 | 2033 | N/A | N/A | N/A | N/A | 30300000 | 49.5 | NO | N/A | N/A | N/A | 2014-02-19 | 2014-06-17 | 9123.51 | SHALLOW WATER | 9223 | 2034.69 | N/A | N/A | N/A | N/A | 22154000 | 37.13 | 8.7 | 8.7 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [27 empty] | Exist
2014-01-01 | 2014-06-06 | EMEPMI | PM | DAMAR | DAMAR-A4 | APPRAISAL CUM DEV/DEVELOPMENT | WEST LEDA | JACK UP | 55.7 | 1800 | 922 | N/A | N/A | N/A | N/A | 35900000 | 48.57 | NO | N/A | DRY TREE | 2014-01-14 | 2014-01-12 19:00 | 2014-04-28 16:00 | 3949.51 | SHALLOW WATER | 4049 | 2036 | N/A | N/A | N/A | N/A | 31454500 | 53.5 | 11.6 | 10.2 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [6 empty] | 9.8 | 10496000 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 2.0 | DUAL | L80 13CR | 50 | True | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
2013-12-24 | 2014-06-04 | PCSB | SB | KENTAL | KENTAL-1 | EXPLORATION/APPRAISAL | TUNGSTEN EXPLORER | DRILLSHIP | 1659.5 | 3730 | 3730 | 64094146 | 64094146 | 42.4 | 42.4 | N/A | N/A | NO | N/A | N/A | 2014-01-08 23:30 | 2014-01-07 10:00 | 2014-04-05 19:45 | 1966 | DEEP WATER | 3657 | 3657 | N/A | 63374989 | N/A | 56.82 | N/A | N/A | 22.4 | 22.4 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 6.77 |  | 9151 |  | 9389 | [27 empty] | Exist
2013-12-24 | 2014-10-14 | PCSB | SB | KINABALU WEST DEEP | KN-B3 | APPRAISAL CUM DEV/DEVELOPMENT | DEEP DRILLER-3 | JACK UP | 59.13 | 4599.21 | 4561.97 | N/A | N/A | N/A | N/A | 66312424 | 85 | NO | N/A | N/A | 2014-02-04 12:30 | 2014-02-03 | 2014-05-12 | 4523.01 | SHALLOW WATER | 4638.83 | 4617.68 | N/A | N/A | N/A | N/A | 63190000 | 97.36 | 11.95 | 11.95 | No DMS category. Having value but not sure refering which version | [7 empty] | 4.89 |  | 3629 |  | 4786 | [27 empty] | Exist
2013-12-20 | 2014-03-31 | PCSB | SB | HEBAT | HEBAT-1 | EXPLORATION/APPRAISAL | TUNGSTEN EXPLORER | DRILLSHIP | 1737 | 3941 | 3924 | 54192038.37 | 54192038.37 | 32 | 32 | N/A | N/A | NO | N/A | N/A | 2014-01-12 | 2014-01-11 | 2014-02-12 | 2173 | DEEP WATER | 3942 | 3912 | N/A | 36706087.18 | N/A | 31.58 | N/A | N/A | 3.92 | 3.92 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 2.7 |  | 4472 |  | 4632 | [27 empty] | Exist
2013-12-19 | 2014-04-11 | PCSB | SK | NAIM | NAIM-1 | EXPLORATION/APPRAISAL | WEST COURAGEOUS | JACK UP | 29.6 | 1743.4 | 1743.4 | 7670000 | 7670000 | 16.3 | 16.3 | N/A | N/A | NO | N/A | N/A | 2014-02-11 | 2014-02-06 06:00 | 2014-02-26 19:00 | 1743.9 | SHALLOW WATER | 1804 | 1803.67 | 7180000 | N/A | 20.54 | N/A | N/A | N/A | 0.2 | 0.2 | SW EXP C1 |  | 2.4 |  | 1375 |  | 3025 |  | 1.04 |  | 318 |  | 1419 | [27 empty] | Exist
2013-12-12 | 2014-07-03 | PCSB | SB | ZUHAL EAST | ZE-B | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 41.9 | 2181 | 1972 | N/A | N/A | N/A | N/A | 12689810 | 21.03 | NO | N/A | DRY TREE | 2014-03-07 | 2014-03-07 18:30 | 2014-03-23 21:30 | 2045.37 | SHALLOW WATER | 2127 | 1860 | N/A | N/A | N/A | N/A | 7346731.69 | 16.13 | 4.78 | 4.78 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 1.68 |  | 561 |  | 1112 | [6 empty] | 3.94 | 1442368.78 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 75.463 | False | INNER STRING WITH SSD | 9CR | 8.5 | NACL | NO | NO | Exist
2013-12-12 | 2014-07-03 | PCSB | SB | ZUHAL EAST | ZUHAL EAST-C | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 41.9 | 2001 | 1968.5 | N/A | N/A | N/A | N/A | 12263600 | 20.86 | NO | N/A | N/A | 2014-02-27 | 2014-02-25 21:30 | 2014-04-14 07:00 | 1840.37 | SHALLOW WATER | 1922 | 1800.55 | N/A | N/A | N/A | N/A | 7259986.65 | 15.98 | 2.5 | 2.5 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 1.64 |  | 618 |  | 1170 | [27 empty] | Exist
2013-12-12 | 2014-07-03 | PCSB | SB | ZUHAL EAST | ZUHAL EAST-A | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 41.9 | 2054 | 1844.73 | N/A | N/A | N/A | N/A | 12359090 | 21.17 | NO | N/A | N/A | 2014-03-04 05:30 | 2014-03-03 14:00 | 2014-04-04 | 1957.37 | SHALLOW WATER | 2039 | 1866.05 | N/A | N/A | N/A | N/A | 7614403.98 | 15.29 | 0.65 | 0.65 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 1.51 |  | 611 |  | 1161 | [27 empty] | Exist
2013-11-27 | 2014-03-24 | PCSB | PM | SEMANTAN | SEMANTAN-1 | EXPLORATION/APPRAISAL | WEST COURAGEOUS | JACK UP | 64.4 | 2905 | 2873 | 16961320 | 21900000 | 33.7 | 49.4 | N/A | N/A | NO | N/A | N/A | 2013-12-17 03:30 | 2013-12-13 22:00 | 2014-01-25 15:30 | 2704.2 | SHALLOW WATER | 2801 | 2798 | N/A | 27300000 | N/A | 43.73 | N/A | N/A | 34 | 4.46 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.48 |  | 881.37 |  | 1518.18 | [27 empty] | Exist
2013-11-20 | 2014-03-19 | PCSB | SK | D18 | D18-8 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 35 | 1700 | 1700 | 18100000 | 30100000 | 26 | 40 | N/A | N/A | NO | N/A | N/A | 2013-12-30 | 2013-12-20 21:00 | 2014-02-17 22:30 | 1639 | SHALLOW WATER | 1704 | 1704 | N/A | 24644730 | N/A | 58.54 | N/A | N/A | 22.9 | 8.1 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 2.41 |  | 1405 |  | 3569 | [27 empty] | Exist
2013-11-19 | 2014-06-09 | PCSB | PM | DUYONG | DUYONG SHALLOW-2 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 76 | 886 | 886 | 8636690 | 9073080 | 19 | 22 | N/A | N/A | NO | N/A | N/A | 2013-11-26 | 2013-11-23 04:00 | 2013-12-14 06:00 | 798 | SHALLOW WATER | 910 | 910 | N/A | 10003394 | N/A | 21.09 | N/A | N/A | 1.97 | 1.97 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 2.67 |  | 2405.68 |  | 3659.03 | [27 empty] | Exist
2013-11-19 | 2014-01-21 | PCSB | SB | SAMARANG | SM-109 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 3272.17 | 2335.57 | N/A | N/A | N/A | N/A | 22824169 | 42.5 | NO | N/A | N/A | 2013-11-21 03:00 | 2013-11-21 03:00 | 2013-12-27 18:30 | 3149.65 | SHALLOW WATER | 3194.15 | 2270.65 | N/A | N/A | N/A | N/A | 18606177 | 36.65 | 2.6 | 1.4 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2015 |  | 2.15 |  | 954.53 |  | 1754.06 | [27 empty] | Exist
2013-11-18 | 2014-03-24 | PTTEP | SK | SERENDAH | SNPA-04 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 2270 | 1483 | N/A | N/A | N/A | N/A | 6287000 | 8.58 | NO | N/A | DRY TREE | N/A | 2013-12-17 06:00 | 2014-01-20 16:00 | 2189.6 | SHALLOW WATER | 2265 | 1489.6 | N/A | N/A | N/A | N/A | 5746248.4 | 7.92 | 3.16 | 3.16 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | 0.68 |  | 649.55 |  | 468.41 | [6 empty] | 0.93 | 1972000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 205.7187 | False | NONE | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2013-11-18 | N/A | PTTEP | SK | SERENDAH | SNPA-06 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1504 | 1360 | N/A | N/A | N/A | N/A | 5577006.5 | 6.5 | NO | N/A | DRY TREE | 2013-12-27 07:30 | 2013-12-19 18:00 | 2014-01-16 09:30 | 1550.6 | SHALLOW WATER | 1626 | 1470.35 | N/A | N/A | N/A | N/A | 4389100.6 | 5.35 |  |  | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | 0.97 |  | 766.43 |  | 1096.64 | [6 empty] | 0.77 | 1561923.32 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 239.513 | False | NONE | L80 | 9.5 | KCL | NO | NO | Exist
2013-11-18 | 2014-05-08 | PTTEP | SK | SERENDAH | SNPA-07 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 1982 | 1269 | N/A | N/A | N/A | N/A | 9329639.5 | 13.33 | SIDETRACK | N/A | N/A | 2013-12-17 23:00 | 2013-12-17 22:00 | 2014-02-09 03:00 | 1884.6 | SHALLOW WATER | 1960 | 1278.87 | N/A | N/A | N/A | N/A | 7807514.73 | 12.77 | 0.33 | 0.33 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | No |  | No |  | No | [27 empty] | Exist
2013-11-18 | 2014-03-24 | PTTEP | SK | SERENDAH | SNPA-05 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 2719 | 1358 | N/A | N/A | N/A | N/A | 5645991 | 7.25 | SIDETRACK | N/A | DRY TREE | 2013-12-25 | 2013-12-01 13:30 | 2014-01-13 | 2925.6 | SHALLOW WATER | 3001 | 1466.7 | N/A | N/A | N/A | N/A | 9751261 | 14.42 | 0.87 | 0.87 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 990 |  | No |  | No |  | No | [6 empty] | 1.61 | 2463263.84 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 447.8565 | False | NONE | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
2013-11-18 | 2014-05-08 | PTTEP | SK | SERENDAH | SNPA-08 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 32 | 2303 | 1310 | N/A | N/A | N/A | N/A | 9539751.8 | 13.75 | SIDETRACK | N/A | N/A | 2013-12-30 05:00 | 2013-12-20 07:30 | 2014-02-13 09:30 | 2275.6 | SHALLOW WATER | 2351 | 1269.15 | N/A | N/A | N/A | N/A | 10507809.49 | 17.69 | 2.94 | 2.94 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | No |  | No |  | No | [27 empty] | Exist
2013-11-08 | 2014-03-24 | PCSB | SB | SAMARANG | EW-104ST3 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 63.86 | 4410 | 2118 | N/A | N/A | N/A | N/A | 19290800 | 45.22 | NO | N/A | N/A | 2013-12-02 | 2013-11-21 | 2014-01-31 | 4374.89 | SHALLOW WATER | 4472 | 2108.27 | N/A | N/A | N/A | N/A | 26150000 | 71.99 | 25.09 | 2.78 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 3.73 |  | 1450 |  | 1780 | [27 empty] | Exist
2013-10-09 | 2014-02-12 | PCSB | PM | INAS | INAS-8 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 65 | 2102 | 2070 | 17560000 | 22400000 | 31.5 | 44.8 | N/A | N/A | NO | N/A | N/A | 2013-10-17 | 2013-10-12 | 2013-11-23 | 2164.17 | SHALLOW WATER | 2265 | 2265 | N/A | 19742005.55 | N/A | 41.69 | N/A | N/A | 15.5 | 10.8 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.9 |  | 985 |  | 1927 | [27 empty] | Exist
2013-10-07 | 2014-02-28 | PCSB | PM | BUJANG | BUJANG-7 | EXPLORATION/APPRAISAL | WEST COURAGEOUS | JACK UP | 69.5 | 2104 | 2066 | 22100000 | 27300000 | 48.5 | 62.5 | N/A | N/A | NO | N/A | N/A | 2013-10-24 | 2013-10-15 | 2013-12-12 | 2018.47 | SHALLOW WATER | 2120 | 2120 | 26081198.69 | N/A | 58.92 | N/A | N/A | N/A | 28 | 2.3 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.95 |  | 948 |  | 2346 | [27 empty] | Exist
2013-09-19 | 2014-01-03 | PCSB | SB | NOSONG | NOSONG-3 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 101.8 | 2329 | 2329 | 22230000 | 37450000 | 37.16 | 65.13 | N/A | N/A | NO | N/A | N/A | 2013-10-04 06:00 | 2013-10-02 | 2013-10-13 18:00 | 2298.2 | SHALLOW WATER | 2429 | 2428.84 | N/A | 22709099.05 | N/A | 44.75 | N/A | N/A | 9.2 | 6.6 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.8 |  | 812.7 |  | 1751.3 | [27 empty] | Exist
2013-09-06 | 2014-01-20 | PCSB | SB | ERB WEST | EW-124 ST3 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 64 | 4246.8 | 2106.07 | N/A | N/A | N/A | N/A | 23093150 | 56 | SIDETRACK | N/A | N/A | 2013-09-08 | 2013-09-08 | 2013-11-21 | 4239.75 | SHALLOW WATER | 4337 | 2099.3 | N/A | N/A | N/A | N/A | 28873698 | 73.75 | 12.6 | 12.6 | SW DEV ST 2HS | SW DEV ST 2HS | 2.4 | 2.4 | 795 | 795 | 1400 | 1400 | Yes | 0.78 | Yes | 800 | Yes | 1270 | [26 empty] | Exist
2013-09-06 | 2013-12-20 | PCSB | SK | ANJUNG KECIL | AJK-A1 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 70.5 | 2562 | 1739 | N/A | N/A | N/A | N/A | 27818489 | 51 | NO | N/A | DRY TREE | 2013-09-14 | 2013-09-14 | 2013-11-11 04:45 | 2480.35 | SHALLOW WATER | 2586 | 1738.2 | N/A | N/A | N/A | N/A | 17670841.56 | 30.1 | 9.66 | 9.66 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.47 |  | 1525 |  | 2083 | [6 empty] | 4.93 | 2971577.05 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 | 803.8058 | True | NONE | 9CR | 8.3 | SEAWATER/DRILLWATER | NO | NO | Exist
2013-09-06 | 2013-12-20 | PCSB | SK | ANJUNG KECIL | AJK-A2 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 70.5 | 2381 | 1739 | N/A | N/A | N/A | N/A | 26753912 | 48 | NO | N/A | DRY TREE | 2013-09-19 05:30 | 2013-09-18 15:30 | 2013-11-15 18:00 | 2275.5 | SHALLOW WATER | 2381 | 1739 | N/A | N/A | N/A | N/A | 16649885.76 | 32 | 18 | 18 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.5 |  | 1382 |  | 2297 | [6 empty] | 8.15 | 4289414.95 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 4-1/2" | 1.0 | SINGLE | L80 | 626.6404 | False | NONE | 9CR | 9.1 | NACL | NO | NO | Exist
2013-09-04 | 2014-09-21 | PTTEP | SB | SIAKAP NORTH PETAI | S-SW1-W1 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1384.3 | 2807 | 2643 | N/A | N/A | N/A | N/A | 45691684 | 36.3 | NO | N/A | WET TREE | 2013-09-21 15:30 | 2013-09-16 | 2014-02-12 | 1431.5 | DEEP WATER | 2842 | 2660.75 | N/A | N/A | N/A | N/A | 49721209.34 | 41.23 | 9.8 | 8.5 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | No |  | No |  | No | [6 empty] | 20.85 | 25038998.99 |  |  | SANDSTONE | NORMAL | CASED HOLE COMPLIANT SCREEN | 2 ZONES | NO | 5-1/2" | 2.0 | SINGLE | L80 1CR | 810.407 | True | ICV | L80 1CR | 10.4 | CACL2 | 1 | NO | Exist
2013-09-04 | 2014-03-19 | PTTEP | SB | SIAKAP NORTH PETAI | S-SW1-P1 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1396 | 2578 | 2558 | N/A | N/A | N/A | N/A | 45633728 | 37.5 | NO | N/A | WET TREE | 2013-12-21 | 2013-12-19 | 2014-03-07 | 1125.8 | DEEP WATER | 2548 | 2526.4 | N/A | N/A | N/A | N/A | 38559386 | 29 | 1.87 | 1.87 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | No |  | No |  | No | [6 empty] | 11.66 | 15503532.44 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 275.9321 | True |  | L80 13CR | 10.4 | NABR | 3 | NO | Exist
2013-08-27 | 2014-04-02 | PCSB | SB | KINABALU | KN-B1 | APPRAISAL CUM DEV/DEVELOPMENT | DEEP DRILLER-3 | JACK UP | 59.13 | 5231.64 | 4398.26 | N/A | N/A | N/A | N/A | 58221926.13 | 66.1 | NO | N/A | N/A | 2013-10-13 | 2013-10-12 18:30 | 2014-02-03 07:30 | 5155.14 | SHALLOW WATER | 5270.95 | 4405.65 | N/A | N/A | N/A | N/A | 71044059.68 | 112.71 | 13.9 | 13.9 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2015 |  | 3.76 |  | 2352 |  | 3684 | [27 empty] | Exist
2013-07-12 | 2013-09-03 | PCSB | SK | PIMENTO | PIMENTO-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 84 | 3286 | 3286 | 25700000 | 33100000 | 39 | 52 | N/A | N/A | NO | N/A | N/A | 2013-07-22 09:45 | 2013-07-18 16:00 | 2013-08-17 18:00 | 2935 | SHALLOW WATER | 3048 | 3048 | 15971600 | N/A | 30.09 | N/A | N/A | N/A | 9.45 | 9.45 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.14 |  | 1295 |  | 1723 | [27 empty] | Exist
2013-07-10 | 2014-04-18 | PTTEP | SB | SIAKAP NORTH PETAI | S-NE1-W5 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1243.14 | 2735 | 2634 | N/A | N/A | N/A | N/A | 49674655 | 40.8 | NO | N/A | WET TREE | 2013-08-04 15:30 | 2013-08-03 12:00 | 2014-03-30 | 1496.26 | DEEP WATER | 2765.6 | 2664.6 | N/A | N/A | N/A | N/A | 37139873 | 27 | 1.31 | 1.31 | DW DEV C1 (Dry Tree) |  | 3.1 |  | 1500 |  | 3540 |  | No |  | No |  | No | [6 empty] | 16.6 | 22834144.14 |  |  | SANDSTONE | NORMAL | CASED HOLE COMPLIANT SCREEN | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 1CR | 275.604 | True |  | L80 1CR | 10.4 | CACL2 | 1 | NO | Exist
2013-07-05 | 2013-10-24 | PCSB | PM | SEPAT BARAT | SEPAT BARAT-3 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 64.62 | 2236 | 2236 | 23202381.24 | 23202381.24 | 34.6 | 50.6 | N/A | N/A | NO | N/A | N/A | 2013-07-08 03:30 | 2013-07-05 19:30 | 2013-08-17 08:00 | 2129.38 | SHALLOW WATER | 2222 | 2222 | N/A | 20456097.9 | N/A | 42.52 | N/A | N/A | 6.84 | 6.84 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.6 |  | 1334 |  | 2437 | [27 empty] | Exist
2013-07-01 | 2014-05-06 | MURPHY | SB | SIAKAP NORTH PETAI | S-NE1-P8 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1237 | 2645 | 2418 | N/A | N/A | N/A | N/A | 54959405 | 43 | SIDETRACK | N/A | N/A | 2013-07-12 | 2013-07-11 16:00 | 2014-03-23 | 1404.8 | DEEP WATER | 2668 | 2456.8 | N/A | N/A | N/A | N/A | 39991895 | 28.83 | 2.38 | 1.66 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | No |  | No |  | No | [27 empty] | Exist
2013-06-07 | 2014-06-23 | MURPHY | SB | SIAKAP NORTH PETAI | S-CN1-P4 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1314 | 2330 | 2259 | N/A | N/A | N/A | N/A | 60144050 | 46.4 | NO | N/A | N/A | 2013-06-16 | 2013-06-16 | 2014-06-10 | 953.3 | DEEP WATER | 2293.5 | 2224.4 | N/A | N/A | N/A | N/A | 55351828 | 39 | 0.16 | 0.16 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | No |  | No |  | No | [27 empty] | Exist
2013-06-06 | 2013-08-28 | PCSB | SB | SAMARANG | SM-106 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 10.06 | 1424.87 | 1176.78 | N/A | N/A | N/A | N/A | 13440000 | 24.65 | NO | N/A | N/A | 2013-06-08 13:30 | 2013-06-08 13:30 | 2013-07-31 18:30 | 1325.82 | SHALLOW WATER | 1373.36 | 1143.01 | N/A | N/A | N/A | N/A | 13323000.49 | 23.71 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 2080 |  | 2.14 |  | 1192.47 |  | 2653.31 | [27 empty] | Exist
2013-06-06 | 2013-09-12 | PCSB | SB | SAMARANG | SM-104 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 10.06 | 1651.33 | 1194.15 | N/A | N/A | N/A | N/A | 15002363 | 28.49 | NO | N/A | N/A | 2013-06-06 | 2013-06-06 12:00 | 2013-08-16 12:00 | 1543.13 | SHALLOW WATER | 1590.67 | 1152.48 | N/A | N/A | N/A | N/A | 14556288.83 | 26.81 | 0 | 0 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.63 |  | 1322.55 |  | 2723.75 | [27 empty] | Exist
2013-06-05 | N/A | KPOC | SB | KEBABANGAN | KBB-A07 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 3344.82 | 2106 | N/A | N/A | N/A | N/A | 32305000 | 34.6 | NO | N/A | N/A | 2013-08-30 | 2013-08-29 16:00 | 2014-04-05 | 2449.5 | SHALLOW WATER | 2616 | 2071 | N/A | N/A | N/A | N/A | 30117819 | 35.27 | 19.1 | 19.05 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 3.36 |  | 2108 |  | 3765 | [27 empty] | Exist
2013-06-05 | 2014-07-02 | KPOC | SB | KEBABANGAN | KBB-A06 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 2609.24 | 2103 | N/A | N/A | N/A | N/A | 29497527 | 36.12 | NO | N/A | N/A | 2013-09-12 13:45 | 2013-09-12 05:00 | 2014-05-05 21:15 | 2141.5 | SHALLOW WATER | 2308 | 2075.6 | N/A | N/A | N/A | N/A | 31120250 | 33.32 | 8.03 | 8.03 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 3.51 |  | 2166 |  | 4457 | [27 empty] | Exist
2013-06-05 | 2014-03-14 | KPOC | SB | KEBABANGAN | KBB-A13 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 2810.12 | 2101 | N/A | N/A | N/A | N/A | 31223368 | 33.02 | NO | N/A | N/A | 2013-08-26 | 2013-08-25 14:30 | 2014-01-20 08:00 | 2686.5 | SHALLOW WATER | 2853 | 2100 | N/A | N/A | N/A | N/A | 39143509 | 49.58 | 29.39 | 23.07 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | No |  | No |  | No | [27 empty] | Exist
2013-06-05 | 2014-02-10 | KPOC | SB | KEBABANGAN | KBB-A02 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 2144.16 | 2076 | N/A | N/A | N/A | N/A | 30405142 | 31.08 | NO | N/A | N/A | 2013-09-06 | 2013-09-05 18:30 | 2013-12-29 17:00 | 1977.68 | SHALLOW WATER | 2144.18 | 2077.89 | N/A | N/A | N/A | N/A | 28357017 | 37.66 | 15.77 | 15.63 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | No |  | No |  | No | [27 empty] | Exist
2013-06-05 | 2014-03-07 | KPOC | SB | KEBABANGAN | KBB-A20 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 2981.96 | 2433 | N/A | N/A | N/A | N/A | 26486380 | 27.3 | NO | N/A | N/A | 2013-08-10 | 2013-07-04 | 2013-08-21 23:00 | 933.5 | SHALLOW WATER | 1100 | 1068 | N/A | N/A | N/A | N/A | 7314013 | 11.89 | 22.7 | 22.69 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | No |  | No |  | No | [27 empty] | Exist
2013-06-05 | 2014-05-19 | KPOC | SB | KEBABANGAN | KBB-A05 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 3769.41 | 2093 | N/A | N/A | N/A | N/A | 32680401 | 42.51 | NO | N/A | N/A | 2013-09-09 19:15 | 2013-09-09 | 2014-03-23 09:00 | 2431.5 | SHALLOW WATER | 2598 | 2070.18 | N/A | N/A | N/A | N/A | 23482323 | 30.88 | 3.07 | 3.07 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 2.95 |  | 21.76 |  | 28.74 | [27 empty] | Exist
2013-06-05 | 2014-03-28 | KPOC | SB | KEBABANGAN | KBB-A03 | APPRAISAL CUM DEV/DEVELOPMENT | SKD ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 141 | 2890.8 | 2190 | N/A | N/A | N/A | N/A | 32256000 | 32.06 | SIDETRACK | N/A | N/A | 2013-09-02 16:45 | 2013-09-02 02:30 | 2014-02-05 12:00 | 2643.5 | SHALLOW WATER | 2810 | 2163 | N/A | N/A | N/A | N/A | 49222998 | 66.57 | 36.3 | 34.77 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | No |  | No |  | No | [27 empty] | Exist
2013-05-23 | 2013-10-16 | PCSB | SK | KMSE | KMSE-A2 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 86 | 1446 | 1190 | N/A | N/A | N/A | N/A | 13464693 | 24 | NO | N/A | DRY TREE | 2013-08-03 05:15 | 2013-08-03 | 2013-09-02 10:30 | 4816.56 | SHALLOW WATER | 4941 | 3940.8 | N/A | N/A | N/A | N/A | 8470423.04 | 32 | 10 | 10 | SW DEV C1 |  | 2.2 |  | 830 |  | 1455 |  | 1.81 |  | 744 |  | 1233 | [6 empty] | 3.69 | 2359596.46 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 125.5639 | True | NONE | 9CR | 9.8 | NACL | NO | NO | Exist
2013-05-22 | 2013-09-13 | PCSB | SK | MAYONG | MAYONG-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 63 | 2904 | 2799 | 22789250 | 28060530 | 38.05 | 48.05 | N/A | N/A | NO | N/A | N/A | 2013-06-12 09:00 | 2013-06-08 | 2013-07-15 16:00 | 2811 | SHALLOW WATER | 2903 | 2799 | 22620810 | N/A | 40.67 | N/A | N/A | N/A | 8.61 | 5.49 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.95 |  | 869.73 |  | 2157 | [27 empty] | Exist
2013-05-20 | 2013-09-12 | PCSB | PM | BERANANG | RAMUNIA-1 | EXPLORATION/APPRAISAL | NAGA-4 | JACK UP | 60 | 3623 | 2700 | 27740000 | 38230000 | 55.25 | 77.25 | N/A | N/A | NO | N/A | N/A | 2013-06-12 02:00 | 2013-06-08 03:30 | 2013-08-04 10:00 | 3596 | SHALLOW WATER | 3688 | 2658.71 | N/A | 18263530 | N/A | 48.1 | N/A | N/A | 8.88 | 8.8 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.65 |  | 1017 |  | 1230 | [27 empty] | Exist
2013-05-02 | 2013-10-16 | PCSB | SK | KMSE | KMSE-A1 | APPRAISAL CUM DEV/DEVELOPMENT | AQUA MARINE DRILLER | JACK UP | 86 | 1383 | 1190 | N/A | N/A | N/A | N/A | 13438536 | 23 | NO | N/A | DRY TREE | 2013-08-09 | 2013-08-08 | 2013-09-08 | 1356.56 | SHALLOW WATER | 1481 | 1204.1 | N/A | N/A | N/A | N/A | 8008370.89 | 18.2 | 19.75 | 10.3 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.27 |  | 990 |  | 1648 | [6 empty] | 3.61 | 2146316.12 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 87.6027 | True | NONE | 9CR | 9.8 | NACL | NO | NO | Exist
2013-04-04 | 2013-08-22 | PCSB | PM | SEPAT | SEPAT-A10 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 3200 | 1711 | N/A | N/A | N/A | N/A | 18328000 | 36.08 | NO | N/A | DRY TREE | 2013-04-25 18:30 | 2013-04-24 16:30 | 2013-07-10 08:00 | 2942 | SHALLOW WATER | 3046 | 1934 | N/A | N/A | N/A | N/A | 17028972 | 43.88 | 12.92 | 12.92 | SW DEV C1 |  | 2.1 |  | 700 |  | 1280 |  | 1.77 |  | 716 |  | 1704 | [6 empty] | 13.79 | 5179388.91 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 210 | True | NONE | L80 13CR | 9.2 | NACL | 1 | NO | Exist
2013-04-04 | 2013-09-10 | PCSB | SK | D35 | D35 EAST-1 | EXPLORATION/APPRAISAL | ENSCO-105 | JACK UP | 45.5 | 2234 | 2234 | 16140000 | 20850000 | 28 | 38 | N/A | N/A | NO | N/A | N/A | 2013-04-21 13:30 | 2013-04-18 14:00 | 2013-05-18 08:00 | 2722.5 | SHALLOW WATER | 2804 | 2804 | 17149290 | N/A | 29.76 | N/A | N/A | N/A | 5.81 | 5.81 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.42 |  | 999 |  | 1903 | [27 empty] | Exist
2013-04-04 | 2014-01-10 | PCSB | PM | PENARA | PENARA NW-1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-4 | JACK UP | 60.4 | 3150 | 2442 | N/A | N/A | N/A | N/A | 17164746.45 | 42.94 | NO | N/A | N/A | 2013-04-26 | 2013-04-05 08:00 | 2013-06-08 03:30 | 3031.6 | SHALLOW WATER | 3122 | 2722.6 | N/A | N/A | N/A | N/A | 22797299.02 | 64.12 | 19.16 | 19.16 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.82 |  | 1013.82 |  | 1867.47 | [27 empty] | Exist
2013-04-04 | 2014-02-21 | PCSB | SB | DANUM | DANUM-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 73 | 3578 | 3033 | 31690000 | 41085000 | 41 | 53 | N/A | N/A | SIDETRACK | N/A | N/A | 2013-05-03 05:30 | 2013-04-28 09:15 | 2013-07-22 18:30 | 2651 | SHALLOW WATER | 2757 | 2757 | 40808000 | N/A | 85.39 | N/A | N/A | N/A | 28.3 | 18.49 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | No |  | No |  | No | [27 empty] | Exist
2013-03-15 | 2013-09-24 | PCSB | PM | ANGSI | ANGSI-D17 | APPRAISAL CUM DEV/DEVELOPMENT | GLEN TANAR | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 4425 | 1833 | N/A | N/A | N/A | N/A | 21891666 | 49.97 | NO | N/A | DRY TREE | 2013-03-30 09:15 | 2013-03-28 10:30 | 2013-05-09 12:00 | 4409 | SHALLOW WATER | 4513 | 1856 | N/A | N/A | N/A | N/A | 18919478.23 | 42.06 | 13.27 | 13.27 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.64 |  | 883.2 |  | 1332.65 | [6 empty] | 10.72 | 4758133.22 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 150.926 | True | NONE | 9CR | 9.8 | NACL | NO | NO | Exist
2013-02-27 | 2013-05-03 | PCSB | PM | DULANG | DULANG A-26 ST1 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 73 | 1844 | 1587 | N/A | N/A | N/A | N/A | 9883250 | 21 | NO | N/A | N/A | 2013-03-15 | 2013-03-15 | 2013-04-04 | 1660.9 | SHALLOW WATER | 1768 | 1526.77 | N/A | N/A | N/A | N/A | 7357348.88 | 20 | 0.31 | 0.31 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 1.28 |  | 470 |  | 1340 | [27 empty] | Exist
2013-02-08 | 2013-05-03 | PCSB | SK | D21 | D21-A3 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 50.59 | 2772.33 | 1965.86 | N/A | N/A | N/A | N/A | 17888110 | 38.92 | SIDETRACK | N/A | N/A | 2013-02-13 23:00 | 2013-02-13 16:30 | 2013-03-28 19:00 | 2469.37 | SHALLOW WATER | 2560.2 | 1998.88 | N/A | N/A | N/A | N/A | 19692772.89 | 43.1 | 6.2 | 6.2 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.79 |  | 1249 |  | 1796 | [27 empty] | Exist
2013-01-09 | 2013-05-28 | PCSB | PM | TANGGA BARAT | TNGB-A11 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 2057 | 1807 | N/A | N/A | N/A | N/A | 13797000 | 26.6 | NO | N/A | DRY TREE | 2013-03-29 | 2013-03-28 06:00 | 2013-05-03 12:00 | 1962.84 | SHALLOW WATER | 2070 | 1810.6 | N/A | N/A | N/A | N/A | 12784258.01 | 31.06 | 16.9 | 16.9 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 3.13 |  | 1268 |  | 1882 | [6 empty] | 12.88 | 3425190.46 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | GRE | 95.149 | False | NONE | 25CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2013-01-09 | 2013-06-21 | PCSB | PM | TANGGA BARAT | TNGB-A12 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 2608 | 1811 | N/A | N/A | N/A | N/A | 14129120 | 28.1 | NO | N/A | DRY TREE | 2013-03-31 | 2013-03-31 | 2013-05-29 10:00 | 2464.84 | SHALLOW WATER | 2572 | 1789.78 | N/A | N/A | N/A | N/A | 10184359.56 | 28.17 | 5.79 | 5.69 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.55 |  | 927 |  | 1299 | [6 empty] | 7.21 | 3078046.13 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | GRE | 91.868 | False | NONE | 25CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
2012-11-29 | 2013-10-31 | PCSB | PM | BEKOK | BEKOK-B13 | APPRAISAL CUM DEV/DEVELOPMENT | ROWAN GORILLA-2 | JACK UP | 71.62 | 3618 | 1681 | N/A | N/A | N/A | N/A | 23659498 | 45.1 | NO | N/A | DRY TREE | 2012-12-07 | 2012-12-06 | 2013-05-23 | 3025.33 | SHALLOW WATER | 3125 | 1661 | N/A | N/A | N/A | N/A | 23565265.5 | 50.44 | 9.42 | 9.32 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 2.33 |  | 1077 |  | 1456 | [6 empty] | 4.63 | 2209590.25 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 88.587 | False | NONE | 9CR | 8.3 | NACL | NO | NO | Exist
2012-11-23 | 2013-07-11 | PCSB | PM | BERANANG WEST | BERANANG WEST-1 | EXPLORATION/APPRAISAL | NAGA-1 | SEMI-SUB | 63 | 2940 | 2782 | 27670000 | 32170000 | 55.48 | 65.98 | N/A | N/A | NO | N/A | N/A | 2013-02-03 05:00 | 2013-01-21 13:45 | 2013-04-03 15:00 | 2950 | SHALLOW WATER | 3040 | 2853 | N/A | 31418760 | N/A | 99 | N/A | N/A | 4.79 | 3.6 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.23 |  | 1811.2 |  | 2019.6 | [27 empty] | Exist
2012-11-16 | 2013-04-01 | PCSB | SB | SAMARANG | SM-84 | APPRAISAL CUM DEV/DEVELOPMENT | MAERSK CONVINCER | JACK UP | 10.06 | 1430.36 | 1129.84 | N/A | N/A | N/A | N/A | 12998765 | 26.92 | SIDETRACK | N/A | N/A | 2012-12-27 | 2012-12-27 09:30 | 2013-02-13 16:00 | 1382.75 | SHALLOW WATER | 1429.44 | 1149.54 | N/A | N/A | N/A | N/A | 12895020.14 | 28.25 | 9.73 | 7.52 | SW DEV C2 |  | 2.5 |  | 1440 |  | 1995 |  | 3.33 |  | 1317.94 |  | 2346.24 | [27 empty] | Exist
2012-11-07 | 2013-03-23 | PCSB | PM | RESAK | RESAK-A19 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 61 | 5365 | 2290.8 | N/A | N/A | N/A | N/A | 26227538 | 54.06 | NO | N/A | DRY TREE | 2012-11-12 | 2012-11-11 | 2012-12-30 | 5136.62 | SHALLOW WATER | 5232 | 2298.1 | N/A | N/A | N/A | N/A | 20264386.93 | 48.77 | 23.16 | 14.55 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.98 |  | 829 |  | 1217 | [6 empty] | 12.63 | 3895032.58 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | SUPER 13CR | 26.248 | False |  | SUPER 13CR | 8.5 | KCL | NO | NO | Exist
2012-11-07 | 2013-02-22 | PCSB | SK | D21 | D21-A4 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 50.59 | 2620.54 | 2033.22 | N/A | N/A | N/A | N/A | 12552520 | 25.9 | NO | N/A | N/A | 2012-11-18 | 2012-11-18 | 2012-12-13 | 2573.61 | SHALLOW WATER | 2664.43 | 2069.31 | N/A | N/A | N/A | N/A | 11710840 | 25.49 | 4.56 | 4.56 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 1.96 |  | 866 |  | 1288 | [27 empty] | Exist
2012-10-22 | N/A | PCSB | PM | DULANG | DULANG-C22ST2 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 1664 | 1328 | N/A | N/A | N/A | N/A | 10122180 | 21.1 | NO | N/A | DRY TREE | 2012-10-25 | 2012-10-25 | 2012-11-08 | 1551.99 | SHALLOW WATER | 1663 | 1327.31 | N/A | N/A | N/A | N/A | 5476538.57 | 13.33 | 0.78 | 0.78 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.62 |  | 510 |  | 1820 | [6 empty] | 3.79 | 1474725.58 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 178 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2012-10-22 | N/A | PCSB | PM | ANGSI | ANGSI-D15 | APPRAISAL CUM DEV/DEVELOPMENT | GLEN TANAR | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 4628 | 2234 | N/A | N/A | N/A | N/A | 25437541 | 58.12 | NO | N/A | DRY TREE | 2012-11-26 | 2012-11-23 | 2013-01-29 | 4396 | SHALLOW WATER | 4500 | 2208 | N/A | N/A | N/A | N/A | 24590534.45 | 67.25 | 28.13 | 15.32 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 2.58 |  | 1596 |  | 1737 | [6 empty] | 20.67 | 6660439.22 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 108.273 | True | NONE | 9CR | 8.5 | NACL | NO | NO | Exist
2012-10-10 | 2013-01-14 | PCSB | SK | F19 | F19 SHALLOW-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 85.8 | 1309 | 1280 | 12099100 | 16997460 | 20.5 | 32 | N/A | N/A | NO | N/A | N/A | 2012-10-21 04:30 | 2012-10-17 13:00 | 2012-11-18 | 1194.2 | SHALLOW WATER | 1309 | 1309 | N/A | 16155920 | N/A | 31.46 | N/A | N/A | 16.52 | 15.33 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.42 |  | 1528 |  | 4124 | [27 empty] | Exist
2012-09-28 | 2013-03-13 | IPC | PM | ARA | ARA-1 | EXPLORATION/APPRAISAL | WEST COURAGEOUS | JACK UP | 72 | 3934 | 3934 | 25761187 | 58142727 | 49.9 | 120.3 | N/A | N/A | NO | N/A | N/A | 2012-11-17 | 2012-11-10 | 2013-02-15 20:00 | 3924 | SHALLOW WATER | 4030 | 4029.7 | N/A | 40800000 | N/A | 97 | N/A | N/A | 8.9 | 8.9 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | No |  | No |  | No | [27 empty] | Exist
2012-09-07 | 2012-11-14 | PCSB | PM | DULANG | DULANG-C29 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 2610 | 1363 | N/A | N/A | N/A | N/A | 10705177 | 20.7 | NO | N/A | DRY TREE | 2012-09-16 | 2012-09-16 | 2012-10-09 | 2508.99 | SHALLOW WATER | 2620 | 1357 | N/A | N/A | N/A | N/A | 8992347.45 | 22.73 | 2.29 | 1.83 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.19 |  | 870 |  | 1090 | [6 empty] | 5.23 | 1843959.55 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 217 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2012-08-11 | 2013-04-12 | PCSB | PM | TANGGA BARAT | TNGB-A6 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 2842 | 1834 | N/A | N/A | N/A | N/A | 17433330 | 33.64 | NO | N/A | N/A | 2012-10-20 04:30 | 2012-10-19 | 2013-04-08 02:40 | 2667.84 | SHALLOW WATER | 2775 | 1798.5 | N/A | N/A | N/A | N/A | 16874680.49 | 51.16 | 15.9 | 15.9 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.69 |  | 974.14 |  | 1903.74 | [27 empty] | Exist
2012-08-09 | 2012-11-07 | IPC | PM | MERAWAN BATU | MERAWAN BATU-1 | EXPLORATION/APPRAISAL | WEST COURAGEOUS | JACK UP | 63.4 | 3584 | 3584 | 18700000 | 23200000 | 45 | 57 | N/A | N/A | NO | N/A | N/A | 2012-08-29 | 2012-08-26 | 2012-10-03 01:00 | 3832.6 | SHALLOW WATER | 3930 | 3929.64 | 16880000 | N/A | 45.35 | N/A | N/A | N/A | 4.59 | 4.59 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | No |  | No |  | No | [27 empty] | Exist
2012-08-03 | 2012-12-03 | PCSB | SB | KAURAN | KAURAN-1 | EXPLORATION/APPRAISAL | DDKG-2 | DRILLSHIP | 934 | 2695 | 2695 | 60907200 | 60907200 | 41.72 | 41.72 | N/A | N/A | NO | N/A | N/A | 2012-08-06 10:15 | 2012-08-05 | 2012-08-29 16:00 | 1655.15 | DEEP WATER | 2614.15 | 2613.8 | N/A | 40300000 | N/A | 24.67 | N/A | N/A | 11.61 | 11.61 | DW EXP C2 |  | 4.4 |  | 4200 |  | 6400 |  | 2.92 |  | 5260 |  | 7074 | [27 empty] | Exist
2012-07-12 | 2012-09-06 | PCSB | PM | RAJAH SHALLOW | RAJAH SHALLOW-1 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 68.5 | 1108 | 1058 | 10800000 | 15400000 | 22 | 33 | N/A | N/A | NO | N/A | N/A | 2012-07-24 01:45 | 2012-07-20 13:00 | 2012-08-10 11:00 | 999.17 | SHALLOW WATER | 1105 | 1105 | N/A | 7769017 | N/A | 15.54 | N/A | N/A | 8.3 | 2.7 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.23 |  | 2337 |  | 4889 | [27 empty] | Exist
2012-07-02 | 2012-10-05 | PCSB | PM | DULANG | DULANG-D28 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 3100 | 1439 | N/A | N/A | N/A | N/A | 12139809 | 21.05 | NO | N/A | DRY TREE | 2012-07-18 | 2012-07-18 | 2012-08-21 | 3231.75 | SHALLOW WATER | 3340 | 1522.5 | N/A | N/A | N/A | N/A | 12658733.75 | 32.23 | 37.17 | 37.17 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 0.94 |  | 570 |  | 1160 | [6 empty] | 18.29 | 5449816.66 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 5.0 | SINGLE | GRE | 270 | False | NONE | 25CR | 8.5 | KCL | NO | NO | Exist
2012-06-15 | 2012-10-18 | PCSB | SB | TAMPARULI | TAMPARULI-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 219.6 | 4129 | 4129 | 28034643.49 | 28034643.49 | 53 | 53 | N/A | N/A | NO | N/A | N/A | 2012-06-25 | 2012-06-20 06:00 | 2012-08-05 12:00 | 3880.4 | SHALLOW WATER | 4129 | 4126.76 | 22642531.6 | N/A | 46.25 | N/A | N/A | N/A | 13.87 | 13 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.28 |  | 1197.94 |  | 1778.64 | [27 empty] | Exist
2012-05-31 | 2012-10-18 | PCSB | PM | DULANG | DULANG-D24ST2 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2535 | 1475 | N/A | N/A | N/A | N/A | 13619420 | 27.5 | NO | N/A | DRY TREE | 2012-06-18 | 2012-06-18 | 2012-07-18 | 2397.75 | SHALLOW WATER | 2506 | 1531.46 | N/A | N/A | N/A | N/A | 11126984.33 | 29.69 | 2.67 | 2.67 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.29 |  | 500 |  | 1350 | [6 empty] | 7.04 | 2781493.06 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 5.0 | SINGLE | GRE | 263 | False | NONE | 25CR | 8.5 | KCL | NO | NO | Exist
2012-05-16 | 2012-07-12 | PCSB | PM | DULANG | DULANG-D32 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 1892 | 1368 | N/A | N/A | N/A | N/A | 10552860 | 20.3 | NO | N/A | N/A | 2012-05-17 | 2012-05-17 12:00 | 2012-06-18 22:00 | 1832.75 | SHALLOW WATER | 1941 | 1391 | N/A | N/A | N/A | N/A | 8325494.65 | 18.63 | 9.39 | 8.96 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.32 |  | 480 |  | 1310 | [27 empty] | Exist
2012-05-11 | 2012-07-12 | PCSB | PM | DULANG | DULANG-D30 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 1495 | 1372 | N/A | N/A | N/A | N/A | 10338318 | 19.5 | NO | N/A | DRY TREE | 2012-05-15 | 2012-05-15 08:00 | 2012-06-07 19:00 | 1394.75 | SHALLOW WATER | 1503 | 1376.46 | N/A | N/A | N/A | N/A | 7362956.36 | 16.7 | 0.37 | 0.37 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.7 |  | 630 |  | 1490 | [6 empty] | 7.58 | 2960056.77 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 5.0 | DUAL | L80 13CR | 312 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2012-04-20 | 2012-06-14 | PCSB | PM | DULANG | DULANG-D31 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2080 | 1403 | N/A | N/A | N/A | N/A | 9476490 | 18.17 | NO | N/A | DRY TREE | 2012-04-30 | 2012-04-30 11:30 | 2012-05-15 | 1922.75 | SHALLOW WATER | 2031 | 1372.37 | N/A | N/A | N/A | N/A | 6724225.08 | 14.85 | 3.65 | 3.65 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.47 |  | 680 |  | 1050 | [6 empty] | 4.65 | 1742122.8 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 368 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2012-02-17 | 2012-12-07 | PCSB | PM | SEPAT | SEPAT-A4 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 3634 | 1532.1 | N/A | N/A | N/A | N/A | 23336560 | 47.31 | NO | N/A | DRY TREE | 2012-02-21 13:15 | 2012-02-20 | 2012-07-30 12:00 | 3530 | SHALLOW WATER | 3634 | 1532.1 | N/A | N/A | N/A | N/A | 20031722 | 47.31 | 8.42 | 8.42 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.73 |  | 1089 |  | 1730 | [6 empty] | 9.25 | 3788936.75 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1896 | True | ICD | L80 13CR | 9 | NACL | 1 | NO | Exist
2012-01-26 | 2012-05-09 | PCSB | PM | TANGGA BARAT | TNGB-A9 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 1894 | 1556 | N/A | N/A | N/A | N/A | 14017130 | 24.57 | NO | N/A | DRY TREE | 2012-02-02 03:00 | 2012-01-29 14:00 | 2012-04-11 12:00 | 1782.84 | SHALLOW WATER | 1890 | 1560 | N/A | N/A | N/A | N/A | 9084218 | 22.83 | 14.97 | 14.97 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.27 |  | 707 |  | 1620 | [6 empty] | 12.09 | 4337694.88 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | 22CR | 159.1285 | False | NONE | 22CR | 9.5 | NABR | NO | NO | Exist
2011-12-29 | 2012-04-13 | PCSB | PM | SEPAT | SEPAT A-03 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 2043.5 | 1708.5 | N/A | N/A | N/A | N/A | 10459750 | 25.11 | NO | N/A | DRY TREE | 2012-01-07 | 2012-01-07 04:00 | 2012-02-19 | 2097.5 | SHALLOW WATER | 2200 | 1701 | N/A | N/A | N/A | N/A | 9590527 | 24.23 | 1.45 | 1.45 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.4 |  | 674.85 |  | 1395 | [6 empty] | 9.88 | 2886369.96 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 131 | True | NONE | L80 13CR | 9 | NACL | 1 | NO | Exist
2011-12-28 | 2012-07-11 | PCSB | PM | TANGGA BARAT | TNGB-A4 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 2175 | 1424 | N/A | N/A | N/A | N/A | 9439509 | 24.76 | SIDETRACK | N/A | DRY TREE | 2012-01-27 14:00 | 2012-01-26 10:00 | 2012-04-29 16:00 | 1849.84 | SHALLOW WATER | 1957 | 1295.9 | N/A | N/A | N/A | N/A | 14599673.9 | 54.13 | 60.93 | 60.47 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 4.9 |  | 1974 |  | 2440 | [6 empty] | 9.48 | 2042280.92 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 3.0 | DUAL | L80 | 236.232 | False | NONE | 9CR | 10.2 | NABR | NO | NO | Exist
2011-12-23 | 2012-04-24 | PCSB | PM | BUJANG | BUJANG-6 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 72.8 | 2149 | 2066 | 16624550 | 21099970 | 38.25 | 49.75 | N/A | N/A | NO | N/A | N/A | 2012-01-05 | 2012-01-01 15:00 | 2012-02-25 18:00 | 2273.4 | SHALLOW WATER | 2382 | 2296.95 | N/A | 22190400 | N/A | 55.14 | N/A | N/A | 10.69 | 10.69 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.15 |  | 1148 |  | 1893 | [27 empty] | Exist
2011-12-05 | 2012-04-20 | PCSB | SK | KEDIDI | KEDIDI-1 | EXPLORATION/APPRAISAL | ACTINIA | JACK UP | 105.6 | 3976 | 3976 | 25543845.84 | 30704286.31 | 56 | 65.3 | N/A | N/A | NO | N/A | N/A | 2012-01-16 | 2012-01-14 08:30 | 2012-03-18 15:45 | 3699.8 | SHALLOW WATER | 3831 | 3831 | 29757147.08 | N/A | 64.3 | N/A | N/A | N/A | 5.43 | 5.17 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.6 |  | 2111.76 |  | 2451.36 | [27 empty] | Exist
2011-11-30 | 2012-05-17 | PCSB | PM | DULANG | DULANG-D27 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 1680 | 1422 | N/A | N/A | N/A | N/A | 10155396 | 21.6 | NO | N/A | DRY TREE | 2012-03-13 | 2012-03-13 02:30 | 2012-04-02 20:00 | 1545.75 | SHALLOW WATER | 1654 | 1385.48 | N/A | N/A | N/A | N/A | 8633504.72 | 20.23 | 2.2 | 2.2 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.97 |  | 598 |  | 1109 | [6 empty] | 4.9 | 1961843.63 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 112 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2011-11-30 | 2012-06-08 | PCSB | PM | DULANG | DULANG-D29 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2780 | 1416 | N/A | N/A | N/A | N/A | 13789239 | 22.3 | NO | N/A | DRY TREE | 2012-04-04 16:00 | 2012-04-02 20:00 | 2012-04-30 11:30 | 2746.76 | SHALLOW WATER | 2855 | 1418.46 | N/A | N/A | N/A | N/A | 11664719.79 | 27.65 | 6.71 | 6.71 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.41 |  | 740 |  | 1250 | [6 empty] | 6.06 | 2373667.13 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 427 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
2011-11-29 | 2012-06-25 | PCSB | SK | KANOWIT | KANOWIT-SS2 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-1 | SEMI-SUB | 78 | 1964 | 1840 | N/A | N/A | N/A | N/A | 37791540 | 61 | NO | N/A | WET TREE | 2011-12-15 | 2011-12-14 | 2012-04-05 | 1859 | SHALLOW WATER | 1964 | 1847.56 | N/A | N/A | N/A | N/A | 44740601.09 | 68.6 | 5.3 | 2.99 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1635 |  | 6.08 |  | 3429.69 |  | 7594.06 | [6 empty] | 13.33 | 13507706.36 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 0 | False | NONE | SUPER 13CR | 15.2 | CSCOOH | NO | NO | Exist
2011-10-19 | 2012-06-25 | PCSB | SK | KANOWIT | KANOWIT-SS1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-1 | SEMI-SUB | 78 | 1869 | 1737 | N/A | N/A | N/A | N/A | 37450000 | 56 | NO | N/A | WET TREE | 2011-11-01 | 2011-10-28 09:00 | 2012-03-24 18:30 | 1764 | SHALLOW WATER | 1869 | 1735 | N/A | N/A | N/A | N/A | 51486560.04 | 91.69 | 8.2 | 6.17 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1635 |  | 9.76 |  | 4473.13 |  | 9183.13 | [6 empty] | 11.52 | 14251186 |  |  | CARBONATE | NORMAL | OPEN HOLE PREDRILLED LINER | NO | NO | 7" | 1.0 | SINGLE | SUPER 13CR | 0 | True | NONE | SUPER 13CR | 15.2 | CSCOOH | NO | NO | Exist
2007-12-19 | N/A | PCSB | SB | SUMANDAK | SUJT-C07 | APPRAISAL CUM DEV/DEVELOPMENT | TRIDENT-17 | JACK UP | 35 | 2293 | 1485 | N/A | N/A | N/A | N/A | 10140000 | 26.88 | NO | N/A | DRY TREE | 2008-01-10 | 2008-01-10 | 2008-02-07 | 2779 | SHALLOW WATER | 2850 | 1471 | N/A | N/A | N/A | N/A | 8250164.52 | 28.91 | 6.99 | 6.99 | SW DEV C1 |  | 1.7 |  | 720 |  | 1285 |  | 2.95 |  | 3277 |  | 3438 | [6 empty] | 4.6 | 2339661.86 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 | 1161.474 | False | NONE | 9CR | 9.2 | NACL | NO | NO | Exist
2007-11-12 | N/A | PCSB | SB | SUMANDAK | SUJT-C05 | APPRAISAL CUM DEV/DEVELOPMENT | TRIDENT-17 | JACK UP | 35 | 1511 | 1432.2 | N/A | N/A | N/A | N/A | 5720000 | 13.93 | NO | N/A | DRY TREE | 2007-12-16 | 2007-12-16 | 2007-12-27 | 1421 | SHALLOW WATER | 1492 | 1428 | N/A | N/A | N/A | N/A | 3811171.42 | 11.79 | 11.22 | 11.22 | SW DEV C1 | SW DEV C1 | 1.7 | 1.7 | 720 | 720 | 1285 | 1285 | Yes | 2.24 | Yes | 2953 | Yes | 3106 | [5 empty] | 5.94 | 3073851.32 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 1049.92 | True | NONE | 9CR | 9.2 | NACL | NO | NO | Exist
N/A | 2018-01-20 | PCSB | SK | TUKAU TIMUR | TT-A3 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 42.97 | 4919.54 | 4567.21 | N/A | N/A | N/A | N/A | 63683684.92 | 145.33 | NO | N/A | DRY TREE | 2017-06-02 | 2017-06-02 10:00 | 2017-12-16 16:30 | 4619.17 | SHALLOW WATER | 4706.49 | 4357.21 | N/A | N/A | N/A | N/A | 52369233.95 | 139.67 | 29.65 | 29.5 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3040 |  | 3.79 |  | 1762.07 |  | 3455.12 | [6 empty] | 17.31 | 11739482 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 5-1/2" | 5.0 | SINGLE | L80 13CR | 2007 | False |  | L80 13CR | 9.9 | NACL | NO | NO | Exist
N/A | 2024-04-09 | PCSB | SK | BOKOR | BOKOR-E508 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 1490 | 1421 | N/A | N/A | N/A | N/A | 9760000 | 21.04 | SUSPEND | N/A | DRY TREE | 2024-01-30 | 2024-01-29 20:00 | 2024-02-13 16:30 | 1356 | SHALLOW WATER | 1465 | 1397.65 | N/A | N/A | N/A | N/A | 7183030 | 15.42 | 3.18 | 3.18 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.09 |  | 977 |  | 1726 | [6 empty] | 6.68 | 3129357 | 1.39 | 651 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | DUAL | L80 13CR | 1394 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
N/A | 2015-06-02 | PCSB | PM | ANGSI | ANGSI-B27 ST3 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 3883 | 1973 | N/A | N/A | N/A | N/A | 43571877 | 76.95 | NO | N/A | DRY TREE | 2015-02-13 | 2015-01-19 10:00 | 2015-05-02 04:00 | 3770.82 | SHALLOW WATER | 3873 | 1972.5 | N/A | N/A | N/A | N/A | 30992318.01 | 75.13 | 8.87 | 8.87 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.4 |  | 1024.93 |  | 2646.4 | [6 empty] | 23.75 | 10193698.53 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 3.0 | DUAL | L80 | 1187.722 | False | INNER STRING WITH SSD | 9CR | 8.5 | NACL | NO | NO | Exist
N/A | 2014-07-14 | PCSB | PM | SELENDANG | SELENDANG-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 103 | 1229 | 1229 | 31100000 | 43600000 | 33.8 | 51.7 | N/A | N/A | NO | N/A | N/A | 2014-03-01 18:45 | 2014-02-28 04:45 | 2014-03-29 19:00 | 1147.63 | SHALLOW WATER | 1279.63 | 1276 | 20512762.48 | N/A | 29.59 | N/A | N/A | N/A | 10.26 | 10.26 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 4.41 |  | 2836 |  | 5169 | [27 empty] | Exist
N/A | 2017-03-15 | PCSB | SK | BARONIA | BN-75 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 77.72 | 2085.64 | 1800.06 | N/A | N/A | N/A | N/A | 15645510.13 | 41.9 | NO | N/A | DRY TREE | 2016-09-12 | 2016-09-12 14:00 | 2017-01-27 | 2023.9 | SHALLOW WATER | 2131.36 | 1785.89 | N/A | N/A | N/A | N/A | 12730555.66 | 39.92 | 12.8 | 12.7 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.9 |  | 799.7 |  | 1453.7 | [6 empty] | 14.06 | 4612698.28 |  |  | SANDSTONE | NORMAL | CASED HOLE GRAVEL PACK | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 21 | True |  | 9CR | 8.5 | SEAWATER/DRILLWATER | NO | NO | Exist
N/A | 2015-01-15 | PTTEP | SK | SOUTH ACIS | SAPA-11 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 35 | 2114.84 | 1549.37 | N/A | N/A | N/A | N/A | 7194032.1 | 8.54 | NO | N/A | N/A | 2014-09-21 | 2014-09-19 21:00 | 2014-12-01 09:00 | 1937.16 | SHALLOW WATER | 2015 | 1498 | N/A | N/A | N/A | N/A | 5617497 | 8.94 | 0 | 0 | SW DEV SLIM HOLE (Without Offline Capability Rig) |  | 1.4 |  | 550 |  | 870 |  | 1.15 |  | 730 |  | 864 | [27 empty] | Exist
N/A | 2012-05-30 | PCSB | PM | TANGGA BARAT | TNGB-A8 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 1661 | 1430 | N/A | N/A | N/A | N/A | 9547010 | 25.9 | NO | N/A | DRY TREE | 2012-01-25 | 2012-01-23 13:30 | 2012-04-20 05:00 | 1549.84 | SHALLOW WATER | 1657 | 1429.86 | N/A | N/A | N/A | N/A | 6028129 | 20.14 | 4.46 | 4.46 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.86 |  | 599 |  | 1109 | [6 empty] | 8.71 | 2480708.59 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | L80 | 217.5303 | False | NONE | 9CR | 10.2 | NABR | NO | NO | Exist
N/A | 2012-03-23 | PCSB | PM | SEPAT | SEPAT A-02 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 2510 | 1658 | N/A | N/A | N/A | N/A | 14474000 | 28.56 | NO | N/A | N/A | 2011-12-07 06:00 | 2011-12-07 06:00 | 2012-02-10 19:00 | 2275.39 | SHALLOW WATER | 2360 | 1721.45 | N/A | N/A | N/A | N/A | 17554160 | 47.27 | 11.23 | 4.98 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.72 |  | 1011 |  | 1832 | [27 empty] | Exist
N/A | 2015-10-16 | IPC | PM | BERTAM | BERTAM A-11 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 2640 | 1656 | N/A | N/A | N/A | N/A | 21000000 | 35.9 | SIDETRACK | N/A | DRY TREE | 2014-08-14 | 2014-08-08 | 2015-08-23 07:30 | 2156.26 | SHALLOW WATER | 2275 | 1657.2 | N/A | N/A | N/A | N/A | 18000000 | 28.4 | 3.6 | 3.6 | SW DEV C2 |  | 3.2 |  | 1300 |  | 2230 |  | 2.81 |  | 1678.83 |  | 2405.34 | [6 empty] | 4.9 | 4200000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 426.53 | True | ICD | L80 | 11.5 | BASE OIL/DIESEL | 1 | NO | Exist
N/A | 2012-11-30 | PCSB | PM | DULANG | DULANG-C31 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 2514 | 1399 | N/A | N/A | N/A | N/A | 10199329 | 20.05 | NO | N/A | DRY TREE | 2012-10-10 | 2012-10-10 | 2012-10-25 | 2399.99 | SHALLOW WATER | 2511 | 1403.87 | N/A | N/A | N/A | N/A | 6916368.27 | 15.67 | 5.32 | 5.32 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.16 |  | 520 |  | 890 | [6 empty] | 5.94 | 1849741.53 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 4-1/2" | 4.0 | SINGLE | GRE | 256 | False | NONE | 25CR | 8.5 | KCL | NO | NO | Exist
N/A | 2020-08-12 | PTTEP | SB | ROTAN | RT-P1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST CARINA | DRILLSHIP | 1189 | 2120 | 2100 | N/A | N/A | N/A | N/A | 22889618 | 17.4 | NO | N/A | WET TREE | 2020-04-25 04:30 | 2020-04-25 | 2020-07-04 | 796 | DEEP WATER | 2009 | 2009 | N/A | N/A | N/A | N/A | 23066336 | 24.2 | 3.87 | 3.87 | DW DEV C2 (Wet Tree) |  | 4 |  | 3640 |  | 8010 |  | 2.6 |  | 1854 |  | 5743 | [6 empty] | 15.46 | 14735766.72 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 5-1/2" | 1.0 | SINGLE | L80 13CR | 127.959 | True |  | L80 13CR | 10.4 | NABR | 2 | NO | Exist
N/A | 2022-01-07 | PTTEP | SK | SOUTH ACIS | SASA-07 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 1906.9 | 1429.13 | N/A | N/A | N/A | N/A | 5463297.17 | 11.17 | NO | N/A | DRY TREE | 2021-07-11 15:45 | 2021-06-15 07:45 | 2021-11-03 18:00 | 1790.15 | SHALLOW WATER | 1877 | 1416.86 | N/A | N/A | N/A | N/A | 5810461.96 | 14.71 | 0.57 | 0.57 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.11 |  | 697 |  | 943 | [6 empty] | 2.89 | 1773504 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 69 | True |  | L80 13CR | 9.3 | CACL2 | NO | NO | Exist
N/A | N/A | PCSB | PM | DULANG | DULANG-C03 | APPRAISAL CUM DEV/DEVELOPMENT | KM-1 | TENDER ASSISTED DRILLING RIG (TADR) | 76.7 | 1903.7 | 1903.7 | N/A | N/A | N/A | N/A | 2512210 | 7 | SIDETRACK | N/A | DRY TREE | 2012-12-06 | 2012-11-18 | 2012-12-19 | 1996.99 | SHALLOW WATER | 2108 | 1339.6 | N/A | N/A | N/A | N/A | 7207518.59 | 19.17 | 1.86 | 1.86 | SW DEV C1 |  | 2.1 |  | 700 |  | 1225 |  | 1.4 |  | 530 |  | 1860 | [6 empty] | 5.21 | 1746215.36 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 4.0 | SINGLE | L80 13CR | 434 | False | INNER STRING WITH SSD | L80 13CR | 8.5 | KCL | NO | NO | Exist
N/A | N/A | PTTEP | SK | SERAMPANG | SEPA-12 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 47.5 | 3349 | 1509 | N/A | N/A | N/A | N/A | 7173379.61 | 15.46 | NO | N/A | N/A | N/A | N/A | N/A | 3498.4 | SHALLOW WATER | 3588 | 1368.85 | N/A | N/A | N/A | N/A | 9887752.68 | 29.73 | 19.38 | 19.38 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1200 |  | 2.7 |  | 599.92 |  | 925.64 | [27 empty] | Exist
N/A | 2014-03-13 | PCSB | PM | BEKOK | BEKOK A-10 | APPRAISAL CUM DEV/DEVELOPMENT | TEKNIK BERKAT | TENDER ASSISTED DRILLING RIG (TADR) | 71.3 | 4258 | 2145 | N/A | N/A | N/A | N/A | 27906260 | 60.95 | SIDETRACK | N/A | DRY TREE | 2013-10-05 | 2013-09-02 | 2014-01-14 | 3953.8 | SHALLOW WATER | 4056 | 2162 | N/A | N/A | N/A | N/A | 37299998.04 | 109.59 | 27.78 | 26.39 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 5.32 |  | 1908 |  | 2565 | [6 empty] | 16.54 | 4399308.38 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | L80 | 3307.248 | True |  | 9CR | 8.4 | NACL | NO | NO | Exist
N/A | 2014-12-03 | PCSB | SB | KINABALU | KN-B2 | APPRAISAL CUM DEV/DEVELOPMENT | DEEP DRILLER-3 | JACK UP | 59.1 | 4849.13 | 4501.9 | N/A | N/A | N/A | N/A | 68522800 | 93.8 | NO | N/A | N/A | 2013-10-15 03:00 | 2013-10-15 03:00 | 2014-07-31 08:00 | 4646.17 | SHALLOW WATER | 4761.96 | 4541.6 | N/A | N/A | N/A | N/A | 47297858 | 79.75 | 5.74 | 5.74 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.16 |  | 2701 |  | 3156 | [27 empty] | Exist
N/A | 2012-12-10 | PCSB | PM | BUNGA BAKAWALI | BUNGA BAKAWALI-2 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 56 | 2060 | 2060 | 20680090 | 29200000 | 46 | 62 | N/A | N/A | NO | N/A | N/A | 2012-08-15 | 2012-08-04 | 2012-10-02 08:00 | 1989.3 | SHALLOW WATER | 2070 | 2069.27 | N/A | 19661850 | N/A | 50.25 | N/A | N/A | 2.18 | 2.18 | SW EXP C1 |  | 1.9 |  | 720 |  | 1370 |  | 1.6 |  | 1022.7 |  | 2452 | [27 empty] | Exist
N/A | 2022-01-07 | PTTEP | SK | SOUTH ACIS | SASA-03 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 1626.81 | 1466.7 | N/A | N/A | N/A | N/A | 6085097.3 | 12.87 | SIDETRACK | N/A | DRY TREE | 2021-07-09 04:15 | 2021-07-02 17:45 | 2021-09-10 17:00 | 1525.15 | SHALLOW WATER | 1612 | 1458.25 | N/A | N/A | N/A | N/A | 6654338.7 | 19.79 | 22.58 | 22.58 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 2.18 |  | 720 |  | 898 | [6 empty] | 2.1 | 1586700 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 72 | True |  | L80 13CR | 9.3 | CACL2 | NO | NO | Exist
N/A | 2013-06-06 | PCSB | PM | SEPAT | SEPAT A-05 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 3273 | 2114 | N/A | N/A | N/A | N/A | 34880710 | 50.22 | NO | N/A | DRY TREE | 2013-01-10 | 2013-01-10 03:30 | 2013-03-22 | 3190 | SHALLOW WATER | 3294 | 1762.99 | N/A | N/A | N/A | N/A | 21171414 | 54.79 | 19.13 | 19.13 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.61 |  | 1080 |  | 2023 | [6 empty] | 9.3 | 4558297.99 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 262 | True | NONE | L80 13CR | 9.2 | NACL | 1 | NO | Exist
N/A | N/A | SHELL | SK | F14 | F14-107 | APPRAISAL CUM DEV/DEVELOPMENT | WEST ALLIANCE | TENDER ASSISTED DRILLING RIG (TADR) | 105.15 | 1667.48 | 1360.26 | N/A | N/A | N/A | N/A | 25819773.75 | 43.12 | NO | N/A | N/A | 2014-06-21 19:45 | 2014-06-17 12:00 | 2014-09-14 | 1533.68 | SHALLOW WATER | 1672.66 | 1360.26 | N/A | N/A | N/A | N/A | 26103166 | 53.68 | 5.94 | 5.08 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1870 |  | 2.63 |  | 2196 |  | 1535 | [27 empty] | Exist
N/A | 2013-02-26 | PCSB | SK | BOKOR | BO-208ST | APPRAISAL CUM DEV/DEVELOPMENT | TEKNIK BERKAT | TENDER ASSISTED DRILLING RIG (TADR) | 67.66 | 1965.86 | 1882.66 | N/A | N/A | N/A | N/A | 16678598.45 | 40 | NO | N/A | N/A | 2012-09-26 | 2012-09-19 | 2012-10-22 | 1882.2 | SHALLOW WATER | 1976.53 | 1895.3 | N/A | N/A | N/A | N/A | 13078655 | 32.58 | 2.88 | 2.88 | SW DEV C1 |  | 2.2 |  | 830 |  | 1790 |  | 1.79 |  | 884 |  | 2523 | [27 empty] | Exist
N/A | 2015-05-25 | PCSB | PM | ENAU | ENAU-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 61.1 | 1660 | 1660 | 16380000 | 24381730.8 | 31.44 | 44.82 | N/A | N/A | NO | N/A | N/A | 2015-02-15 | 2015-02-01 23:15 | 2015-03-14 17:30 | 1594 | SHALLOW WATER | 1690 | 1690 | N/A | 20219467 | N/A | 40.76 | N/A | N/A | 4.71 | 2.58 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.22 |  | 865.4 |  | 3647.3 | [27 empty] | Exist
N/A | 2014-06-30 | SHELL | SB | ROSMARI | ROSMARI-1 | EXPLORATION/APPRAISAL | DOO SUNG | SEMI-SUB | 47.85 | 3698.26 | 2682.11 | 54940000 | 63890000 | 46.96 | 58.13 | N/A | N/A | SUSPEND | N/A | N/A | 2014-01-08 | 2014-01-04 12:00 | 2014-03-31 15:30 | 842.12 | SHALLOW WATER | 915.88 | 647.36 | N/A | 59588211 | N/A | 83.5 | N/A | N/A |  |  | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2015-06-04 | PTTEP | SK | BELUM | BESA-02 | APPRAISAL CUM DEV/DEVELOPMENT | ENSCO-52 | JACK UP | 27 | 2420.74 | 1028.95 | N/A | N/A | N/A | N/A | 7564516.47 | 8.4 | NO | N/A | DRY TREE | 2015-03-29 | 2015-03-26 17:00 | 2015-04-17 12:00 | 2354.1 | SHALLOW WATER | 2413.3 | 1021.99 | N/A | N/A | N/A | N/A | 4867233.37 | 6.73 | 0.31 | 0.31 | SW DEV C1 | SW DEV C1 | 2.2 | 2.2 | 830 | 830 | 1395 | 1395 | Yes | 1.7 | Yes | 580 | Yes | 1100 | [5 empty] | 1.11 | 2117000 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 201.7815 | False | NONE | L80 13CR | 6.68 | BASE OIL/DIESEL | NO | NO | Exist
N/A | N/A | PTTEP | SK | SASA | SASA-01 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 1938.36 | 1489.88 | N/A | N/A | N/A | N/A | 6101546.4 | 13.91 | SIDETRACK | N/A | DRY TREE | N/A | N/A | N/A | 1828.15 | SHALLOW WATER | 1915 | 1515.46 | N/A | N/A | N/A | N/A | 6101546.4 | 13.9 | 0.75 | 0.75 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 1.79 |  | 770 |  | 1185 | [6 empty] | 2.15 | 1960296 |  |  | SANDSTONE | NORMAL | OPEN HOLE COMPLIANT SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 108 | True |  | L80 13CR | 9.3 | CACL2 | NO | NO | Exist
N/A | 2015-03-17 | PCSB | SK | D28 | D28-2 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 35.8 | 1558 | 1558 | 34353608 | 34947765 | 37 | 54 | N/A | N/A | NO | N/A | N/A | 2014-11-29 17:30 | 2014-11-26 05:00 | 2015-01-07 | 1560.7 | SHALLOW WATER | 1618 | 1618 | 21800000 | N/A | 42.35 | N/A | N/A | N/A | 4.18 | 3.37 | SW EXP C2 |  | 2.7 |  | 1490 |  | 2760 |  | 1.98 |  | 849 |  | 2238 | [27 empty] | Exist
N/A | 2020-01-23 | SAPURA OMV | SK | BAKONG | BAKONG A-01 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 85 | 1825 | 1825 | N/A | N/A | N/A | N/A | 14889715 | 27.59 | NO | N/A | N/A | 2019-10-31 | 2019-10-31 15:00 | 2019-11-28 15:00 | 1707.76 | SHALLOW WATER | 1835 | 1834.57 | N/A | N/A | N/A | N/A | 9486109 | 27.34 | 1.68 | 1.52 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.6 |  | 1320 |  | 1870 | [27 empty] | Exist
N/A | 2015-11-16 | IPC | PM | BERTAM | BERTAM A-12 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3676 | 1650 | N/A | N/A | N/A | N/A | 19302544 | 32 | NO | N/A | DRY TREE | 2014-08-13 | 2014-08-08 | 2015-09-22 09:00 | 3392.26 | SHALLOW WATER | 3511 | 1656 | N/A | N/A | N/A | N/A | 18200000 | 33 | 1.2 | 1.2 | SW DEV C3 |  | 2.2 |  | 915 |  | 1450 |  | 1.88 |  | 1054.57 |  | 1587.62 | [6 empty] | 5.8 | 3900000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 1279.59 | True | ICD | L80 | 9.5 | BASE OIL/DIESEL | 1 | NO | Exist
N/A | 2014-04-24 | MUBADALA | SK | SIRIH | SIRIH-1 | EXPLORATION/APPRAISAL | SONGA VENUS | SEMI-SUB | 108.2 | 2910 | 2910 | 17791790.95 | 17791790.95 | 23.94 | 23.94 | N/A | N/A | NO | N/A | N/A | 2014-01-04 | 2014-01-03 04:00 | 2014-02-24 16:00 | 2867.1 | SHALLOW WATER | 3000 | 3000 | N/A | 28273123 | N/A | 51.04 | N/A | N/A | 17.2 | 9.31 | SW EXP C4 |  | 4.4 |  | 1980 |  | 2760 |  | 2.9 |  | 1584 |  | 3006 | [27 empty] | Exist
N/A | 2014-04-28 | PCSB | SB | SAMARANG | SM-103 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 10.06 | 2686.8 | 2027.97 | N/A | N/A | N/A | N/A | 16720000 | 36.33 | NO | N/A | DRY TREE | 2014-01-06 22:30 | 2014-01-06 22:30 | 2014-04-01 09:00 | 2957.63 | SHALLOW WATER | 3002.13 | 2190.28 | N/A | N/A | N/A | N/A | 16558841.83 | 37.66 | 19.14 | 19.14 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 1.98 |  | 773.6 |  | 1650.79 | [6 empty] | 14.79 | 6142773.4 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 6.0 | SINGLE | L80 13CR | 2018 | True | NONE | 13CR | 8.9 | KCL | NO | NO | Exist
N/A | 2013-03-12 | PCSB | SK | D21 | D21-A1 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 50.59 | 2007.62 | 1967.39 | N/A | N/A | N/A | N/A | 13400000 | 26.3 | NO | N/A | DRY TREE | 2012-12-13 | 2012-12-13 | 2013-01-11 | 2163.06 | SHALLOW WATER | 2252.36 | 2054.25 | N/A | N/A | N/A | N/A | 11877666 | 28.6 | 1.55 | 1.55 | SW DEV C1 |  | 2.2 |  | 830 |  | 1395 |  | 2.2 |  | 342.03 |  | 544.75 | [6 empty] | 6.21 | 2249786.19 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 5.0 | SINGLE | L80 13CR | 131 | False |  | 13CR | 8.3 | NABR | NO | NO | Exist
N/A | 2024-05-10 | PCSB | SK | BOKOR | BOKOR-E504 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 840 | 785 | N/A | N/A | N/A | N/A | 7650115.25 | 15.83 | NO | N/A | DRY TREE | 2024-01-08 | 2024-01-08 21:00 | 2024-03-11 | 745.01 | SHALLOW WATER | 854.01 | 795.63 | N/A | N/A | N/A | N/A | 7645949.78 | 15.19 | 0.41 | 0.41 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 3.1 |  | 1434 |  | 2857 | [6 empty] | 4 | 1000314 | 1.4 | 357 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 13CR | 1073 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
N/A | 2013-10-17 | PCSB | PM | ANGSI | ANGSI-D16 | APPRAISAL CUM DEV/DEVELOPMENT | GLEN TANAR | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 4159 | 1677 | N/A | N/A | N/A | N/A | 22259173 | 53.45 | NO | N/A | DRY TREE | 2013-02-04 | 2012-11-19 | 2013-05-19 | 4029 | SHALLOW WATER | 4133 | 1662.08 | N/A | N/A | N/A | N/A | 29446367.74 | 72.35 | 22 | 22 | SW DEV C3 |  | 2.2 |  | 915 |  | 1520 |  | 4.16 |  | 1927.27 |  | 2121.71 | [6 empty] | 13.65 | 5773966.34 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 843.217 | False | NONE | 9CR | 8.5 | NACL | NO | NO | Exist
N/A | 2013-12-31 | PCSB | PM | BEKOK | BEKOK A-01 | APPRAISAL CUM DEV/DEVELOPMENT | TEKNIK BERKAT | TENDER ASSISTED DRILLING RIG (TADR) | 71.3 | 3181 | 1647 | N/A | N/A | N/A | N/A | 16992853.06 | 34.14 | NO | N/A | DRY TREE | 2013-07-31 | 2013-06-01 | 2013-09-02 17:00 | 3187.8 | SHALLOW WATER | 3290 | 1647 | N/A | N/A | N/A | N/A | 16685414.49 | 44.9 | 3.85 | 3.74 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1400 |  | 2.81 |  | 1110 |  | 1780 | [6 empty] | 8.01 | 2586311.8 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 2404.973 | False | NONE | 9CR | 8.4 | NACL | NO | NO | Exist
N/A | 2014-05-23 | COASTAL ENERGY KBM (CEKBM) | PM | MERANTI | MERANTI M1 | APPRAISAL CUM DEV/DEVELOPMENT | ATWOOD MANTA | JACK UP | 58.52 | 2377.93 | 2202.99 | N/A | N/A | N/A | N/A | 8262691 | 17.16 | SIDETRACK | N/A | N/A | 2014-01-29 | 2013-12-26 11:30 | 2014-02-16 01:30 | 2215.27 | SHALLOW WATER | 2308.84 | 2196.28 | N/A | N/A | N/A | N/A | 6857051.31 | 19.44 | 14.04 | 14.04 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2012-04-20 | PCSB | PM | TANGGA BARAT | TNGB-A3 | APPRAISAL CUM DEV/DEVELOPMENT | TRIUMPH-101 | TENDER ASSISTED DRILLING RIG (TADR) | 73.4 | 1716 | 1544 | N/A | N/A | N/A | N/A | 14330860 | 26.71 | NO | N/A | DRY TREE | 2011-12-03 16:00 | 2011-12-02 | 2012-01-23 13:30 | 1626.84 | SHALLOW WATER | 1734 | 1560 | N/A | N/A | N/A | N/A | 12510337 | 52.56 | 52.99 | 16.12 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 2.51 |  | 2844 |  | 8796.8 | [6 empty] | 10.59 | 2520336.14 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | DUAL | 22CR | 187.017 | False | NONE | 22CR | 9.3 | NACL | NO | NO | Exist
N/A | 2015-04-14 | IPC | PM | BERTAM | BERTAM A-5 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3151 | 1641.37 | N/A | N/A | N/A | N/A | 20169983 | 33.8 | SIDETRACK | N/A | DRY TREE | 2014-08-09 | 2014-08-08 | 2015-03-12 | 3132.26 | SHALLOW WATER | 3251 | 1642.52 | N/A | N/A | N/A | N/A | 20454349 | 34.5 | 4.59 | 4.59 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 2.02 |  | 1118.39 |  | 1507.74 | [6 empty] | 5.8 | 4500000 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | 1 | 3-1/2" | 1.0 | SINGLE | L80 | 2039.5844 | True | ICD | L80 | 9.7 | BASE OIL/DIESEL | 1 | NO | Exist
N/A | N/A | PCSB | SK | BIDARA | BIDARA-1 | EXPLORATION/APPRAISAL | DDKG-2 | DRILLSHIP | 1306 | 3275 | 3275 | 51795490 | 51795490 | 41.37 | 41.37 | N/A | N/A | NO | N/A | N/A | 2012-06-10 | 2012-05-31 00:01 | 2012-07-10 | 1944.3 | DEEP WATER | 3275 | 3275 | N/A | 42816270 | N/A | 41 | N/A | N/A | 10.42 | 10.42 | DW EXP C3 |  | 5.4 |  | 5090 |  | 7920 |  | 2.5 |  | 3171 |  | 6723 | [27 empty] | Exist
N/A | 2014-04-08 | PCSB | PM | SONGKET | SONGKET-1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 68 | 3159 | 3139 | 54105446.76 | 71504218.1 | 69.64 | 92.58 | N/A | N/A | NO | N/A | N/A | 2013-12-01 | 2013-11-13 18:00 | 2014-01-20 12:00 | 3062 | SHALLOW WATER | 3159 | 3159 | 45375724.31 | N/A | 67.75 | N/A | N/A | N/A | 15.7 | 15.5 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.77 |  | 1725.04 |  | 2397.88 | [27 empty] | Exist
N/A | 2014-04-07 | PCSB | PM | BUNGA BAKAWALI | BUNGA BAKAWALI DEEP-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 56 | 2734 | 2734 | 46309725.12 | 46309725.12 | 70.6 | 92.7 | N/A | N/A | NO | N/A | N/A | 2013-12-15 | 2013-11-21 01:15 | 2014-02-23 03:45 | 2535 | SHALLOW WATER | 2625 | 2624.9 | 36856193.73 | N/A | 80.4 | N/A | N/A | N/A | 5.31 | 5.31 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 4.14 |  | 2897 |  | 3841 | [27 empty] | Exist
N/A | 2013-08-22 | PCSB | PM | SEPAT | SEPAT A-09 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-3 | JACK UP | 63 | 1772 | 1655 | N/A | N/A | N/A | N/A | 23182000 | 42.46 | NO | N/A | N/A | 2013-03-23 | 2013-03-23 | 2013-06-28 02:00 | 1689 | SHALLOW WATER | 1793 | 1676 | N/A | N/A | N/A | N/A | 19127207 | 49.52 | 20.95 | 20.95 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 3.9 |  | 1770 |  | 3452 | [27 empty] | Exist
N/A | 2014-07-25 | PCSB | SK | CERI | CERI-1 | EXPLORATION/APPRAISAL | AQUA MARINE DRILLER | JACK UP | 7.5 | 2547 | 1706 | 23790000 | 26130000 | 30.5 | 36.25 | N/A | N/A | SIDETRACK | N/A | N/A | 2014-03-17 | 2014-02-23 03:45 | 2014-04-18 08:00 | 1772.5 | SHALLOW WATER | 1813 | 1296 | N/A | 27690000 | N/A | 44.28 | N/A | N/A | 24.36 | 24.36 | SW EXP SLIM HOLE | SW EXP SLIM HOLE | 1.2 | 1.2 | 385 | 385 | 930 | 930 | Yes | 2.45 | yes | 1463 | Yes | 2346 | [26 empty] | Exist
N/A | 2018-02-12 | HESS | PM | BERGADING | BERGADING-A6(G) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 2705.27 | 2671.75 | N/A | N/A | N/A | N/A | 66260000 | 126 | NO | N/A | DRY TREE | 2017-02-04 | 2017-02-04 13:00 | 2017-12-11 | 5007.92 | SHALLOW WATER | 5108.5 | 2709.96 | N/A | N/A | N/A | N/A | 54820000 | 145.02 | 23.9 | 23.7 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.6 |  | 1494 |  | 3269 | [6 empty] | 13.64 | 6960000 |  |  | SANDSTONE | HPHT | CASED HOLE | NO | NO | 4-1/2" | 1.0 | SINGLE | 22CR | 0 | True |  | 718 | 8.4 | SEAWATER/DRILLWATER | NO | NO | Exist
N/A | 2013-04-03 | PCSB | SK | D21 | D21-A2 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 50.59 | 3352.33 | 1936.91 | N/A | N/A | N/A | N/A | 19186550 | 32.1 | NO | N/A | DRY TREE | 2012-12-14 | 2012-12-14 | 2013-02-13 | 3216.09 | SHALLOW WATER | 3306.92 | 2021.03 | N/A | N/A | N/A | N/A | 15776212.36 | 33.5 | 12.94 | 12.94 | SW DEV C2 |  | 2 |  | 725 |  | 1325 |  | 2.03 |  | 1028 |  | 1454 | [6 empty] | 10.83 | 3870453.02 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 3.0 | SINGLE | L80 13CR | 237 | False | NONE | 13CR | 10.8 | NABR | NO | NO | Exist
N/A | 2015-06-12 | PCSB | PM | ANGSI | ANGSI-B20ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 2794 | 1672 | N/A | N/A | N/A | N/A | 25739615 | 41.89 | NO | N/A | DRY TREE | 2015-05-03 | 2015-03-29 19:00 | 2015-05-24 08:00 | 2549.82 | SHALLOW WATER | 2652 | 1671.78 | N/A | N/A | N/A | N/A | 14038542.52 | 28.88 | 0.8 | 0.8 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | 2.06 |  | 873 |  | 1753 | [6 empty] | 4.76 | 3737995.14 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 843.217 | True | NONE | 9CR | 9 | NACL | NO | NO | Exist
N/A | 2013-08-14 | PCSB | SB | SAMARANG | SM-105 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 10.06 | 1505.64 | 1427.57 | N/A | N/A | N/A | N/A | 12792640.18 | 22.94 | NO | N/A | N/A | 2013-06-07 15:00 | 2013-06-07 15:00 | 2013-07-17 19:00 | 1488.57 | SHALLOW WATER | 1536.12 | 1445.78 | N/A | N/A | N/A | N/A | 11841232.98 | 20.69 | 0.48 | 0.48 | SW DEV C1 |  | 1.7 |  | 720 |  | 1270 |  | 2.29 |  | 1022.61 |  | 2314.91 | [27 empty] | Exist
N/A | 2015-05-26 | IPC | PM | BERTAM | BERTAM A-7 | APPRAISAL CUM DEV/DEVELOPMENT | WEST PROSPERO | JACK UP | 74.7 | 3060.6 | 1657.34 | N/A | N/A | N/A | N/A | 23500000 | 42.6 | SIDETRACK | N/A | N/A | 2014-08-11 | 2014-08-08 | 2015-04-16 15:00 | 2906.26 | SHALLOW WATER | 3025 | 1658.1 | N/A | N/A | N/A | N/A | 19300000 | 32.3 | 2 | 2 | SW DEV C2 |  | 3.2 |  | 1300 |  | 2230 |  | 2.1 |  | 1162.78 |  | 1592.72 | [27 empty] | Exist
N/A | 2014-08-12 | HESS | PM | BUNGA KAMANJU | BUNGA KAMANJU-1 RDR1 | EXPLORATION/APPRAISAL | HAKURYU-5 | SEMI-SUB | 63.4 | 2983.85 | 2983.85 | 24400000 | 32438230 | 39.3 | 67.2 | N/A | N/A | NO | N/A | N/A | 2014-05-18 | 2014-05-10 06:00 | 2014-06-21 09:00 | 2455.65 | SHALLOW WATER | 2553.19 | 2553.19 | 18700000 | N/A | 42.15 | N/A | N/A | N/A | 15 | 13.5 | SW EXP C3 |  | 3.8 |  | 2125 |  | 3315 |  | 2.8 |  | 1565 |  | 2776 | [27 empty] | Exist
N/A | 2015-10-16 | PCSB | SB | PENDEKAR | PENDEKAR-1 | EXPLORATION/APPRAISAL | MAERSK CONVINCER | JACK UP | 83.7 | 3180 | 3180 | 52488545.72 | 52488545.72 | 85 | 85 | N/A | N/A | SIDETRACK | N/A | N/A | 2015-05-16 22:00 | 2015-05-03 03:30 | 2015-08-18 14:00 | 1957.85 | SHALLOW WATER | 2076 | 2074 | N/A | 58334712.43 | N/A | 107.44 | N/A | N/A | 11.84 | 11.84 | No DMS category. Having value but not sure refering which version | [7 empty] | 6.58 |  | 3529 |  | 4326 | [27 empty] | Exist
N/A | 2023-07-11 | PTTEP | SK | WEST PATRICIA | WPPB-17 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.2 | 1780.23 | 1076.71 | N/A | N/A | N/A | N/A | 6675190 | 13.02 | NO | N/A | DRY TREE | 2022-06-21 | 2022-06-19 21:00 | 2022-11-06 18:00 | 1026.2 | SHALLOW WATER | 1118 | 974 | N/A | N/A | N/A | N/A | 19455107.14 | 38.19 | 20.85 | 20.85 | SW DEV SLIM HOLE (With Offline Capability Rig) |  | 1.1 |  | 420 |  | 680 |  | 6.37 |  | 3061.6 |  | 3554.9 | [6 empty] | 3.4 | 2129820 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 13CR | 55 | True |  | L80 13CR | 8.6 | NACL/NABR | NO | NO | Exist
N/A | N/A | PTTEP | SK | SASA | SASA-16 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 2160.7 | 1606.65 | N/A | N/A | N/A | N/A | 5481251.18 | 11.84 | NO | N/A | DRY TREE | 2021-08-10 | N/A | N/A | 2005.15 | SHALLOW WATER | 2092 | 1565.35 | N/A | N/A | N/A | N/A | 5481251.17 | 11.8 | 5.65 | 5.65 | SW DEV C2 |  | 2 |  | 725 |  | 1295 |  | 0.9 |  | 370 |  | 436 | [6 empty] | 0.67 | 1022736 |  |  | SANDSTONE | NORMAL | CASED HOLE CEMENTED MONOBORE | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 115 | False |  | L80 | 8.6 | SEAWATER/DRILLWATER | NO | NO | Exist
N/A | 2014-07-17 | PTTEP | SB | SIAKAP NORTH PETAI | S-SW1-P9 | APPRAISAL CUM DEV/DEVELOPMENT | OCEAN ROVER | SEMI-SUB | 1394.4 | 3080 | 2460 | N/A | N/A | N/A | N/A | 54331710 | 41 | SIDETRACK | N/A | WET TREE | 2014-02-12 | 2014-02-12 | 2014-07-02 | 1029.4 | DEEP WATER | 2450 | 2393 | N/A | N/A | N/A | N/A | 43184040 | 32 | 2.73 | 2.73 | DW DEV C3 (Dry Tree) |  | 5.1 |  | 1525 |  | 3370 |  | 3.69 |  | 4978 |  | 9209 | [6 empty] | 17.95 | 19815305.85 |  |  | SANDSTONE | NORMAL | OPEN HOLE GRAVEL PACK | NO | NO | 4-1/2" | 1.0 | VIT | L80 13CR | 1099.135 | True |  | L80 13CR | 10.6 | NABR | 3 | NO | Exist
N/A | N/A | SHELL | SB | MALIKAI NFE | MLK-103 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 2499.24 | 1439.5 | N/A | N/A | N/A | N/A | 19956723 | 33 | NO | N/A | N/A | 2014-11-10 14:00 | 2014-10-16 21:30 | 2018-01-24 | 1895.92 | DEEP WATER | 2427.31 | 1432.62 | N/A | N/A | N/A | N/A | 16343216 | 42.83 | 26 | 26 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | 2.36 |  | 1872.41 |  | 3202.81 | [27 empty] | Exist
N/A | 2024-03-27 | PCSB | SK | BOKOR | BOKOR-E503 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 1219.14 | 1148.13 | N/A | N/A | N/A | N/A | 10444407.27 | 20.57 | SUSPEND | N/A | DRY TREE | 2024-01-08 | 2024-01-08 | 2024-01-27 20:00 | 1130 | SHALLOW WATER | 1239 | 1146.87 | N/A | N/A | N/A | N/A | 7658577.17 | 16.9 | 2.96 | 2.96 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.6 |  | 1270 |  | 2239 | [6 empty] | 7.72 | 3817035 | 1.9 | 939 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | DUAL | L80 13CR | 915 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
N/A | 2020-02-24 | SAPURA OMV | SK | BAKONG | BAKONG A-02 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 85 | 1864 | 1784.5 | N/A | N/A | N/A | N/A | 14954542 | 27.77 | NO | N/A | N/A | 2019-10-31 | 2019-10-31 | 2019-12-30 | 1717.76 | SHALLOW WATER | 1845 | 1804.44 | N/A | N/A | N/A | N/A | 10812704.55 | 33.36 | 32.38 | 24.73 | SW DEV C4 |  | 2.5 |  | 1010 |  | 1705 |  | 2.34 |  | 627.16 |  | 1395.3 | [27 empty] | Exist
N/A | N/A | SHELL | SB | MALIKAI | MLK-120 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 485.98 | 2035.66 | 1255.71 | N/A | N/A | N/A | N/A | 22234050 | 34.56 | NO | N/A | N/A | 2014-10-20 | 2014-10-20 | 2017-06-05 | 1502.74 | DEEP WATER | 2034.14 | 1299.18 | N/A | N/A | N/A | N/A | 15830000 | 22.91 | 3.06 | 3.06 | DW DEV C2 (Dry Tree) |  | 4.1 |  | 2635 |  | 3590 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2020-03-06 | PCSB | SK | BARONIA | BN-82ST1 | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-6 | JACK UP | 75.6 | 3676.93 | 3072.51 | N/A | N/A | N/A | N/A | 16585637.92 | 44.92 | NO | N/A | N/A | N/A | 2019-01-09 15:00 | 2019-05-06 15:00 | 3590.48 | SHALLOW WATER | 3714.72 | 3076.74 | N/A | N/A | N/A | N/A | 25353354.35 | 94.75 | 30.12 | 29.6 | SW HP/HPHT |  | 5 |  | 2360 |  | 4280 |  | 5.39 |  | 1622.73 |  | 2127.08 | [27 empty] | Exist
N/A | 2014-08-28 | COASTAL ENERGY KBM (CEKBM) | PM | BANANG | BANANG-B2 | APPRAISAL CUM DEV/DEVELOPMENT | ATWOOD MANTA | JACK UP | 58.21 | 2986.89 | 1701.62 | N/A | N/A | N/A | N/A | 10907402 | 22.11 | NO | N/A | N/A | 2014-04-18 | 2014-04-15 | 2014-05-27 | 3227.98 | SHALLOW WATER | 3322.16 | 1703.84 | N/A | N/A | N/A | N/A | 12449358 | 33.73 | 11.86 | 11.86 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2014-02-24 | EMEPMI | PM | DAMAR | DAMAR-A10 | APPRAISAL CUM DEV/DEVELOPMENT | SEADRILL WEST LEDA | JACK UP | 55.7 | 2722.59 | 2031.07 | N/A | N/A | N/A | N/A | 20600000 | 39.12 | NO | N/A | N/A | 2013-11-08 | 2013-11-08 20:30 | 2014-01-12 12:00 | 2624.51 | SHALLOW WATER | 2724 | 2031.78 | N/A | N/A | N/A | N/A | 15200000 | 30.17 | 2.92 | 2.92 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2018-12-20 | ENQUEST | PM | SELIGI | SEC-39 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 72.1 | 2579 | 2049 | N/A | N/A | N/A | N/A | 8774697 | 24.6 | NO | N/A | DRY TREE | 2018-05-20 | 2018-05-15 16:00 | 2018-07-11 | 2486.4 | SHALLOW WATER | 2592 | 2055 | N/A | N/A | N/A | N/A | 8381789 | 34.4 | 0.51 | 0.51 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1830 |  | 1.9 |  | 444 |  | 903 | [6 empty] | 9.9 | 2326115 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 4.0 | DUAL | L80 13CR | 75.463 | False | NONE | L80 13CR | 9.9 | NACL | NO | NO | Exist
N/A | 2015-05-27 | PCSB | PM | ARENGA | ARENGA-1 | EXPLORATION/APPRAISAL | PERISAI PACIFIC-101 | JACK UP | 61 | 1785 | 1785 | 14476123.31 | 14476123.31 | 25.4 | 25.4 | N/A | N/A | NO | N/A | N/A | 2015-03-17 | 2015-03-14 17:30 | 2015-03-31 20:00 | 1706.6 | SHALLOW WATER | 1802.5 | 1802 | 9828593.25 | N/A | 17.27 | N/A | N/A | N/A | 2.89 | 2.89 | SW EXP SLIM HOLE |  | 1.2 |  | 385 |  | 930 |  | 1.1 |  | 685.17 |  | 1124.52 | [27 empty] | Exist
N/A | 2018-01-25 | HESS | PM | BERGADING | BERGADING-A5(N) | APPRAISAL CUM DEV/DEVELOPMENT | NAGA-8 | JACK UP | 57.36 | 3647.06 | 2771.11 | N/A | N/A | N/A | N/A | 43796975 | 83 | SIDETRACK | N/A | N/A | 2017-02-09 23:00 | 2017-02-09 20:30 | 2017-11-24 17:30 | 3512.65 | SHALLOW WATER | 3613.23 | 2747.64 | N/A | N/A | N/A | N/A | 45000000 | 94.4 | 40.52 | 40.5 | SW HPHT/HT |  | 3.7 |  | 1585 |  | 3400 |  | 3.5 |  | 1900 |  | 3897 | [27 empty] | Exist
N/A | 2015-04-29 | PCSB | PM | ANGSI | ANGSI-B32 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 69 | 3480 | 1691 | N/A | N/A | N/A | N/A | 24018380 | 34.09 | NO | N/A | DRY TREE | 2014-09-30 10:30 | 2014-09-30 10:30 | 2015-03-29 19:00 | 3496.82 | SHALLOW WATER | 3600 | 1725 | N/A | N/A | N/A | N/A | 18500000 | 28.98 | 0.95 | 0.95 | SW DEV C1 |  | 2.1 |  | 700 |  | 1220 |  | 1.59 |  | 648.84 |  | 1612.39 | [6 empty] | 7.73 | 5643439.04 |  |  | SANDSTONE | NORMAL | CASED HOLE | NO | NO | 3-1/2" | 2.0 | SINGLE | L80 | 52.496 | True | NONE | 9CR | 8.7 | NACL | NO | NO | Exist
N/A | N/A | SHELL | SB | MALIKAI | MLK-108 | APPRAISAL CUM DEV/DEVELOPMENT | SAPURA ESPERANZA | SEMI-SUB | 486.06 | 1491.62 | 1446.21 | N/A | N/A | N/A | N/A | 19900000 | 42.9 | NO | N/A | N/A | 2014-10-28 11:00 | N/A | N/A | 2814.16 | DEEP WATER | 3345.63 | 1564.21 | N/A | N/A | N/A | N/A | 14769520 | 30.15 | 1.04 | 1.04 | DW DEV C3 (Wet Tree) |  | 3.6 |  | 2590 |  | 4150 |  | 3.87 |  | 1664 |  | 2628 | [27 empty] | Exist
N/A | 2014-07-08 | COASTAL ENERGY KBM (CEKBM) | PM | BANANG | BANANG-B1 | APPRAISAL CUM DEV/DEVELOPMENT | ATWOOD MANTA | JACK UP | 58.21 | 2268.52 | 1773.06 | N/A | N/A | N/A | N/A | 8706987 | 17.82 | NO | N/A | N/A | 2014-03-13 | 2014-03-11 | 2014-06-12 | 2358.12 | SHALLOW WATER | 2452.3 | 1743.37 | N/A | N/A | N/A | N/A | 8949982 | 24.5 | 3.23 | 3.23 | SW DEV C2 |  | 3.2 |  | 1300 |  | 1600 |  | No |  | No |  | No | [27 empty] | Exist
N/A | 2018-05-02 | PCSB | PM | DULANG | DULANG-D20ST1 | APPRAISAL CUM DEV/DEVELOPMENT | T-9 | TENDER ASSISTED DRILLING RIG (TADR) | 74.22 | 2023 | 1521.2 | N/A | N/A | N/A | N/A | 13724086 | 30.72 | NO | N/A | N/A | 2017-11-15 | 2017-10-15 | 2018-03-13 07:00 | 1991.23 | SHALLOW WATER | 2098 | 1515.2 | N/A | N/A | N/A | N/A | 10877057 | 34.79 | 6.2 | 4.2 | SW DEV ST 1HS |  | 1.8 |  | 600 |  | 2170 |  | 1.71 |  | 528.75 |  | 1818.48 | [27 empty] | Exist
N/A | N/A | PTTEP | SK | SOUTH ACIS | SASA-17 | APPRAISAL CUM DEV/DEVELOPMENT | BORR GUNNLOD | JACK UP | 40.85 | 1801.5 | 1538.7 | N/A | N/A | N/A | N/A | 3433741 | 6.44 | NO | N/A | N/A | 2021-10-05 07:00 | 2021-07-02 03:30 | 2021-10-20 01:30 | 1721.15 | SHALLOW WATER | 1808 | 1545.7 | N/A | N/A | N/A | N/A | 3773937 | 7.72 | 0 | 0 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 1.07 |  | 464 |  | 636 | [27 empty] | Exist
N/A | 2024-05-29 | PCSB | SK | BOKOR | BOKOR-E502 | APPRAISAL CUM DEV/DEVELOPMENT | PVD-6 | JACK UP | 69.49 | 1409.89 | 1144.91 | N/A | N/A | N/A | N/A | 8956274 | 23.05 | NO | N/A | DRY TREE | N/A | 2024-03-21 04:30 | 2024-04-21 03:00 | 1296 | SHALLOW WATER | 1405 | 1148.57 | N/A | N/A | N/A | N/A | 9988882 | 17.96 | 11.95 | 11.66 | SW DEV C1 |  | 2.2 |  | 830 |  | 1380 |  | 2.61 |  | 1454 |  | 2349 | [6 empty] | 6.82 | 3351470 | 1.48 | 727 | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | DUAL | L80 13CR | 1247 | True | INNER STRING WITH SSD | L80 13CR | 9 | NACL | NO | NO | Exist
N/A | 2015-02-25 | PCSB | PM | ANGSI | ANGSI-B19 | APPRAISAL CUM DEV/DEVELOPMENT | T-10 | TENDER ASSISTED DRILLING RIG (TADR) | 68 | 2861 | 1672 | N/A | N/A | N/A | N/A | 25923380 | 46.52 | NO | N/A | DRY TREE | 2014-12-07 | 2014-10-09 | 2015-01-19 | 2787.82 | SHALLOW WATER | 2890 | 1672 | N/A | N/A | N/A | N/A | 25243452.34 | 55.6 | 30.91 | 9.61 | No DMS category. Having value but not sure refering which version | [7 empty] | 2.55 |  | 1369.11 |  | 2591.39 | [6 empty] | 6.72 | 5661902.78 |  |  | SANDSTONE | NORMAL | OPEN HOLE STAND ALONE SCREEN | NO | NO | 3-1/2" | 1.0 | SINGLE | L80 | 6119.065 | True | NONE | 9CR | 8.4 | SEAWATER/DRILLWATER | NO | NO | Exist
N/A | N/A | SHELL | SB | SOUTH FURIOUS | SF-15 | APPRAISAL CUM DEV/DEVELOPMENT | WEST VIGILANT | JACK UP | 49.07 | 1138.46 | 958.55 | N/A | N/A | N/A | N/A | 117390000 | 41.81 | SIDETRACK | N/A | N/A | 2014-11-20 14:00 | 2014-11-20 14:00 | 2015-03-09 15:00 | 471.52 | SHALLOW WATER | 563.72 | 498.76 | N/A | N/A | N/A | N/A | 28597516.15 | 40.94 | 9.85 | 9.85 | SW DEV ST 2HS |  | 2.4 |  | 795 |  | 1580 |  | No |  | No |  | No | [27 empty] | Exist

## Data Upload-prod
PIC | Status | ReportJournalId | WellId | WellName | Id | IsReport | Type | ContentType | Size | UploadAt | CreatedBy | CreatedAt | UpdatedBy | UpdatedAt | IsSuccess | DeletedBy | IsDeleted | FileName | FileName (ETL) |  | FileSize | Path | Availability
Mursyid | Yes | 8AA810DC-2B3D-46BD-9491-9F16C59EE792 | DE852130-D7D6-4B59-A0FB-001DEBCCE3EB | SAMARANG-B123 | C4BFE42D-6C6A-4722-8265-7492D0FEB38F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B123 NOOP.pdf | SAMARANG-B123 NOOP.pdf | Yes |  | Uploads\c4bfe42d-6c6a-4722-8265-7492d0feb38f.pdf | Exist
Mursyid | Yes | 5FF025AE-E7FD-4902-ACDD-C7BA0594F8FE | DE852130-D7D6-4B59-A0FB-001DEBCCE3EB | SAMARANG-B123 | 0A421437-1633-46AD-BC15-0B7E164DB2E2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B123 FWR.pdf | SAMARANG-B123 FWR.pdf | Yes |  | Uploads\0a421437-1633-46ad-bc15-0b7e164db2e2.pdf | Exist
Mursyid | Yes | 5E04E6D7-8AFE-4D45-8E01-992A7CABFC22 | 59815EB3-C163-450B-A924-00CD25EED857 | HADRAH-1 | F2A753FA-4F94-4E04-BA19-FD5DD3C20070 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hadrah-1 Final Well Report_with attachments.pdf | Hadrah-1 Final Well Report_with attachments.pdf | Yes |  | Uploads\f2a753fa-4f94-4e04-ba19-fd5dd3c20070.pdf | Exist
Mursyid | Yes | 08E63DE3-4F92-467E-9934-5744194F510A | 59815EB3-C163-450B-A924-00CD25EED857 | HADRAH-1 | 28E6B044-E20C-48C0-9464-8C0385877FCA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hadrah-1 NOOP.pdf | Hadrah-1 NOOP.pdf | Yes |  | Uploads\28e6b044-e20c-48c0-9464-8c0385877fca.pdf | Exist
Mursyid | Yes | 9C582344-803A-4408-B364-165E54F1AC33 | E2E37CDE-4762-4283-8993-00D4920B267D | WD-A13 | F1BD3C71-CE1A-4942-9D06-A028C51DD1D4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3WDESWS14_WD-A13.pdf | PMO3WDESWS14_WD-A13.pdf | Yes |  | Uploads\f1bd3c71-ce1a-4942-9d06-a028c51dd1d4.pdf | Exist
Mursyid | Yes | A7CCB483-E533-4705-9ABC-E4170E4CB088 | E2E37CDE-4762-4283-8993-00D4920B267D | WD-A13 | 908E1F2C-E3D8-4F44-8EF6-1EC2D56677F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3WDESWS49_WD-A13.pdf | PMO3WDESWS49_WD-A13.pdf | Yes |  | Uploads\908e1f2c-e3d8-4f44-8ef6-1ec2d56677f4.pdf | Exist
Mursyid | Yes | 2802568D-0803-40F3-8168-FC03FB34CE58 | C844197F-4206-492F-9856-010FFE56793F | SUMANDAK SELATAN-B16ST1 | 963A123D-1A47-4F8E-A984-359B05959C6C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report B16 ST2 rev 3.pdf | Petronas Final Well Report B16 ST2 rev 3.pdf | Yes |  | Uploads\963a123d-1a47-4f8e-a984-359b05959c6c.pdf | Exist
Mursyid | Yes | 75C6ECC4-711E-4529-973B-64E4C3CE7ECB | C844197F-4206-492F-9856-010FFE56793F | SUMANDAK SELATAN-B16ST1 | FB5E6977-EDDE-47A9-8D74-8CC0C45C66AD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B16 ST1 NOOP (FINAL).pdf | Sumandak Selatan B16 ST1 NOOP (FINAL).pdf | Yes |  | Uploads\fb5e6977-edde-47a9-8d74-8cc0c45c66ad.pdf | Exist
Mursyid | Yes | 9E3730FF-FD4F-43C6-92A6-61045B607718 | 1626FB0A-7458-414B-B820-015880FA6921 | D21-A3 | 5D18B9F3-4EA1-41F5-8B05-08B27AFA51CD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS47_D21-A3.pdf | SKO3D21-WS47_D21-A3.pdf | Yes |  | Uploads\5d18b9f3-4ea1-41f5-8b05-08b27afa51cd.pdf | Exist
Mursyid | Yes | 06D82BA6-E854-4453-BE79-1882F19FFFE1 | 1626FB0A-7458-414B-B820-015880FA6921 | D21-A3 | 6725064A-4CAD-40BA-A806-3A8CB1AF511F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS50_D21-A3.pdf | SKO3D21-WS50_D21-A3.pdf | Yes |  | Uploads\6725064a-4cad-40ba-a806-3a8cb1af511f.pdf | Exist
Mursyid | Yes | 692DEF30-8075-4FFB-A121-D02B881F214C | 024D8DAB-F83E-4087-8CA7-016D8C5687AC | KMSE-A1 | E02CC16F-4304-4215-9107-34A100D9B785 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE-A1-FWR.pdf |  | No |  | Uploads\e02cc16f-4304-4215-9107-34a100d9b785.pdf | Exist
Mursyid | Yes | 8FD94B8F-6F3E-458C-8D62-DD64F3CCB550 | 024D8DAB-F83E-4087-8CA7-016D8C5687AC | KMSE-A1 | C1707397-8860-41BE-811B-55766483FDD8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE A1_NOOP_2013_SK.pdf | KMSE A1_NOOP_2013_SK.pdf | Yes |  | Uploads\c1707397-8860-41be-811b-55766483fdd8.pdf | Exist
Mursyid | Yes | FB8E0A8B-2E89-4B43-846F-FED38257C652 | 5E15C965-E999-48C8-9069-01877D2A515F | DULANG-D10ST1 (WI) | 49B1239B-C9CC-44EC-A244-675514BD5F66 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG-D10ST1 FWR.pdf | DULANG-D10ST1 FWR.pdf | Yes |  | Uploads\49b1239b-c9cc-44ec-a244-675514bd5f66.pdf | Exist
Mursyid | Yes | C33F0AD0-0E2D-4FF6-B493-128A3680FADA | 5E15C965-E999-48C8-9069-01877D2A515F | DULANG-D10ST1 (WI) | 32AB8B2B-48C2-4149-BF0C-581722E48E7F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang EMP D10ST1 (W1) - WI Final Submission to MPM.pdf | Dulang EMP D10ST1 (W1) - WI Final Submission to MPM.pdf | Yes |  | Uploads\32ab8b2b-48c2-4149-bf0c-581722e48e7f.pdf | Exist
Mursyid | Yes | 1BA09680-BDD0-4F15-8448-4F3976417F1C | 16119A4E-13CE-49EC-953A-023BB4B36713 | BENTARA-A4 | EB9CF70E-C7D9-4DD3-B329-6C976EE0E827 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bentara-A4 Final Well Report_.pdf | Bentara-A4 Final Well Report_.pdf | Yes |  | Uploads\eb9cf70e-c7d9-4dd3-b329-6c976ee0e827.pdf | Exist
Mursyid | Yes | 9492E4B7-C6B1-47ED-BC1D-D8F7EBF4CB75 | 16119A4E-13CE-49EC-953A-023BB4B36713 | BENTARA-A4 | 71E2CFC6-F653-4CEB-93A7-3BE85AF92416 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bentara-A4_Signed_rev01.pdf | NOOP Bentara-A4_Signed_rev01.pdf | Yes |  | Uploads\71e2cfc6-f653-4ceb-93a7-3be85af92416.pdf | Exist
Mursyid | Yes | 9325DC20-1891-4F21-8CFB-1E9D80830BAE | 853C8EE9-7432-41BC-A655-024326B964D0 | OPHIR-A3 | 9B2021DE-FE26-4D41-A86D-3CF9D89BECC6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | OPHIR-A3 EOWR [FINAL].pdf | OPHIR-A3 EOWR [FINAL].pdf | Yes |  | Uploads\9b2021de-fe26-4d41-a86d-3cf9d89becc6.pdf | Exist
Mursyid | Yes | 8226D588-54E3-4054-8DA7-A7E421DFE6A2 | 853C8EE9-7432-41BC-A655-024326B964D0 | OPHIR-A3 | CD1CD901-F56C-44B5-94C6-6B34D541C2C9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Ophir-A3 Azry.pdf | NOOP Ophir-A3 Azry.pdf | Yes |  | Uploads\cd1cd901-f56c-44b5-94c6-6b34d541c2c9.pdf | Exist
Mursyid | Yes | EA7128A4-2AFA-484B-BA6F-2B537FD225C6 | 90ABE30C-CFE5-4B96-AD6A-029E6883FD37 | D18-208A | 21EBEC4F-0D88-464F-8D4A-162F5407907F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-GL29_D18_208A.pdf | SKO3D18-GL29_D18_208A.pdf | Yes |  | Uploads\21ebec4f-0d88-464f-8d4a-162f5407907f.pdf | Exist
Mursyid | Yes | 41F76A10-EB81-4CD3-911F-4F373500EE57 | 90ABE30C-CFE5-4B96-AD6A-029E6883FD37 | D18-208A | AA2252D7-590F-43EE-9CF7-88DBD8E45919 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D-18 208 A Final Well Report 208A-OP6 Signed.pdf | D-18 208 A Final Well Report 208A-OP6 Signed.pdf | Yes |  | Uploads\aa2252d7-590f-43ee-9cf7-88dbd8e45919.pdf | Exist
Mursyid | Yes | 1B0340CC-880F-4F44-BADA-9A2397381E8F | 56C05C64-A50C-4B2A-802E-02D40CDEE213 | BUNGA KANGSAR-1 | 37AD2524-37E7-4E17-9815-CFB73152015E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Kangsar-1 NOOP.pdf | Bunga Kangsar-1 NOOP.pdf | Yes |  | Uploads\37ad2524-37e7-4e17-9815-cfb73152015e.pdf | Exist
Mursyid | Yes | 72F451A6-55FD-4566-A61E-D7B8A3E61EC5 | 56C05C64-A50C-4B2A-802E-02D40CDEE213 | BUNGA KANGSAR-1 | 639814D0-FA66-46D5-AC1E-3DA444319404 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Kangsar-1 n ST1 EoWR - Signed.pdf | Bunga Kangsar-1 n ST1 EoWR - Signed.pdf | Yes |  | Uploads\639814d0-fa66-46d5-ac1e-3da444319404.pdf | Exist
Mursyid | Yes | D9D333FA-0B6F-4C84-9F21-B6BEF1D5C00A | A1A933A4-9D40-420C-89FE-0323004F37C0 | F14-107 | 907F858F-735B-460C-89E8-77A3C270C6E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-107 FDCR.pdf | F14-107 FDCR.pdf | Yes |  | Uploads\907f858f-735b-460c-89e8-77a3c270c6e8.pdf | Exist
Mursyid | Yes | 7AEB8C5F-3F31-4E4C-A8EE-43CAD0DB7FE2 | A1A933A4-9D40-420C-89FE-0323004F37C0 | F14-107 | 8C25344F-4963-4A7F-98BA-15C138FE1A9C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F14-GL02_F14-A104, F14-A105, F14-A107_SHELL_NOOP.pdf | SKO3F14-GL02_F14-A104, F14-A105, F14-A107_SHELL_NOOP.pdf | Yes |  | Uploads\8c25344f-4963-4a7f-98ba-15c138fe1a9c.pdf | Exist
Mursyid | Yes | CC046533-72C1-4CA5-9820-D1CA438DAE45 | 216A2CEC-A146-4481-B58F-042860677FDC | SJ-105B | A1566789-2451-40A3-B609-81788A5C796C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hibiscus Platform St Joseph well SJ-105B NOOP.pdf | Hibiscus Platform St Joseph well SJ-105B NOOP.pdf | Yes |  | Uploads\a1566789-2451-40a3-b609-81788a5c796c.pdf | Exist
Mursyid | Yes | C685184F-CD37-4521-A21E-F1ED5F504419 | 216A2CEC-A146-4481-B58F-042860677FDC | SJ-105B | 683EED7D-E49B-4E6C-B767-B83ECABF3F77 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-105B EOWR (PCSB JV).pdf | SJ-105B EOWR (PCSB JV).pdf | Yes |  | Uploads\683eed7d-e49b-4e6c-b767-b83ecabf3f77.pdf | Exist
Mursyid | Yes | 3CB3E716-DFBA-466E-B983-4943844F34C9 | AA5EE92B-3C85-4669-B458-04982D57F884 | SATONG-1 | E0622FC5-A821-4C3B-A8DE-CFF149BBCF17 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Satong-1_EOWR_20-June-2024_Signed.pdf | Satong-1_EOWR_20-June-2024_Signed.pdf | Yes |  | Uploads\e0622fc5-a821-4c3b-a8de-cff149bbcf17.pdf | Exist
Mursyid | Yes | D09E6C10-5361-4907-B980-B15A2B6D6DEF | AA5EE92B-3C85-4669-B458-04982D57F884 | SATONG-1 | 2848C598-1106-4857-AC53-4809B7F04A78 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK405B_Satong-1_NOOP.pdf | SK405B_Satong-1_NOOP.pdf | Yes |  | Uploads\2848c598-1106-4857-ac53-4809b7f04a78.pdf | Exist
Mursyid | Yes | 5ECF0704-5652-44A8-8C70-6F0D2DB220C8 | 7B04A1F3-6C63-458A-9DD7-05338CA76373 | BESTARI-3 | C50ECEED-EA8C-47EA-BEF8-EE588E59224B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JXN-DWR-DRG-6-TCR-011-Rev.03 (FINAL)_Bestari-3_EOWR with Appendix.pdf | JXN-DWR-DRG-6-TCR-011-Rev.03 (FINAL)_Bestari-3_EOWR with Appendix.pdf | Yes |  | Uploads\c50eceed-ea8c-47ea-bef8-ee588e59224b.pdf | Exist
Mursyid | Yes | 11B07E50-C2B0-47A7-AF35-58FB019495F4 | 7B04A1F3-6C63-458A-9DD7-05338CA76373 | BESTARI-3 | A4F54413-7861-408B-A6B1-B32A431128B5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bestari-3 NOOP.pdf |  | No |  | Uploads\a4f54413-7861-408b-a6b1-b32a431128b5.pdf | Exist
Mursyid | Yes | 8C019F30-392E-4DCE-8632-76BD7BCA9905 | DD10A50F-B668-4097-82FB-062F0BEFFFBF | BRWA-17 | A074076C-196B-4972-8DB3-E3464433F3CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BRWA17.pdf | NOOP BRWA17.pdf | Yes |  | Uploads\a074076c-196b-4972-8db3-e3464433f3cd.pdf | Exist
Mursyid | Yes | 1E45B69E-C78A-400B-8216-783CD6D389D6 | DD10A50F-B668-4097-82FB-062F0BEFFFBF | BRWA-17 | 7DB6A500-455C-4031-9D46-C7558BAF9B13 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | VPSB-BEF3-DRL-WWR-0003 BRWA-17 Final Well Report Rev.1.pdf | VPSB-BEF3-DRL-WWR-0003 BRWA-17 Final Well Report Rev.1.pdf | Yes |  | Uploads\7db6a500-455c-4031-9d46-c7558baf9b13.pdf | Exist
Mursyid | Yes | 0384D4C4-7AFC-463A-9878-1A22D1A11744 | 8C9D4BBF-95D2-490B-82A4-0652024B90A1 | PESA-02 | C45EF873-F468-42E3-ACC8-6A5D3BC1AE7E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PEMANIS PESA-1, PESA-2, PESA-3 and PESA-4 NOOP Revised.pdf | PEMANIS PESA-1, PESA-2, PESA-3 and PESA-4 NOOP Revised.pdf | Yes |  | Uploads\c45ef873-f468-42e3-acc8-6a5d3bc1ae7e.pdf | Exist
Mursyid | Yes | 2A125C18-480B-468B-9731-DF24D0785D58 | 8C9D4BBF-95D2-490B-82A4-0652024B90A1 | PESA-02 | 9C463DFF-0A22-4B77-B88A-B2C7364349BD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PESA-2 EOWR FINAL (APPROVED).pdf | PESA-2 EOWR FINAL (APPROVED).pdf | Yes |  | Uploads\9c463dff-0a22-4b77-b88a-b2c7364349bd.pdf | Exist
Mursyid | Yes | AE4C98D3-7731-43E4-9834-7C32980803E1 | D2179E06-3BAA-4D3C-A29F-06A51D43ACD6 | PUTERI A-05 | 6BD835FF-3184-41A0-8603-42F41E09C4AC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Puteri A-5 End of Well Report - FINAL - signed.pdf | Puteri A-5 End of Well Report - FINAL - signed.pdf | Yes |  | Uploads\6bd835ff-3184-41a0-8603-42f41e09c4ac.pdf | Exist
Mursyid | Yes | C0BB2163-87F8-429B-8087-9406A91951E7 | D2179E06-3BAA-4D3C-A29F-06A51D43ACD6 | PUTERI A-05 | B9AE50FE-7783-41DF-8B4F-E1FE94897BD0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3PTRIGL04_PUTERI-A05_SOMV.pdf | PMO3PTRIGL04_PUTERI-A05_SOMV.pdf | Yes |  | Uploads\b9ae50fe-7783-41df-8b4f-e1fe94897bd0.pdf | Exist
Mursyid | Yes | 97BFA078-E9FD-4462-9F8D-A8E6750D7282 | E06E5C20-4565-4AC3-BB56-06EBD3970E37 | BKC-17 | BFB119B0-5FCF-4894-AD29-F7B01946E94E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWAGL71_BKC-17ST1(C).pdf | PMO3BKWAGL71_BKC-17ST1(C).pdf | Yes |  | Uploads\bfb119b0-5fcf-4894-ad29-f7b01946e94e.pdf | Exist
Mursyid | Yes | 104C9AFD-33A2-4DDB-B821-5AB3E835C9C1 | E06E5C20-4565-4AC3-BB56-06EBD3970E37 | BKC-17 | CA34D36C-1813-449B-B2C8-09EACF5E947A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWAWSB5_BKC-17ST1(C).pdf | PMO3BKWAWSB5_BKC-17ST1(C).pdf | Yes |  | Uploads\ca34d36c-1813-449b-b2c8-09eacf5e947a.pdf | Exist
Mursyid | Yes | B1BA5BF3-8952-4573-8A97-76564FD873F4 | 90978F74-C776-46A8-B2CC-06FF8CB0ED05 | BERANTAI WEST-1 | A29CBF93-5C02-47E9-B051-126315B08A52 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Berantai West.pdf | NOOP Berantai West.pdf | Yes |  | Uploads\a29cbf93-5c02-47e9-b051-126315b08a52.pdf | Exist
Mursyid | Yes | 9A7DA3BA-3772-40F9-BEEE-C01F0ACC01A9 | 90978F74-C776-46A8-B2CC-06FF8CB0ED05 | BERANTAI WEST-1 | 821ADA6E-4271-46F0-BD36-654B2A723C91 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRW-1 Final Well Report 2018-Final.pdf | BRW-1 Final Well Report 2018-Final.pdf | Yes |  | Uploads\821ada6e-4271-46f0-bd36-654b2a723c91.pdf | Exist
Mursyid | Yes | 7306B53A-D376-4F0F-B2DF-5E069DCA04F3 | E58C22EA-C774-4ED6-8796-072482B46DCD | TOMAN-1 | 10EB5179-8327-4EA8-BF91-814D97BAEE2F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TMANWS03_TOMAN-1.pdf | SKO3TMANWS03_TOMAN-1.pdf | Yes |  | Uploads\10eb5179-8327-4ea8-bf91-814d97baee2f.pdf | Exist
Mursyid | Yes | 7B507B7F-245C-4CC5-8E66-94365A3CE471 | E58C22EA-C774-4ED6-8796-072482B46DCD | TOMAN-1 | 10B4BC09-5717-4652-825E-307AD6235D4B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TMANWS01_TOMAN-1.pdf | SKO3TMANWS01_TOMAN-1.pdf | Yes |  | Uploads\10b4bc09-5717-4652-825e-307ad6235d4b.pdf | Exist
Mursyid | Yes | FB510231-D3EB-41AC-8A62-1B8432AD1D76 | 70EE8F9B-20C5-4567-9461-072BFA4D3F21 | TELOK-B7 | 97922E5C-16DD-4872-94E9-472221233477 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Telok B7 Final Well Report (MPM Submission).pdf | Telok B7 Final Well Report (MPM Submission).pdf | Yes |  | Uploads\97922e5c-16dd-4872-94e9-472221233477.pdf | Exist
Mursyid | Yes | 1F5C693A-2AD4-4D1F-A9B5-14B41E74A568 | 70EE8F9B-20C5-4567-9461-072BFA4D3F21 | TELOK-B7 | 26E9326C-9339-4D10-B1DE-FF5DF864DC8F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TELOWS58_TELOK-B7.pdf |  | No |  | Uploads\26e9326c-9339-4d10-b1de-ff5df864dc8f.pdf | Exist
Mursyid | Yes | EEEA4236-9924-4D3B-9499-626E2A28BD1F | 0A22AC6B-DDCD-42DF-A124-073F9E73111F | D21-A1 | DD36B1B2-5439-4647-8A85-B68CC43759F3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-GL11_BERANANG WEST-1_PCSB_NOOP.pdf | SKO3D21-GL11_BERANANG WEST-1_PCSB_NOOP.pdf | Yes |  | Uploads\dd36b1b2-5439-4647-8a85-b68cc43759f3.pdf | Exist
Mursyid | Yes | F10C99CE-4F45-4263-86D0-69689AAEA801 | 0A22AC6B-DDCD-42DF-A124-073F9E73111F | D21-A1 | AC73EF69-B808-49F2-8EBB-A2290E9138BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS66_BERANANG WEST-1_PCSB_FWR.pdf | SKO3D21-WS66_BERANANG WEST-1_PCSB_FWR.pdf | Yes |  | Uploads\ac73ef69-b808-49f2-8ebb-a2290e9138be.pdf | Exist
Mursyid | Yes | 5A3F6AE6-BFBE-42A4-B128-81F0019A03C7 | 3F58C90E-E39C-485F-A58A-07710A847553 | E06-106 | E931EA5D-6C92-4462-AB92-4011F2B495FD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-106 End of Well Report.pdf | E06-106 End of Well Report.pdf | Yes |  | Uploads\e931ea5d-6c92-4462-ab92-4011f2b495fd.pdf | Missing
Mursyid | Yes | AD77BF2F-9A1B-495E-8D1E-58AB44A16C6F | 3F58C90E-E39C-485F-A58A-07710A847553 | E06-106 | AAE22BEA-B16D-4E0B-8B6D-465ACCDD9479 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3E6--GL6008_E06-101-102-106-108_SHELL.pdf | E06-106 (N2) NOOP R2 Final - signed.pdf | No |  | Uploads\aae22bea-b16d-4e0b-8b6d-465accdd9479.pdf | Missing
Mursyid | Yes | 1AB305DF-3A58-4E80-B618-4EED30F78C97 | AC9164DC-3DFB-4E89-B845-07B6E935B1E7 | SEPAT-A4 | 77F4721D-BE69-4091-8B28-AF0CBAB2303F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sepat A4 FWR.pdf | Sepat A4 FWR.pdf | Yes |  | Uploads\77f4721d-be69-4091-8b28-af0cbab2303f.pdf | Exist
Mursyid | Yes | 2C0A2A4F-B103-4C60-91B3-7A37D6F88C8A | AC9164DC-3DFB-4E89-B845-07B6E935B1E7 | SEPAT-A4 | 7F483FA6-066D-41A7-B110-216CD556479B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL44_SEPAT-A4.pdf | PMO3SPATGL44_SEPAT-A4.pdf | Yes |  | Uploads\7f483fa6-066d-41a7-b110-216cd556479b.pdf | Exist
Mursyid | Yes | 4ECE03FF-0ED8-45C6-BCE9-6C255919C5C1 | 65C02843-ACE7-4E11-B4E5-08FB22C2C2D1 | BUNGA ANGGERIK A-4(C) | 6E07F49E-1879-4A82-AF07-B0AFFB59D796 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BAA_4C and 3E_Rev0_Final.pdf | NOOP - BAA_4C and 3E_Rev0_Final.pdf | Yes |  | Uploads\6e07f49e-1879-4a82-af07-b0affb59d796.pdf | Exist
Mursyid | Yes | E41DF2D7-27C0-4D9D-A041-03C5A0A9D95C | 65C02843-ACE7-4E11-B4E5-08FB22C2C2D1 | BUNGA ANGGERIK A-4(C) | 91609D82-5AB0-490E-B2D7-1068D091DDE5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NMB-DRI-RPT-01174.pdf | NMB-DRI-RPT-01174.pdf | Yes |  | Uploads\91609d82-5ab0-490e-b2d7-1068d091dde5.pdf | Exist
Mursyid | Yes | 172B7A70-8233-4C32-ABC8-88D61A519E60 | DCB9EA9A-6672-4E1F-AE2A-0946E9A5D490 | SERAWA-1 | A0918E0E-084F-4020-8CB2-82672D1457D4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SERAWA-1_NOOP_Internal.pdf | SERAWA-1_NOOP_Internal.pdf | Yes |  | Uploads\a0918e0e-084f-4020-8cb2-82672d1457d4.pdf | Exist
Mursyid | Yes | 97D93545-8C29-4ABC-9EC4-E98E30993431 | DCB9EA9A-6672-4E1F-AE2A-0946E9A5D490 | SERAWA-1 | 2092F69F-3526-498F-827A-735FEF7CC4F9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SERAWA-1 FWR ALFIAN SIGNED.pdf | SERAWA-1 FWR ALFIAN SIGNED.pdf | Yes |  | Uploads\2092f69f-3526-498f-827a-735fef7cc4f9.pdf | Exist
Mursyid | Yes | D7336E90-BE91-480E-A79D-FC0759B5A6C1 | 1D9CA263-7677-4D36-BCAF-095C8E03B23E | EC-A06 | 60E61C03-6403-49A4-AE5E-C0D1BAB93A08 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0004_Rev00 NOOP WELL EC-A06 (Slot 3A ECW-A Platform) Rev 00 DS.pdf | ECN-GEN-D-0004_Rev00 NOOP WELL EC-A06 (Slot 3A ECW-A Platform) Rev 00 DS.pdf | Yes |  | Uploads\60e61c03-6403-49a4-ae5e-c0d1bab93a08.pdf | Exist
Mursyid | Yes | F829C46B-07AB-467E-8F3A-634CC86E6D2D | 1D9CA263-7677-4D36-BCAF-095C8E03B23E | EC-A06 | 30B42411-1683-4893-8FDA-05B766470F79 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A06 Final Well Report (Final).pdf | EC-A06 Final Well Report (Final).pdf | Yes |  | Uploads\30b42411-1683-4893-8fda-05b766470f79.pdf | Exist
Mursyid | Yes | 0C24E71B-5821-442A-823B-6037117CFFE5 | 6A984092-1D9D-415B-8DB1-09CA3776E081 | TINGGI M-1 | 9874CF15-FB61-4242-A29E-EF2AF052824B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tinggi M-1 NOOP Internal PCSB (1).pdf | Tinggi M-1 NOOP Internal PCSB (1).pdf | Yes |  | Uploads\9874cf15-fb61-4242-a29e-ef2af052824b.pdf | Exist
Mursyid | Yes | 1DEBAF2F-63E4-4C3A-A833-4727BCDB14D6 | 6A984092-1D9D-415B-8DB1-09CA3776E081 | TINGGI M-1 | D8A10067-CA9F-4944-84DB-3993178489B4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tinggi M-1 FWR_Approved with attachments.pdf | Tinggi M-1 FWR_Approved with attachments.pdf | Yes |  | Uploads\d8a10067-ca9f-4944-84db-3993178489b4.pdf | Exist
Mursyid | Yes | 7242906A-D938-4886-8DCA-5063D11DEB8E | 67281EBF-8F93-4BF7-8093-0A0C9B005694 | SM-106 | 4C759E1D-9FBB-463B-A4DB-6CF796FC880B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL31_SM-106_PCSB_NOOP.pdf | SBO3SMRGGL31_SM-106_PCSB_NOOP.pdf | Yes |  | Uploads\4c759e1d-9fbb-463b-a4db-6cf796fc880b.pdf | Exist
Mursyid | Yes | B1C152C4-B50D-452B-A9C7-3AE14CA51117 | 67281EBF-8F93-4BF7-8093-0A0C9B005694 | SM-106 | A0D1ACD7-DFFC-4110-A143-E957D40E5A13 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSBS_SM-106_pcsb_fwr.pdf | SBO3SMRGWSBS_SM-106_pcsb_fwr.pdf | Yes |  | Uploads\a0d1acd7-dffc-4110-a143-e957d40e5a13.pdf | Exist
Mursyid | Yes | E813183C-A110-4955-BA60-FACAEF4B40D2 | 0F9F950C-67DD-45BC-A010-0A28F887FB78 | PAPRIKA-1 | D2CE0814-5BDD-43B7-A18A-3A2E6D3CE48A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Paprika-1 end of well report - combined.pdf | Paprika-1 end of well report - combined.pdf | Yes |  | Uploads\d2ce0814-5bdd-43b7-a18a-3a2e6d3ce48a.pdf | Exist
Mursyid | Yes | EBDE31C8-0E4F-4CF0-8268-FF2BDDEF8BDE | 0F9F950C-67DD-45BC-A010-0A28F887FB78 | PAPRIKA-1 | DCA0F3B2-439F-44AB-A3AA-D12E9E7862DE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Paprika-1_NOOP_signed.pdf | Paprika-1_NOOP_signed.pdf | Yes |  | Uploads\dca0f3b2-439f-44ab-a3aa-d12e9e7862de.pdf | Exist
Mursyid | Yes | 5B5A91EC-5D37-4D63-A98B-2D6DEF87915F | E3B4313E-954D-4297-83F6-0A5653045544 | NANGKA-1 | 003D052E-18B8-4422-BC60-1BA1875CB15B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Nangka-1 Drilling Final Well Report.pdf | Nangka-1 Drilling Final Well Report.pdf | Yes |  | Uploads\003d052e-18b8-4422-bc60-1ba1875cb15b.pdf | Exist
Mursyid | Yes | 073027B0-DF17-49E0-AD99-672DC1411B47 | E3B4313E-954D-4297-83F6-0A5653045544 | NANGKA-1 | 6DE1BEFC-B35E-48A3-86AC-03D54112E15F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK417 Nangka-1 NOOP Final.pdf | SK417 Nangka-1 NOOP Final.pdf | Yes |  | Uploads\6de1befc-b35e-48a3-86ac-03d54112e15f.pdf | Exist
Mursyid | Yes | 8D58A7D9-7C9C-4918-AE8A-5A0FC76CDA8A | A83022C6-F379-4B7B-AAD9-0A6B2FB1AEBF | SUMANDAK UTARA-1 | 8D93DEE0-52CB-4034-88DB-A4843922B686 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Utara 1 Final Well Report.pdf | Sumandak Utara 1 Final Well Report.pdf | Yes |  | Uploads\8d93dee0-52cb-4034-88db-a4843922b686.pdf | Exist
Mursyid | Yes | E79F15D0-47A2-4CD9-84B1-EE21B18EB02B | A83022C6-F379-4B7B-AAD9-0A6B2FB1AEBF | SUMANDAK UTARA-1 | 6EC59C10-DED2-4979-8CD5-794E7090461C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Utara NOOP-1.pdf | Sumandak Utara NOOP-1.pdf | Yes |  | Uploads\6ec59c10-ded2-4979-8cd5-794e7090461c.pdf | Exist
Mursyid | Yes | 9471972A-9D4C-4CB3-A600-6FB239612E8C | 47CEAC94-CCD6-4CEB-996E-0A8190E7E609 | WPPB-14 | E2A175F2-A646-45D4-91AF-2FBEC4091412 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK309-61-DNC-RP-0001-00_WPPB Infill Campaign EOWR.pdf | MY-SK309-61-DNC-RP-0001-00_WPPB Infill Campaign EOWR.pdf | Yes |  | Uploads\e2a175f2-a646-45d4-91af-2fbec4091412.pdf | Exist
Mursyid | Yes | 96462F02-3B7E-4219-AB61-A30BCB545CE4 | 47CEAC94-CCD6-4CEB-996E-0A8190E7E609 | WPPB-14 | 1C0CEF0E-5E0E-4ABC-9A16-747C6DF6CC4B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf | Yes |  | Uploads\1c0cef0e-5e0e-4abc-9a16-747c6df6cc4b.pdf | Exist
Mursyid | Yes | 7F6DAEF3-1496-4907-9D87-A9174B56FA69 | 64A76E03-5C03-40C7-8EC3-0AA5D98E04A1 | KUMANG-A6 | 13FF1C0A-36BE-468C-9017-EB0EF310D040 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KUMANG-A6ST1 FWR (Approved).pdf | KUMANG-A6ST1 FWR (Approved).pdf | Yes |  | Uploads\13ff1c0a-36be-468c-9017-eb0ef310d040.pdf | Exist
Mursyid | Yes | DAF7CD6C-348B-44A3-85B7-D7241130CE5F | 64A76E03-5C03-40C7-8EC3-0AA5D98E04A1 | KUMANG-A6 | E55FBE8A-62D1-46F9-A637-0A7B40CD5C62 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kumang-A6 NOOP.pdf | Kumang-A6 NOOP.pdf | Yes |  | Uploads\e55fbe8a-62d1-46f9-a637-0a7b40cd5c62.pdf | Exist
Mursyid | Yes | 697A3A70-5304-4813-8C7C-6C0C9C66E788 | 56E41B87-E96E-4B6C-9EAA-0B8E51FBD403 | GAGAU-1 | 1290B1A6-6407-4FBA-B334-2E383819973B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gagau-1_Apr2022_signed.pdf | Gagau-1_Apr2022_signed.pdf | Yes |  | Uploads\1290b1a6-6407-4fba-b334-2e383819973b.pdf | Exist
Mursyid | Yes | 3799BCA7-D13B-4D4D-845B-4B92BA6BA672 | 56E41B87-E96E-4B6C-9EAA-0B8E51FBD403 | GAGAU-1 | 597935D5-FE29-4781-89E0-B015E3BAB4DF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gagau-1_EndofWell_Report_Final_Signed.pdf | Gagau-1_EndofWell_Report_Final_Signed.pdf | Yes |  | Uploads\597935d5-fe29-4781-89e0-b015e3bab4df.pdf | Exist
Mursyid | Yes | 14298B22-9183-4136-BA90-313315969F0C | 181BD3CB-02E4-492C-A082-0C518E653C2E | SONGKET-1 | E2FA02F9-FF91-41FF-9741-52C7495CBDAF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SGKTWS04_SONGKET_1.pdf | PMO3SGKTWS04_SONGKET_1.pdf | Yes |  | Uploads\e2fa02f9-ff91-41ff-9741-52c7495cbdaf.pdf | Exist
Mursyid | Yes | 098BE62E-80AE-49B4-B4CD-8086229A2C09 | 181BD3CB-02E4-492C-A082-0C518E653C2E | SONGKET-1 | 92B6C94E-3EBB-4566-AF8E-67205FE5E4CA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SGKTWS02_SONGKET_1.pdf | PMO3SGKTWS02_SONGKET_1.pdf | Yes |  | Uploads\92b6c94e-3ebb-4566-af8e-67205fe5e4ca.pdf | Exist
Mursyid | Yes | F44FED2F-470D-42CF-B0DE-93B947DB7059 | ACCFDFE7-F5F2-4E40-B2CD-0CB1E3599D21 | BU-1 | B926807C-1FF8-4D33-9E9F-579BFCD81D30 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU1 NOOP.pdf | BU1 NOOP.pdf | Yes |  | Uploads\b926807c-1ff8-4d33-9e9f-579bfcd81d30.pdf | Exist
Mursyid | Yes | B232A11A-7BF7-4EA4-AC6E-C8FBC18A5729 | ACCFDFE7-F5F2-4E40-B2CD-0CB1E3599D21 | BU-1 | 47299C7C-FA51-44C8-A55F-6304CF77CFCD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU-1.BU1ST1 EOWR (Signed).pdf | BU-1.BU1ST1 EOWR (Signed).pdf | Yes |  | Uploads\47299c7c-fa51-44c8-a55f-6304cf77cfcd.pdf | Exist
Mursyid | Yes | 5BB78D51-16EA-4C2A-B90E-DDF48A3E2B3E | 02C107BA-5DF7-4606-B961-0CB248F56286 | BEKOK-BB19 | E71A7BED-DA17-4ED8-9DFB-52E946B43481 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BB-19ST2_Petronas Final Well Report_FINAL.pdf | BB-19ST2_Petronas Final Well Report_FINAL.pdf | Yes |  | Uploads\e71a7bed-da17-4ed8-9dfb-52e946b43481.pdf | Exist
Mursyid | Yes | 8C726C3D-030B-49F4-AC25-8F9E05DF4641 | 02C107BA-5DF7-4606-B961-0CB248F56286 | BEKOK-BB19 | DA3F9544-F048-41F9-BA66-B4BB58D50C66 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok BB19_Final Rev1_01052022.pdf | NOOP Bekok BB19_Final Rev1_01052022.pdf | Yes |  | Uploads\da3f9544-f048-41f9-ba66-b4bb58d50c66.pdf | Exist
Mursyid | Yes | 48BBFA13-09D3-4FDE-B641-53505506883F | 4CEB7F03-E6D4-46B3-A620-0CC484D62555 | D35A-111ST1 | 1A1917A3-28B3-4BA4-865A-A4A3A6D888B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPA-111ST1 End Of Well Report Final.pdf | D35DPA-111ST1 End Of Well Report Final.pdf | Yes |  | Uploads\1a1917a3-28b3-4ba4-865a-a4a3a6d888b7.pdf | Exist
Mursyid | Yes | F9804246-EC3D-4EF7-AFBE-061A6D7CFDC4 | 4CEB7F03-E6D4-46B3-A620-0CC484D62555 | D35A-111ST1 | D8FC57A6-F330-4841-8E4D-C1E817A5DFC7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35A-111ST1 NOOP Final1.pdf | D35A-111ST1 NOOP Final1.pdf | Yes |  | Uploads\d8fc57a6-f330-4841-8e4d-c1e817a5dfc7.pdf | Exist
Mursyid | Yes | EBC14FAE-D27B-4153-B398-114110345C15 | C05A392C-B2EA-43D3-8F55-0D02C275CBE6 | GK-W721C | 8C8C18FD-CBB8-4D7A-BE99-9A1C354F7AC1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR GK-W721C.pdf | EOWR GK-W721C.pdf | Yes |  | Uploads\8c8c18fd-cbb8-4d7a-be99-9a1c354f7ac1.pdf | Exist
Mursyid | Yes | CC68727C-A2A1-4C1A-817B-6CCE2FDE7839 | C05A392C-B2EA-43D3-8F55-0D02C275CBE6 | GK-W721C | 6996B6AF-57B4-411D-AB15-CC4C8C834756 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-W721C NOOP.pdf | GK-W721C NOOP.pdf | Yes |  | Uploads\6996b6af-57b4-411d-ab15-cc4c8c834756.pdf | Exist
Mursyid | Yes | BE200A28-1668-402A-9DFE-CE35517A2A18 | 58CE1F1C-5C0E-45CF-B89C-0D32CF989AEC | EAST BELUMUT A-10 ST1 | 88367B35-C598-48BC-B9CA-6E8728BCF29B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA10ST1 NOOP.pdf |  | No |  | Uploads\88367b35-c598-48bc-b9ca-6e8728bcf29b.pdf | Exist
Mursyid | Yes | CFD0CE73-F519-40BE-B256-C83F144395E0 | 58CE1F1C-5C0E-45CF-B89C-0D32CF989AEC | EAST BELUMUT A-10 ST1 | C684E8FF-D7A0-457B-AE12-ED2736873A10 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-10ST1 FWR_SOMV.pdf |  | No |  | Uploads\c684e8ff-d7a0-457b-ae12-ed2736873a10.pdf | Exist
Mursyid | Yes | 8412839E-EB89-4345-AA49-E3923EABCDCB | 2D8C210A-CD05-4ED9-804D-0D44A3D7A384 | D21-A7ST1 | 94B4A3DF-82D8-43B5-A704-3EBF180DC9BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21 U1ST1 (A7) EOWR.pdf | D21 U1ST1 (A7) EOWR.pdf | Yes |  | Uploads\94b4a3df-82d8-43b5-a704-3ebf180dc9be.pdf | Exist
Mursyid | Yes | FE370956-3921-43D4-AE0D-02187DC69EE6 | 2D8C210A-CD05-4ED9-804D-0D44A3D7A384 | D21-A7ST1 | 977F599D-4EED-41D5-9468-DB08910B95BF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-C2A-FB3 (D21-A7)NOOP.pdf |  | No |  | Uploads\977f599d-4eed-41d5-9468-db08910b95bf.pdf | Exist
Mursyid | Yes | 7089545A-2575-46D9-A058-4D91E180A936 | 7274F7BD-E2AD-45E9-B7C4-0E1A960E53EA | KERANJI-1 | DB7ECE0A-FB2D-4573-BC90-3BA18DDE31FE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3KNJIGL6274_KERANJI-1_FWR.pdf | PMO3KNJIGL6274_KERANJI-1_FWR.pdf | Yes |  | Uploads\db7ece0a-fb2d-4573-bc90-3ba18dde31fe.pdf | Exist
Mursyid | Yes | 855AC8E8-CA9F-4361-A658-B9123ECCF434 | 7274F7BD-E2AD-45E9-B7C4-0E1A960E53EA | KERANJI-1 | E6DC9DE2-51B0-4464-8879-AF5E18027EA7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Keranji-1 Notice of Operation (NOOP)_C1_signed_WGS.pdf | Keranji-1 Notice of Operation (NOOP)_C1_signed_WGS.pdf | Yes |  | Uploads\e6dc9de2-51b0-4464-8879-af5e18027ea7.pdf | Exist
Mursyid | Yes | BCF23954-3DDE-48BF-9F6A-C8C1D8617DC3 | 72545402-E934-4905-8407-0E38DABC371B | KALUNG EMAS-1 | 6E2455E0-217F-4A4F-A358-9E932A00601A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kalung Emas-1 NOOP - SK315 (2023).pdf | Kalung Emas-1 NOOP - SK315 (2023).pdf | Yes |  | Uploads\6e2455e0-217f-4a4f-a358-9e932a00601a.pdf | Exist
Mursyid | Yes | 8462A360-DA7D-4D0A-808E-487255BE818D | 72545402-E934-4905-8407-0E38DABC371B | KALUNG EMAS-1 | 792B5EB9-DB98-47EA-8B5A-88C392E76941 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kalung Emas-1 Final Well Report.pdf | Kalung Emas-1 Final Well Report.pdf | Yes |  | Uploads\792b5eb9-db98-47ea-8b5a-88c392e76941.pdf | Exist
Mursyid | Yes | 07B7DE95-C290-4ADF-939B-0984F2FC8F19 | 10018C77-4BE1-43E4-B058-0E3D77C1FD13 | RESAK-A19 | 1BF54ED1-3F5A-4497-965A-5212D2913883 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RESKWS3C_RESAK_A19.pdf | PMO3RESKWS3C_RESAK_A19.pdf | Yes |  | Uploads\1bf54ed1-3f5a-4497-965a-5212d2913883.pdf | Exist
Mursyid | Yes | E6060644-CB89-4F02-AAF3-7B8356D98598 | 10018C77-4BE1-43E4-B058-0E3D77C1FD13 | RESAK-A19 | 2644175F-56D8-4C63-9BC9-2666253A6597 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RESKWS3H_RESAK_A19.pdf | PMO3RESKWS3H_RESAK_A19.pdf | Yes |  | Uploads\2644175f-56d8-4c63-9bc9-2666253a6597.pdf | Exist
Mursyid | Yes | 29990A66-9FDA-483D-86CB-935E4448126F | B9C0218C-C674-4B3B-BF3B-0E564F158392 | BUJANG-7 | 1CC6570A-70A5-4655-B585-3239D4F874AB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BUJGWS51_BUJANG-7_FWR.pdf | PMO3BUJGWS51_BUJANG-7_FWR.pdf | Yes |  | Uploads\1cc6570a-70a5-4655-b585-3239d4f874ab.pdf | Exist
Mursyid | Yes | 7CE09D66-CF86-4A2F-BE33-02EA6307CC24 | B9C0218C-C674-4B3B-BF3B-0E564F158392 | BUJANG-7 | 05C8B027-F774-4DDD-832F-A868B9395F4A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BUJGWS47_BUJANG-7_PCSB_NOOP.pdf | PMO3BUJGWS47_BUJANG-7_PCSB_NOOP.pdf | Yes |  | Uploads\05c8b027-f774-4ddd-832f-a868b9395f4a.pdf | Exist
Mursyid | Yes | 6F4CFDC8-C746-43D4-8D5E-C22A4230278D | 612FB073-5C1D-4A68-9C56-0F6D89697212 | SASA-19 | 585D60EB-34A7-4E9F-BBBF-BB5886BC57FA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA 19nST NOOP- Rev1 (Compacted) (2).pdf |  | No |  | Uploads\585d60eb-34a7-4e9f-bbbf-bb5886bc57fa.pdf | Exist
Mursyid | Yes | 648AD323-63C3-42AC-B3C7-F67AAEFE61BF | 612FB073-5C1D-4A68-9C56-0F6D89697212 | SASA-19 | 542BB74D-E588-4DEA-9C74-8BC3C1C46753 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA-19_19ST1 EOWR.pdf | SASA-19_19ST1 EOWR.pdf | Yes |  | Uploads\542bb74d-e588-4dea-9c74-8bc3c1c46753.pdf | Exist
Mursyid | Yes | 81848184-14E1-4C37-93C0-FEC536A80158 | B5F16F5B-C55D-44A1-B62C-0FD07C95858F | KESIDANG-2 | 55F4CBF8-4317-420C-8ABB-8FAAE202C8B0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Kesidang-1 End of Well Report_SOMV.pdf | SK408 Kesidang-1 End of Well Report.pdf | No |  | Uploads\55f4cbf8-4317-420c-8abb-8faae202c8b0.pdf | Exist
Mursyid | Yes | 592A0430-A732-4A11-853B-4CEC8A954E51 | B5F16F5B-C55D-44A1-B62C-0FD07C95858F | KESIDANG-2 | 7BB65CD3-33CF-4888-9722-B5536E361E33 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kesidang-1 NOOP_Oct 2019_signed_SOMV.pdf |  | No |  | Uploads\7bb65cd3-33cf-4888-9722-b5536e361e33.pdf | Exist
Mursyid | Yes | 06E8C015-8C2D-4F84-8C24-4548BA770121 | 1F0B8FC3-A4EA-44C4-95F2-108CA75CAE46 | BO-208ST | 4251C55E-1553-4D02-B4AE-FAD75C986AC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-B208ST NOOP.pdf | BO-B208ST NOOP.pdf | Yes |  | Uploads\4251c55e-1553-4d02-b4ae-fad75c986ac6.pdf | Exist
Mursyid | Yes | 442D0704-88F6-4144-8AF6-A081EED77972 | 1F0B8FC3-A4EA-44C4-95F2-108CA75CAE46 | BO-208ST | C9C83E91-E306-47EF-8096-2F537BB5F2C7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO 208 ST FWR.pdf |  | No |  | Uploads\c9c83e91-e306-47ef-8096-2f537bb5f2c7.pdf | Exist
Mursyid | Yes | 42A5D44E-D673-478A-BB37-2C365A18EF8D | 249FCBA4-82A7-4B10-A96E-10B0B469A066 | LANGSAT-1 | 5B8C099F-B0AF-4022-9B38-5260F1BBE904 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Langsat-1 End of Well Report.pdf | Langsat-1 End of Well Report.pdf | Yes |  | Uploads\5b8c099f-b0af-4022-9b38-5260f1bbe904.pdf | Exist
Mursyid | Yes | B9DD0AA8-F9B3-41AB-9D56-CA31673EA9FE | 249FCBA4-82A7-4B10-A96E-10B0B469A066 | LANGSAT-1 | F3C83F05-C010-4F18-85E9-654A614685FE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Langsat-1 NOOP _Final.pdf | Langsat-1 NOOP _Final.pdf | Yes |  | Uploads\f3c83f05-c010-4f18-85e9-654a614685fe.pdf | Exist
Mursyid | Yes | 5B48B7F7-8C85-4EAD-A73D-C227817A49A5 | 6D4DFCED-7CA6-46A9-8B18-11F5BC967ED2 | ZUHAL NORTH - 1 | B21AF505-3B8D-4311-972B-29CD186FD175 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ZUHNGL01_ZUHAL NORTH-1.pdf | SBO3ZUHNGL01_ZUHAL NORTH-1.pdf | Yes |  | Uploads\b21af505-3b8d-4311-972b-29cd186fd175.pdf | Exist
Mursyid | Yes | 90C01E4B-0B44-4A93-8B45-9E622C7B53C6 | 6D4DFCED-7CA6-46A9-8B18-11F5BC967ED2 | ZUHAL NORTH - 1 | 67657DEB-AE93-4217-A8D6-785980F15472 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ZUHNWS05_ZUHAL NORTH-1.pdf | SBO3ZUHNWS05_ZUHAL NORTH-1.pdf | Yes |  | Uploads\67657deb-ae93-4217-a8d6-785980f15472.pdf | Exist
Mursyid | Yes | 9D50A38A-42BE-4388-8FA3-9E6E3385CA07 | 0589C3C7-6DC2-465C-9F58-12C6A5555B30 | D35-215ST1 | E129C284-6364-476B-8E3D-E4DA086AFE72 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-215ST1 NOOP_signed.pdf | D35B-215ST1 NOOP_signed.pdf | Yes |  | Uploads\e129c284-6364-476b-8e3d-e4da086afe72.pdf | Exist
Mursyid | Yes | AA82B3B3-A785-41E0-A149-A3B6805839A4 | 0589C3C7-6DC2-465C-9F58-12C6A5555B30 | D35-215ST1 | C6C74C8B-3424-42C0-AC9C-C20BAF273829 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-215ST1 EOWR - 1.pdf | D35B-215ST1 EOWR - 1.pdf | Yes |  | Uploads\c6c74c8b-3424-42c0-ac9c-c20baf273829.pdf | Exist
Mursyid | Yes | 4E3DE9FE-39BE-4665-B401-A1992A44A222 | 7EEF8196-E443-481C-AA6C-12D2516EF957 | BN-78 | 05CD3DC7-EC5A-43F4-9360-1DE175EB6390 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-78 Final (Internal) Rev1.pdf | NOOP BN-78 Final (Internal) Rev1.pdf | Yes |  | Uploads\05cd3dc7-ec5a-43f4-9360-1de175eb6390.pdf | Exist
Mursyid | Yes | BC1368A4-4EFE-446A-9042-C89AC552C4F8 | 7EEF8196-E443-481C-AA6C-12D2516EF957 | BN-78 | 82B0047A-3C50-476F-8896-CBB27A793BEA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN78_0_Final Well Report.pdf | BN78_0_Final Well Report.pdf | Yes |  | Uploads\82b0047a-3c50-476f-8896-cbb27a793bea.pdf | Exist
Mursyid | Yes | 5304CED2-DA81-4B63-9E72-21E0083C21E5 | C888CEDE-6448-4BC7-A453-13AE10AE14B2 | E06-101 | 4A5C16D5-509A-4DE7-9E21-91D9F9D9E379 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-101 (N2) NOOP Rev2.pdf | E06-101 (N2) NOOP Rev2.pdf | Yes |  | Uploads\4a5c16d5-509a-4de7-9e21-91d9f9d9e379.pdf | Exist
Mursyid | Yes | D703DF48-ADEA-497E-9BF8-4BDDD6DC9622 | C888CEDE-6448-4BC7-A453-13AE10AE14B2 | E06-101 | 0B317304-B3E6-47CE-93E3-2CB56E7B277D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-101 End of Well Report Final.pdf | E06-101 End of Well Report Final.pdf | Yes |  | Uploads\0b317304-b3e6-47ce-93e3-2cb56e7b277d.pdf | Exist
Mursyid | Yes | 664B00B8-8A44-454E-AE65-ACEF35C74671 | A17216D9-C1A2-4435-B86B-13EF8133CCD8 | KMSE-A04 | 3EC6BB5D-9BE1-45A6-9EB2-1731EAD24883 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE-A04 (NOOP) Rev.0.pdf | KMSE-A04 (NOOP) Rev.0.pdf | Yes |  | Uploads\3ec6bb5d-9be1-45a6-9eb2-1731ead24883.pdf | Exist
Mursyid | Yes | E606A6BD-05C0-4CD4-B5D2-82810967AEF7 | A17216D9-C1A2-4435-B86B-13EF8133CCD8 | KMSE-A04 | 8219E229-7D53-4C7A-B5BA-71992D4B8992 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE-A04 Final Well Report (1).pdf | KMSE-A04 Final Well Report (1).pdf | Yes |  | Uploads\8219e229-7d53-4c7a-b5ba-71992d4b8992.pdf | Exist
Mursyid | Yes | 7A0334BA-96EC-4E2D-BAD4-3380836B0953 | 7402BCC4-B9CB-439E-8D6B-13F387F9D593 | AXINIT-1 | 9CF72792-7640-40A4-9278-9B689DCA2694 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Axinit-1 EOWR.pdf | Axinit-1 EOWR.pdf | Yes |  | Uploads\9cf72792-7640-40a4-9278-9b689dca2694.pdf | Exist
Mursyid | Yes | 0D451E47-A6D3-4F7C-B6FB-0E2D4159C120 | 7402BCC4-B9CB-439E-8D6B-13F387F9D593 | AXINIT-1 | 0EF93DE5-3F25-41DE-85EC-01E4BABC11E5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3AXNTGL02_AXINIT-1_REPSOL-NOOP.pdf | SBO3AXNTGL02_AXINIT-1_REPSOL-NOOP.pdf | Yes |  | Uploads\0ef93de5-3f25-41de-85ec-01e4babc11e5.pdf | Exist
Mursyid | Yes | FC1B3373-CE8B-42C2-85D2-51E03591612B | 4862C4EF-5AB6-4794-AB49-1417587BC393 | PX12 (150) | 47317A27-39F6-45B9-A2F5-BD912117BB13 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kikeh Phase 3a Development_PX12(150)_NOOP_REV0.pdf | Kikeh Phase 3a Development_PX12(150)_NOOP_REV0.pdf | Yes |  | Uploads\47317a27-39f6-45b9-a2f5-bd912117bb13.pdf | Exist
Mursyid | Yes | EE7DDB50-08F1-4CB0-9534-E086C95DBF9C | 4862C4EF-5AB6-4794-AB49-1417587BC393 | PX12 (150) | 0F0F71E6-C3CE-43ED-93CF-DD08475849DD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-K-40-DNC-RP-0003-00_PX12(150)_EOWR_Final 2.pdf | MY-K-40-DNC-RP-0003-00_PX12(150)_EOWR_Final 2.pdf | Yes |  | Uploads\0f0f71e6-c3ce-43ed-93cf-dd08475849dd.pdf | Exist
Mursyid | Yes | BEEFC53A-3DEB-4B06-A9AD-DEA2891CBA34 | 2F38857B-E0D8-4F9C-8546-14360AA10758 | BEKOK-B13 | 456750E1-5632-4979-B97E-1560C8055085 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK-B13ST1 FWR.pdf | BEKOK-B13ST1 FWR.pdf | Yes |  | Uploads\456750e1-5632-4979-b97e-1560c8055085.pdf | Exist
Mursyid | Yes | 41374903-6FFD-40CA-8A06-4531665E1985 | 2F38857B-E0D8-4F9C-8546-14360AA10758 | BEKOK-B13 | D95D36F2-2F61-42E6-8368-066E4A9F43ED | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK B13_NOOP_2012_PM.pdf | BEKOK B13_NOOP_2012_PM.pdf | Yes |  | Uploads\d95d36f2-2f61-42e6-8368-066e4a9f43ed.pdf | Exist
Mursyid | Yes | ACE5D51C-C746-445B-8394-D330719545AB | 723C6B80-313B-413A-B52A-14A3A9D26691 | TUNTONG-1 | 205309F3-1B0A-4818-AD66-89213F0BF30C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tuntong-1 FINAL NOOP 12Oct2015.pdf | Tuntong-1 FINAL NOOP 12Oct2015.pdf | Yes |  | Uploads\205309f3-1b0a-4818-ad66-89213f0bf30c.pdf | Exist
Mursyid | Yes | F27F0EBE-141C-411B-9826-B9C4BD040CA0 | 723C6B80-313B-413A-B52A-14A3A9D26691 | TUNTONG-1 | 49BF2BAC-C30B-46BC-B807-E5F3C632879A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tuntong-1.pdf | Tuntong-1.pdf | Yes |  | Uploads\49bf2bac-c30b-46bc-b807-e5f3c632879a.pdf | Exist
Mursyid | Yes | 25BDD107-9BD9-498C-8C87-25323BB0415E | D6048237-B1F2-4032-8A1B-14D5C0C4D62A | INAI-1 | 12C5C62E-6CCE-49B9-9E63-C1D47078B61A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Inai-1_Final MLNGx_NOOP.pdf | Inai-1_Final MLNGx_NOOP.pdf | Yes |  | Uploads\12c5c62e-6cce-49b9-9e63-c1d47078b61a.pdf | Exist
Mursyid | Yes | 2BA28760-BB27-43DC-AC41-892F7A8449FB | D6048237-B1F2-4032-8A1B-14D5C0C4D62A | INAI-1 | 764B7702-A671-4BD5-B39A-30E88415EB86 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Inai-1- SMEP - MLNG Exploration - EOWR.pdf | Inai-1- SMEP - MLNG Exploration - EOWR.pdf | Yes |  | Uploads\764b7702-a671-4bd5-b39a-30e88415eb86.pdf | Exist
Mursyid | Yes | 7381DFAF-8EE6-4F46-823B-DABC7F755B50 | 42199651-5ADD-4ACF-B9ED-14D893EF586C | KNDW-D18 | 6EF6E080-5FCA-4647-9C05-5DE62F156A27 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS6064_KNDW - D18_NOOP.pdf | SBO3KNBLWS6064_KNDW - D18_NOOP.pdf | Yes |  | Uploads\6ef6e080-5fca-4647-9c05-5de62f156a27.pdf | Exist
Mursyid | Yes | 402BE419-8D4C-433F-8896-FA9B9BC0A908 | 42199651-5ADD-4ACF-B9ED-14D893EF586C | KNDW-D18 | 3010AEEF-78EA-4B68-8AF6-6A7DFFB07177 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW-D18_Final.pdf | EOWR KNDW-D18_Final.pdf | Yes |  | Uploads\3010aeef-78ea-4b68-8af6-6a7dffb07177.pdf | Exist
Mursyid | Yes | 0AFADD0A-084A-4D58-B0B8-EFCA89BA60EA | 6DDB2F2F-5DF5-472C-882C-14FD2C17F275 | EW-102ST2 | BC71F7D3-02EB-4CF0-9600-9655569446B6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report EW-102 ST2.pdf | Petronas Final Well Report EW-102 ST2.pdf | Yes |  | Uploads\bc71f7d3-02eb-4cf0-9600-9655569446b6.pdf | Exist
Mursyid | Yes | A5E43C30-E0F5-4910-88BD-52401A597B16 | 6DDB2F2F-5DF5-472C-882C-14FD2C17F275 | EW-102ST2 | 7E05AC35-F3D5-45A5-80BB-F13E810836CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Erb West EW102 ST2 NOOP.pdf | Erb West EW102 ST2 NOOP.pdf | Yes |  | Uploads\7e05ac35-f3d5-45a5-80bb-f13e810836cd.pdf | Exist
Mursyid | Yes | 51AEEA32-BBEE-4342-B604-AE893AF43682 | 8AF1C868-C086-4BCB-B90D-15A3D5FF347E | LEGUNDI-1 | FD2DA99F-E3ED-4B07-84D9-8CB6EC1B1296 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LGNDWS04_LEGUNDI-1.pdf | SKO3LGNDWS04_LEGUNDI-1.pdf | Yes |  | Uploads\fd2da99f-e3ed-4b07-84d9-8cb6ec1b1296.pdf | Exist
Mursyid | Yes | DCC91C23-0C0A-4200-A92C-B5EB2E3D61A8 | 8AF1C868-C086-4BCB-B90D-15A3D5FF347E | LEGUNDI-1 | 4977979A-B255-4E5A-8C16-0173235DF85A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LGNDWS05_LEGUNDI-1.pdf | SKO3LGNDWS05_LEGUNDI-1.pdf | Yes |  | Uploads\4977979a-b255-4e5a-8c16-0173235df85a.pdf | Exist
Mursyid | Yes | 8FBC33C1-CDA9-4E8B-BAB5-BDF04E23A72F | 9223BF09-7D7E-4979-8DB9-15AF3047D02D | KAURAN-1 | 8278C789-3190-49BD-8A61-4DD53DDB8954 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KARNWS02_KAURAN-1_PCSB.pdf | SBO3KARNWS02_KAURAN-1_PCSB.pdf | Yes |  | Uploads\8278c789-3190-49bd-8a61-4dd53ddb8954.pdf | Exist
Mursyid | Yes | DFC348AD-99D8-4AC2-ABEB-9BA05CBB479C | 9223BF09-7D7E-4979-8DB9-15AF3047D02D | KAURAN-1 | B9E918D8-C179-4447-86B0-285FF22293D5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kauran-1 FWR_PCSB.pdf | Kauran-1 FWR_PCSB.pdf | Yes |  | Uploads\b9e918d8-c179-4447-86b0-285ff22293d5.pdf | Exist
Mursyid | Yes | 87275562-0821-4172-9779-7353EE63A57D | 721BB7AC-D529-46C1-8581-15D559367D49 | SEPA-12 | 1679841A-4ACF-40A9-93BB-01367D76553C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEPA12ST1RD EOWR_ FINAL (APPROVED).pdf | SEPA12ST1RD EOWR_ FINAL (APPROVED).pdf | Yes |  | Uploads\1679841a-4acf-40a9-93bb-01367d76553c.pdf | Exist
Mursyid | Yes | 798E198A-3B06-4D58-88D4-31A1AEB27A58 | 721BB7AC-D529-46C1-8581-15D559367D49 | SEPA-12 | 3493ECEC-3CF9-4106-8C65-CF0C276174B2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SEPA-10,SEPA-12.pdf | NOOP SEPA-10,SEPA-12.pdf | Yes |  | Uploads\3493ecec-3cf9-4106-8c65-cf0c276174b2.pdf | Exist
Mursyid | Yes | 38FCBE81-0A7E-4A3B-87F4-447D49AF4B4B | A2754879-793A-4FC5-9ECE-16526DFEFC7E | EAST BELUMUT A-13 ST2 | B8BE4952-68C2-4F87-A387-1DAF6B88029C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-13ST2 FWR Final.pdf |  | No |  | Uploads\b8be4952-68c2-4f87-a387-1daf6b88029c.pdf | Exist
Mursyid | Yes | 0BA3F808-266F-4FC6-8600-0FA6959A90F7 | A2754879-793A-4FC5-9ECE-16526DFEFC7E | EAST BELUMUT A-13 ST2 | 20DECB29-22D0-4FC7-AAE3-B56DD1B6A1CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA13ST2 NOOP.pdf |  | No |  | Uploads\20decb29-22d0-4fc7-aae3-b56dd1b6a1cd.pdf | Exist
Mursyid | Yes | C292CF5A-641C-45D3-A672-0AD96DFBCFD7 | D096C26F-6123-4C02-AC7C-166615DC47E1 | MLK-116 | 5D724888-6161-4D76-AECE-56E43BA0792F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-116 EOWR Final 201117.pdf | MLK-116 EOWR Final 201117.pdf | Yes |  | Uploads\5d724888-6161-4d76-aece-56e43ba0792f.pdf | Missing
Mursyid | Yes | 4A6ACA88-FE9C-4309-8516-5904204880D8 | D096C26F-6123-4C02-AC7C-166615DC47E1 | MLK-116 | B0F57192-080C-4BB1-8D4C-D6F284445DF3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL22_MLK-116_SHELL_NOOP.pdf | SBO3MKAIGL22_MLK-116_SHELL_NOOP.pdf | Yes |  | Uploads\b0f57192-080c-4bb1-8d4c-d6f284445df3.pdf | Missing
Mursyid | Yes | 9CDE0568-266B-4B0F-9B76-6A0DF4DA7CB3 | B83D49E0-E860-4C5E-A8D0-173B8D7AF7F2 | SNPA-13 | 8EEDA14A-3C3D-4A6E-A49B-476DBA08487E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRDHWS71_SNPA_13.pdf | SKO3SRDHWS71_SNPA_13.pdf | Yes |  | Uploads\8eeda14a-3c3d-4a6e-a49b-476dba08487e.pdf | Exist
Mursyid | Yes | 6D0D80BF-4B8C-4207-A35C-AEAAC21E00F6 | B83D49E0-E860-4C5E-A8D0-173B8D7AF7F2 | SNPA-13 | 6AD0BF61-1515-42B1-9F68-A2464C4A5FD9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf | Yes |  | Uploads\6ad0bf61-1515-42b1-9f68-a2464c4a5fd9.pdf | Exist
Mursyid | Yes | E8E4DEB1-6AD6-4E99-ABDE-A7A46327EB65 | 55D3100B-81B5-4D62-9B87-175A1BD14946 | BUNGA DAHLIA A-1 | 700CC823-4E64-4AE6-8CC0-5286D10B37ED | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BDL-A1 - final - signed.pdf |  | No |  | Uploads\700cc823-4e64-4ae6-8cc0-5286d10b37ed.pdf | Exist
Mursyid | Yes | 608C469E-FE1A-46F0-A1A7-CCEED732B98F | 55D3100B-81B5-4D62-9B87-175A1BD14946 | BUNGA DAHLIA A-1 | F81FA9C3-5895-4E35-8F20-4C2045253EFF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Bunga Dahlia-A1_ BDL-A1.pdf | NOOP_Bunga Dahlia-A1_ BDL-A1.pdf | Yes |  | Uploads\f81fa9c3-5895-4e35-8f20-4c2045253eff.pdf | Exist
Mursyid | Yes | 68E42185-47FB-4775-A3A0-E97CC82B5EE3 | D3D88475-0467-410E-B708-17C8B7A22861 | KENTAL-1 | 89CCE446-E3E1-421F-BB05-208484D711B5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNTLWS05_KENTAL-1_PCSB_FWR.pdf | SBO3KNTLWS05_KENTAL-1_PCSB_FWR.pdf | Yes |  | Uploads\89cce446-e3e1-421f-bb05-208484d711b5.pdf | Exist
Mursyid | Yes | B84FAA11-1DE5-49E3-90C3-3A2843CEADE9 | D3D88475-0467-410E-B708-17C8B7A22861 | KENTAL-1 | 054A70F6-5B35-4960-9A88-E333D2654698 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kental-1-NOOP signed.pdf | Kental-1-NOOP signed.pdf | Yes |  | Uploads\054a70f6-5b35-4960-9a88-e333d2654698.pdf | Exist
Mursyid | Yes | 10053987-9D43-41C5-A983-357A53D03FC3 | A1CF9B37-CF17-4F60-9A5D-17ECF405C98C | DULANG-B31ST1 | 1FB3FA45-4471-4295-B1E1-723663460806 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Dulang B31ST1_(Internal Copy).pdf | NOOP_Dulang B31ST1_(Internal Copy).pdf | Yes |  | Uploads\1fb3fa45-4471-4295-b1e1-723663460806.pdf | Exist
Mursyid | Yes | 50323378-8181-4EED-A7B2-19315A519966 | A1CF9B37-CF17-4F60-9A5D-17ECF405C98C | DULANG-B31ST1 | 931D53C1-AEDF-42C2-BE34-5DBDD48E1007 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang B31ST1 Final Well Report.pdf | Dulang B31ST1 Final Well Report.pdf | Yes |  | Uploads\931d53c1-aedf-42c2-be34-5dbdd48e1007.pdf | Exist
Mursyid | Yes | 4B7D5426-F67D-4A9F-A73E-17BDA7B505C1 | EE3CDA0B-0790-4EEE-84E2-18028F71BF4A | TNGB-A8 | 6A47F64B-CFE3-474A-8B3A-671C77C148E6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS74_TNGB-A8_PCSB_NOOP.pdf | PMO3TNGBWS74_TNGB-A8_PCSB_NOOP.pdf | Yes |  | Uploads\6a47f64b-cfe3-474a-8b3a-671c77c148e6.pdf | Exist
Mursyid | Yes | 266530B0-CB86-41CE-858B-2EA7E2350951 | EE3CDA0B-0790-4EEE-84E2-18028F71BF4A | TNGB-A8 | 4C9DA848-2CF5-4867-9283-E60B6475BB25 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS67_TNGB-A8_PCSB_FWR.pdf | PMO3TNGBWS67_TNGB-A8_PCSB_FWR.pdf | Yes |  | Uploads\4c9da848-2cf5-4867-9283-e60b6475bb25.pdf | Exist
Mursyid | Yes | 4DF58BD5-C6CD-40C6-A9CA-A7C026E2BEA4 | 9C1E6ACA-D7C4-4517-80FB-186C65797D45 | BOKOR-D403 | ECCC5300-C1A4-40F8-BC75-C7CE25AFF7BA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BO-403 ADDENDUM SIGNED_PCSB.pdf |  | No |  | Uploads\eccc5300-c1a4-40f8-bc75-c7ce25aff7ba.pdf | Exist
Mursyid | Yes | 49DCB309-31AF-46FF-B22A-C9EA6140D966 | 9C1E6ACA-D7C4-4517-80FB-186C65797D45 | BOKOR-D403 | B5118C05-07BB-4EE4-828D-B5B40C7854B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report BO-403.pdf |  | No |  | Uploads\b5118c05-07bb-4ee4-828d-b5b40c7854b7.pdf | Exist
Mursyid | Yes | 0643435C-101F-4F46-840A-2799153C8FD5 | 0CED9DB4-E278-4196-A375-195729B6A22F | SJ-610A | ACC979F8-C272-4EFB-93BA-10EDF29E544C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-610A EOWR (MPM Drilling).pdf | SJ-610A EOWR (MPM Drilling).pdf | Yes |  | Uploads\acc979f8-c272-4efb-93ba-10edf29e544c.pdf | Exist
Mursyid | Yes | 62641FAB-9CF2-4CAD-BF32-195DE501D09E | 0CED9DB4-E278-4196-A375-195729B6A22F | SJ-610A | D6BE6C6D-0A2F-4FAF-9A60-58C044427882 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-610A NOOP - MPM Drilling.pdf | SJ-610A NOOP - MPM Drilling.pdf | Yes |  | Uploads\d6be6c6d-0a2f-4faf-9a60-58c044427882.pdf | Exist
Mursyid | Yes | E885BE21-5AB3-4797-BD5F-9370ED31CB2F | 8D8B0AE6-66CA-4ACD-8A00-198E0C04B8CF | JTG-A1 | A5EEA14B-D5F5-423E-A2FF-E71255A532A2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP JTG-A1.pdf | NOOP JTG-A1.pdf | Yes |  | Uploads\a5eea14b-d5f5-423e-a2ff-e71255a532a2.pdf | Exist
Mursyid | Yes | 2DAB3924-71EC-472D-80B6-856812F5981E | 8D8B0AE6-66CA-4ACD-8A00-198E0C04B8CF | JTG-A1 | 5517A109-1176-41E9-981B-469B5028C6BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JTG-A1 Final Well Report_2020_01_22.pdf | JTG-A1 Final Well Report_2020_01_22.pdf | Yes |  | Uploads\5517a109-1176-41e9-981b-469b5028c6be.pdf | Exist
Mursyid | Yes | 7BB55B6C-88C6-43D4-A65C-79641F83E1EE | D9C009EB-5218-4F19-96CB-1A2FCD236D3B | BOC-30 (T1) | C1FD34ED-A1FE-4594-BFDF-ABB29505F583 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-30 (T1) EOWR.pdf | BOC-30 (T1) EOWR.pdf | Yes |  | Uploads\c1fd34ed-a1fe-4594-bfdf-abb29505f583.pdf | Exist
Mursyid | Yes | DFFB2B53-A8B4-4988-992D-BF79D9BA2D3D | D9C009EB-5218-4F19-96CB-1A2FCD236D3B | BOC-30 (T1) | 1B8E062C-DEB4-4375-8B73-4BC59484FE5D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-30 (T1) NOOP Rev 1.0.pdf | BOC-30 (T1) NOOP Rev 1.0.pdf | Yes |  | Uploads\1b8e062c-deb4-4375-8b73-4bc59484fe5d.pdf | Exist
Mursyid | Yes | 8D00DEA3-5CA3-4FA4-9F53-D679840D4E5C | 2EC335A4-A4C4-4E11-9D7F-1A4464B88CD0 | BPA-3 | A0F81B65-DFE2-4759-88FE-D7370FDC2AB3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-3 EOWR.pdf | BPA-3 EOWR.pdf | Yes |  | Uploads\a0f81b65-dfe2-4759-88fe-d7370fdc2ab3.pdf | Exist
Mursyid | Yes | A69A9087-8253-4D7B-B38B-E7B5E4620805 | 2EC335A4-A4C4-4E11-9D7F-1A4464B88CD0 | BPA-3 | 33D583EA-9939-4244-AD11-31E5DD09DBA0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-3 (C) NOOP.pdf | BPA-3 (C) NOOP.pdf | Yes |  | Uploads\33d583ea-9939-4244-ad11-31e5dd09dba0.pdf | Exist
Mursyid | Yes | 67201C7E-F8BA-40BB-A238-092BE9CF5BF3 | 8320AF34-770C-4E36-9C5B-1A57CEAD4150 | WB A-03ST2 | 852013E0-B885-4D35-A1F1-292D21CDC311 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A-03ST2 EOWR.pdf | WB A-03ST2 EOWR.pdf | Yes |  | Uploads\852013e0-b885-4d35-a1f1-292d21cdc311.pdf | Exist
Mursyid | Yes | 8047E39C-8A2E-4D55-9B74-08306081C508 | 8320AF34-770C-4E36-9C5B-1A57CEAD4150 | WB A-03ST2 | A1F35A29-89C8-4F6F-9092-BF269EEF8019 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A-03ST2 Final.pdf | WB A-03ST2 Final.pdf | Yes |  | Uploads\a1f35a29-89c8-4f6f-9092-bf269eef8019.pdf | Exist
Mursyid | Yes | A6308D3A-5C39-449F-8E2E-2329076E3F2A | AD23C7DC-7E8A-4863-9C4B-1A5C0A6BF01F | TBG-A01 ST1 | D195A0BF-ADBF-46DF-A7AD-D0248A90C33C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS9D_TBG-A01 ST1.pdf | SBO3TMBGWS9D_TBG-A01 ST1.pdf | Yes |  | Uploads\d195a0bf-adbf-46df-a7ad-d0248a90c33c.pdf | Exist
Mursyid | Yes | 056AD695-4C6F-420D-BE48-FCFEC7B50949 | AD23C7DC-7E8A-4863-9C4B-1A5C0A6BF01F | TBG-A01 ST1 | D3C0435D-F775-48CD-8E9E-40BE3C71DAC0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS8L_TBG-A01 ST1.pdf | SBO3TMBGWS8L_TBG-A01 ST1.pdf | Yes |  | Uploads\d3c0435d-f775-48cd-8e9e-40be3c71dac0.pdf | Exist
Mursyid | Yes | 18FCBEAD-F6BB-4412-93CD-C3567905C991 | 2DD75F44-0CA1-446F-AA25-1AE3A914C0F2 | JERUN-A6 | ED836F54-DFE2-4530-807A-8D82A2876D66 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\ed836f54-dfe2-4530-807a-8d82a2876d66.pdf | Exist
Mursyid | Yes | 8DA845FD-0D2C-471E-8EC4-983F25D82431 | 2DD75F44-0CA1-446F-AA25-1AE3A914C0F2 | JERUN-A6 | 7971697C-5474-448B-9402-AD1B9F6DB351 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Jerun-A6 Final Well Report_FINAL.pdf | SK408 Jerun-A6 Final Well Report_FINAL.pdf | Yes |  | Uploads\7971697c-5474-448b-9402-ad1b9f6db351.pdf | Exist
Mursyid | Yes | 72A1286D-6E03-4772-83C5-40A8EE9E7F71 | C83E9977-98E0-48B1-A4D8-1BA99F0D574F | KNDW-D04 | 03CAD961-6B8F-4595-8BA8-75F85A053AFF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D04, NOOP, 15 Jan 2020.pdf | KNDW-D04, NOOP, 15 Jan 2020.pdf | Yes |  | Uploads\03cad961-6b8f-4595-8ba8-75f85a053aff.pdf | Exist
Mursyid | Yes | 60776489-833F-464B-9C6F-D1EE8F7AEFF2 | C83E9977-98E0-48B1-A4D8-1BA99F0D574F | KNDW-D04 | 9C488BD2-6FB3-478F-88F9-AB1FD20BEB32 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW-D04.pdf | EOWR KNDW-D04.pdf | Yes |  | Uploads\9c488bd2-6fb3-478f-88f9-ab1fd20beb32.pdf | Exist
Mursyid | Yes | DDB878A9-B08C-4197-8AEF-559984F9E6A1 | FCEFA5FE-B806-44EA-82A5-1BD25C6D64B2 | SM-102 | DF863AC9-153B-448A-9FFD-8771C9F0AD3D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Samarang-E102 FWR.pdf |  | No |  | Uploads\df863ac9-153b-448a-9ffd-8771c9f0ad3d.pdf | Exist
Mursyid | Yes | BCD3F539-3EAB-4C1B-A601-AA81DDB2E6DE | FCEFA5FE-B806-44EA-82A5-1BD25C6D64B2 | SM-102 | A2431A1B-461F-4846-AFCB-C9415730383A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-102 (E-01)_NOOP_2014_SB.pdf |  | No |  | Uploads\a2431a1b-461f-4846-afcb-c9415730383a.pdf | Exist
Mursyid | Yes | 9C7CB73A-2170-4CC0-9902-51ECC0961B74 | 0D184390-82E0-4412-B8FD-1BE818F46D45 | SNPA-14 | F9EF33B7-E45D-4481-8C00-65FEA8EA7B17 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf |  | No |  | Uploads\f9ef33b7-e45d-4481-8c00-65fea8ea7b17.pdf | Exist
Mursyid | Yes | 25AC2429-7AAA-4E41-992C-5A0A6270F453 | 0D184390-82E0-4412-B8FD-1BE818F46D45 | SNPA-14 | 3E912B46-4726-4FD6-9160-B83334489788 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRDHWS72_SNPA-14.pdf | SKO3SRDHWS72_SNPA-14.pdf | Yes |  | Uploads\3e912b46-4726-4fd6-9160-b83334489788.pdf | Exist
Mursyid | Yes | 214DC1C4-C4B1-4EBC-A053-933EF00D2B4C | 7A0A74BE-8917-49B0-9DDF-1C33FBA4C055 | BERGADING DEEP-4 | 96B32E5A-9A72-48AE-B7FC-3F00132A0B0A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BD-4 Rev0.pdf |  | No |  | Uploads\96b32e5a-9a72-48ae-b7fc-3f00132a0b0a.pdf | Exist
Mursyid | Yes | A8931281-B57C-48B5-BCCF-F941C4A39C07 | 7A0A74BE-8917-49B0-9DDF-1C33FBA4C055 | BERGADING DEEP-4 | 041DE044-3997-4E7F-8B4D-74BDE226C7CC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading Deep-4_BD-4_signed.pdf | EOWR_Bergading Deep-4_BD-4_signed.pdf | Yes |  | Uploads\041de044-3997-4e7f-8b4d-74bde226c7cc.pdf | Exist
Mursyid | Yes | 4E7F2B6B-4E65-46EF-8118-DA63D4DCF916 | 307072D6-FA11-4DF1-B034-1C493991391B | BN-82ST1 | 8DDC0B33-09B3-4BF6-AE70-FCFE78832912 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN82-ST1 FINAL SIGNED.pdf | NOOP BN82-ST1 FINAL SIGNED.pdf | Yes |  | Uploads\8ddc0b33-09b3-4bf6-ae70-fcfe78832912.pdf | Exist
Mursyid | Yes | 81282EB9-1F1B-467C-8FFA-685DA25F6A55 | 307072D6-FA11-4DF1-B034-1C493991391B | BN-82ST1 | B5E3C5C6-C663-4316-B090-B179E6EEE2D0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BN-82ST1 FINAL - for submission.pdf | FWR BN-82ST1 FINAL - for submission.pdf | Yes |  | Uploads\b5e3c5c6-c663-4316-b090-b179e6eee2d0.pdf | Exist
Mursyid | Yes | 84A87D8B-AC2F-4A39-85C5-0F46760CBD97 | E5A45F92-8234-46AE-9CD3-1C4F79568714 | BEKOK-BB17 | 87F9E2CE-9E7E-4264-88BC-79B619857980 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok BB17_Final Rev1_01052022.pdf | NOOP Bekok BB17_Final Rev1_01052022.pdf | Yes |  | Uploads\87f9e2ce-9e7e-4264-88bc-79b619857980.pdf | Exist
Mursyid | Yes | D4AA1EB7-A8AD-4DE8-A0D7-F6C0E3C78A4E | E5A45F92-8234-46AE-9CD3-1C4F79568714 | BEKOK-BB17 | D63A1A4B-42B8-4536-8118-0328CBF25596 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BB17_Petronas Final Well Report_18102022.pdf |  | No |  | Uploads\d63a1a4b-42b8-4536-8118-0328cbf25596.pdf | Exist
Mursyid | Yes | CEF2EB6C-6884-403A-BF50-ED987059ABF9 | 6B8B7B5C-D0C4-4532-B985-1C63D094C9E2 | LIMAU MANIS-1 | 2B5EAD52-C6D2-4DD7-8ABE-49ADACBBB5C9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Limau Manis-1 NOOP.pdf |  | No |  | Uploads\2b5ead52-c6d2-4dd7-8abe-49adacbbb5c9.pdf | Exist
Mursyid | Yes | BBE772FC-E897-435B-8317-38439B22065B | 6B8B7B5C-D0C4-4532-B985-1C63D094C9E2 | LIMAU MANIS-1 | D17211C7-AB26-4172-B951-17A837365A68 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LMISWS08_LIMAU-MANIS-01_PCSB.pdf |  | No |  | Uploads\d17211c7-ab26-4172-b951-17a837365a68.pdf | Exist
Mursyid | Yes | 354E2CCD-8BDC-4FD8-A744-442FB160B3C4 | 44DCFDEB-9E07-48B4-9762-1C6C112BA31A | LADA PUTIH-1 | AB871B2A-9A96-4DBE-A398-2CAD6490D4DE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lada Putih-1 MP_EOWR_FINAL_26 August 2022.pdf | Lada Putih-1 MP_EOWR_FINAL_26 August 2022.pdf | Yes |  | Uploads\ab871b2a-9a96-4dbe-a398-2cad6490d4de.pdf | Exist
Mursyid | Yes | 579702F9-A60E-494C-988C-8098507FA7E3 | 44DCFDEB-9E07-48B4-9762-1C6C112BA31A | LADA PUTIH-1 | BE08F75C-E0D8-49D1-8FEB-9954AB5F5BED | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LADA PUTIH-1 NOOP Final Version 1.pdf | LADA PUTIH-1 NOOP Final Version 1.pdf | Yes |  | Uploads\be08f75c-e0d8-49d1-8feb-9954ab5f5bed.pdf | Exist
Mursyid | Yes | DD06FAA3-54FD-4A6E-AAB6-43A35EB1A067 | 944526CC-0FDB-481F-B644-1C6D8E33471C | ARAPAIMA-1 | 4553A7B4-047C-40BB-A49E-B48B07487834 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Arapaima-1 Internal_FINAL_NOOP - 16112019_3.pdf | Arapaima-1 Internal_FINAL_NOOP - 16112019_3.pdf | Yes |  | Uploads\4553a7b4-047c-40bb-a49e-b48b07487834.pdf | Exist
Mursyid | Yes | 2698C39F-1983-4159-86BC-4760970E2410 | 944526CC-0FDB-481F-B644-1C6D8E33471C | ARAPAIMA-1 | 9B28A801-7891-42AD-9C4E-7CA7B9E54E2C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Arapaima-1 Final Well Report_FINAL.pdf | Arapaima-1 Final Well Report_FINAL.pdf | Yes |  | Uploads\9b28a801-7891-42ad-9c4e-7ca7b9e54e2c.pdf | Exist
Mursyid | Yes | F567F5FC-08C4-4084-B37D-3FF7D3EA0710 | EBF2DC12-B503-47DD-8EE8-1C9FB4A15273 | SM-104 | 154D7F53-3CBC-47A5-8602-1F46A45C2956 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG SM-104 FWR.pdf | SAMARANG SM-104 FWR.pdf | Yes |  | Uploads\154d7f53-3cbc-47a5-8602-1f46a45c2956.pdf | Exist
Mursyid | Yes | 935B3603-63CF-484C-AE93-612E83914BBE | EBF2DC12-B503-47DD-8EE8-1C9FB4A15273 | SM-104 | A80EBD1F-9C9C-4D0B-8808-99CF10543CD1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL29_SM-104.pdf | SBO3SMRGGL29_SM-104.pdf | Yes |  | Uploads\a80ebd1f-9c9c-4d0b-8808-99cf10543cd1.pdf | Exist
Mursyid | Yes | 153CCD92-7BDF-4CC2-B29C-6000C4ACA653 | 4B276C9C-CA00-4F8C-BC02-1CC094816649 | SEPAT-A12 | A27B0827-5389-4A06-9DE3-E7D09E7F509A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Approved NOOP Sepat A12.pdf | Approved NOOP Sepat A12.pdf | Yes |  | Uploads\a27b0827-5389-4a06-9de3-e7d09e7f509a.pdf | Exist
Mursyid | Yes | D84D672A-33AF-446E-82E9-D531E2C10001 | 4B276C9C-CA00-4F8C-BC02-1CC094816649 | SEPAT-A12 | A6BAC2C3-24D1-4739-A86F-ED8BAFEAA58C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR A12 5 July 2020 rev3_FINAL-signed-signed.pdf |  | No |  | Uploads\a6bac2c3-24d1-4739-a86f-ed8bafeaa58c.pdf | Exist
Mursyid | Yes | D206D224-81B9-4943-A12B-5833B620FDFD | 77D02427-9C82-428F-BF04-1CF22CA055E5 | BAKONG A-01 | 02FD4B24-3ABD-4A9C-911D-07AF2B6D35AF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A1 NOOP 2-July-2019 FINAL.pdf |  | No |  | Uploads\02fd4b24-3abd-4a9c-911d-07af2b6d35af.pdf | Exist
Mursyid | Yes | 771F3871-3CB9-4197-B2DE-13843C7B0360 | 77D02427-9C82-428F-BF04-1CF22CA055E5 | BAKONG A-01 | 3ABE6C28-7DFC-4161-B54E-24913733C2FC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 BKG-A1 FINAL WELL REPORT FINAL.pdf |  | No |  | Uploads\3abe6c28-7dfc-4161-b54e-24913733c2fc.pdf | Exist
Mursyid | Yes | 64C8042A-0DDD-41DC-B74C-76FE23973245 | A33B5AF5-F478-4B57-B673-1D2AE9736C14 | SAPA-09 | 581AC2BA-F0B5-416F-9252-7197C2472BE0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-09 EOWR.pdf | SAPA-09 EOWR.pdf | Yes |  | Uploads\581ac2ba-f0b5-416f-9252-7197c2472be0.pdf | Missing
Mursyid | Yes | 9E2691EC-A215-4338-A919-8B2128753F93 | A33B5AF5-F478-4B57-B673-1D2AE9736C14 | SAPA-09 | B6D5B943-AE76-4293-8C74-B7995524BE66 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-08 & SAPA-09 NOOP.pdf | SAPA-08 & SAPA-09 NOOP.pdf | Yes |  | Uploads\b6d5b943-ae76-4293-8c74-b7995524be66.pdf | Missing
Mursyid | Yes | 3C69AA3E-B412-43B3-830E-21491B8D5B11 | 52C5AF32-29CF-4A31-AFF8-1E046A7321A3 | LIMBAYONG-4 | FC9F4DEE-EFA2-45B9-B73D-428A00CF7C37 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Limbayong-4.pdf | Limbayong-4 RDR(1).pdf | No |  | Uploads\fc9f4dee-efa2-45b9-b73d-428a00cf7c37.pdf | Exist
Mursyid | Yes | DE17D205-8180-4170-AE5C-341765489CC4 | 52C5AF32-29CF-4A31-AFF8-1E046A7321A3 | LIMBAYONG-4 | 396BBE69-054A-48E0-A1B0-4465B10387AA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Limbayong-4.pdf | Limbayong-4.pdf | Yes |  | Uploads\396bbe69-054a-48e0-a1b0-4465b10387aa.pdf | Exist
Mursyid | Yes | F9D10E0E-BCCF-4980-B7E2-B0DAC8FA3913 | BF3B18CB-485D-47BF-B29A-1F0B1720E9ED | KASAWARI-A7 | 19286826-30FA-4D8F-9B9C-331171C8BEC4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kasawari A7 NOOP_Final.pdf | Kasawari A7 NOOP_Final.pdf | Yes |  | Uploads\19286826-30fa-4d8f-9b9c-331171c8bec4.pdf | Exist
Mursyid | Yes | D1EBFD7E-1025-457B-A5F3-ECF8F9C38207 | BF3B18CB-485D-47BF-B29A-1F0B1720E9ED | KASAWARI-A7 | A061F63C-6A79-4BF2-AC5E-520F2BC913DC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report (FWR) Well A7_Kasawari_rev1 (002) TR.pdf |  | No |  | Uploads\a061f63c-6a79-4bf2-ac5e-520f2bc913dc.pdf | Exist
Mursyid | Yes | 5A1D8EB1-56D3-4359-8F7F-D7D7579B8B31 | AF73AD10-5225-4B91-9619-1F80DF9C9388 | BERTAM-3 | 0F0E3230-F60D-4D9B-8A0C-D5F3A4075B4D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A3 NOOP.pdf | PMO3BTAMWS30_BERTAM-3_NOOP.pdf | No |  | Uploads\0f0e3230-f60d-4d9b-8a0c-d5f3a4075b4d.pdf | Exist
Mursyid | Yes | 0C114BAB-47B1-4835-85BC-B91952A3139C | AF73AD10-5225-4B91-9619-1F80DF9C9388 | BERTAM-3 | 837A5C9B-A26C-4D81-9712-269B84CF326D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A3 EOWR.pdf | PMO3BTAMDR08_BERTAM-3.pdf | No |  | Uploads\837a5c9b-a26c-4d81-9712-269b84cf326d.pdf | Exist
Mursyid | Yes | 16B07C41-2E56-420A-8CF4-F34740B7E153 | 288AA648-B63E-4977-BD17-20296303F906 | EW-104ST3 | 69943AD9-C516-43A5-A3A3-78C204C56DE4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ERBWWS8W_EW-104ST3_PCSB_FWR.pdf | SBO3ERBWWS8W_EW-104ST3_PCSB_FWR.pdf | Yes |  | Uploads\69943ad9-c516-43a5-a3a3-78c204c56de4.pdf | Exist
Mursyid | Yes | 8EA99699-6BC9-49C6-87E5-FEA2A3E87E36 | 288AA648-B63E-4977-BD17-20296303F906 | EW-104ST3 | 1956C1CA-ED09-4096-89CE-788A918B0B32 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ERBWWS9H_EW-104ST3_PCSB_NOOP.pdf | SBO3ERBWWS9H_EW-104ST3_PCSB_NOOP.pdf | Yes |  | Uploads\1956c1ca-ed09-4096-89ce-788a918b0b32.pdf | Exist
Mursyid | Yes | ABB580C0-985D-46BB-AEC1-A8CC9B008F96 | 61F57B54-AB75-40C6-AB41-20A8E951D6EF | TAMPAN-1 | EB4FFF91-0AAF-47B5-9E1A-4A5B8CB1B1EC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tampan-1 Final Well Report with Attachments.pdf | Tampan-1 Final Well Report with Attachments.pdf | Yes |  | Uploads\eb4fff91-0aaf-47b5-9e1a-4a5b8cb1b1ec.pdf | Exist
Mursyid | Yes | 082C963B-1FDE-4A41-9DFC-1A1C508C19DF | 61F57B54-AB75-40C6-AB41-20A8E951D6EF | TAMPAN-1 | 4855C47B-13F7-4B05-8113-224060A0D050 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tampan-1 NOOP Final Internal.pdf | Tampan-1 NOOP Final Internal.pdf | Yes |  | Uploads\4855c47b-13f7-4b05-8113-224060a0d050.pdf | Exist
Mursyid | Yes | EA122C63-21D0-4B5F-9D88-9E8DD65C71A0 | 1DD5E5E2-0A8B-4EE9-8689-219AE9B483EE | SAPA-21 | F11B0C2D-227F-43C4-9490-3683555276AF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK311-91-DR-TN-0001-00_SAPA Revisit 1 Phase I NOOP_Rev 0.pdf |  | No |  | Uploads\f11b0c2d-227f-43c4-9490-3683555276af.pdf | Exist
Mursyid | Yes | 4F3E0DE9-FA22-4B40-B572-73AB003E09F5 | 1DD5E5E2-0A8B-4EE9-8689-219AE9B483EE | SAPA-21 | 904A84C6-5E64-40C8-B48D-D861334B5935 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-21ST1 EOWR (2).pdf | SAPA-21ST1 EOWR (2).pdf | Yes |  | Uploads\904a84c6-5e64-40c8-b48d-d861334b5935.pdf | Exist
Mursyid | Yes | BCD4D9C8-F442-4784-955A-9E1A2D6362C2 | 6367637A-B3CA-4657-A2AF-226988ED4E5A | BRWA-13ST | 129B05FC-970C-448A-B70E-3F121E62A029 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | VPSB-BEF3-DRL-WWR-0002 BRWA-13ST1 Final Well Report Rev.1.pdf | VPSB-BEF3-DRL-WWR-0002 BRWA-13ST1 Final Well Report Rev.1.pdf | Yes |  | Uploads\129b05fc-970c-448a-b70e-3f121e62a029.pdf | Exist
Mursyid | Yes | A6F07F33-F049-4A3A-8B56-A0E49287E7CD | 6367637A-B3CA-4657-A2AF-226988ED4E5A | BRWA-13ST | 1A8DD5FF-6C98-4462-9BA9-BEFF2927EF41 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BRWA13ST1.pdf | NOOP BRWA13ST1.pdf | Yes |  | Uploads\1a8dd5ff-6c98-4462-9ba9-beff2927ef41.pdf | Exist
Mursyid | Yes | 77F10B73-2B42-40DB-A330-7B39300894B6 | 88B69B02-CA5E-48B3-9BCD-22A030AC3633 | WEST LUTONG-A13ST2 | DFDB17D0-D9AA-43BE-ACE1-8250E5989DB0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report WL13ST2.pdf |  | No |  | Uploads\dfdb17d0-d9aa-43be-ace1-8250e5989db0.pdf | Exist
Mursyid | Yes | 9A648E96-458A-430A-90C1-6A2C400299D4 | 88B69B02-CA5E-48B3-9BCD-22A030AC3633 | WEST LUTONG-A13ST2 | C0B8BD45-605F-44D1-AB09-05B073321FD8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP WL13ST2 Final_signed (1).pdf |  | No |  | Uploads\c0b8bd45-605f-44d1-ab09-05b073321fd8.pdf | Exist
Mursyid | Yes | 5C73F84E-7407-4C72-B589-78BE1D7CCB16 | 5958809C-79F4-4670-AEC4-2367DCBD817A | BUNGA KESUMBA-A2(B) | 4DE31669-578F-4C21-B6F3-4A2DDF27E654 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | B.Kesumba A-2_ Rev0_02072017 - PETRONAS SUBMISSION_FINAL.pdf |  | No |  | Uploads\4de31669-578f-4c21-b6f3-4a2ddf27e654.pdf | Exist
Mursyid | Yes | AE8C1DC8-8AFE-4CBD-8351-25FD51571898 | 5958809C-79F4-4670-AEC4-2367DCBD817A | BUNGA KESUMBA-A2(B) | 309B7A98-0D3E-4561-9A1F-A97310600C38 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Kesumba A-2 (B)_Final.pdf |  | No |  | Uploads\309b7a98-0d3e-4561-9a1f-a97310600c38.pdf | Exist
Mursyid | Yes | 22325BEF-ECB0-49AC-BDC4-DE7CFEA09F92 | 7BC00E72-6EC5-4D48-8F16-24267269F5BA | SEPAT-10 | 6E8295FC-F5B3-42FF-8A24-8BE32FCEFC95 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Sepat-10(approved).pdf | NOOP Sepat-10(approved).pdf | Yes |  | Uploads\6e8295fc-f5b3-42ff-8a24-8be32fcefc95.pdf | Exist
Mursyid | Yes | 937A3402-D061-487E-84AE-CBE4F975278C | 7BC00E72-6EC5-4D48-8F16-24267269F5BA | SEPAT-10 | 3834F4C9-F2AB-4ED9-87A5-6DDC5FF31FCC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sepat-10 FWR finalized.pdf | Sepat-10 FWR finalized.pdf | Yes |  | Uploads\3834f4c9-f2ab-4ed9-87a5-6ddc5ff31fcc.pdf | Exist
Mursyid | Yes | 4A9F17C2-AA56-4401-83C0-1248BCA63BA2 | 100CBEB6-8229-4F1C-A4DF-244493AA02F2 | SELENDANG-1 | 8D8F00FF-9EA2-4225-B3D3-6442B5010FBC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SLDGGL03_SELENDANG-1_PCSB_NOOP.pdf | PMO3SLDGGL03_SELENDANG-1_PCSB_NOOP.pdf | Yes |  | Uploads\8d8f00ff-9ea2-4225-b3d3-6442b5010fbc.pdf | Exist
Mursyid | Yes | 08D84EFD-BB40-4C52-8137-0E214AD3BA4B | 100CBEB6-8229-4F1C-A4DF-244493AA02F2 | SELENDANG-1 | 496D070D-D368-451C-872A-36CE0426DA94 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SLDGWS05_SELENDANG-1_PCSB_FWR.pdf | PMO3SLDGWS05_SELENDANG-1_PCSB_FWR.pdf | Yes |  | Uploads\496d070d-d368-451c-872a-36ce0426da94.pdf | Exist
Mursyid | Yes | CDCAE5D2-A53A-42AB-8D1F-05C14C4CCC1D | D4CB29BF-3FB8-40B9-813D-24B422F0A35E | LARUT A-35 | 3972E34D-3029-499E-9728-791B35831318 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-35 (NOOP_OP2)-Rev2.pdf | LARUT A-35 (NOOP_OP2)-Rev2.pdf | Yes |  | Uploads\3972e34d-3029-499e-9728-791b35831318.pdf | Exist
Mursyid | Yes | 4D458DC9-542C-4648-A2D1-CCBBDBB70356 | D4CB29BF-3FB8-40B9-813D-24B422F0A35E | LARUT A-35 | D65D5A52-0845-483F-836D-104F5D35342D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-35 (OP2) Final Well Report Rev. 0.pdf | LARUT A-35 (OP2) Final Well Report Rev. 0.pdf | Yes |  | Uploads\d65d5a52-0845-483f-836d-104f5d35342d.pdf | Exist
Mursyid | Yes | 6A5B7BC3-C944-4D09-90E6-0C70C63E26AE | 37735D40-5C98-4801-9694-254BB8930EDC | TNGB-A6 | C4739645-40D3-450A-8B46-5253F47FFF05 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS1G_TNGB-A6_PCSB_FWR.pdf | PMO3TNGBWS1G_TNGB-A6_PCSB_FWR.pdf | Yes |  | Uploads\c4739645-40d3-450a-8b46-5253f47fff05.pdf | Exist
Mursyid | Yes | 81EA7328-AA4B-4A0A-89F7-A7700F3FBD33 | 37735D40-5C98-4801-9694-254BB8930EDC | TNGB-A6 | E95FC575-369A-4AD5-97BF-B5A1B69F6226 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS61_TNGB-A6_PCSB_NOOP.pdf | PMO3TNGBWS61_TNGB-A6_PCSB_NOOP.pdf | Yes |  | Uploads\e95fc575-369a-4ad5-97bf-b5a1b69f6226.pdf | Exist
Mursyid | Yes | 668CF2E2-8844-4CED-A96A-C8BA96F405D6 | 1D10055F-631D-49F6-A9E7-2599E26C0165 | BERTAM A-6 | FDE0E01C-47B7-4C85-AD2F-F602DAAB735B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-6 Notice of Operations 20150425.pdf |  | No |  | Uploads\fde0e01c-47b7-4c85-ad2f-f602daab735b.pdf | Exist
Mursyid | Yes | 8C073B04-A1C2-4C34-9783-EBCC61D4A56E | 1D10055F-631D-49F6-A9E7-2599E26C0165 | BERTAM A-6 | BB0574B4-73D5-46C1-9011-12EA459B4B69 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-6 EOWR FINAL Part1.pdf |  | No |  | Uploads\bb0574b4-73d5-46c1-9011-12ea459b4b69.pdf | Exist
Mursyid | Yes | 446C941C-B15B-4DDC-9B08-66E024DB9483 | 51BAE098-5BB4-4199-B7B0-26A7D8EAC23E | SEMANTAN-1 | B292F1C0-20D6-4619-8A9C-36C8B5F300C6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEMANTAN-1 FWR.pdf |  | No |  | Uploads\b292f1c0-20d6-4619-8a9c-36c8b5f300c6.pdf | Exist
Mursyid | Yes | 23D7FC70-0E55-4BE1-92E5-3EA6AB3A6F69 | 51BAE098-5BB4-4199-B7B0-26A7D8EAC23E | SEMANTAN-1 | 41FAC71D-9660-45B6-BA3E-DBB83DFA5760 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SMTNWS01_SEMANTAN-1_PCSB.pdf | PMO3SMTNWS01_SEMANTAN-1_PCSB.pdf | Yes |  | Uploads\41fac71d-9660-45b6-ba3e-dbb83dfa5760.pdf | Exist
Mursyid | Yes | B8072EEF-D573-472A-8650-302052E7EE62 | 1E1A5194-1615-4590-A760-26B84C4888D2 | DUYONG SHALLOW-2 | 9050E596-6550-46D2-B61A-9085D6A438B6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DYSHWS06_DUYONG_SHALLOW_2.pdf | PMO3DYSHWS06_DUYONG_SHALLOW_2.pdf | Yes |  | Uploads\9050e596-6550-46d2-b61a-9085d6a438b6.pdf | Exist
Mursyid | Yes | 97F838BA-6449-4F3A-9C23-8A26B3EC8BAC | 1E1A5194-1615-4590-A760-26B84C4888D2 | DUYONG SHALLOW-2 | BD09FBB5-13AF-4E60-826D-72405F3FC7E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DYSHWS10_DUYONG_SHALLOW_2.pdf | PMO3DYSHWS10_DUYONG_SHALLOW_2.pdf | Yes |  | Uploads\bd09fbb5-13af-4e60-826d-72405f3fc7e8.pdf | Exist
Mursyid | Yes | 4ADF7D60-55BF-4352-8F4E-6ADA39C4C522 | 61C1CFF7-7A36-4D60-8588-26F3C02AE38E | ARA-1 | 2882FE6F-DE2D-4AB1-A035-2320525F07C6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ARA-WS04_ARA_1.pdf |  | No |  | Uploads\2882fe6f-de2d-4ab1-a035-2320525f07c6.pdf | Exist
Mursyid | Yes | 3821F75B-DE21-407D-8D6D-17173FDE8723 | 61C1CFF7-7A36-4D60-8588-26F3C02AE38E | ARA-1 | 47F24E90-BFFC-4CB1-A589-CFADE5BF7CB3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ARA-WS03_ARA_1.pdf |  | No |  | Uploads\47f24e90-bffc-4cb1-a589-cfade5bf7cb3.pdf | Exist
Mursyid | Yes | DD069232-3D01-4473-B298-0089C598FC9B | EE262CDB-1C4A-424F-8848-2746A5A4D103 | NAHARA-2 | 78EA59C4-685D-4106-984C-7CACE3861DC8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Nahara-2_Final for Submission to MPM.pdf | FWR Nahara-2_Final for Submission to MPM.pdf | Yes |  | Uploads\78ea59c4-685d-4106-984c-7cace3861dc8.pdf | Exist
Mursyid | Yes | 7E0EA099-AE6A-439C-9B0C-E277C4FFEE0A | EE262CDB-1C4A-424F-8848-2746A5A4D103 | NAHARA-2 | DA3B941F-527C-4D13-B361-D66C51E2D7BA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Nahara-2 Final for Submission to MPM with Attachment.pdf | NOOP Nahara-2 Final for Submission to MPM with Attachment.pdf | Yes |  | Uploads\da3b941f-527c-4d13-b361-d66c51e2d7ba.pdf | Exist
Mursyid | Yes | DE0F1EA0-F868-4F3E-B2FE-EADDE90A2229 | 521992F6-F69C-4132-AB18-2764E18C29DC | LARAK-1 | 960ED507-99C8-4CB6-BE79-591DBDD47DA5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LARKWS05_LARAK_1.pdf | 1.0 Larak-1 Final Well Report 17 Oct 2014.pdf | No |  | Uploads\960ed507-99c8-4cb6-be79-591dbdd47da5.pdf | Exist
Mursyid | Yes | E9681F13-B5A4-41F3-9B7E-EF161FEE4DB3 | 521992F6-F69C-4132-AB18-2764E18C29DC | LARAK-1 | 8C33571F-1848-4547-A495-391AB7BA38DF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LARKWS01_LARAK_1.pdf | SKO3LARKWS01_LARAK_1.pdf | Yes |  | Uploads\8c33571f-1848-4547-a495-391ab7ba38df.pdf | Exist
Mursyid | Yes | 81C28F61-793F-41DF-9D7F-553C54239D0A | 07F2CE31-CA7C-4998-B955-27E0C16A922F | BEKOK-AA19 | 86663017-608B-47FD-8B11-65BA9052A3A2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report AA19.pdf | Final Well Report AA19.pdf | Yes |  | Uploads\86663017-608b-47fd-8b11-65ba9052a3a2.pdf | Exist
Mursyid | Yes | 6AEF97EB-96D4-415B-BB66-AC6AAE5740C6 | 07F2CE31-CA7C-4998-B955-27E0C16A922F | BEKOK-AA19 | F03550FE-9FC9-426E-A2C4-23F25B875405 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA19.pdf | NOOP Bekok AA19.pdf | Yes |  | Uploads\f03550fe-9fc9-426e-a2c4-23f25b875405.pdf | Exist
Mursyid | Yes | 9BDF2C5A-5B8D-4A61-87FD-7E5F0B330BF1 | A45B64AE-B041-45B9-940B-2885DD54DC85 | CEKUR MANIS-1 | E477E568-5BED-4808-9B2C-A8344B0FD837 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3CKRMWS03_CEKUR MANIS-1_PCSB_FWR.pdf | SKO3CKRMWS03_CEKUR MANIS-1_PCSB_FWR.pdf | Yes |  | Uploads\e477e568-5bed-4808-9b2c-a8344b0fd837.pdf | Exist
Mursyid | Yes | BC4CC0E1-BE45-4B1D-9359-5C882B760BC0 | A45B64AE-B041-45B9-940B-2885DD54DC85 | CEKUR MANIS-1 | ED38F016-0314-4395-B207-73F78183D30D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3CKRMWS01_CEKUR MANIS-1_PCSB_NOOP_sep 14.pdf | SKO3CKRMWS01_CEKUR MANIS-1_PCSB_NOOP_sep 14.pdf | Yes |  | Uploads\ed38f016-0314-4395-b207-73f78183d30d.pdf | Exist
Mursyid | Yes | FF71D010-F73C-4019-A9E4-3DABFFA26526 | 9BA4F880-8050-4EF8-8E4B-28C2C0C18B74 | OPHIR-A1 | 640DFD88-A228-4F3D-8FA3-EC7FB826DB94 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | OPHIR-A1 ST1 EOWR [FINAL].pdf | OPHIR-A1 ST1 EOWR [FINAL].pdf | Yes |  | Uploads\640dfd88-a228-4f3d-8fa3-ec7fb826db94.pdf | Exist
Mursyid | Yes | 3317E2B4-B86C-400C-A727-FCF9062FE0FB | 9BA4F880-8050-4EF8-8E4B-28C2C0C18B74 | OPHIR-A1 | A7BEA7AB-2B2A-4497-A441-4FB3FC958CFF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Ophir-A1 well.pdf | NOOP Ophir-A1 well.pdf | Yes |  | Uploads\a7bea7ab-2b2a-4497-a441-4fb3fc958cff.pdf | Exist
Mursyid | Yes | 91FAC5D5-1DD2-46E5-9555-A8769826D0A8 | F235BE84-EA2E-4EDA-B16F-28E47A95AFEB | KNDW-D02 | 8785D2EF-EAD0-4FA4-BF3F-608772091E08 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D02 EOWR.pdf | KNDW-D02 EOWR.pdf | Yes |  | Uploads\8785d2ef-ead0-4fa4-bf3f-608772091e08.pdf | Exist
Mursyid | Yes | 7089E7D9-C75D-42AD-9862-8D2F504B57C6 | F235BE84-EA2E-4EDA-B16F-28E47A95AFEB | KNDW-D02 | D68F40CF-A5DD-44B2-AAFE-0B986BD3E7C0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-02 NOOP.pdf | KNDW D-02 NOOP.pdf | Yes |  | Uploads\d68f40cf-a5dd-44b2-aafe-0b986bd3e7c0.pdf | Exist
Mursyid | Yes | 57744C4D-7597-4E9C-8B61-95CFAEF5F9F8 | 9A86E73D-28EB-4BF5-AB67-290384BA99A2 | BUNGA KANGSAR A-4 | A277018B-C6D5-4AAA-83C6-E3EDE85A3389 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A4 NOOP.pdf |  | No |  | Uploads\a277018b-c6d5-4aaa-83c6-e3ede85a3389.pdf | Exist
Mursyid | Yes | D49419C1-4E30-4AA7-A456-14D553A4EB2B | 9A86E73D-28EB-4BF5-AB67-290384BA99A2 | BUNGA KANGSAR A-4 | 454468A6-EC2B-4511-896F-1DA504046F9E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A4 EOWR.pdf |  | No |  | Uploads\454468a6-ec2b-4511-896f-1da504046f9e.pdf | Exist
Mursyid | Yes | D4F46845-4E85-496B-9E88-99CBAEDAFCA8 | 6E1114A0-A0F7-4D83-8F26-298C1C647DF7 | SJ-609A | 8B406ACA-1377-4A0E-B660-C5731ACFA1F6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609A NOOP - MPM Drilling.pdf | SJ-609A NOOP - MPM Drilling.pdf | Yes |  | Uploads\8b406aca-1377-4a0e-b660-c5731acfa1f6.pdf | Exist
Mursyid | Yes | C1D90A12-F04F-4021-BCAA-C110392C5840 | 6E1114A0-A0F7-4D83-8F26-298C1C647DF7 | SJ-609A | 0D0B9CBE-8756-4900-A2D0-82DBC5E7C233 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609A EOWR_MPM.pdf | SJ-609A EOWR_MPM.pdf | Yes |  | Uploads\0d0b9cbe-8756-4900-a2d0-82dbc5e7c233.pdf | Exist
Mursyid | Yes | 333F7325-C82B-46DA-B63F-9FD8D312B7B0 | 7A492736-C78E-4B65-AB90-29DBCB5476F0 | TBG-B3ST2 | 63E3CC49-0F4D-49F8-87A9-EB1A58BCE369 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS8U_TBG-B5ST1_PCSB_FWR.pdf |  | No |  | Uploads\63e3cc49-0f4d-49f8-87a9-eb1a58bce369.pdf | Exist
Mursyid | Yes | D41E0504-F070-4C14-84F0-72EBB4EF5EE6 | 7A492736-C78E-4B65-AB90-29DBCB5476F0 | TBG-B3ST2 | 5DD6B0E7-E7AC-4067-9435-D9A0AF230C8D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS8N_TBG-B5ST1_PCSB_NOOP.pdf |  | No |  | Uploads\5dd6b0e7-e7ac-4067-9435-d9a0af230c8d.pdf | Exist
Mursyid | Yes | C25B15B4-C645-4E71-948C-76D27C0E5CDD | 11B95227-81C9-4388-A95B-29FF84A93AB4 | BUNGA DAHLIA A-3 | 0AFC540A-8EFB-45D6-8075-E86B811DE84D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BDL-A3 - signed.pdf |  | No |  | Uploads\0afc540a-8efb-45d6-8075-e86b811de84d.pdf | Exist
Mursyid | Yes | 11A24E41-4823-4520-BB85-4528351CF40F | 11B95227-81C9-4388-A95B-29FF84A93AB4 | BUNGA DAHLIA A-3 | 7D335E98-6C2A-496E-89F0-6BECDC0FE9E6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Bunga Dahlia-A3_ BDL-A3.pdf | NOOP_Bunga Dahlia-A3_ BDL-A3.pdf | Yes |  | Uploads\7d335e98-6c2a-496e-89f0-6becdc0fe9e6.pdf | Exist
Mursyid | Yes | 7BAEA2C5-C9F1-4CCF-A605-80FE50068611 | 3E2C7A61-27CF-46C2-AFDE-2AA8AE8086FC | BUNGA BAKAWALI DEEP-1 | 646E23A2-6100-4D52-BBBF-A0CAF61A6CEB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Bakawali Deep-1 NOOP Final - External.pdf | BUNGA BAKAWALI DEEP-1_NOOP_2013_PM.pdf | No |  | Uploads\646e23a2-6100-4d52-bbbf-a0caf61a6ceb.pdf | Exist
Mursyid | Yes | 5084D5C7-E411-4363-9F62-81CE2807D251 | 3E2C7A61-27CF-46C2-AFDE-2AA8AE8086FC | BUNGA BAKAWALI DEEP-1 | 7D2DA106-A7FC-46DF-B1B1-94BDCA9F8B46 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BUNGA BAKAWALI DEEP-1 FWR Final.pdf | BUNGA BAKAWALI DEEP-1 FWR Final.pdf | Yes |  | Uploads\7d2da106-a7fc-46df-b1b1-94bdca9f8b46.pdf | Exist
Mursyid | Yes | 92FADBD2-FA81-401C-8F42-3298FD983F21 | 34C790F1-1188-4690-B735-2AF42CDC460F | SUJT-C07 | 9B944210-ECBE-4D8E-B3D1-B661F1BB148D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMDPWS19_SUJT-C07.pdf | SBO3SMDPWS19_SUJT-C07.pdf | Yes |  | Uploads\9b944210-ecbe-4d8e-b3d1-b661f1bb148d.pdf | Exist
Mursyid | Yes | 9C9E4476-2401-414F-A198-F0B86296C1BC | 34C790F1-1188-4690-B735-2AF42CDC460F | SUJT-C07 | 28D4D733-B264-4780-81C8-710F0C05A9E5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMDPWS29_SUJT-C07.pdf | SBO3SMDPWS29_SUJT-C07.pdf | Yes |  | Uploads\28d4d733-b264-4780-81c8-710f0c05a9e5.pdf | Exist
Mursyid | Yes | E4A92676-6FA2-41C0-8498-38C9051F7986 | 78743B71-F2D6-40D5-B3FE-2B7C6921C569 | BERTAM A-2 | 3030244F-CE05-4BD0-A982-4D31F9B3BEC4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A02ST1 NOOP.pdf |  | No |  | Uploads\3030244f-ce05-4bd0-a982-4d31f9b3bec4.pdf | Exist
Mursyid | Yes | 161924DF-2D42-48A8-B982-90D59555ADBD | 78743B71-F2D6-40D5-B3FE-2B7C6921C569 | BERTAM A-2 | 58569AA5-2E83-4D16-B51B-23DD8FA37126 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A02ST1 EOWR.pdf |  | No |  | Uploads\58569aa5-2e83-4d16-b51b-23dd8fa37126.pdf | Exist
Mursyid | Yes | 265B4F6F-023B-4760-B6E4-4A7BD419F0AC | 9A1BE3FE-3AEA-496C-9CE3-2BAF00761A3E | BUNGA TERATAI C-2 | 6FDC1C6A-76B7-4A32-86EE-F9FC6DD2FE88 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BTR-C2.pdf |  | No |  | Uploads\6fdc1c6a-76b7-4a32-86ee-f9fc6dd2fe88.pdf | Exist
Mursyid | Yes | 87A8447C-BE65-415F-83D8-CE4817E7E1F4 | 9A1BE3FE-3AEA-496C-9CE3-2BAF00761A3E | BUNGA TERATAI C-2 | FB8D0E4D-11D9-4126-9DD4-B9DD5A1B528D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BTR-C2 NOOP (DWP).pdf |  | No |  | Uploads\fb8d0e4d-11d9-4126-9dd4-b9dd5a1b528d.pdf | Exist
Mursyid | Yes | CE815D8D-CE65-455F-8DAD-F2262C6A59F8 | C7C06C94-0D41-4840-86A8-2BB8D6F0D32E | BESAR-A5 | A989734E-ED8A-46B7-822B-259705C664CB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Besar-A5.pdf | NOOP Besar-A5.pdf | Yes |  | Uploads\a989734e-ed8a-46b7-822b-259705c664cb.pdf | Exist
Mursyid | Yes | 097E4D27-50D6-4553-AE23-E50AF43AA222 | C7C06C94-0D41-4840-86A8-2BB8D6F0D32E | BESAR-A5 | 936CBF86-EF0B-4C6B-9C1B-0BAF98A34593 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Besar-A5.pdf | FWR Besar-A5.pdf | Yes |  | Uploads\936cbf86-ef0b-4c6b-9c1b-0baf98a34593.pdf | Exist
Mursyid | Yes | 6477AF4C-C983-4A3F-8F51-C0079D78AD90 | 7FEADBB5-438B-43C1-AA37-2BBE9DF563A0 | ANJUNG-A2 | 967A27B8-E808-427D-A913-2B7EA1162BCA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Anjung Gas Development AJJT-A2 NOOP SIGNED (1).pdf |  | No |  | Uploads\967a27b8-e808-427d-a913-2b7ea1162bca.pdf | Exist
Mursyid | Yes | E317A43B-7361-4FAF-ADB6-B93243132E08 | 7FEADBB5-438B-43C1-AA37-2BBE9DF563A0 | ANJUNG-A2 | B006EAAF-A13D-475C-9311-D30FDB13B63C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Anjung Gas Development AJJT-A2 Final Well Report.pdf |  | No |  | Uploads\b006eaaf-a13d-475c-9311-d30fdb13b63c.pdf | Exist
Mursyid | Yes | 4FEA70B5-30C9-49C1-91AE-FAA5D8A8DDA3 | 17737BD7-CE16-4127-8E9C-2BC560C393EF | TBK-A1 | C1C6A5D5-29A3-47B9-9A8D-FE028FDE2166 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A1ST1 Final Well Report final.pdf |  | No |  | Uploads\c1c6a5d5-29a3-47b9-9a8d-fe028fde2166.pdf | Exist
Mursyid | Yes | 8E8420EE-0DBC-4E7E-B402-9BA251A5676F | 17737BD7-CE16-4127-8E9C-2BC560C393EF | TBK-A1 | E4621B8A-B413-4C34-81B8-CFF9700591A7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TBK-A1.pdf | NOOP TBK-A1.pdf | Yes |  | Uploads\e4621b8a-b413-4c34-81b8-cff9700591a7.pdf | Exist
Mursyid | Yes | FE972F7A-CD1F-463F-99AB-B33C153283CD | 4E5E4549-4759-41C3-9DC8-2C1534CBAD9A | BN-79 | D13C0E5C-EC24-4172-8A7C-D1716688481A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-79 Final (Internal).pdf | NOOP BN-79 Final (Internal).pdf | Yes |  | Uploads\d13c0e5c-ec24-4172-8a7c-d1716688481a.pdf | Exist
Mursyid | Yes | 586A7687-4DE2-4EA1-AD8C-E767B4DD12DB | 4E5E4549-4759-41C3-9DC8-2C1534CBAD9A | BN-79 | A0252F88-781B-448E-AFF3-F482263AA4ED | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN79_0_Final Well Report.pdf | BN79_0_Final Well Report.pdf | Yes |  | Uploads\a0252f88-781b-448e-aff3-f482263aa4ed.pdf | Exist
Mursyid | Yes | E5B00ACC-1A48-43A1-B82D-720B376EEFF4 | 20BAD509-7DE0-4E1D-8B75-2C63E987CAD9 | F13ESC-A6 | B66B3829-8319-4605-AB1F-246D0D54FF26 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PETRONAS Final Well Report F13ESC-6 (Signed).pdf |  | No |  | Uploads\b66b3829-8319-4605-ab1f-246d0d54ff26.pdf | Exist
Mursyid | Yes | 02C07E64-B926-4745-992F-4DF35E820BFF | 20BAD509-7DE0-4E1D-8B75-2C63E987CAD9 | F13ESC-A6 | 3AF49D8D-67F8-4311-AE5E-12B2B547D710 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Notice of Operations (NOOP)_Shallow Clastics F13ESC-6 [INTERNAL].pdf |  | No |  | Uploads\3af49d8d-67f8-4311-ae5e-12b2b547d710.pdf | Exist
Mursyid | Yes | F0BD39F8-2128-479C-85B2-2F820EF4B71A | 389A898C-4A54-4A75-B2BE-2C9E59EFCAE4 | SM-B59ST2 | 832BE719-F00E-495B-BC32-6B4B495F7820 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B59S2 FWR.pdf |  | No |  | Uploads\832be719-f00e-495b-bc32-6b4b495f7820.pdf | Exist
Mursyid | Yes | 49F801A2-2184-4B95-9AD5-A8FD95168484 | 389A898C-4A54-4A75-B2BE-2C9E59EFCAE4 | SM-B59ST2 | 8EF14212-A0FB-486B-A0CB-DFD77BC72924 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-B59S2 NOOP.pdf | SM-B59ST2 NOOP Addendum.pdf | No |  | Uploads\8ef14212-a0fb-486b-a0cb-dfd77bc72924.pdf | Exist
Mursyid | Yes | 2CBF245F-72F6-4BBD-9208-9BA18308566F | 1779F7AB-C644-4707-8A9F-2CEC290BF547 | PELAJO-1 | EB156B48-403F-4237-8AAD-04E8C25072DF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pelajo-1 ST1 PCSB FWR.pdf | Pelajo-1 ST1 PCSB FWR.pdf | Yes |  | Uploads\eb156b48-403f-4237-8aad-04e8c25072df.pdf | Exist
Mursyid | Yes | 9BB4DB3A-0D0C-46C4-816C-C277F12430F5 | 1779F7AB-C644-4707-8A9F-2CEC290BF547 | PELAJO-1 | 66D89C66-00B2-4DD9-BCE0-A1DAF0B8BDEC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pelajo-1 NOOP_rev0.pdf | Pelajo-1 NOOP_rev0.pdf | Yes |  | Uploads\66d89c66-00b2-4dd9-bce0-a1daf0b8bdec.pdf | Exist
Mursyid | Yes | 4B7FC77F-13C5-4081-A7C5-835E21DE3586 | 59B50BFF-7995-4B0C-99AD-2DDF1FACA83B | GAHARU-1 | 2685A6BF-0D91-46D5-8083-BAE314DE0B28 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Gaharu-1 Internal (Rev.1)_signed.pdf |  | No |  | Uploads\2685a6bf-0d91-46d5-8083-bae314de0b28.pdf | Exist
Mursyid | Yes | B3768649-EF08-4BC3-A0C9-1DB425A7A765 | 59B50BFF-7995-4B0C-99AD-2DDF1FACA83B | GAHARU-1 | 007D1587-CA3F-45E3-90CE-B8D420526201 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gaharu-1 Final Well Report with Attachments.pdf | Gaharu-1 Final Well Report with Attachments.pdf | Yes |  | Uploads\007d1587-ca3f-45e3-90ce-b8d420526201.pdf | Exist
Mursyid | Yes | A4058FBE-319A-428A-8DEE-5872F5DC3E81 | 60E75136-E366-4B00-82CF-2DEE2B8ED352 | LARAK-A2 | ABABB286-02B6-48F5-B82F-C9C431DDAA29 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 LRK-A2 FINAL WELL REPORT.pdf |  | No |  | Uploads\ababb286-02b6-48f5-b82f-c9c431ddaa29.pdf | Exist
Mursyid | Yes | AEB4ED12-72F0-4EC9-845E-ADA2787679E3 | 60E75136-E366-4B00-82CF-2DEE2B8ED352 | LARAK-A2 | 4F855739-A0E4-4C99-827A-83EC2E481E80 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LRK A2 NOOP 3-July-2019 FINAL Rev1.pdf |  | No |  | Uploads\4f855739-a0e4-4c99-827a-83ec2e481e80.pdf | Exist
Mursyid | Yes | 554AD539-7D54-4F2F-B6A5-A052155E98ED | 5D5F8188-C45C-4F5F-9E3A-2DF76BBC95C3 | LARUT-A23ST1 | D0A2ACEB-6C40-4671-A4B4-AD7ECA06A9E5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-23ST1 (OP5_NOOP) rev.3.pdf | LARUT A-23ST1 (OP5_NOOP) rev.3.pdf | Yes |  | Uploads\d0a2aceb-6c40-4671-a4b4-ad7eca06a9e5.pdf | Exist
Mursyid | Yes | E33E3198-C180-433A-A54D-342F6D0E2F4E | 5D5F8188-C45C-4F5F-9E3A-2DF76BBC95C3 | LARUT-A23ST1 | 9CDC4400-C4BC-433B-857A-0900C9DFDED4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-23ST1 (OP5) Final Well Report_Rev0.pdf | LARUT A-23ST1 (OP5) Final Well Report_Rev0.pdf | Yes |  | Uploads\9cdc4400-c4bc-433b-857a-0900c9dfded4.pdf | Exist
Mursyid | Yes | 40403A88-A0C8-47CF-9253-379F9845E8BA | 1E541D8D-E1B8-4108-995D-2E2C142FA1E6 | F12-A2 | 4263BBD3-5950-459B-907E-D3269E383111 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP F12-A2 FINAL.pdf | NOOP F12-A2 FINAL.pdf | Yes |  | Uploads\4263bbd3-5950-459b-907e-d3269e383111.pdf | Exist
Mursyid | Yes | 49395640-7497-4F90-9EA3-08D7FB351239 | 1E541D8D-E1B8-4108-995D-2E2C142FA1E6 | F12-A2 | 8A193171-349C-40B9-96EA-4B6B8538590C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F12-A2 FWR.pdf |  | No |  | Uploads\8a193171-349c-40b9-96ea-4b6b8538590c.pdf | Exist
Mursyid | Yes | E1AC60F7-C6ED-4450-A33E-B122D5ACA5BA | 0659EC77-8C37-4A84-9EFE-2E4700D97E46 | PGA-05 | 8AC7E38D-D1B9-4381-B9C4-3FD7822F948A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-05_NOOP 20th Apr 2020.pdf | PGA-05 NOOP Rev 1.0_Supplemental.pdf | No |  | Uploads\8ac7e38d-d1b9-4381-b9c4-3fd7822f948a.pdf | Exist
Mursyid | Yes | B0461BCB-D572-4A77-8438-FB22144840F1 | 0659EC77-8C37-4A84-9EFE-2E4700D97E46 | PGA-05 | 3566FE4B-DE23-44E6-AC2F-76B4B37DFDED | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-05 EOWR_FINAL.pdf | PGA-05 EOWR_FINAL.pdf | Yes |  | Uploads\3566fe4b-de23-44e6-ac2f-76b4b37dfded.pdf | Exist
Mursyid | Yes | FB6BA8ED-D6B0-43D4-BD8F-DB303EE8C384 | 0407A029-C3FD-4B3B-BEB2-2E6D23882474 | SM-114 | F335AC54-E21C-4E3B-82EB-BE91C7447835 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-114 NOOP.pdf |  | No |  | Uploads\f335ac54-e21c-4e3b-82eb-be91c7447835.pdf | Exist
Mursyid | Yes | 369398AF-8A64-49C4-95F6-22BBEFA2BFC7 | 0407A029-C3FD-4B3B-BEB2-2E6D23882474 | SM-114 | EE791BAB-EA50-4427-890B-048B8B4BD113 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-114 EOWR (Revised Cost).pdf |  | No |  | Uploads\ee791bab-ea50-4427-890b-048b8b4bd113.pdf | Exist
Mursyid | Yes | 70AEB13C-A12C-4E1B-89C7-8E703E3CD765 | 905CD9B5-95FF-468F-B344-2E8196548DF8 | BERGADING-A3(B) | BA463054-B9A8-4EA9-A13A-E85B12DE45B6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading-A3(B) EoWR_FINAL (2).pdf | Bergading-A3(B) EoWR_FINAL (2).pdf | Yes |  | Uploads\ba463054-b9a8-4ea9-a13a-e85b12de45b6.pdf | Exist
Mursyid | Yes | 4F66FEC5-C9AD-48AC-8281-65FA81EA858B | 905CD9B5-95FF-468F-B344-2E8196548DF8 | BERGADING-A3(B) | 5977A995-7E37-4C68-B2F0-534306BB3B89 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading A-3 (B) FINAL_SIGNED.pdf | Bergading A-3 (B) FINAL_SIGNED.pdf | Yes |  | Uploads\5977a995-7e37-4c68-b2f0-534306bb3b89.pdf | Exist
Mursyid | Yes | E9C64F94-F3D5-4757-9ECA-9334820D53E1 | 312EC3A4-A94B-4D0E-A8CD-2F02ABB90C64 | BAKONG A-02 | A1ED007C-504D-465F-A44B-3A750EA47F16 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 BKG-A2 FINAL WELL REPORT - FINAL wo attachments.pdf |  | No |  | Uploads\a1ed007c-504d-465f-a44b-3a750ea47f16.pdf | Exist
Mursyid | Yes | 3B4B1976-C16D-451B-9F63-C16F531B9559 | 312EC3A4-A94B-4D0E-A8CD-2F02ABB90C64 | BAKONG A-02 | 03397B67-F4A4-4714-8555-3BC090614841 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A2 NOOP 17-July-2019 FINAL.pdf |  | No |  | Uploads\03397b67-f4a4-4714-8555-3bc090614841.pdf | Exist
Mursyid | Yes | 7EF334DB-AC4C-4368-BF29-96AA7639FA2F | CD3EFF66-A102-4C50-9772-2F657999B09D | BN-76 | E45585CF-E377-4CF3-B5B7-D9234CB369D3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-76 FWR Final.pdf | BN-76 FWR Final.pdf | Yes |  | Uploads\e45585cf-e377-4cf3-b5b7-d9234cb369d3.pdf | Exist
Mursyid | Yes | 43464B15-4A5C-4EE7-8FD6-5A6DBD7C8924 | CD3EFF66-A102-4C50-9772-2F657999B09D | BN-76 | 63FD27FB-7A05-4CCE-8E8D-B3026D722989 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-76 Final Rev2 (Internal).pdf | NOOP BN-76 Final Rev2 (Internal).pdf | Yes |  | Uploads\63fd27fb-7a05-4cce-8e8d-b3026d722989.pdf | Exist
Mursyid | Yes | BAA94AFA-0177-4963-A3FC-563B0ABE514C | 2DFBB79A-FB78-493B-BD59-2F84B1A255F8 | ANGSI-B31 | 53D15997-66C9-4699-9A11-355152078985 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIGL13_ANGSI-B31.pdf | PMO3ANSIGL13_ANGSI-B31.pdf | Yes |  | Uploads\53d15997-66c9-4699-9a11-355152078985.pdf | Exist
Mursyid | Yes | 9526C074-6A04-4B2D-82D8-B68DC89E8770 | 2DFBB79A-FB78-493B-BD59-2F84B1A255F8 | ANGSI-B31 | 5A3E8944-96EE-4B5A-B633-652CA2A8EDE6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Angsi B31 Final Well Report.pdf | Angsi B31 Final Well Report.pdf | Yes |  | Uploads\5a3e8944-96ee-4b5a-b633-652ca2a8ede6.pdf | Exist
Mursyid | Yes | 420AC9BC-CB93-4250-8923-1815D8C24E0F | B43C4211-6A1E-4A4E-B6BC-2FB55E604220 | SNPA-04 | 062B3C50-0311-458D-AB75-6B4B30813180 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0001-00_SNPA Dev Project Revisit 2 Phase I - NOOP.pdf |  | No |  | Uploads\062b3c50-0311-458d-ab75-6b4b30813180.pdf | Exist
Mursyid | Yes | E7CE376B-5013-4B3A-ACD6-9A884C99C8CB | B43C4211-6A1E-4A4E-B6BC-2FB55E604220 | SNPA-04 | 414A22AC-9A47-444F-A53B-7FB6ADB042AC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0010-00_SNPA-04 EOWR.pdf | MOM-SK309-72-DNC-RP-0010-00_SNPA-04 EOWR.pdf | Yes |  | Uploads\414a22ac-9a47-444f-a53b-7fb6adb042ac.pdf | Exist
Mursyid | Yes | CC50907F-55D1-466C-A16C-95CE352D0E82 | 70F7CEF4-1009-4F6C-A1B1-3114782121FB | CD-C10 | CFFBF9FD-0F73-440A-9427-59B56D13B992 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CDORWS3D_CD-C10_FWR_PETROFAC.pdf | PMO3CDORWS1S_CD-C10_NOOP_PETROFAC.pdf | No |  | Uploads\cffbf9fd-0f73-440a-9427-59b56d13b992.pdf | Exist
Mursyid | Yes | E3A7E599-310E-46BF-8807-B717649F3C14 | 70F7CEF4-1009-4F6C-A1B1-3114782121FB | CD-C10 | D9169008-534B-4E5C-A237-2190CED94D66 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CDORWS1S_CD-C10_NOOP_PETROFAC.pdf |  | No |  | Uploads\d9169008-534b-4e5c-a237-2190ced94d66.pdf | Exist
Mursyid | Yes | 27914EF0-3AFA-44CC-B20A-AC2D6EA176B0 | EA53CBC7-80EC-436A-9B65-31E9CB199614 | TT-A5 | DA41BFE4-25A8-4B47-8362-4EBF294D012D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A5 Final.pdf | TT-A5 Final.pdf | Yes |  | Uploads\da41bfe4-25a8-4b47-8362-4ebf294d012d.pdf | Exist
Mursyid | Yes | 4B058724-7392-4EB3-9615-38168B17EB31 | EA53CBC7-80EC-436A-9B65-31E9CB199614 | TT-A5 | 831EB44E-AD91-43C1-BE8A-48C72B7FF379 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A5_FWR 2017 Final-for MPM.pdf | TT-A5_FWR 2017 Final-for MPM.pdf | Yes |  | Uploads\831eb44e-ad91-43c1-be8a-48c72b7ff379.pdf | Exist
Mursyid | Yes | 49F5DA78-3FBC-4B04-83C8-34F223ADC2E8 | CA1E3BB1-0553-431B-8763-31ED28249935 | BENDAI-1 | 90A5E4C8-935F-4F7E-B8E8-286587B10E88 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BENDGL6643_BENDAI-1_PCSB_FWR.pdf | SKO3BENDGL6643_BENDAI-1_PCSB_FWR.pdf | Yes |  | Uploads\90a5e4c8-935f-4f7e-b8e8-286587b10e88.pdf | Exist
Mursyid | Yes | 47010087-EF0F-461E-A1A5-BC5E9EE723C2 | CA1E3BB1-0553-431B-8763-31ED28249935 | BENDAI-1 | E36A4B3C-21A9-4D59-A5FD-C79771C826D8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BENDAI-1 APPRAISAL WELL NOOP.pdf | BENDAI-1 APPRAISAL WELL NOOP.pdf | Yes |  | Uploads\e36a4b3c-21a9-4d59-a5fd-c79771c826d8.pdf | Exist
Mursyid | Yes | 9DD68AAF-0C2F-40D4-8C9B-AD96767E8D73 | 23BEABC4-F49D-4D7B-9A11-31FB2122A780 | TBK-A3 | 33F5675C-6082-44B0-A6C2-48BA0C7D4B0C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TBK-A3.pdf | NOOP TBK-A3.pdf | Yes |  | Uploads\33f5675c-6082-44b0-a6c2-48ba0c7d4b0c.pdf | Exist
Mursyid | Yes | EC28DC1D-586C-47CF-A37A-7908AEE3615E | 23BEABC4-F49D-4D7B-9A11-31FB2122A780 | TBK-A3 | C1E57EDC-B787-4CCD-97C2-48ABD315FE48 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A3ST1ST2 Final Well Report.pdf |  | No |  | Uploads\c1e57edc-b787-4ccd-97c2-48abd315fe48.pdf | Exist
Mursyid | Yes | 3B4830EC-A70F-4AA0-9BFB-CAC477A0E31E | DCE80E19-DA20-453E-B5A3-3241F492E6A2 | MERPAUH-1 | 537384E2-BEF2-46E4-8335-09CC60487050 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Merpauh-1 Notice of Operations rev9.pdf | Merpauh-1 Notice of Operations rev9.pdf | Yes |  | Uploads\537384e2-bef2-46e4-8335-09cc60487050.pdf | Exist
Mursyid | Yes | 980FBDD1-7BAA-484C-B325-EF30FDC59EAB | DCE80E19-DA20-453E-B5A3-3241F492E6A2 | MERPAUH-1 | B3CA7089-E2C2-4862-82CF-F7B2603866F5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Merpauh-1 and ST1_V2EOWR_.pdf | Merpauh-1 and ST1_V2EOWR_.pdf | Yes |  | Uploads\b3ca7089-e2c2-4862-82cf-f7b2603866f5.pdf | Exist
Mursyid | Yes | 93DB1ED1-0A7B-48E1-AAB0-D042D495A18A | 42122C2D-E48B-4016-A622-3275658E40F4 | KAMOMIL-1 | 588FC151-D7C8-40BB-B06A-2C48473531C5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kamomil-1_NOOP_Internal.pdf | Kamomil-1_NOOP_Internal.pdf | Yes |  | Uploads\588fc151-d7c8-40bb-b06a-2c48473531c5.pdf | Exist
Mursyid | Yes | 52215DCE-48DE-4EEF-89C1-5054F42A7957 | 42122C2D-E48B-4016-A622-3275658E40F4 | KAMOMIL-1 | 85351F40-1D68-4995-86A3-C0CEFC7F1AD6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FINAL WELL REPORT (FWR) KAMOMIL-1, SK 316, OFFSHORE SARAWAK.pdf | FINAL WELL REPORT (FWR) KAMOMIL-1, SK 316, OFFSHORE SARAWAK.pdf | Yes |  | Uploads\85351f40-1d68-4995-86a3-c0cefc7f1ad6.pdf | Exist
Mursyid |  | 9CFA87D7-12C3-4C04-B72B-65EDD44A7F53 | CCB99400-EBD9-4E9D-8237-32F0C84D0D76 | WPPB-15/15ST1 | 8C33E588-465A-4E55-9113-E4F95DFCF11E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NULL |  | No |  | Uploads\8c33e588-465a-4e55-9113-e4f95dfcf11e.pdf | Exist
Mursyid | Yes | 65F9E53F-3102-4620-972B-B744749C75BE | CCB99400-EBD9-4E9D-8237-32F0C84D0D76 | WPPB-15/15ST1 | 5B2952BB-284D-42B0-9870-E2A1D808B84F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf |  | No |  | Uploads\5b2952bb-284d-42b0-9870-e2a1d808b84f.pdf | Exist
Mursyid | Yes | E7DB2C2F-AA4A-4456-B5F8-6423BD4CD739 | A54A13F0-184B-465D-9C88-3301DDD7BDA4 | GEDOMBAK-2 | E6FAB8E7-F3D4-4E83-8FBC-6DF65D851875 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GEDOMBAK-2 FINAL WELL REPORT.pdf | GEDOMBAK-2 FINAL WELL REPORT.pdf | Yes |  | Uploads\e6fab8e7-f3d4-4e83-8fbc-6df65d851875.pdf | Exist
Mursyid | Yes | 0EA21D1D-874E-4793-9114-5B3BB2A2B29E | A54A13F0-184B-465D-9C88-3301DDD7BDA4 | GEDOMBAK-2 | B6B6EAE4-542F-462C-B30A-7E3D0D9EDAA2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - GEDOMBAK-2_APPROVED.pdf | NOOP - GEDOMBAK-2.pdf | No |  | Uploads\b6b6eae4-542f-462c-b30a-7e3d0d9edaa2.pdf | Exist
Mursyid | Yes | A8C02939-33F1-406C-A171-26FDF173A022 | 018474E6-0BDF-419C-8FDE-33A2B63D66C3 | LARUT A-34 | B70E57EB-B84D-4828-9F02-95E64B5A1E00 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-34 (OP1) Final Well Report.pdf | LARUT A-34 (OP1) Final Well Report.pdf | Yes |  | Uploads\b70e57eb-b84d-4828-9f02-95e64b5a1e00.pdf | Exist
Mursyid | Yes | 2F3DA142-FF77-493B-BFA9-BDF1B7917C26 | 018474E6-0BDF-419C-8FDE-33A2B63D66C3 | LARUT A-34 | 23D42890-8CF3-43B4-A792-127999F21E30 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-34 (NOOP_OP1)-Rev2.pdf | LARUT A-34 (NOOP_OP1)-Rev2.pdf | Yes |  | Uploads\23d42890-8cf3-43b4-a792-127999f21e30.pdf | Exist
Mursyid | Yes | E9790C9A-B997-474C-BBD3-20CF25A609D7 | EED5E706-8C27-4CC9-9494-33BAE9B9B11F | TADOM-1 | 795F2ABB-2E92-4A96-8A62-6D4B5B45356E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tadom-1 Internal NOOP.pdf | NOOP TADOM-1RDR1 EXP.pdf | No |  | Uploads\795f2abb-2e92-4a96-8a62-6d4b5b45356e.pdf | Exist
Mursyid | Yes | 65C7E09D-BEFD-4B73-BD56-37001A5318A1 | EED5E706-8C27-4CC9-9494-33BAE9B9B11F | TADOM-1 | 07FD7506-3A82-4C61-9F85-234DEF592563 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tadom-1RDR1_with attachement-Petronas Final Well Report.pdf | Tadom-1RDR1_with attachement-Petronas Final Well Report.pdf | Yes |  | Uploads\07fd7506-3a82-4c61-9f85-234def592563.pdf | Exist
Wadi | Yes | D03644D0-6FBC-44FB-91B5-1C4CFFB3FD28 | F7ECEE17-B575-416A-9B96-344C3B7BCE73 | SASA-15 | 3007D75B-D152-4398-A390-0C7BEEC934D7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Ph1_BATCH 2 NOOP.pdf |  | No |  | Uploads\3007d75b-d152-4398-a390-0c7beec934d7.pdf | Exist
Mursyid | Yes | 7E705BBE-6065-40EE-9FC4-97D82EAEB018 | F7ECEE17-B575-416A-9B96-344C3B7BCE73 | SASA-15 | 4B65D833-4BDF-4295-910F-81120E73ABC7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA-15 EOWR.pdf | SASA-15 EOWR.pdf | Yes |  | Uploads\4b65d833-4bdf-4295-910f-81120e73abc7.pdf | Exist
Mursyid | Yes | F45865F8-B82E-4E27-B4A5-AEE227A2D9BD | 91667EAD-C07B-4ED8-975A-34737D1993DC | WEST LUTONG-A08ST3 | 1CCD2027-E05F-471C-81C5-A331FC3B2557 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report WL8ST3 - FINAL.pdf |  | No |  | Uploads\1ccd2027-e05f-471c-81c5-a331fc3b2557.pdf | Exist
Mursyid | Yes | 48873B25-EFFE-424A-916E-60E1AE96DEFA | 91667EAD-C07B-4ED8-975A-34737D1993DC | WEST LUTONG-A08ST3 | 4226DE9F-B75C-4D37-8BCF-21A5EF1B424F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP WL8ST3.pdf |  | No |  | Uploads\4226de9f-b75c-4d37-8bcf-21a5ef1b424f.pdf | Exist
Mursyid | Yes | F452656D-0812-4005-9CA9-35B278C40E97 | F366EF79-8F10-4890-9A63-34CA4365AB6E | SAPA-07 | 65BC80C6-6E68-4AB2-9468-DA1898F8C420 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS1K_SAPA-07_PTTEP.pdf | SKO3ACISWS1K_SAPA-07_PTTEP.pdf | Yes |  | Uploads\65bc80c6-6e68-4ab2-9468-da1898f8c420.pdf | Exist
Mursyid | Yes | AD35F4E8-D219-460F-B126-B9E762E5C912 | F366EF79-8F10-4890-9A63-34CA4365AB6E | SAPA-07 | E99C70DF-6124-4D35-84CB-3A95D232334E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-07 EOWR.pdf | SAPA-07 EOWR.pdf | Yes |  | Uploads\e99c70df-6124-4d35-84cb-3a95d232334e.pdf | Exist
Mursyid | Yes | 51D343DB-EEBB-4B2E-8A78-C1911579EE2A | 19BC8D1B-3823-4EB1-9506-34CCE94FB591 | DULANG-B30ST1 | 3D2AECEA-3884-48BE-A8D4-0DA020B70631 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | B30ST1 Petronas Final Well Report_DULANG-B30_PCSB.pdf |  | No |  | Uploads\3d2aecea-3884-48be-a8d4-0da020b70631.pdf | Exist
Mursyid | Yes | 42337823-5A5A-482A-BD12-A4835C53E66E | 19BC8D1B-3823-4EB1-9506-34CCE94FB591 | DULANG-B30ST1 | BAF99512-1EE4-40C3-B21D-2455B3D7F343 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang Rev 2 - NOOP_B30ST1 (Internal Copy).pdf |  | No |  | Uploads\baf99512-1ee4-40c3-b21d-2455b3d7f343.pdf | Exist
Mursyid | Yes | E4DDFAC4-43FB-49D6-9873-84E234953DFA | 3A85B961-CCD4-49FD-BD64-35F31F532C09 | PRPA-13 | E2ABA7C6-1FB2-4A3D-ACAE-6585561EA728 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-94-DNC-PR-0002-00-0_PRPA_INFILL_NOOP_PRPA-13_PTTEP.pdf |  | No |  | Uploads\e2aba7c6-1fb2-4a3d-acae-6585561ea728.pdf | Exist
Mursyid | Yes | 7EBEA8FA-2D0C-4416-9F59-472AF4CED495 | 3A85B961-CCD4-49FD-BD64-35F31F532C09 | PRPA-13 | A594DDCB-3585-4B74-ACF4-9E78CBA467C3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-94-DNC-RP-0001_PRPA-13 EOWR.pdf | MY-SK311-94-DNC-RP-0001_PRPA-13 EOWR.pdf | Yes |  | Uploads\a594ddcb-3585-4b74-acf4-9e78cba467c3.pdf | Exist
Mursyid | Yes | D5FE935E-4AC1-4F3D-B65C-2F98311D5CF9 | CCD1DF43-AA8A-447F-914C-362DBEED16B5 | MIRDANGA-1 | 2FF071AC-9066-4C2F-B0E6-C6A6AB7DC75D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mirdanga-1 Final Well Report w Attachements.pdf | Mirdanga-1 Final Well Report w Attachements.pdf | Yes |  | Uploads\2ff071ac-9066-4c2f-b0e6-c6a6ab7dc75d.pdf | Exist
Mursyid | Yes | C49B0C02-ECB3-4674-BE9D-A1FCD6F8AFFF | CCD1DF43-AA8A-447F-914C-362DBEED16B5 | MIRDANGA-1 | 34F04187-2A17-4043-90CB-8D0DE9A6F084 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mirdanga-1 - SK GARUDA NOOP.pdf | Mirdanga-1 - SK GARUDA NOOP.pdf | Yes |  | Uploads\34f04187-2a17-4043-90cb-8d0de9a6f084.pdf | Exist
Mursyid | Yes | 174F479E-4833-4823-9838-0E7E0C5C740B | 761BDFB6-9187-4BC6-B31C-36A3EBAA9540 | GK-W515B | 4B9ED68A-BA45-42F2-8C4A-0E615D540B3B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-W515B NOOP_SHELL.pdf |  | No |  | Uploads\4b9ed68a-ba45-42f2-8c4a-0e615d540b3b.pdf | Exist
Mursyid | Yes | E35E2B6F-43AD-4280-B946-D4ED61E150B3 | 761BDFB6-9187-4BC6-B31C-36A3EBAA9540 | GK-W515B | D72A9FBF-5E7F-437A-BE1A-C1C041E76A6A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK W515B FINAL EOWR .pdf | GK W515B FINAL EOWR .pdf | Yes |  | Uploads\d72a9fbf-5e7f-437a-be1a-c1c041e76a6a.pdf | Exist
Mursyid | Yes | A787DE76-DEFB-4F3A-B0C6-CEA7382B2674 | 76A0AEFF-D425-4C23-B637-3726CEE4F349 | KNDW-D01 | F29A0DA4-7FB3-4490-8C8B-F41A4F8EFF7F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D01 EOWR.pdf | KNDW-D01 EOWR.pdf | Yes |  | Uploads\f29a0da4-7fb3-4490-8c8b-f41a4f8eff7f.pdf | Exist
Mursyid | Yes | 19337C22-A9A3-4520-9C61-351004BD2246 | 76A0AEFF-D425-4C23-B637-3726CEE4F349 | KNDW-D01 | 7DF1E4D4-5DB4-4FD5-8EB3-41005483EA50 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-01 NOOP.pdf | KNDW D-01 NOOP.pdf | Yes |  | Uploads\7df1e4d4-5db4-4fd5-8eb3-41005483ea50.pdf | Exist
Mursyid | Yes | DF32867B-B7AE-46AB-BBEC-4CD967B9D2A7 | 8FCD42D5-820B-42DF-883C-374129306299 | TEJA-1 | E639C647-9234-4E66-AD41-C0EEBB8050F8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TEJAGL01_TEJA-1_SAPURA OMV_NOOP.pdf | SKO3TEJAGL01_TEJA-1_SAPURA OMV_NOOP.pdf | Yes |  | Uploads\e639c647-9234-4e66-ad41-c0eebb8050f8.pdf | Exist
Mursyid | Yes | FF0FF404-A4CB-4C52-9F1D-0F0015A442DD | 8FCD42D5-820B-42DF-883C-374129306299 | TEJA-1 | F6F35524-4ECA-44C6-8864-1BDB36F48CEE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Teja-1 End of Well Report 22 May 2014.pdf | Teja-1 End of Well Report 22 May 2014.pdf | Yes |  | Uploads\f6f35524-4eca-44c6-8864-1bdb36f48cee.pdf | Exist
Mursyid | Yes | 73B1F670-3871-43CD-A704-8F962F090411 | 1CB6B52A-8136-440B-B4F6-37AE8CE6E190 | DAMAR-A12 | 1FBA8AAF-47FB-4803-950B-FAEB6F6412F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DAMAR-A12 EOWR.pdf | DAMAR-A12 EOWR.pdf | Yes |  | Uploads\1fba8aaf-47fb-4803-950b-faeb6f6412f4.pdf | Exist
Mursyid | Yes | 6BA18B42-6C76-439E-8C0E-765FE7AF382B | 1CB6B52A-8136-440B-B4F6-37AE8CE6E190 | DAMAR-A12 | 26D5AD5E-E3D6-4A01-908B-BEB14E7CDBC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARGL02_DAMAR-12_EMEPMI.pdf |  | No |  | Uploads\26d5ad5e-e3d6-4a01-908b-beb14e7cdbc6.pdf | Exist
Mursyid | Yes | 249D989B-825F-478C-91F0-8C8703B12A9A | A8F78279-862A-4158-BACE-38D2C65F18C8 | DULANG-D27 | 8B882E5E-5BC3-4C53-BC8D-3FD9C6DE7085 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXO_DULANG-D27_PCSB_NOOP.pdf | PMO3DULGWSXO_DULANG-D27_PCSB_NOOP.pdf | Yes |  | Uploads\8b882e5e-5bc3-4c53-bc8d-3fd9c6de7085.pdf | Exist
Mursyid | Yes | 29DB40F8-61FC-44BE-852E-1C8E6DB5E315 | A8F78279-862A-4158-BACE-38D2C65F18C8 | DULANG-D27 | 840B58C8-DBAA-49F9-89AA-5B444986F301 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYE_DULANG-D27_PCSB_FWR.pdf | PMO3DULGWSYE_DULANG-D27_PCSB_FWR.pdf | Yes |  | Uploads\840b58c8-dbaa-49f9-89aa-5b444986f301.pdf | Exist
Mursyid |  | CA9C75A8-2F3B-4E5F-A065-AF98F144CBAF | D022734A-B47B-48D4-8B02-38E872DB24C7 | BOKOR-E507 | 7DEB9642-2745-4735-933D-16EA910AEC9B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NULL |  | No |  | Uploads\7deb9642-2745-4735-933d-16ea910aec9b.pdf | Exist
Mursyid | Yes | 327E8897-0C03-4FC6-B960-855AE18ADC9A | D022734A-B47B-48D4-8B02-38E872DB24C7 | BOKOR-E507 | F6D831D8-81C1-4983-A12F-6D0680250E17 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR_E507 (1).pdf | FWR BOKOR_E507 (1).pdf | Yes |  | Uploads\f6d831d8-81c1-4983-a12f-6d0680250e17.pdf | Exist
Mursyid | Yes | F2763E7D-563A-4EE0-938F-88BF7142A7EC | E5A5D73C-205F-4D6F-8818-3904DDFD8902 | WEST LUTONG DEEP-1 | 15A73CFA-7BD9-420A-B47D-CD20A36C7DE1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LTGWGL10_WEST LUTONG DEEP-1_PCSB_NOOP.pdf |  | No |  | Uploads\15a73cfa-7bd9-420a-b47d-cd20a36c7de1.pdf | Exist
Mursyid | Yes | C8BBBAE2-A540-4D82-A845-0A6068227489 | E5A5D73C-205F-4D6F-8818-3904DDFD8902 | WEST LUTONG DEEP-1 | 37D1F526-0DA9-4373-8D8E-C7DA74034AB4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LTGWWS1D_WEST LUTONG DEEP-1_PCSB_FWR.pdf |  | No |  | Uploads\37d1f526-0da9-4373-8d8e-c7da74034ab4.pdf | Exist
Mursyid | Yes | 7AFFE1CB-B041-442E-BC16-D167B573CDE0 | 09940047-093B-44AD-9E3E-391FAACC21F0 | BAKONG-1 | 79BDC503-4552-4A2E-8227-36492AB32860 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BKNGWS03_BAKONG-1_SAPURA OMV_FWR_28 Dec 2014.pdf | SKO3BKNGWS03_BAKONG-1_SAPURA OMV_FWR_28 Dec 2014.pdf | Yes |  | Uploads\79bdc503-4552-4a2e-8227-36492ab32860.pdf | Exist
Mursyid | Yes | 918534D7-09F0-4354-BF74-C1EFF087090E | 09940047-093B-44AD-9E3E-391FAACC21F0 | BAKONG-1 | F5093DDB-31DD-4AE5-95EA-886EB8082B35 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BKNGGL01_BAKONG-1_SAPURA OMV_NOOP rev 1.pdf | SKO3BKNGGL01_BAKONG-1_SAPURA OMV_NOOP rev 1.pdf | Yes |  | Uploads\f5093ddb-31dd-4ae5-95ea-886eb8082b35.pdf | Exist
Mursyid | Yes | 2BE992BF-96BD-451C-B051-CE78133BFC04 | 65AD927E-5624-4BFF-8AE1-392B0A768B1D | SUMANDAK SELATAN-B11ST1 | 0AF96168-08D3-4D8E-A352-E1541F3DBB7B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B11 ST1 NOOP_20190131.pdf | Sumandak Selatan B11 ST1 NOOP_20190131.pdf | Yes |  | Uploads\0af96168-08d3-4d8e-a352-e1541f3dbb7b.pdf | Exist
Mursyid | Yes | 8F93A5E8-4030-4F5E-85B3-6C66D96E52C4 | 65AD927E-5624-4BFF-8AE1-392B0A768B1D | SUMANDAK SELATAN-B11ST1 | 50558CFF-5BFD-4D37-B5C7-2AD84933B2C0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PCSB Final Well Report (Sumandak Selatan B11 ST1).pdf | PCSB Final Well Report (Sumandak Selatan B11 ST1).pdf | Yes |  | Uploads\50558cff-5bfd-4d37-b5c7-2ad84933b2c0.pdf | Exist
Mursyid | Yes | BA5DF5DD-065E-41AE-8EA8-5F7F435B95FC | 451FD30C-996B-48AC-B6B9-39CDEFFF16DE | SUMAZAU-1 | 3BB9FB8A-2AE0-4452-AFF7-58E91B061A27 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SUMAZAU-1 FWR with ATTACHMENT (FINAL).pdf | SUMAZAU-1 FWR with ATTACHMENT (FINAL).pdf | Yes |  | Uploads\3bb9fb8a-2ae0-4452-aff7-58e91b061a27.pdf | Exist
Mursyid | Yes | 1F11A42C-232B-437D-9024-111DA4F7531F | 451FD30C-996B-48AC-B6B9-39CDEFFF16DE | SUMAZAU-1 | 40197DB6-C1F2-46C0-9831-9CE78630FD29 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SUMAZAU-1 NOOP_INTERNAL .pdf | SUMAZAU-1 NOOP_INTERNAL .pdf | Yes |  | Uploads\40197db6-c1f2-46c0-9831-9ce78630fd29.pdf | Exist
Mursyid | Yes | B7ADC9A3-9897-48C9-86D5-529BB8CFD682 | C6981AF6-642D-45D4-8B65-39CED04CAD61 | LARAK-A1 | 51AAFB99-F253-4C05-BA09-9C9E90408164 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 LRK-A1 FINAL WELL REPORT.pdf |  | No |  | Uploads\51aafb99-f253-4c05-ba09-9c9e90408164.pdf | Exist
Mursyid | Yes | C7AFD003-01CB-4B21-996A-70155C9A3DA1 | C6981AF6-642D-45D4-8B65-39CED04CAD61 | LARAK-A1 | B14AA937-AD60-4026-ACEF-ED4253A4F9C0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LRK A1 NOOP 3-July-2019 FINAL Rev1.pdf |  | No |  | Uploads\b14aa937-ad60-4026-acef-ed4253a4f9c0.pdf | Exist
Mursyid | Yes | 1DBE0D74-9854-47D0-8421-216C51BD8826 | 1F7D1558-AEF6-4FE7-8795-3A19646C9633 | KANOWIT-SS2 | EBA2AD6E-6D06-49C2-8AA6-F221D29F7AAF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KNWTWS12_KANOWIT_SS2.pdf | SKO3KNWTWS12_KANOWIT_SS2.pdf | Yes |  | Uploads\eba2ad6e-6d06-49c2-8aa6-f221d29f7aaf.pdf | Exist
Mursyid | Yes | 22FF615A-D961-491E-8631-D7737E113BF2 | 1F7D1558-AEF6-4FE7-8795-3A19646C9633 | KANOWIT-SS2 | 3C6F5476-252E-4F25-BE30-B392EDEB3267 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KNWTGL04_KANOWIT_SS2.pdf | SKO3KNWTGL04_KANOWIT_SS2.pdf | Yes |  | Uploads\3c6f5476-252e-4f25-be30-b392edeb3267.pdf | Exist
Mursyid | Yes | DBD85289-3A56-4FC8-AF6D-E3BAC2CE97CE | CDE52883-9019-4C62-8D1D-3A2A66343C20 | NURI-1 | 8C45D1F7-CA8B-40A8-96CE-5B6127F94B80 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Nuri-1 Nuri-1 RDR1 FWR (with Attachment) (1).pdf | Nuri-1 Nuri-1 RDR1 FWR (with Attachment) (1).pdf | Yes |  | Uploads\8c45d1f7-ca8b-40a8-96ce-5b6127f94b80.pdf | Exist
Mursyid | Yes | CCEBA16B-8A1C-4F5E-9314-A3E60EF20E00 | CDE52883-9019-4C62-8D1D-3A2A66343C20 | NURI-1 | 670728FE-3BF9-4356-8C6E-EEB8BE609B55 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Nuri-1 MPM.pdf | NOOP - Nuri-1 MPM.PDF | Yes |  | Uploads\670728fe-3bf9-4356-8c6e-eeb8be609b55.pdf | Exist
Mursyid | Yes | 00A4D6B4-1908-44F1-BA04-566467991EAC | 0A003F3E-FB3F-4A2C-A2C3-3A49737997E3 | D21-A4 | 6098EFF0-1FD1-4E16-BA82-FB4536950796 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS45_D21_A4.pdf | SKO3D21-WS45_D21_A4.pdf | Yes |  | Uploads\6098eff0-1fd1-4e16-ba82-fb4536950796.pdf | Exist
Mursyid | Yes | 2FCBC576-38B5-4ED7-AD8A-44C29CF6794D | 0A003F3E-FB3F-4A2C-A2C3-3A49737997E3 | D21-A4 | 2CA7065B-01F4-4D3E-9312-06DC42484C74 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS51_D21_A4.pdf | SKO3D21-WS51_D21_A4.pdf | Yes |  | Uploads\2ca7065b-01f4-4d3e-9312-06dc42484c74.pdf | Exist
Mursyid | Yes | C8F5EC5E-AE61-465A-88A2-4CBF1E55B127 | E3AB7483-D571-4BA7-AE7D-3A59AC76B9F9 | SM112 | 33549DA0-1CD0-4EBC-AC04-98DA34A1C187 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-G112 FWR (Cost revised).pdf |  | No |  | Uploads\33549da0-1cd0-4ebc-ac04-98da34a1c187.pdf | Exist
Mursyid | Yes | 022AB5B8-C5E5-4113-9DC2-EF81033C4EEA | E3AB7483-D571-4BA7-AE7D-3A59AC76B9F9 | SM112 | E395DE2F-0B54-4D88-A6A2-E5DB0645BC1F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL48_SM112_PCSB_NOOP.pdf | SBO3SMRGGL48_SM112_PCSB_NOOP.pdf | Yes |  | Uploads\e395de2f-0b54-4d88-a6a2-e5db0645bc1f.pdf | Exist
Mursyid | Yes | 2AAE2781-FDF2-4412-8836-F4BE5D5F0AEF | 2388796F-E046-45B3-950B-3A8E164A03FF | SAPA-05 | EA7B1190-8C37-4252-A685-F38D8B0BCEC5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-05 EOWR.pdf | SAPA-05 EOWR.pdf | Yes |  | Uploads\ea7b1190-8c37-4252-a685-f38d8b0bcec5.pdf | Missing
Mursyid | Yes | 41E1565A-ED09-4703-B354-9EC360E72DDF | 2388796F-E046-45B3-950B-3A8E164A03FF | SAPA-05 | F0A032EE-3BA5-47B1-B706-C3E75EF9A5CE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS67_SAPA-05-06-13-15_PTTEP.pdf | SKO3ACISWS67_SAPA-05-06-13-15_PTTEP.pdf | Yes |  | Uploads\f0a032ee-3ba5-47b1-b706-c3e75ef9a5ce.pdf | Missing
Mursyid | Yes | E51667BC-86A3-4431-AC93-4431140C437F | 77B1425A-47F7-4F57-A276-3AE04B503734 | BERTAM A-15ST1 | 561D6A52-5666-4390-ACDD-F2DF21DD9BA3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-15 ST1 EOWR_Final_Complete.pdf | Bertam A-15 ST1 EOWR_Final_Complete.pdf | Yes |  | Uploads\561d6a52-5666-4390-acdd-f2df21dd9ba3.pdf | Exist
Mursyid | Yes | 05A622C6-2B15-4C72-B8FF-085A937B2740 | 77B1425A-47F7-4F57-A276-3AE04B503734 | BERTAM A-15ST1 | 53A0A5F2-3DDE-4056-AE20-A68DBE99E6BC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-15 ST1 NOOP.pdf | Bertam A-15 ST1 NOOP.pdf | Yes |  | Uploads\53a0a5f2-3dde-4056-ae20-a68dbe99e6bc.pdf | Exist
Mursyid | Yes | 1592EE2B-1DEA-4D65-A0DC-4F60AA453134 | 87FBD696-E5A0-47F4-BDC9-3AE0A8144DCD | D28-2 | EA4AA409-ACAF-43E0-BC8C-4738EBAA1493 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D28-GL03_D28-2_PCSB.pdf | SKO3D28-GL03_D28-2_PCSB.pdf | Yes |  | Uploads\ea4aa409-acaf-43e0-bc8c-4738ebaa1493.pdf | Exist
Mursyid | Yes | 64FFC150-9DE2-439B-9E62-DF4398E05505 | 87FBD696-E5A0-47F4-BDC9-3AE0A8144DCD | D28-2 | 85DC18FA-EAEB-497C-AF76-5AF8541C7E0A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D28-WS06_D28-2_PCSB.pdf | SKO3D28-WS06_D28-2_PCSB.pdf | Yes |  | Uploads\85dc18fa-eaeb-497c-af76-5af8541c7e0a.pdf | Exist
Mursyid | Yes | 14575532-4DC2-4DB6-830F-5698B8FFA1CC | 0E7C3139-0842-4837-A974-3B489295A6C8 | BERGADING-B4(J2) | D448D733-9EA3-497C-8D85-667F82EE400E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading B-4(J2) - signed.pdf | EOWR_Bergading B-4(J2) - signed.pdf | Yes |  | Uploads\d448d733-9ea3-497c-8d85-667f82ee400e.pdf | Exist
Mursyid | Yes | 9F3401AC-35D0-44A2-A6AC-2ED25400403E | 0E7C3139-0842-4837-A974-3B489295A6C8 | BERGADING-B4(J2) | 19A2F5D6-9298-46D4-A1F6-CC261B569DCC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRGB-4(J2), Bergading B-4(J2).pdf | NOOP - BRGB-4(J2), Bergading B-4(J2).pdf | Yes |  | Uploads\19a2f5d6-9298-46d4-a1f6-cc261b569dcc.pdf | Exist
Mursyid | Yes | 8330AD40-319A-4DC0-8DF0-089F5436A960 | 6C2FDEEC-3954-41EA-8509-3B61606CAB83 | KIKEH_WX16(119) | C38DF178-FD25-4B85-B2DE-271E3B0E0BF0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KIKHWS2L_KIKEH_WX16.pdf |  | No |  | Uploads\c38df178-fd25-4b85-b2de-271e3b0e0bf0.pdf | Exist
Mursyid | Yes | AA3C2BC5-F009-4206-806D-C81AD788DDBD | 6C2FDEEC-3954-41EA-8509-3B61606CAB83 | KIKEH_WX16(119) | 4DA8BA42-1C4F-45FB-9FAF-AB613DB7A151 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KIKHWSX7_KIKEH_WX16.pdf |  | No |  | Uploads\4da8ba42-1c4f-45fb-9faf-ab613db7a151.pdf | Exist
Mursyid | Yes | C5B7697B-D820-4407-B072-173D89822DB6 | 2EFC76B6-D08F-480E-8525-3B66AE2C5CD5 | JERUN-A1 | 9F4B43B9-7DFC-4195-8316-422F451A5009 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\9f4b43b9-7dfc-4195-8316-422f451a5009.pdf | Exist
Mursyid | Yes | 39CF2D14-FCBE-440F-857F-773F84DA42D2 | 2EFC76B6-D08F-480E-8525-3B66AE2C5CD5 | JERUN-A1 | BD27EE06-9CAB-4473-84EF-14A5373CA01B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Jerun-A1 Final Well Report - FINAL.pdf | SK408 Jerun-A1 Final Well Report - FINAL.pdf | Yes |  | Uploads\bd27ee06-9cab-4473-84ef-14a5373ca01b.pdf | Exist
Mursyid | Yes | A6E7E1F0-A1FE-437C-86F5-669CFA34BB75 | 740F6802-264B-4833-A750-3B831CB5AA28 | SM-116 | 2706F729-A367-42F8-81D9-FF6244B6EA8B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL55_SM-116.pdf | SBO3SMRGGL55_SM-116.pdf | Yes |  | Uploads\2706f729-a367-42f8-81d9-ff6244b6ea8b.pdf | Exist
Mursyid | Yes | E9DFE7C8-F7A6-48E6-8069-4039EC46F0C7 | 740F6802-264B-4833-A750-3B831CB5AA28 | SM-116 | 8CBBCA7C-CA4B-4072-BEDA-06248A877846 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSEK_SM-116.pdf | SBO3SMRGWSEK_SM-116.pdf | Yes |  | Uploads\8cbbca7c-ca4b-4072-beda-06248a877846.pdf | Exist
Mursyid | Yes | E2D8102A-5696-46A0-A59A-2381D2D6504B | B64B00AF-2104-4E59-BD41-3BC8ECC471A3 | DULANG-C31 | D9F37E72-D048-4488-9E86-75287B0ED0EB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGGL82_DULANG-C31.pdf | PMO3DULGGL82_DULANG-C31.pdf | Yes |  | Uploads\d9f37e72-d048-4488-9e86-75287b0ed0eb.pdf | Exist
Mursyid | Yes | A11256CD-9715-4436-A642-BE87E4860886 | B64B00AF-2104-4E59-BD41-3BC8ECC471A3 | DULANG-C31 | 73B63310-B3F2-4F80-99AB-977D0E69EADF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWS7N_DULANG-C31.pdf | PMO3DULGWS7N_DULANG-C31.pdf | Yes |  | Uploads\73b63310-b3f2-4f80-99ab-977d0e69eadf.pdf | Exist
Mursyid | Yes | 2529A475-4981-4DC6-8743-C5129E7E14A8 | C848A266-D601-48A5-9637-3C4EC1967806 | D18-209B | 77FC35A1-CD03-4CE9-B2BC-FEB13B1EA44A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D-18 209B Final Well Report 209B (Signed).pdf | D-18 209B Final Well Report 209B (Signed).pdf | Yes |  | Uploads\77fc35a1-cd03-4ce9-b2bc-feb13b1ea44a.pdf | Exist
Mursyid | Yes | CBF8B37A-B7AF-43F8-BF83-EA5A3E529F0D | C848A266-D601-48A5-9637-3C4EC1967806 | D18-209B | 57B447F5-3E4E-49E2-A6D6-E4A5A2F4751F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-GL30_D18-209B.pdf | SKO3D18-GL30_D18-209B.pdf | Yes |  | Uploads\57b447f5-3e4e-49e2-a6d6-e4a5a2f4751f.pdf | Exist
Mursyid | Yes | 8C331858-427D-4DA9-A2E8-DBB4A69DBE90 | 0183ABCA-117A-4754-BF3B-3C501A8B962A | BUNGA LAVATERA-1 | E31102D8-1E68-41F1-A2D0-661589CE300E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Bunga Lavatera-1_Rev1.pdf | EOWR Bunga Lavatera-1_Rev1.pdf | Yes |  | Uploads\e31102d8-1e68-41f1-a2d0-661589ce300e.pdf | Exist
Mursyid | Yes | 2CE4272B-22C7-4AED-9B78-DD03ADFAFAF2 | 0183ABCA-117A-4754-BF3B-3C501A8B962A | BUNGA LAVATERA-1 | 4A228F7E-2379-4AF5-BE85-1872C1B333C4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Bunga Lavatera-1_signed.pdf | NOOP_Bunga Lavatera-1_signed.pdf | Yes |  | Uploads\4a228f7e-2379-4af5-be85-1872c1b333c4.pdf | Exist
Mursyid | Yes | B69B0CC3-0B1D-4395-8783-46851DBF60DE | E5C5F8CF-6EC4-4968-8F72-3C55785EA6C4 | KNDW-D13 | A58D7675-6511-4418-B530-627D345B26F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW-D13.pdf | EOWR KNDW-D13.pdf | Yes |  | Uploads\a58d7675-6511-4418-b530-627d345b26f4.pdf | Exist
Mursyid | Yes | B0006E6C-30D0-4D3C-B580-932EED49F230 | E5C5F8CF-6EC4-4968-8F72-3C55785EA6C4 | KNDW-D13 | 0A067198-5172-45EB-9F05-B1A74AB0A3CC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D13, NOOP, 18 Feb 2020.pdf | KNDW-D13, NOOP, 18 Feb 2020.pdf | Yes |  | Uploads\0a067198-5172-45eb-9f05-b1a74ab0a3cc.pdf | Exist
Mursyid | Yes | 5BABB973-E7F1-4106-8E44-6B3074740745 | FDDBB895-CBFE-47C5-A557-3D7F8BDD37CE | BERTAM A-12 | 67121D9A-2084-4772-B500-B25F148C88D6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAMDR06_BERTAM A-12_IPC_LUNDIN_FWR.pdf | PMO3BTAMDR06_BERTAM A-12_IPC_LUNDIN_FWR.pdf | Yes |  | Uploads\67121d9a-2084-4772-b500-b25f148c88d6.pdf | Exist
Mursyid | Yes | F7EA1C9B-1BB9-4F11-8F08-5CA82D61291B | FDDBB895-CBFE-47C5-A557-3D7F8BDD37CE | BERTAM A-12 | 68553374-75A2-4383-A03D-1BFE986F95AB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAMWS25_BERTAM A-12_IPC_LUNDIN_NOOP.pdf | PMO3BTAMWS25_BERTAM A-12_IPC_LUNDIN_NOOP.pdf | Yes |  | Uploads\68553374-75a2-4383-a03d-1bfe986f95ab.pdf | Exist
Mursyid | Yes | 0C661B41-7639-43B7-92A0-6D25D4741EB8 | E33C6831-E784-4EEF-A5F1-3E5354B4EAEF | KERUING-1 | 4A6950C3-FF46-484D-B158-2495B492B0EC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Keruing-1 EOWR_Final.pdf | Keruing-1 EOWR_Final.pdf | Yes |  | Uploads\4a6950c3-ff46-484d-b158-2495b492b0ec.pdf | Exist
Mursyid | Yes | 6AC61A1A-CDDE-4EB1-9CCF-820F87BA27CC | E33C6831-E784-4EEF-A5F1-3E5354B4EAEF | KERUING-1 | D136AC70-14B3-4181-A132-81F15D070503 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Keruing-1 ST1 NOOP.pdf | Keruing-1 ST1 NOOP.pdf | Yes |  | Uploads\d136ac70-14b3-4181-a132-81f15d070503.pdf | Exist
Mursyid | Yes | 89A60878-F156-456B-9A9A-0DD70CC3BFD6 | B5F2FB8F-99BA-4D3E-8A72-3F30EB144ADA | ECA-02 | FB45F973-2F04-4D5C-83BB-8E6EA97671C8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 210302_NOTICE OF OPERATIONS - WELL EC-A02 Signed.pdf | 210302_NOTICE OF OPERATIONS - WELL EC-A02 (Slot 2C)-Rev 0.0 Signed.pdf | No |  | Uploads\fb45f973-2f04-4d5c-83bb-8e6ea97671c8.pdf | Exist
Mursyid | Yes | 0BDF810E-B2F5-4771-80FB-DD0C30B6B4EB | B5F2FB8F-99BA-4D3E-8A72-3F30EB144ADA | ECA-02 | CD48F1B7-51EF-408E-97C5-0607983E3E07 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A02 Final Well Report.pdf | EC-A02 Final Well Report.pdf | Yes |  | Uploads\cd48f1b7-51ef-408e-97c5-0607983e3e07.pdf | Exist
Mursyid | Yes | 5737E6A4-4EC9-45B7-B6A8-473CC4A4E602 | D22322E0-A9BE-4105-858E-3F8EFB8FAC92 | MLK-123 | 2FA77019-FF96-4F2A-B9A4-62C492D8AFE6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL26_MALIKAI-123_NOOP_SHELL.pdf |  | No |  | Uploads\2fa77019-ff96-4f2a-b9a4-62c492d8afe6.pdf | Exist
Mursyid | Yes | D091BA31-9536-4D8B-A60E-6D05D81DC36A | D22322E0-A9BE-4105-858E-3F8EFB8FAC92 | MLK-123 | CC284183-253E-4DB0-A514-5A83079C733D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-123 EOWR For Petronas.pdf | MLK-123 EOWR For Petronas.pdf | Yes |  | Uploads\cc284183-253e-4db0-a514-5a83079c733d.pdf | Exist
Mursyid | Yes | 0D315C51-2349-4D42-9736-98F18F8281BC | A3F21024-4DD5-47BE-983C-403FEF42C3AE | SAPA-04 | 7AC9710A-232C-49BE-92D9-0E85559AAE00 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS1L_SAPA-04_NOOP_PTTEP.pdf | SKO3ACISWS1L_SAPA-04_NOOP_PTTEP.pdf | Yes |  | Uploads\7ac9710a-232c-49be-92d9-0e85559aae00.pdf | Exist
Mursyid | Yes | 9B14DC82-D2B1-47D5-BDAC-AE4EE5734017 | A3F21024-4DD5-47BE-983C-403FEF42C3AE | SAPA-04 | 4F3CF0A0-8CE7-46D2-B912-6B61EEC27B48 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-04ST2 EOWR.pdf | SAPA-04ST2 EOWR.pdf | Yes |  | Uploads\4f3cf0a0-8ce7-46d2-b912-6b61eec27b48.pdf | Exist
Mursyid | Yes | 54A254D7-16D7-4AEF-9D2B-9ACE73305E67 | FA28D0F3-E812-4EE8-B8CD-40865BCA9538 | LARUT A-36ST1 | 2C1FC1DC-925D-4C59-9FC3-5EC5C374EC5A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-36 (OP6_NOOP) rev 2.pdf |  | No |  | Uploads\2c1fc1dc-925d-4c59-9fc3-5ec5c374ec5a.pdf | Exist
Mursyid | Yes | AAD9B25B-DB4E-4695-85DF-70C4D42A3251 | FA28D0F3-E812-4EE8-B8CD-40865BCA9538 | LARUT A-36ST1 | AA96E963-8C15-4A02-BD73-82537E92261B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-36ST1 (OP6) Final Well Report_Rev0.pdf | LARUT A-36ST1 (OP6) Final Well Report_Rev0.pdf | Yes |  | Uploads\aa96e963-8c15-4a02-bd73-82537e92261b.pdf | Exist
Wadi | Yes | AA2EAEC0-0F87-41A9-8258-6E15E075B347 | 0E48523A-02F2-42D4-BDB1-408EB6F80BB0 | PESA-01 | C37E3D1E-1A8A-46F4-8A20-38B81FE3E07B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PESA-1 EOWR FINAL (APPROVED).pdf |  | No |  | Uploads\c37e3d1e-1a8a-46f4-8a20-38b81fe3e07b.pdf | Exist
Wadi | Yes | 2F378AA7-F97C-4CB6-B205-10FCC65A9EFE | 0E48523A-02F2-42D4-BDB1-408EB6F80BB0 | PESA-01 | 60C0BB70-F620-4848-92B4-78A28E34425E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PEMANIS PESA-1, PESA-2, PESA-3 and PESA-4 NOOP Revised.pdf |  | No |  | Uploads\60c0bb70-f620-4848-92b4-78a28e34425e.pdf | Exist
Mursyid | Yes | 3B489B14-FB13-4EC1-8B18-60C1C21E0034 | 5D489043-70A7-43A7-A6C5-40B4B099AFE2 | BERGADING-C1 (A) | 6E0AFC72-8E2A-45A0-B189-63A31A0A7F04 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading C-1 (A) R0_Final.pdf | Bergading C-1 (A) R0_Final.pdf | Yes |  | Uploads\6e0afc72-8e2a-45a0-b189-63a31a0a7f04.pdf | Exist
Mursyid | Yes | 0F9A3AC5-FE6E-4BA6-9C6E-788277890ADF | 5D489043-70A7-43A7-A6C5-40B4B099AFE2 | BERGADING-C1 (A) | AA2866DF-622D-49F0-AA2F-0F70C003B964 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading C-1_ Rev2_25082017 - PETRONAS SUBMISSION.pdf |  | No |  | Uploads\aa2866df-622d-49f0-aa2f-0f70c003b964.pdf | Exist
Mursyid | Yes | 5615BF43-539E-4F58-BE1A-0B989D220F13 | B66391F8-1DD9-4505-B0E6-414095C763AA | DULANG-A11ST2 | D5F4D71B-D513-4E83-87A6-1B201BDE6797 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG-A11ST2_Petronas Final Well Report_Final.pdf | DULANG-A11ST2_Petronas Final Well Report_Final.pdf | Yes |  | Uploads\d5f4d71b-d513-4e83-87a6-1b201bde6797.pdf | Exist
Mursyid | Yes | CC19B113-0692-47F1-A50E-D97DF7BB5C7E | B66391F8-1DD9-4505-B0E6-414095C763AA | DULANG-A11ST2 | 096F0669-489B-4B4B-8776-9AA3145347C3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang _A11ST2(OP1)_Final_Rev01.pdf | Dulang _A11ST2(OP1)_Final_Rev01.pdf | Yes |  | Uploads\096f0669-489b-4b4b-8776-9aa3145347c3.pdf | Exist
Mursyid | Yes | AB384FE2-47FF-44DA-83F3-80D012E749DE | 546C41AB-33D9-4BAD-851B-415DB7689EAC | D35C-305ST3 | 84FEBC09-5154-4CE9-BE35-6FDD6CE702CD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-305ST3 End Of Well Report.pdf | D35C-305ST3 End Of Well Report.pdf | Yes |  | Uploads\84febc09-5154-4ce9-be35-6fdd6ce702cd.pdf | Exist
Mursyid | Yes | 0E015355-3742-4E64-BB9A-A241A1D0800C | 546C41AB-33D9-4BAD-851B-415DB7689EAC | D35C-305ST3 | 5F3B7280-4D84-405F-96A3-2FCEEDF1D031 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-305ST3 Well NOOP Final.pdf | D35C-305ST3 Well NOOP Final.pdf | Yes |  | Uploads\5f3b7280-4d84-405f-96a3-2fceedf1d031.pdf | Exist
Mursyid | Yes | EBF1C41E-BD95-4ACC-B4EF-9C9CC26EFC53 | 4101B450-D906-4874-BCE1-41B0470DA307 | SERDAM-01 | B6009AC9-8576-47A5-B6CD-F87E266C62D6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Serdam-1 NOOP.pdf |  | No |  | Uploads\b6009ac9-8576-47a5-b6cd-f87e266c62d6.pdf | Exist
Mursyid | Yes | 372CC15F-5C92-42DA-88C4-63BA7176E694 | 4101B450-D906-4874-BCE1-41B0470DA307 | SERDAM-01 | 4CD77B99-A32A-4A22-95AA-F443B26B639C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Serdam-01 End of Well Report.pdf | Serdam-01 End of Well Report.pdf | Yes |  | Uploads\4cd77b99-a32a-4a22-95aa-f443b26b639c.pdf | Exist
Mursyid | Yes | D79BC86B-DE78-42CD-9168-720E0D071BDA | A2B18ED2-9FF9-465E-8A2D-42417E9269AB | SM-121 | CB00022D-12C7-414B-887E-C6D5BF9BCCF4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-121 EOWR Final.pdf | SM-121 EOWR Final.pdf | Yes |  | Uploads\cb00022d-12c7-414b-887e-c6d5bf9bccf4.pdf | Exist
Mursyid | Yes | C732E7BE-42BA-4C9C-86F1-BEF3F6F9A709 | A2B18ED2-9FF9-465E-8A2D-42417E9269AB | SM-121 | EE6B44CB-71D5-4BD5-8568-2065699A6D7E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM121 w Signature.pdf | SM121 w Signature.pdf | Yes |  | Uploads\ee6b44cb-71d5-4bd5-8568-2065699a6d7e.pdf | Exist
Mursyid | Yes | E2AE8C6B-063B-4914-9E9F-79FD04813108 | 7DED9134-350F-4858-A3B5-434B1B821B07 | BERTAM A-5 | 83DD1513-A5E6-439B-9D5C-DEE7EF33F1A3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAMWS21_BERTAM-A5.pdf | PMO3BTAMWS21_BERTAM-A5.pdf | Yes |  | Uploads\83dd1513-a5e6-439b-9d5c-dee7ef33f1a3.pdf | Exist
Mursyid | Yes | 5A2AB612-8F93-41F4-891E-ACD2E6B4FF51 | 7DED9134-350F-4858-A3B5-434B1B821B07 | BERTAM A-5 | 952F8812-0E07-4CF2-B00D-F645AEB535F7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam-5 EOWR_Final_Complete.pdf |  | No |  | Uploads\952f8812-0e07-4cf2-b00d-f645aeb535f7.pdf | Exist
Mursyid | Yes | 613CB5D8-9F45-40C6-8B8C-E7CB16698A3A | 02DF2FC8-5E1A-4B68-AD8A-438EC72A85B6 | GANDARUSA-1 | 7CE12094-9C28-478F-BF26-C8A37827CA3A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gandarusa-1 NOOP_FINAL.pdf | Gandarusa-1 NOOP_FINAL.pdf | Yes |  | Uploads\7ce12094-9c28-478f-bf26-c8a37827ca3a.pdf | Exist
Mursyid | Yes | 536DC096-8B7E-4892-A780-E52EB13B002E | 02DF2FC8-5E1A-4B68-AD8A-438EC72A85B6 | GANDARUSA-1 | A208AF3A-6619-4E02-BBD0-93136816F1F6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gandarusa-1 End of Well Report (FINAL).pdf | Gandarusa-1 End of Well Report (FINAL).pdf | Yes |  | Uploads\a208af3a-6619-4e02-bbd0-93136816f1f6.pdf | Exist
Mursyid | Yes | 340F598A-32CC-435A-AC12-DAFD104867FB | 85A68FC2-C40B-4C3C-B5A9-43A39479D0ED | F14-106 | 60C3EECD-FCF3-49C0-A7DC-440166E8E503 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-106 End of Well Report - Final.pdf | F14-106 End of Well Report - Final.pdf | Yes |  | Uploads\60c3eecd-fcf3-49c0-a7dc-440166e8e503.pdf | Exist
Mursyid | Yes | B7418980-3582-4802-81F0-A3A8258D7B07 | 85A68FC2-C40B-4C3C-B5A9-43A39479D0ED | F14-106 | C0CB9392-A8A0-4685-958E-D01358C6CD2C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-106 (N2) NOOP R2 Final - signed.pdf | F14-106 (N2) NOOP R2 Final - signed.pdf | Yes |  | Uploads\c0cb9392-a8a0-4685-958e-d01358c6cd2c.pdf | Exist
Mursyid | Yes | E51B6440-D63F-4230-9F20-08622C2E6B54 | E76978CB-E90B-4EC7-97F1-43AF81B9A2DC | D21-A14 | 7A6330B2-22A0-4F69-9E9B-1267B6F8533F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A14 NOOP_FINAL.pdf | D21-A14 NOOP_FINAL.pdf | Yes |  | Uploads\7a6330b2-22a0-4f69-9e9b-1267b6f8533f.pdf | Exist
Mursyid | Yes | 227E2C23-19B2-41B5-8D1D-12341D5A7C85 | E76978CB-E90B-4EC7-97F1-43AF81B9A2DC | D21-A14 | D8CDCBB4-F9E0-4CEB-A275-4F503EE7142F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A14 End of Well Report_Final.pdf | D21-A14 End of Well Report_Final.pdf | Yes |  | Uploads\d8cdcbb4-f9e0-4ceb-a275-4f503ee7142f.pdf | Exist
Mursyid | Yes | 2D1FBB54-7FB6-47C2-87FB-D1A3FD942318 | 529C04BF-E94B-4409-AE9B-43FC3AD5F4EB | BUNGA ANGGERIK A-2(A) | 9E6F1E9A-CBD3-4F74-A370-8BB961D45A5D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Anggerik A-2A FINAL.pdf | EOWR_Bunga Anggerik A-2A FINAL.pdf | Yes |  | Uploads\9e6f1e9a-cbd3-4f74-a370-8bb961d45a5d.pdf | Exist
Mursyid | Yes | 8826FA5B-72E7-4F05-8CCA-E6BF7C4DF94F | 529C04BF-E94B-4409-AE9B-43FC3AD5F4EB | BUNGA ANGGERIK A-2(A) | 75A87156-0CF3-4B32-AF37-270B3EE23AB3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BAA_SxS_Rev0.pdf |  | No |  | Uploads\75a87156-0cf3-4b32-af37-270b3ee23ab3.pdf | Exist
Mursyid | Yes | 19D1BB2F-6934-4748-9370-07520D928DB4 | 2A9CC296-5A9F-4C01-AC9F-43FD392EFC22 | BOKOR-E508 | 877B551F-FEF8-4059-8CB2-0C53E2CA4F31 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BOKOR-E508 FINAL.pdf | NOOP BOKOR-E508 FINAL.pdf | Yes |  | Uploads\877b551f-fef8-4059-8cb2-0c53e2ca4f31.pdf | Exist
Mursyid | Yes | DD79BF04-9C74-4EE1-931A-7C3348921EE8 | 2A9CC296-5A9F-4C01-AC9F-43FD392EFC22 | BOKOR-E508 | 5D430F9B-CA99-4CE1-AE8B-2D2C3CADBCD0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR_BOKOR-E508.pdf | FWR_BOKOR-E508.pdf | Yes |  | Uploads\5d430f9b-ca99-4ce1-ae8b-2d2c3cadbcd0.pdf | Exist
Mursyid | Yes | 1D17FE0C-C617-494C-8289-1777DA63C703 | D87E84CF-DC6C-446A-9183-442CA53D15D4 | DULANG-D28 | 604EF7D3-AC46-4E23-B0BB-4FEE1AD7938D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXJ_DULANG-D28.pdf | PMO3DULGWSXJ_DULANG-D28.pdf | Yes |  | Uploads\604ef7d3-ac46-4e23-b0bb-4fee1ad7938d.pdf | Exist
Mursyid | Yes | BB0CCC49-D4D0-408D-A3EE-DF8849807103 | D87E84CF-DC6C-446A-9183-442CA53D15D4 | DULANG-D28 | F702B7A9-BB77-4E58-8B4E-450DBF5E6EC4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYF_DULANG-D28.pdf | PMO3DULGWSYF_DULANG-D28.pdf | Yes |  | Uploads\f702b7a9-bb77-4e58-8b4e-450dbf5e6ec4.pdf | Exist
Mursyid | Yes | C75E031C-8EF2-4818-B6E5-C3BF2CFB6E2D | F03F3694-3C1D-46BA-807E-4493B01BD994 | BKC-10ST1 (B) | 2FB6F6FA-C81D-4B24-B3C5-514D872D82CE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKC-10ST1 EOWR.pdf | BKC-10ST1 EOWR.pdf | Yes |  | Uploads\2fb6f6fa-c81d-4b24-b3c5-514d872d82ce.pdf | Exist
Mursyid | Yes | 0A6995A2-71F9-4B2A-8B0F-52008DB81B56 | F03F3694-3C1D-46BA-807E-4493B01BD994 | BKC-10ST1 (B) | 5918415C-0626-43BC-A36A-BAC5FD880010 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWAGL66_BKC-10ST1 (B).pdf | PMO3BKWAGL66_BKC-10ST1 (B).pdf | Yes |  | Uploads\5918415c-0626-43bc-a36a-bac5fd880010.pdf | Exist
Mursyid | Yes | A2702A01-BD96-4FFE-8D8E-00CFB09EBF13 | C92D16DB-B8EE-4229-BBE7-44C0074B16F6 | PRPA-10ST2 | DBBFB09B-F3A7-4114-9127-3A21E8662E83 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PERMAS Revisit 1 PHASE 1 NOOP_Rev 1 (1)_PRPA-10-11-12.pdf |  | No |  | Uploads\dbbfb09b-f3a7-4114-9127-3a21e8662e83.pdf | Exist
Mursyid | Yes | B4C55531-70E4-41A8-AF2C-65A14D3BB148 | C92D16DB-B8EE-4229-BBE7-44C0074B16F6 | PRPA-10ST2 | CA9089C7-6B56-4835-805D-E08CACA95B9D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-10ST2 EOWR.pdf | PRPA-10ST2 EOWR.pdf | Yes |  | Uploads\ca9089c7-6b56-4835-805d-e08caca95b9d.pdf | Exist
Mursyid | Yes | 88803753-72FC-4974-AC5D-2327805F3DE9 | 67BE7986-D965-4720-B9D3-4504DFDAC633 | SM-109 | F0D20EC7-A6AB-40E6-9258-BB1DE725ED72 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSCW_SM-109.pdf | SBO3SMRGWSCW_SM-109.pdf | Yes |  | Uploads\f0d20ec7-a6ab-40e6-9258-bb1de725ed72.pdf | Exist
Mursyid | Yes | 7CB3538E-31B5-4276-AD22-38EFCD593C92 | 67BE7986-D965-4720-B9D3-4504DFDAC633 | SM-109 | 939FCF87-DCCE-401B-9E24-73DC1006B65E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL34_SM-109.pdf | SBO3SMRGGL34_SM-109.pdf | Yes |  | Uploads\939fcf87-dcce-401b-9e24-73dc1006b65e.pdf | Exist
Mursyid | Yes | D1F5C78B-8E20-445B-93EA-4EF1AFAB5805 | 235065B8-0C5A-4238-88F2-45AB5C107E0D | KECAPI-1 | 5E7DFF38-B3D6-4CB0-A9CB-C4F2AC59168A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kecapi-1_End_Of_Well_Report_270423.pdf | Kecapi-1_End_Of_Well_Report_270423.pdf | Yes |  | Uploads\5e7dff38-b3d6-4cb0-a9cb-c4f2ac59168a.pdf | Exist
Mursyid | Yes | 51C0594A-6D00-4EAF-B48E-4E22EF1D6BFF | 235065B8-0C5A-4238-88F2-45AB5C107E0D | KECAPI-1 | 833AC3B7-0466-4C01-92B6-FFFCFDC1B54F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kecapi-1_NOOP_signed.pdf | Kecapi-1_NOOP_signed.pdf | Yes |  | Uploads\833ac3b7-0466-4c01-92b6-fffcfdc1b54f.pdf | Exist
Mursyid | Yes | EFFC72FB-2CCC-45AB-99D8-97CB40A9053C | 1BD6F1C6-F8D7-4A98-8277-45B3849CF0C2 | ANJUNG-A3 | 7D77D3F7-3AE6-4271-B939-6F0F14F535E2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | AJJT-A3 FWR_ANJUNG-A3_PCSB.pdf |  | No |  | Uploads\7d77d3f7-3ae6-4271-b939-6f0f14f535e2.pdf | Exist
Mursyid | Yes | 1CA05DC2-6A93-46ED-9BD5-94FE2EA06757 | 1BD6F1C6-F8D7-4A98-8277-45B3849CF0C2 | ANJUNG-A3 | CE726A5E-8EB6-410C-83F9-C8F7D5DF8AD7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Anjung Gas Development AJJT-A3 NOOP SIGNED.pdf |  | No |  | Uploads\ce726a5e-8eb6-410c-83f9-c8f7d5df8ad7.pdf | Exist
Mursyid | Yes | 4CD7BC76-8241-44BD-A787-8D381E567A28 | E9421686-9855-4672-82CB-45B50296EC9E | SASA-02 | 8BA3410D-63EB-4639-B28D-3D0E8DBAF656 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf |  | No |  | Uploads\8ba3410d-63eb-4639-b28d-3d0e8dbaf656.pdf | Exist
Mursyid | Yes | EEFE5B4D-991F-4686-8A27-02DC07243D97 | E9421686-9855-4672-82CB-45B50296EC9E | SASA-02 | EEECA648-F330-4601-AF8A-B353889A3015 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf |  | No |  | Uploads\eeeca648-f330-4601-af8a-b353889a3015.pdf | Exist
Mursyid |  | 1A55BFBE-414C-49FE-B95B-DED357C03FA9 | 85DC6FD1-123F-4457-962A-4609A35E14C5 | WPPB-16 | 2E3F7F1B-C51E-4969-812B-78EEC19E9F3E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NULL |  | No |  | Uploads\2e3f7f1b-c51e-4969-812b-78eec19e9f3e.pdf | Exist
Mursyid | Yes | 596720A5-D1D6-41C0-9740-E81BAB669DDB | 85DC6FD1-123F-4457-962A-4609A35E14C5 | WPPB-16 | 324B2BFF-47A0-40BB-A5C8-D6BCF98BD1E4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf |  | No |  | Uploads\324b2bff-47a0-40bb-a5c8-d6bcf98bd1e4.pdf | Exist
Mursyid | Yes | F021EFDE-B4A8-4760-92C6-D89FEEE97580 | B2BCAB5A-5D07-447D-A2AB-46300482FE00 | NAFIRI-1 | C3D1895B-7765-4CF2-BB47-093AA38DBBB2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Nafiri-1 FWR_Final (002).pdf | Nafiri-1 FWR_Final (002).pdf | Yes |  | Uploads\c3d1895b-7765-4cf2-bb47-093aa38dbbb2.pdf | Exist
Mursyid | Yes | 46A381A6-8D6D-48C9-AFC7-AB08F3BAF868 | B2BCAB5A-5D07-447D-A2AB-46300482FE00 | NAFIRI-1 | CE59A411-2633-45B7-AE52-EB729FD34DB2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NAFIRI-1 NOOP.pdf | NAFIRI-1 NOOP.pdf | Yes |  | Uploads\ce59a411-2633-45b7-ae52-eb729fd34db2.pdf | Exist
Mursyid | Yes | EC706CB6-8A9A-43FD-A5A1-A56375E39E02 | AAB7539C-4724-487E-A77B-467966ED160E | D35B-219ST2 | D6106FF7-734B-44F7-BF87-4D59C28D22ED | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPB-219ST2 End Of Well Report Final.pdf |  | No |  | Uploads\d6106ff7-734b-44f7-bf87-4d59c28d22ed.pdf | Exist
Mursyid | Yes | C5B73A3F-4171-4DA8-BC88-45E0FB04E70B | AAB7539C-4724-487E-A77B-467966ED160E | D35B-219ST2 | 5C88D90E-8E2D-47BA-89C9-EBD236943FCF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-219ST2 NOOP_signed.pdf | D35B-219ST2 NOOP_signed.pdf | Yes |  | Uploads\5c88d90e-8e2d-47ba-89c9-ebd236943fcf.pdf | Exist
Mursyid | Yes | D81F9F6B-F3BC-450D-B3F5-CCF31AE5001F | 1DA73D73-4C81-4747-8266-473EC6024B0B | BARAM-B42 | 02C278E6-7AE4-40FA-8ADE-C5A8FD28576A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARAM-B42 NOOP.pdf | BARAM-B42 NOOP.pdf | Yes |  | Uploads\02c278e6-7ae4-40fa-8ade-c5a8fd28576a.pdf | Exist
Mursyid | Yes | 3DB6AF6B-5394-4772-A839-B653FF3397A8 | 1DA73D73-4C81-4747-8266-473EC6024B0B | BARAM-B42 | 84DCEFEB-BA55-407E-A42E-70384180423C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BARMGL6647_Baram-B42.pdf | SKO3BARMGL6647_Baram-B42.pdf | Yes |  | Uploads\84dcefeb-ba55-407e-a42e-70384180423c.pdf | Exist
Mursyid | Yes | BC4A66D8-F450-434E-819C-403ACF59BCF2 | 72548658-F280-4B73-9AA6-475F8F9AF155 | BEBARU-2 | 4CD52AD2-5C4F-4CB3-962E-CFD14F8977FD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEBARU-1 EOWR_Final (full)_Submission.pdf |  | No |  | Uploads\4cd52ad2-5c4f-4cb3-962e-cfd14f8977fd.pdf | Exist
Mursyid | Yes | 4BC52536-7074-46B6-AF6D-ACC456B16BDC | 72548658-F280-4B73-9AA6-475F8F9AF155 | BEBARU-2 | EFCE21A9-5F94-4D78-93CA-9B689C8ACC7F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bebaru-1 NOOP_FINAL_Rev1.pdf |  | No |  | Uploads\efce21a9-5f94-4d78-93ca-9b689c8acc7f.pdf | Exist
Mursyid | Yes | C358E0A9-1382-403D-83B3-A40875072BCD | 0A8AC405-1B88-49D8-93A5-479BD31AB65D | SELUANG-1RDR1 | 8EAF9FC5-164B-4154-9651-6FE360BA165C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Seluang-1 NOOP Internal.pdf |  | No |  | Uploads\8eaf9fc5-164b-4154-9651-6fe360ba165c.pdf | Exist
Mursyid | Yes | 32A0405C-F87E-4EC2-98C8-C2DFD4CC3B7C | 0A8AC405-1B88-49D8-93A5-479BD31AB65D | SELUANG-1RDR1 | 2C2507B3-3169-486D-8DDD-DB02BA69A4DA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SELUANG-1RDR1 FWR without Appendix_signed.pdf | SELUANG-1RDR1 FWR without Appendix_signed.pdf | Yes |  | Uploads\2c2507b3-3169-486d-8ddd-db02ba69a4da.pdf | Exist
Mursyid | Yes | 81FD0DAD-8953-4E90-8FFD-821676059577 | 62F2EFB7-6F74-449F-9106-48030830EC10 | ANGSI-D15 | 3FF1A734-D54E-4827-9980-6947BD30A914 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIGL23_ANGSI_D15.pdf | PMO3ANSIGL23_ANGSI_D15.pdf | Yes |  | Uploads\3ff1a734-d54e-4827-9980-6947bd30a914.pdf | Exist
Mursyid | Yes | ACD280F0-64A2-427D-B3E8-21DAC7C833A4 | 62F2EFB7-6F74-449F-9106-48030830EC10 | ANGSI-D15 | A424CDA2-F217-4A29-8F7D-BFBE04B9A3E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWSJ3_ANGSI_D15.pdf | PMO3ANSIWSJ3_ANGSI_D15.pdf | Yes |  | Uploads\a424cda2-f217-4a29-8f7d-bfbe04b9a3e8.pdf | Exist
Mursyid | Yes | 2D177256-1B82-42B9-AA4E-5E841752BC39 | E8E53181-FD48-4AB6-B65E-480F47C9E91D | TEMBAKAU-2 | 76994A64-652C-47E0-AE48-17D7B03F3756 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TMBAWS03_TEMBAKAU-2_LUNDIN_IPC_NOOP.pdf | PMO3TMBAWS03_TEMBAKAU-2_LUNDIN_IPC_NOOP.pdf | Yes |  | Uploads\76994a64-652c-47e0-ae48-17d7b03f3756.pdf | Exist
Mursyid | Yes | 76DE1A05-0219-44AE-99A6-C7553BCFB884 | E8E53181-FD48-4AB6-B65E-480F47C9E91D | TEMBAKAU-2 | 4538A00D-EE04-4049-9D25-ABB16E56370F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TMBAWS04_TEMBAKAU-2_LUNDIN_IPC_FWR.pdf | PMO3TMBAWS04_TEMBAKAU-2_LUNDIN_IPC_FWR.pdf | Yes |  | Uploads\4538a00d-ee04-4049-9d25-abb16e56370f.pdf | Exist
Mursyid | Yes | 93B8A527-1362-46DD-A7F2-723100C1776F | 25EA6A85-8FF5-447B-BE91-485DF311A9CD | HEBAT-1 | 593DABE7-9AEF-40D6-B7F5-AE2D35B0E831 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hebat-1 FWR.pdf | Hebat-1 FWR.pdf | Yes |  | Uploads\593dabe7-9aef-40d6-b7f5-ae2d35b0e831.pdf | Exist
Mursyid | Yes | FF2533EA-D7D0-4346-B342-A3E1D8FCAD29 | 25EA6A85-8FF5-447B-BE91-485DF311A9CD | HEBAT-1 | FBB5377F-BC1A-4B6B-BE65-CF5A23C8DD5B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | HEBAT-1 NOOP.pdf | HEBAT-1 NOOP.pdf | Yes |  | Uploads\fbb5377f-bc1a-4b6b-be65-cf5a23c8dd5b.pdf | Exist
Mursyid | Yes | 0EAA436F-8BE3-4944-8C9D-1EC7B087C42A | 822400CF-FE0C-4607-A386-48F6AF3BE52B | SM-84 | 1D5C7E78-CC4A-4354-BF12-D83B9CF8D39A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-SM 84 ST1 (F14) NOOP.pdf | SAMARANG-SM 84 ST1 (F14) NOOP.pdf | Yes |  | Uploads\1d5c7e78-cc4a-4354-bf12-d83b9cf8d39a.pdf | Exist
Mursyid | Yes | A51C8CC4-4F50-4F93-925E-5AD55AABF003 | 822400CF-FE0C-4607-A386-48F6AF3BE52B | SM-84 | 6FEE9A24-C775-4246-A34A-B72B5F7A2BB4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSCT_SM_84.pdf | SAMARANG SM-84 ST1 EOWR.pdf | No |  | Uploads\6fee9a24-c775-4246-a34a-b72b5f7a2bb4.pdf | Exist
Mursyid | Yes | D6D519FE-35C4-486D-8D0B-348591BAEE2B | 446A2F5A-17F7-4A85-8634-49B0380203F9 | RT-P3 | B9853CCE-0AD4-49B0-84D0-238C213DF568 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_Block H Phase 1A Development Notice of Operation Rev0.pdf |  | No |  | Uploads\b9853cce-0ad4-49b0-84d0-238c213df568.pdf | Exist
Mursyid | Yes | B93B995D-8151-4699-84D2-AD0BCEBAE7D4 | 446A2F5A-17F7-4A85-8634-49B0380203F9 | RT-P3 | 6644A6E0-44AB-4C75-9695-5537D1910642 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | RT-P3_EOWR.pdf | RT-P3_EOWR.pdf | Yes |  | Uploads\6644a6e0-44ab-4c75-9695-5537d1910642.pdf | Exist
Mursyid | Yes | 2A4EE8AF-116F-4E5A-B60C-0AB785A134E7 | 06CEB6DB-C557-4F67-97AE-49C189C712ED | D35B-214ST1 | 4C2E043B-27EA-4A15-B74E-DDD18EC50E00 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP D35B-214 (RESUBMISSION).pdf |  | No |  | Uploads\4c2e043b-27ea-4a15-b74e-ddd18ec50e00.pdf | Exist
Mursyid | Yes | A5CA26CA-EF0A-4CEC-A41B-D2681802A0FD | 06CEB6DB-C557-4F67-97AE-49C189C712ED | D35B-214ST1 | 86AEACB6-1913-48CC-9BA0-EC777CFC54D1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPB-214ST1 End Of Well Report.pdf |  | No |  | Uploads\86aeacb6-1913-48cc-9ba0-ec777cfc54d1.pdf | Exist
Mursyid | Yes | 44EB4320-2628-450D-AEBD-CAC7C58A24FA | 99A4AC81-3D2E-43BB-8AAB-4A4B43885893 | BAKAU-A10 | 2A2DF451-5E1C-42CD-9E2B-F1BB20103343 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAKAU-A10 NOOP.pdf | BAKAU-A10 NOOP.pdf | Yes |  | Uploads\2a2df451-5e1c-42cd-9e2b-f1bb20103343.pdf | Exist
Mursyid | Yes | DD9531D4-ADFB-4888-8A55-D5690AF8764D | 99A4AC81-3D2E-43BB-8AAB-4A4B43885893 | BAKAU-A10 | C7AF3FF4-E7CC-4D0E-96A3-83DE957318B4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAKAU-A10 FWR.pdf | BAKAU-A10 FWR.pdf | Yes |  | Uploads\c7af3ff4-e7cc-4d0e-96a3-83de957318b4.pdf | Exist
Mursyid | Yes | 4284F629-0320-49C8-B2FC-4FCF65A6B6AD | 7A4A3B84-DA6F-4AE3-9F43-4A6960979D6A | KASAWARI-A5 | 083FAAED-DA46-45A7-84E7-0685251BB013 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KASAWARI-A5 Petronas FWR - FINAL.pdf | KASAWARI-A5 Petronas FWR - FINAL.pdf | Yes |  | Uploads\083faaed-da46-45a7-84e7-0685251bb013.pdf | Exist
Mursyid | Yes | F46E2A40-FBA1-4795-92D1-8681BE5A50A5 | 7A4A3B84-DA6F-4AE3-9F43-4A6960979D6A | KASAWARI-A5 | E88AD9CB-3BD1-481F-8FA9-3A0A24C68C0E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DWP NOOP KASAWARI-A5_Final.pdf | DWP NOOP KASAWARI-A5_Final.pdf | Yes |  | Uploads\e88ad9cb-3bd1-481f-8fa9-3a0a24c68c0e.pdf | Exist
Mursyid | Yes | 132DDFA1-9F4F-4A4B-A724-C5BC342837BB | 8A6B8136-D5F7-4DCB-B1CE-4AA138AC496D | F12-A1 | 4F4EDF22-63AC-4DCF-8884-E2CF512CE321 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP F12-A1 FINAL.pdf | NOOP F12-A1 FINAL.pdf | Yes |  | Uploads\4f4edf22-63ac-4dcf-8884-e2cf512ce321.pdf | Exist
Mursyid | Yes | EC3D6A41-9BE1-496C-9372-C199196C1A2F | 8A6B8136-D5F7-4DCB-B1CE-4AA138AC496D | F12-A1 | 17443F25-1181-4734-B5AF-83C7E7C72783 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F12-WS10_F12_A1.pdf | SKO3F12-WS10_F12_A1.pdf | Yes |  | Uploads\17443f25-1181-4734-b5af-83c7e7c72783.pdf | Exist
Mursyid | Yes | 22C29AF2-EB2F-4862-8F00-602D91E9CA77 | FB272D91-FBC6-4508-92D6-4B1E594AE8DD | LEDANG-4SS | D3470DAB-C511-47C3-A9BA-ADBB68D91560 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Ledang-4 SS ST3 Final Well Report (circulate for signature).pdf | Ledang-4 SS ST3 Final Well Report (circulate for signature).pdf | Yes |  | Uploads\d3470dab-c511-47c3-a9ba-adbb68d91560.pdf | Exist
Mursyid | Yes | 82EA4BAE-3489-4431-9E00-54C22AC26808 | FB272D91-FBC6-4508-92D6-4B1E594AE8DD | LEDANG-4SS | 140F42A6-04A8-4E42-A166-9DD0400EF43A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Ledang-4SS Signed.pdf | NOOP Ledang-4SS Signed.pdf | Yes |  | Uploads\140f42a6-04a8-4e42-a166-9dd0400ef43a.pdf | Exist
Mursyid | Yes | 754CDF36-FAC8-48D9-8F49-BD1E6B3BF39E | A25C4BD2-C404-4DF4-8261-4B28868E771B | BOC-25 (DD) | 7D2E7F60-E5A0-4917-AD13-8BA2D86F8277 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-25 (DD) NOOP.pdf | BOC-25 (DD) NOOP.pdf | Yes |  | Uploads\7d2e7f60-e5a0-4917-ad13-8ba2d86f8277.pdf | Exist
Mursyid | Yes | 1B9EB207-F30A-46A3-B3AE-CC8E8F21C5CB | A25C4BD2-C404-4DF4-8261-4B28868E771B | BOC-25 (DD) | D602C0AF-7CB4-43AF-9089-512B2848411A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR BOC-25 (DD).pdf | EOWR BOC-25 (DD).pdf | Yes |  | Uploads\d602c0af-7cb4-43af-9089-512b2848411a.pdf | Exist
Mursyid | Yes | EACE47D4-6534-4BFE-967D-3BF8451A2776 | 3CED81CA-1D77-444B-AFE0-4B509A57C416 | BUNGA BAKAWALI-2 | 1871A034-3D2B-4852-A7B0-F98109CB6C6F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWIWS11_BUNGA_BAKAWALI_2.pdf | PMO3BKWIWS11_BUNGA_BAKAWALI_2.pdf | Yes |  | Uploads\1871a034-3d2b-4852-a7b0-f98109cb6c6f.pdf | Exist
Mursyid | Yes | 5F42C114-7850-4B73-BA32-723A0E558986 | 3CED81CA-1D77-444B-AFE0-4B509A57C416 | BUNGA BAKAWALI-2 | C6B28FA6-D80E-46EF-AC16-E58EE289ABC0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWIWS15_BUNGA_BAKAWALI_2.pdf | PMO3BKWIWS15_BUNGA_BAKAWALI_2.pdf | Yes |  | Uploads\c6b28fa6-d80e-46ef-ac16-e58ee289abc0.pdf | Exist
Mursyid | Yes | 97361840-C647-4F0D-981B-590985C1B33E | BB1C78F9-32D9-4B61-AFF4-4B704352C9CD | SAPA-20 | C9EE4BBC-FB13-493C-A8A5-DABC9FEA3624 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK311-91-DR-TN-0001-00_SAPA Revisit 1 Phase I NOOP_Rev 0.pdf |  | No |  | Uploads\c9ee4bbc-fb13-493c-a8a5-dabc9fea3624.pdf | Exist
Mursyid | Yes | CFAFEDA4-C35A-4FDC-9742-18BF70FC574D | BB1C78F9-32D9-4B61-AFF4-4B704352C9CD | SAPA-20 | D615D9F1-D629-4B49-A810-6825B42AACEF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-20 EOWR.pdf | SAPA-20 EOWR.pdf | Yes |  | Uploads\d615d9f1-d629-4b49-a810-6825b42aacef.pdf | Exist
Mursyid | Yes | 5AA9BEB2-FDD8-4F3B-B3F8-0DEE980C7574 | 7CB35667-EC81-491B-9206-4BCD1DE5B600 | BESAH-1 | 4E22E181-A83C-46E0-BC19-510244357BCA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Besah1 and Besah1ST1 w Attachments Signed.pdf | FWR Besah1 and Besah1ST1 w Attachments Signed.pdf | Yes |  | Uploads\4e22e181-a83c-46e0-bc19-510244357bca.pdf | Exist
Mursyid | Yes | 9891B292-06E5-4438-93EC-5F5FD97ABA89 | 7CB35667-EC81-491B-9206-4BCD1DE5B600 | BESAH-1 | 1E482425-9D80-43CF-BCCD-1421E21AC7AD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besah-1 NOOP 2.pdf | Besah-1 NOOP 2.pdf | Yes |  | Uploads\1e482425-9d80-43cf-bccd-1421e21ac7ad.pdf | Exist
Mursyid | Yes | 4EBB88EE-7E09-4DF9-BA22-449C8011FF77 | 6885C496-346A-4EC6-98B1-4CBDD2083A41 | BANANG-B4 | 9DC40CC2-7BEE-4499-9F02-F23C9F2B64E1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS09_BANANG_B4.pdf | PMO3BANGWS09_BANANG_B4.pdf | Yes |  | Uploads\9dc40cc2-7bee-4499-9f02-f23c9f2b64e1.pdf | Exist
Mursyid | Yes | 666442BC-26B2-4DD9-8511-E74C1EB9A05F | 6885C496-346A-4EC6-98B1-4CBDD2083A41 | BANANG-B4 | 7B09787C-9ADD-43CB-8A2C-002F5D96FC27 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS13_BANANG_B4.pdf | PMO3BANGWS13_BANANG_B4.pdf | Yes |  | Uploads\7b09787c-9add-43cb-8a2c-002f5d96fc27.pdf | Exist
Mursyid | Yes | 38B473AE-1283-47A7-B097-5365042D7C01 | FA13D90F-F07F-45E9-9B24-4D5DC2CD0208 | SNPA-06 | 1140108A-EE5F-4CA1-B83F-8F72182BD9D9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0012-00_SNPA-06 EOWR.pdf | MOM-SK309-72-DNC-RP-0012-00_SNPA-06 EOWR.pdf | Yes |  | Uploads\1140108a-ee5f-4ca1-b83f-8f72182bd9d9.pdf | Exist
Mursyid | Yes | 7AD2E618-E035-45BB-BA3A-50DD0D23B316 | FA13D90F-F07F-45E9-9B24-4D5DC2CD0208 | SNPA-06 | 233CA198-2B4A-46B0-948A-76234380A7F0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0001-00_SNPA Dev Project Revisit 2 Phase I - NOOP.pdf |  | No |  | Uploads\233ca198-2b4a-46b0-948a-76234380a7f0.pdf | Exist
Mursyid | Yes | 7F77E529-8998-47F4-B1BD-7F859FDA48A2 | 8212B893-E2E1-487F-9463-4DBA1D7C527E | NC3-A1 | D762D39D-1CC2-4F84-BA26-50D902A58FC8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NC3-A1 NOOP.pdf | NC3-A1 NOOP.pdf | Yes |  | Uploads\d762d39d-1cc2-4f84-ba26-50d902a58fc8.pdf | Exist
Mursyid | Yes | 736529DB-0ED7-4F04-91FB-7BDDD9495404 | 8212B893-E2E1-487F-9463-4DBA1D7C527E | NC3-A1 | 8C8E0DAD-CFFB-4FE2-89BB-DFF898453FE5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NC3-A1 FWR.pdf | NC3-A1 FWR.pdf | Yes |  | Uploads\8c8e0dad-cffb-4fe2-89bb-dff898453fe5.pdf | Exist
Mursyid | Yes | 6336EE62-FE58-4760-BEC9-8ABE83037426 | EB36A7E8-8EFC-43DC-85DF-4E09EA116D6A | GUNTONG-C11ST1 | C8485CB1-3540-4AF4-926B-1C8FB1105B63 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Guntong C-11.pdf |  | No |  | Uploads\c8485cb1-3540-4af4-926b-1c8fb1105b63.pdf | Exist
Mursyid | Yes | 779F4F5D-8653-49A1-8A2D-E680D2A961AB | EB36A7E8-8EFC-43DC-85DF-4E09EA116D6A | GUNTONG-C11ST1 | EC64F027-DA1B-4FA5-A468-186CBF167C3D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GuC11ST1 (35) NOOP - MPM.pdf |  | No |  | Uploads\ec64f027-da1b-4fa5-a468-186cbf167c3d.pdf | Exist
Mursyid | Yes | 664F371C-9A1E-4E74-9083-BF909FD5BED1 | 54166B8C-15D9-49FC-B159-4E1EC569204D | PGA-07 | 7F536C27-FE83-4B78-9FFC-810535DC30F6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-07 EOWR (1).pdf | PGA-07 EOWR (1).pdf | Yes |  | Uploads\7f536c27-fe83-4b78-9ffc-810535dc30f6.pdf | Exist
Mursyid | Yes | 2C28247C-FE88-4B70-8DCB-AB36F1DD36B5 | 54166B8C-15D9-49FC-B159-4E1EC569204D | PGA-07 | 33843284-35A3-4BB5-8F30-081E95FD0587 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-07_NOOP 20th Apr 2020.pdf | PGA-07_NOOP 20th Apr 2020.pdf | Yes |  | Uploads\33843284-35a3-4bb5-8f30-081e95fd0587.pdf | Exist
Mursyid | Yes | 78D76B67-F011-49F4-B8D8-86A48604EE36 | 76E85A5C-B547-401F-893C-4EDF9F3B3D57 | MLK-107 | 67AFFEF9-30D2-4DBA-9D7F-B8C6ED5F8EFF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL19_MLK-107_SHELL-NOOP.pdf | SBO3MKAIGL19_MLK-107_SHELL-NOOP.pdf | Yes |  | Uploads\67affef9-30d2-4dba-9d7f-b8c6ed5f8eff.pdf | Missing
Mursyid | Yes | F6656837-9001-46C1-A286-B4553B73A7E2 | 76E85A5C-B547-401F-893C-4EDF9F3B3D57 | MLK-107 | 14113BCF-4799-49F1-BEE1-FC55407E0A63 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-107 EOWR v1 Final.pdf | MLK-107 EOWR v1 Final.pdf | Yes |  | Uploads\14113bcf-4799-49f1-bee1-fc55407e0a63.pdf | Missing
Mursyid | Yes | 55152544-D09B-4E3F-8586-CEF2BFA546D2 | 80BF7F90-CBE5-472E-A9E9-4EFBF9978942 | BUNGA KAMANJU-1 | DE3A730B-5713-44E4-9AB8-10C6843CC945 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKMJWS04_1_BUNGA_KAMANJU_1.pdf | PMO3BKMJWS04_1_BUNGA_KAMANJU_1.pdf | Yes |  | Uploads\de3a730b-5713-44e4-9ab8-10c6843cc945.pdf | Exist
Mursyid | Yes | AB81BA32-5F88-4703-B010-6A78FB5C9B1F | 80BF7F90-CBE5-472E-A9E9-4EFBF9978942 | BUNGA KAMANJU-1 | 6009911F-BB2F-4E3E-A7DB-492A6829D772 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Kamanju-1_EOWR.pdf | Bunga Kamanju-1_EOWR.pdf | Yes |  | Uploads\6009911f-bb2f-4e3e-a7db-492a6829d772.pdf | Exist
Mursyid | Yes | BF743E8A-08E6-4F30-8DA4-070E013CAF9D | FC802CBD-FA47-4744-9F7B-4F40B71118DA | BUNGA TERATAI-4 | 2CEBBE63-FC91-4BD9-87AE-CA26321D5B26 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Teratai 4_Final.pdf | Bunga Teratai 4_Final.pdf | Yes |  | Uploads\2cebbe63-fc91-4bd9-87ae-ca26321d5b26.pdf | Exist
Mursyid | Yes | C32302D5-8E0B-4A3C-9233-2043F0C3E9C9 | FC802CBD-FA47-4744-9F7B-4F40B71118DA | BUNGA TERATAI-4 | D3156EBC-9B13-40F3-B38B-317B0C026460 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BT4(NE) signed.pdf |  | No |  | Uploads\d3156ebc-9b13-40f3-b38b-317b0c026460.pdf | Exist
Mursyid | Yes | 7BD0BAE2-FDF7-4BF3-B7B8-56D9CC744AA0 | 03D5780E-3206-411B-B60E-4F9FF9580A73 | KNDW-D11 | 9A007CB2-E46E-4EC6-8BC7-4E18AD3D7F0B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-11 NOOP.pdf | KNDW D-11 NOOP.pdf | Yes |  | Uploads\9a007cb2-e46e-4ec6-8bc7-4e18ad3d7f0b.pdf | Exist
Mursyid | Yes | 028CC082-594B-4EF6-8EF1-AE8595177C39 | 03D5780E-3206-411B-B60E-4F9FF9580A73 | KNDW-D11 | 72F8E011-ABB5-46AE-ADE2-42AA8E8E7770 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D11 EOWR.pdf | KNDW-D11 EOWR.pdf | Yes |  | Uploads\72f8e011-abb5-46ae-ade2-42aa8e8e7770.pdf | Exist
Mursyid | Yes | 7BF36AD3-F299-41D6-9FE0-82AD03CF9F3E | CBD28A78-0B8B-4FC1-9A90-4FE55489CA9F | MERAWAN BATU-1 | 3832760B-8066-4B64-A79A-0F2DE2B6AA9D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MRBTWS05_MERAWAN BATU-1_IPC_FWR.pdf | PMO3MRBTWS05_MERAWAN BATU-1_IPC_FWR.pdf | Yes |  | Uploads\3832760b-8066-4b64-a79a-0f2de2b6aa9d.pdf | Exist
Mursyid | Yes | 4C32275F-E62E-43B5-A2FE-3CB55F6644AB | CBD28A78-0B8B-4FC1-9A90-4FE55489CA9F | MERAWAN BATU-1 | 4F75BDA1-097D-4240-BE9C-3104AB0D6E45 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Marwan Batu-1.pdf |  | No |  | Uploads\4f75bda1-097d-4240-be9c-3104ab0d6e45.pdf | Exist
Mursyid | Yes | C8E53919-EE29-45D9-875E-AF286FF03929 | B8474252-4143-491A-B2F0-50251B625F4B | LARUT-A24 | 70BF69E1-1E59-4C78-B0E3-F3F94AA44598 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-24ST1 (OP7) Final Well Report.pdf | LARUT A-24ST1 (OP7) Final Well Report.pdf | Yes |  | Uploads\70bf69e1-1e59-4c78-b0e3-f3f94aa44598.pdf | Exist
Mursyid | Yes | F31793CA-4512-4A92-B877-CF079FED133C | B8474252-4143-491A-B2F0-50251B625F4B | LARUT-A24 | 1F7F4EFC-8418-4F11-BFA3-2882063F5874 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-24ST1 (OP7_NOOP) rev.2.pdf | LARUT A-24ST1 (OP7_NOOP) rev.2.pdf | Yes |  | Uploads\1f7f4efc-8418-4f11-bfa3-2882063f5874.pdf | Exist
Mursyid | Yes | 98656D9F-2B87-40D0-84C5-5AA5D5EF6FBA | 36E03D06-4A19-43B6-B14D-50AA37C3E8FA | WD-A18 | 95AD5744-DD33-4276-8742-0F6C5C6E0801 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WD-A18 NOOP.pdf | WD-A18 NOOP.pdf | Yes |  | Uploads\95ad5744-dd33-4276-8742-0f6c5c6e0801.pdf | Exist
Mursyid | Yes | EE008946-D121-49E5-893F-05B361214242 | 36E03D06-4A19-43B6-B14D-50AA37C3E8FA | WD-A18 | D9E2E28D-684A-4200-8710-C5969C22F5BA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WD-A18 Final Well Report.pdf | WD-A18 Final Well Report.pdf | Yes |  | Uploads\d9e2e28d-684a-4200-8710-c5969c22f5ba.pdf | Exist
Mursyid | Yes | 369B17DB-EA00-4A7F-80BE-0288C45F932E | B2F9DB37-49BF-4B5D-8EDD-516BD6F1FBB1 | MLK-108 | E5BF109D-967D-4BC9-9A53-A306C0EDAB9B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-108 FINAL.pdf |  | No |  | Uploads\e5bf109d-967d-4bc9-9a53-a306c0edab9b.pdf | Exist
Mursyid | Yes | 13A9C44B-6934-44AF-A2EB-E39BBDAE11BD | B2F9DB37-49BF-4B5D-8EDD-516BD6F1FBB1 | MLK-108 | 28A88B4F-CCCB-4D74-8A4D-02EC4ED8380D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-108 KMU2 South WI - NOOP v2.pdf | MLK-108 KMU2 South WI - NOOP v2.pdf | Yes |  | Uploads\28a88b4f-cccb-4d74-8a4d-02ec4ed8380d.pdf | Exist
Mursyid | Yes | 8EB4B481-61AA-41CC-8DD8-F723CF8CF041 | 9293A259-E791-4E62-9AF8-5172D06C924A | BENTARA-A1 | 4DC7B1C3-825E-4E76-A7A6-657BA318B0BF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bentara A1.pdf | Bentara A1.pdf | Yes |  | Uploads\4dc7b1c3-825e-4e76-a7a6-657ba318b0bf.pdf | Exist
Mursyid | Yes | 07AC054B-4EEA-4552-B161-969343109897 | 9293A259-E791-4E62-9AF8-5172D06C924A | BENTARA-A1 | 258B0741-BC06-4CED-A2DD-CA73EADF876C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bentara-A1 Final Well Report-Final Signed Copy.pdf | Bentara-A1 Final Well Report-Final Signed Copy.pdf | Yes |  | Uploads\258b0741-bc06-4ced-a2dd-ca73eadf876c.pdf | Exist
Mursyid | Yes | B0D33D8C-767B-409E-93CA-8FC55F25273B | 70A88FA4-EF13-4282-9DCF-51A08C88A794 | BUNGA-SAFFRON-1 | EAB06E7F-0E5B-4919-B64E-9A6DF5EA6613 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Saffron-1 ST1 NOOP.pdf | Bunga Saffron-1 ST1 NOOP.pdf | Yes |  | Uploads\eab06e7f-0e5b-4919-b64e-9a6df5ea6613.pdf | Exist
Mursyid | Yes | B6D6C491-F4AF-45E5-B028-1A1BC1B90ECA | 70A88FA4-EF13-4282-9DCF-51A08C88A794 | BUNGA-SAFFRON-1 | EC2C6094-22E9-459F-82FA-A91D92A5C8A7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BS-1ST1_FINAL _signed_BUNGA-SAFFRON-1_REPSOL.pdf |  | No |  | Uploads\ec2c6094-22e9-459f-82fa-a91d92a5c8a7.pdf | Exist
Mursyid | Yes | F5D021F2-F7DA-4A8D-8523-01BB36822F7B | DFE7B19F-7981-4156-A468-51DA63424B62 | SM-120 | F8BD6707-D469-4127-9B8D-39F3C826508F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR SM120 SM-EFAD-PCLO-DRL-JE-DRL-16-2018 .pdf | FWR SM120 SM-EFAD-PCLO-DRL-JE-DRL-16-2018 .pdf | Yes |  | Uploads\f8bd6707-d469-4127-9b8d-39f3c826508f.pdf | Exist
Mursyid | Yes | 311B9FCA-340C-4CA9-B517-13185D9A59C1 | DFE7B19F-7981-4156-A468-51DA63424B62 | SM-120 | DDB067DE-00AE-49CF-ABD3-2A922BEF9AB5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM120 w Signature (1).pdf | SM120 w Signature (1).pdf | Yes |  | Uploads\ddb067de-00ae-49cf-abd3-2a922bef9ab5.pdf | Exist
Mursyid | Yes | F1CDF665-917F-44BC-A37E-2F38018DD391 | 14301809-3EA7-4F89-82BD-51DFF2B6FA6D | BABADON-1 | 099894B4-F4B6-4319-8FB8-68539F192807 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Babadon-1 NOOP (R1).pdf | Babadon-1 NOOP (R1).pdf | Yes |  | Uploads\099894b4-f4b6-4319-8fb8-68539f192807.pdf | Exist
Mursyid | Yes | 1E22E886-F3C2-4F8C-89B1-95D60C72A18D | 14301809-3EA7-4F89-82BD-51DFF2B6FA6D | BABADON-1 | 74F58D29-DC56-4A48-81C8-81EB80B22511 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BDONDR6781_BABADON-1_PTTEP_FWR.pdf | SKO3BDONDR6781_BABADON-1_PTTEP_FWR.pdf | Yes |  | Uploads\74f58d29-dc56-4a48-81c8-81eb80b22511.pdf | Exist
Mursyid | Yes | BE4400C7-7052-4AA3-920A-89A20FAABFFB | 253183ED-32BE-481C-BEAE-51F284F57D46 | BN-86 | A0140DA4-4EA8-49C0-9932-643D1576D4CA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-86-FINAL.pdf | NOOP BN-86-FINAL.pdf | Yes |  | Uploads\a0140da4-4ea8-49c0-9932-643d1576d4ca.pdf | Exist
Mursyid | Yes | CCAFA602-34D0-4AD6-A97B-5A796A10E686 | 253183ED-32BE-481C-BEAE-51F284F57D46 | BN-86 | 1B454148-2B56-4D1E-B3B6-537301C401CE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-86 Petronas Final Well Report TR.pdf | BN-86 Petronas Final Well Report TR.pdf | Yes |  | Uploads\1b454148-2b56-4d1e-b3b6-537301c401ce.pdf | Exist
Mursyid | Yes | 6CED5B7B-26A7-4B41-9FBA-52D2FEF77266 | 28B4B03B-EE31-46B9-8837-526F8C0200FE | DULANG-D24ST2 | D5CF0076-C8E7-40A6-BFA1-8D88FD5A7949 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXQ_DULANG_D24ST2.pdf | PMO3DULGWSXQ_DULANG_D24ST2.pdf | Yes |  | Uploads\d5cf0076-c8e7-40a6-bfa1-8d88fd5a7949.pdf | Exist
Mursyid | Yes | 35205A31-ADAD-4703-A38F-DADD386914C4 | 28B4B03B-EE31-46B9-8837-526F8C0200FE | DULANG-D24ST2 | 2CC966AD-2E73-4AD3-80FC-2CCDD241F556 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXM_DULANG_D24ST2.pdf | PMO3DULGWSXM_DULANG_D24ST2.pdf | Yes |  | Uploads\2cc966ad-2e73-4ad3-80fc-2ccdd241f556.pdf | Exist
Mursyid | Yes | 019C1D7B-D7AC-4495-B711-C0FD16E06A39 | 34E7E58A-A448-4F33-8709-5295C0665FAD | BERANTAI EAST-2 | 9B3C9E11-D398-4952-BE8D-3720DE9A999C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Berantai East-2 and Sidetrack-2 .pdf | NOOP Berantai East-2 and Sidetrack-2 .pdf | Yes |  | Uploads\9b3c9e11-d398-4952-be8d-3720de9a999c.pdf | Exist
Mursyid | Yes | B85559F0-F444-415E-A55C-9E8D41957543 | 34E7E58A-A448-4F33-8709-5295C0665FAD | BERANTAI EAST-2 | D8AAE7AC-F9D5-489C-AC7A-612981B75ED9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRE-2 Final Well Report Rev 1.pdf |  | No |  | Uploads\d8aae7ac-f9d5-489c-ac7a-612981b75ed9.pdf | Exist
Mursyid | Yes | 0531A1B7-EE17-4D03-A10B-A26F8ABB1DCE | F94AC7BE-7C7D-4C0D-B8E2-531984B4962C | MALIGAN-1 | 61A5BB15-A95E-40D3-9535-B5F658E8F84F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Maligan-1 EOWR_FINAL w Appendix_P2.pdf | Maligan-1 EOWR_FINAL w Appendix_P2.pdf | Yes |  | Uploads\61a5bb15-a95e-40d3-9535-b5f658e8f84f.pdf | Exist
Mursyid | Yes | 367B6E8E-8CF3-49E4-8728-A63F13E94D85 | F94AC7BE-7C7D-4C0D-B8E2-531984B4962C | MALIGAN-1 | 7D8A9313-88CA-4BC2-BB0F-39985C8DCEC3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Maligan-1 NOOP_FINAL signed.pdf | Maligan-1 NOOP_FINAL signed.pdf | Yes |  | Uploads\7d8a9313-88ca-4bc2-bb0f-39985c8dcec3.pdf | Exist
Mursyid | Yes | F54BF9EF-E4D0-4EA0-8ED3-76E97740D71A | B8D35E42-AFEF-4A83-B413-532A48D91DC4 | BESAR-A1 | 1FCCE193-90D5-4C7E-A21A-6D5B217AFD73 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar- A1_FINAL.pdf | Besar- A1_FINAL.PDF | Yes |  | Uploads\1fcce193-90d5-4c7e-a21a-6d5b217afd73.pdf | Exist
Mursyid | Yes | 23EFA327-2468-4AA7-B6B8-CBAA43051F64 | B8D35E42-AFEF-4A83-B413-532A48D91DC4 | BESAR-A1 | 019AC713-B1E4-4F97-88B1-E27307833B49 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Besar-A1.pdf | FWR Besar-A1.pdf | Yes |  | Uploads\019ac713-b1e4-4f97-88b1-e27307833b49.pdf | Exist
Mursyid | Yes | 3776CA92-2EAF-498A-8A0B-F43F5AE3A4EA | 86B0ED6E-92EC-4CF6-A1D5-53C37882E311 | GK-P718AR2 | E65EE17D-9D62-4F20-825E-8370118E116F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK P718AR2 EOWR.pdf | GK P718AR2 EOWR.pdf | Yes |  | Uploads\e65ee17d-9d62-4f20-825e-8370118e116f.pdf | Exist
Mursyid | Yes | CE27C063-5C29-458B-B272-260A260F90D7 | 86B0ED6E-92EC-4CF6-A1D5-53C37882E311 | GK-P718AR2 | CED91E00-6DE2-4582-9AAF-C37522F37714 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-P718A NOOP Rev2.pdf |  | No |  | Uploads\ced91e00-6de2-4582-9aaf-c37522f37714.pdf | Exist
Mursyid | Yes | 359E06B1-A372-46A1-A82D-894DFF7CC50A | 0CEAB225-9F03-4F33-8FEE-53E88E269CF7 | KNDW-D09 | 92577BB7-D6A3-486D-9DDD-0350E88B2B9A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNWD-D09 Rev.01.pdf |  | No |  | Uploads\92577bb7-d6a3-486d-9ddd-0350e88b2b9a.pdf | Exist
Mursyid | Yes | 15B6C0C8-6224-4BAB-80E0-8B3378382630 | 0CEAB225-9F03-4F33-8FEE-53E88E269CF7 | KNDW-D09 | 9246B0E8-D21F-42DA-82A0-9ABE39C75BE7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D09_NOOP_signed.pdf | KNDW-D09_NOOP_signed.pdf | Yes |  | Uploads\9246b0e8-d21f-42da-82a0-9abe39c75be7.pdf | Exist
Mursyid | Yes | CC30B4A6-6353-4C09-B768-72727B6BE3F6 | 80843FBD-9077-42C2-B040-54ABE2A5DDB4 | BESAR-A7 | E1AEEA38-A00D-48D1-9ADC-573E9058B4D6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Besar-A7 (Internal Copy).pdf | NOOP Besar-A7 (Internal Copy).pdf | Yes |  | Uploads\e1aeea38-a00d-48d1-9adc-573e9058b4d6.pdf | Exist
Mursyid | Yes | CD51CB57-B06F-4E73-A053-645EE6D88DF1 | 80843FBD-9077-42C2-B040-54ABE2A5DDB4 | BESAR-A7 | 2B8216D8-A51F-44C6-9D12-11258E79E441 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar A7 FWR Final.pdf | Besar A7 FWR Final.pdf | Yes |  | Uploads\2b8216d8-a51f-44c6-9d12-11258e79e441.pdf | Exist
Mursyid | Yes | 0E6118F2-582F-4F71-A9BE-8625B337FD64 | 4E965EDB-F116-46B6-AA09-54B6F2C438D3 | SNPA-05 | 0A72D3E5-F8A1-4D80-8527-23EA56D8AAC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0001-00_SNPA Dev Project Revisit 2 Phase I - NOOP.pdf |  | No |  | Uploads\0a72d3e5-f8a1-4d80-8527-23ea56d8aac6.pdf | Exist
Mursyid | Yes | 6AD75621-CCDC-466D-9218-1F350492BE20 | 4E965EDB-F116-46B6-AA09-54B6F2C438D3 | SNPA-05 | A1601922-DA40-424C-99A2-D1E59A1D505B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0011-00_SNPA-05ST1 EOWR.pdf | MOM-SK309-72-DNC-RP-0011-00_SNPA-05ST1 EOWR.pdf | Yes |  | Uploads\a1601922-da40-424c-99a2-d1e59a1d505b.pdf | Exist
Mursyid | Yes | D882B1B6-98AF-45AE-ADE9-537F7EA843FA | 003B6CA2-2104-4737-BE40-55ACDCFBBEC0 | TEMANA-T76 | 4FF8D4FC-B585-40A1-88DD-1D24A24BE394 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TMNAGL25_TEMANA_T76.pdf | SKO3TMNAGL25_TEMANA_T76.pdf | Yes |  | Uploads\4ff8d4fc-b585-40a1-88dd-1d24a24be394.pdf | Exist
Mursyid | Yes | F7DB203F-247D-4BE8-9546-F316D6F463F0 | 003B6CA2-2104-4737-BE40-55ACDCFBBEC0 | TEMANA-T76 | 7E6B7B06-B2AD-4777-911C-EA5DCF2ADD67 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TMNAWS94_TEMANA_T76.pdf | SKO3TMNAWS94_TEMANA_T76.pdf | Yes |  | Uploads\7e6b7b06-b2ad-4777-911c-ea5dcf2add67.pdf | Exist
Mursyid | Yes | A351991B-D777-44BD-9D64-CBC93C1FBFD9 | 093AFE49-8D9B-4396-922F-565DD3586818 | TEPAT-1 | F6E027C4-AD0D-4CCB-9AF5-BE6F6D11D962 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tepat-1_NOOP_v171117.pdf | Tepat-1_NOOP_v171117.pdf | Yes |  | Uploads\f6e027c4-ad0d-4ccb-9af5-be6f6d11d962.pdf | Exist
Mursyid | Yes | 0EA4D918-5983-477D-9BC2-100080C6A1AF | 093AFE49-8D9B-4396-922F-565DD3586818 | TEPAT-1 | 95EFF5D8-16BD-471B-96D2-4DC5607AC8E7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TEPAT-1 - FDCR - FINAL V0 - ALL.pdf | TEPAT-1 - FDCR - FINAL V0 - ALL.pdf | Yes |  | Uploads\95eff5d8-16bd-471b-96d2-4dc5607ac8e7.pdf | Exist
Mursyid | Yes | 3AEFF6F9-F428-4171-B277-424B3EE535DC | AAB307D8-6615-4794-A600-56BCB53A15F4 | DULANG-D12ST1 | E1AC34D3-0BCD-4DCE-B060-4E25E2392B88 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang EMUP Addendum D12ST1 - OP2 Final Submission to MPM.pdf |  | No |  | Uploads\e1ac34d3-0bcd-4dce-b060-4e25e2392b88.pdf | Exist
Mursyid | Yes | DC2E2D02-90EA-4BD1-934B-EC5690DBE97B | AAB307D8-6615-4794-A600-56BCB53A15F4 | DULANG-D12ST1 | B6E8BD28-5992-45CB-BA53-00C2B8E2CD80 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang D12ST1 OP2 FWR Complete Attachment.pdf | Dulang D12ST1 OP2 FWR Complete Attachment.pdf | Yes |  | Uploads\b6e8bd28-5992-45cb-ba53-00c2b8e2cd80.pdf | Exist
Mursyid | Yes | 66569BA4-0378-426C-BEDD-B7D71881296A | 05D5CF1A-30E7-494B-B9E8-56DAB27EDB81 | F19 SHALLOW-1 | 25C40CAA-D783-464C-887C-EC5D9163B439 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F19 Shallow-1 FWR.pdf | F19 Shallow-1 FWR.pdf | Yes |  | Uploads\25c40caa-d783-464c-887c-ec5d9163b439.pdf | Exist
Mursyid | Yes | 84DEDBF9-C34F-4CB4-A6C4-6A52D5DAB878 | 05D5CF1A-30E7-494B-B9E8-56DAB27EDB81 | F19 SHALLOW-1 | 5EA1BA56-5AA0-4102-BD12-07367E9FBEE5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F19HWS01_F19 SHALLOW-1_PCSB_NOOP.pdf | SKO3F19HWS01_F19 SHALLOW-1_PCSB_NOOP.pdf | Yes |  | Uploads\5ea1ba56-5aa0-4102-bd12-07367e9fbee5.pdf | Exist
Mursyid | Yes | 06F396DE-360D-4659-BDC4-649CECD894C5 | 01ED95BC-E79B-486F-B85B-577683AE5B0B | CD-B17 | A7189AAB-0591-40CB-9F46-BB503E3CD57E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-B17 NOOP.pdf | CD-B17 NOOP.pdf | Yes |  | Uploads\a7189aab-0591-40cb-9f46-bb503e3cd57e.pdf | Exist
Mursyid | Yes | 67CE8A67-8C5C-4BA3-B85E-CE0F5A1EE7DB | 01ED95BC-E79B-486F-B85B-577683AE5B0B | CD-B17 | 3709B239-B6C9-4D87-9B2C-874EF792BBEA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD B17 Final Well Report PMY REP D 0005.pdf | CD B17 Final Well Report PMY REP D 0005.pdf | Yes |  | Uploads\3709b239-b6c9-4d87-9b2c-874ef792bbea.pdf | Exist
Mursyid | Yes | 0A4F3FF6-B3DA-4088-A0C6-9C8CC97D7CE9 | 02D4AAEB-E256-4029-976D-57A10D6FCD6F | TT-A7 | D6A1CE1A-D06F-4137-B2BB-0F3C5B0C33AC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A7 Petronas Final Well Report_A7-signed.pdf | TT-A7 Petronas Final Well Report_A7-signed.pdf | Yes |  | Uploads\d6a1ce1a-d06f-4137-b2bb-0f3c5b0c33ac.pdf | Exist
Mursyid | Yes | A54A29FC-C2AF-4D22-8745-54E2FF368A8E | 02D4AAEB-E256-4029-976D-57A10D6FCD6F | TT-A7 | 29AEA295-023D-4B62-8A9E-B0AEF1981B27 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TT-A7.pdf | NOOP TT-A7.pdf | Yes |  | Uploads\29aea295-023d-4b62-8a9e-b0aef1981b27.pdf | Exist
Mursyid | Yes | 9CE46649-3B61-4E98-8A49-737A8F36E858 | F2D05074-C8F4-484F-8E7F-57F2A6C84D0B | BERGADING-A8(K) | 23686F62-A564-400C-BBC6-84AE591941D5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRG A-8(K).pdf |  | No |  | Uploads\23686f62-a564-400c-bbc6-84ae591941d5.pdf | Exist
Mursyid | Yes | 6D4B1139-610F-4198-881C-B99B3A262F6C | F2D05074-C8F4-484F-8E7F-57F2A6C84D0B | BERGADING-A8(K) | 0778A47D-9964-45F6-8DB9-B00F283DBB10 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading A-8.pdf |  | No |  | Uploads\0778a47d-9964-45f6-8db9-b00f283dbb10.pdf | Exist
Mursyid | Yes | FCA1627B-0B01-4B9C-B917-635EA03FD3D5 | 2C087354-5F64-463B-A594-58606516F126 | BKC-8 | 7211604A-FD0A-48DB-8222-F864F7FE83FF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWAGL67_BKC-8ST1€.pdf | PMO3BKWAGL67_BKC-8ST1€.pdf | Yes |  | Uploads\7211604a-fd0a-48db-8222-f864f7fe83ff.pdf | Exist
Mursyid | Yes | 580B22A2-D07E-47D5-AD03-2B2D738F8845 | 2C087354-5F64-463B-A594-58606516F126 | BKC-8 | B3E45C4D-2295-46DD-9D5F-A5E6031ABC42 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKC-8ST1_EOWR Updated.pdf | BKC-8ST1_EOWR Updated.pdf | Yes |  | Uploads\b3e45c4d-2295-46dd-9d5f-a5e6031abc42.pdf | Exist
Mursyid | Yes | 305ABCB7-AD2A-422F-BC07-2F9895BE1ABE | 0C454A3E-9CE3-4847-A48F-58929448F25C | SM-37ST | 4F92946D-B864-408B-9468-B22492657B9A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-37ST EOWR_FINAL_signed.pdf | SM-37ST EOWR_FINAL_signed.pdf | Yes |  | Uploads\4f92946d-b864-408b-9468-b22492657b9a.pdf | Exist
Mursyid | Yes | BC347BAD-C212-4D65-BF68-E2E4B44C34A7 | 0C454A3E-9CE3-4847-A48F-58929448F25C | SM-37ST | D1D4893A-A734-4327-9FF1-5BD1CA83F795 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM37ST NOOP SM - 2EOR - DD - DRL - DB - DRL - - 26 - 2018.pdf | SM37ST NOOP SM - 2EOR - DD - DRL - DB - DRL - - 26 - 2018.pdf | Yes |  | Uploads\d1d4893a-a734-4327-9ff1-5bd1ca83f795.pdf | Exist
Mursyid | Yes | C5ADC2AE-7625-42E4-8AE9-E5CDBA6FE8F6 | 8BDAACAB-B8C0-40C6-AD01-58C0C82624CC | AJK-A1ST1 | E40BF9B6-F26D-4E1B-8CA6-840F66E8545A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | AJK-A1 ST1.pdf | AJK-A1 ST1.pdf | Yes |  | Uploads\e40bf9b6-f26d-4e1b-8ca6-840f66e8545a.pdf | Exist
Mursyid | Yes | D6D3C83D-2F0B-4F70-98AB-2F954C32FEB2 | 8BDAACAB-B8C0-40C6-AD01-58C0C82624CC | AJK-A1ST1 | AC4A1527-7F2F-42E7-B10F-B45808DC0068 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | AJK-A1 ST1 and ST2 Final Well Report.pdf | AJK-A1 ST1 and ST2 Final Well Report.pdf | Yes |  | Uploads\ac4a1527-7f2f-42e7-b10f-b45808dc0068.pdf | Exist
Mursyid | Yes | 851DF544-02AB-44FC-A8A4-9E467241DF76 | B4F698D0-89B7-4119-B093-58FACA57D315 | D35A-108ST5 | DCDCACA9-DF22-4A29-8BC7-E3B21C6BC07A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35A-108ST6 NOOP Final.pdf | D35A-108ST6 NOOP Final.pdf | Yes |  | Uploads\dcdcaca9-df22-4a29-8bc7-e3b21c6bc07a.pdf | Exist
Mursyid | Yes | D3C76A7A-CC78-4760-AEAB-CAB0AAF30EEF | B4F698D0-89B7-4119-B093-58FACA57D315 | D35A-108ST5 | 7E85BFAC-E6BA-41F9-83A2-18C519B881E6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPA-108ST5 End Of Well Report - Signed1.pdf | D35DPA-108ST5 End Of Well Report - Signed1.pdf | Yes |  | Uploads\7e85bfac-e6ba-41f9-83a2-18c519b881e6.pdf | Exist
Mursyid | Yes | 9EBCBDD9-2643-42DE-9B42-A271FA533458 | A7E2822A-DA28-4BCB-B36B-59348A1F2CD8 | BERGADING-D1 (C) | 0CEA3F99-49C4-4C39-A725-9280E67D9F89 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading D-1 (C) R0_FINAL_NOOP.pdf | Bergading D-1 (C) R0_FINAL.pdf | No |  | Uploads\0cea3f99-49c4-4c39-a725-9280e67d9f89.pdf | Exist
Wadi | Yes | 3756670F-1D8F-45FD-8638-965068F3E1C6 | A7E2822A-DA28-4BCB-B36B-59348A1F2CD8 | BERGADING-D1 (C) | 44A57FA3-727E-4888-93B5-E3345212F03C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading D-1_ Rev0_21062017 - PETRONAS SUBMISSION_FINAL.pdf |  | No |  | Uploads\44a57fa3-727e-4888-93b5-e3345212f03c.pdf | Exist
Mursyid | Yes | 1A57ABCA-8472-489F-A2DD-AB1D717A80CB | FEFC0A6C-D14F-4C49-8220-59448EDEF4C1 | SNPA-23 | C6AFC9D0-0E89-46BA-A8CE-D17139371CE6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRDHWS1C_SNPA-23_PTTEP_FWR.pdf | MOM-SK309-72-DNC-RP-0020-00_SNPA-23 EOWR.pdf | No |  | Uploads\c6afc9d0-0e89-46ba-a8ce-d17139371ce6.pdf | Missing
Mursyid | Yes | 09A294A3-BBC8-4DF6-8F4D-C4C30DF255D0 | FEFC0A6C-D14F-4C49-8220-59448EDEF4C1 | SNPA-23 | 6A53927D-7CE0-4CC8-BFB2-1240E8EF1278 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0002-00_1_SNPA 23_24_Revisit 2 Phase 3_Rev 1.pdf | MOM-SK309-72-DR-TN-0002-00_1_SNPA 23_24_Revisit 2 Phase 3_Rev 1.pdf | Yes |  | Uploads\6a53927d-7ce0-4cc8-bfb2-1240e8ef1278.pdf | Missing
Mursyid | Yes | CE748A72-6CD6-4189-B53B-752F7BD7CFD7 | A0E78DE6-936D-4882-93C0-5969795E7780 | BOC-26 (3B) | 0D75EB7F-436B-43F5-9F00-243276539554 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-3B (SWI) NOOP_signed copy_BOC-26 (36)_HML.pdf |  | No |  | Uploads\0d75eb7f-436b-43f5-9f00-243276539554.pdf | Exist
Mursyid | Yes | A249E1A5-365A-4C33-89B0-82827C84EC78 | A0E78DE6-936D-4882-93C0-5969795E7780 | BOC-26 (3B) | C34CACAD-49DB-4E35-B2BF-0323512D619F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR BOC-26 (3B)_Final Signed.pdf | EOWR BOC-26 (3B)_Final Signed.pdf | Yes |  | Uploads\c34cacad-49db-4e35-b2bf-0323512d619f.pdf | Exist
Mursyid | Yes | A51C74E2-DD12-4A0E-AEEF-93AE52B38EDD | 376FCE23-13F0-4F8C-B7F6-5AC0EEA348EA | E06-108 | 909F7A9B-F10D-4703-A5DE-5AA962B00C0B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-108 (N1) NOOP R2 Final - signed.pdf | E06-108 (N1) NOOP R2 Final - signed.pdf | Yes |  | Uploads\909f7a9b-f10d-4703-a5de-5aa962b00c0b.pdf | Exist
Mursyid | Yes | AF57D632-62A7-473A-976D-3541BE62ABF6 | 376FCE23-13F0-4F8C-B7F6-5AC0EEA348EA | E06-108 | AD2ACCA4-DFED-4157-978B-4D443919E15A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-108 End of Well Report.pdf | E06-108 End of Well Report.pdf | Yes |  | Uploads\ad2acca4-dfed-4157-978b-4d443919e15a.pdf | Exist
Mursyid | Yes | 700D5C05-6F3C-4B25-953D-410BF2BB08F4 | B3DA8456-474E-431D-8A33-5B0DD59DC1F2 | MONG-01 | EF44C726-8D7B-4964-B19A-2C4B44B783A2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mong-01 End of Well Report.pdf | Mong-01 End of Well Report.pdf | Yes |  | Uploads\ef44c726-8d7b-4964-b19a-2c4b44b783a2.pdf | Exist
Mursyid | Yes | 448719AA-796A-452F-824A-7D6159484502 | B3DA8456-474E-431D-8A33-5B0DD59DC1F2 | MONG-01 | CFBC4395-737F-4C5E-A808-8EB55E679716 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mong-1 NOOPs (Signed).pdf |  | No |  | Uploads\cfbc4395-737f-4c5e-a808-8eb55e679716.pdf | Exist
Mursyid | Yes | 77322D0F-880C-487F-B60B-75F7FA2AB6E1 | 2466B1F0-0CFC-4FA4-98AA-5B99252AE6BC | BN-84 | A87B14ED-0175-48F2-A577-6227C4A9C15E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BN-84 FINAL - for submission.pdf | FWR BN-84 FINAL - for submission.pdf | Yes |  | Uploads\a87b14ed-0175-48f2-a577-6227c4a9c15e.pdf | Exist
Mursyid | Yes | 4CFB7859-4867-4472-8167-1D3471B3176A | 2466B1F0-0CFC-4FA4-98AA-5B99252AE6BC | BN-84 | 9C809EE4-232E-4300-B25B-E3A88AB1F839 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-84 Final Signed.pdf | NOOP BN-84 Final Signed.pdf | Yes |  | Uploads\9c809ee4-232e-4300-b25b-e3a88ab1f839.pdf | Exist
Mursyid | Yes | 58EC40C5-DE2F-4499-A2F7-058385BE386D | 7B642852-6A2A-4826-9161-5C75572EF513 | D35 EAST-1 | 589485FA-5283-4798-9B9A-7E316ED6E907 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D35EWS03_D35 EAST-1_PCSB_FWR.pdf | SKO3D35EWS03_D35 EAST-1_PCSB_FWR.pdf | Yes |  | Uploads\589485fa-5283-4798-9b9a-7e316ed6e907.pdf | Exist
Mursyid | Yes | 9712605F-AF82-47BD-975F-BE71AA368210 | 7B642852-6A2A-4826-9161-5C75572EF513 | D35 EAST-1 | 4E63377B-A43B-498F-A8D5-5BABF1B2535D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D35EWS02_D35 EAST-1_PCSB_NOOP.pdf | SKO3D35EWS02_D35 EAST-1_PCSB_NOOP.pdf | Yes |  | Uploads\4e63377b-a43b-498f-a8d5-5babf1b2535d.pdf | Exist
Mursyid | Yes | 00D750D9-5078-4FEA-A743-F0D7FE22A283 | 46DD044D-A3D0-456A-B5A8-5D7F6A6722C6 | CENMUMUR-1 | E9FB5BE5-38C6-4938-B938-32F816306EB7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Cenmumur-1_Final NOOP_MLNG Ph1 Expl_.pdf | Cenmumur-1_Final NOOP_MLNG Ph1 Expl_.pdf | Yes |  | Uploads\e9fb5be5-38c6-4938-b938-32f816306eb7.pdf | Exist
Mursyid | Yes | 5515E07D-F037-498C-8DF5-6F081149C89F | 46DD044D-A3D0-456A-B5A8-5D7F6A6722C6 | CENMUMUR-1 | F990C4E2-7ECF-4D59-A1D7-AA4D48A383BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Cenmumur-1 EOWR.pdf | Cenmumur-1 EOWR.pdf | Yes |  | Uploads\f990c4e2-7ecf-4d59-a1d7-aa4d48a383be.pdf | Exist
Mursyid | Yes | 773098F6-1103-4071-BB89-ADD0896D3914 | 0F9E6AFD-2B59-4A38-B596-5DCDC6E00FE4 | WEST BELUMUT A-05 | DD3F2CCC-04D0-459E-B249-4B5608136348 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A05-signed.pdf |  | No |  | Uploads\dd3f2ccc-04d0-459e-b249-4b5608136348.pdf | Exist
Mursyid | Yes | E047FA21-E10C-4191-BDCE-E060CCAB9EEC | 0F9E6AFD-2B59-4A38-B596-5DCDC6E00FE4 | WEST BELUMUT A-05 | 55D8AC7B-1E27-4F94-8D06-AD379FD0CE51 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WBA-05 FWR.pdf |  | No |  | Uploads\55d8ac7b-1e27-4f94-8d06-ad379fd0ce51.pdf | Exist
Mursyid | Yes | C7224323-9DE3-4BD3-A287-B8B086F965EE | BC148C77-24B2-4256-8E3E-5E43DC211695 | BAYAN-C313ST1 | C7ABFE09-39D1-4AC0-A617-2C9641E49922 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-313 Loc P Notice of Operations_APPROVED.pdf |  | No |  | Uploads\c7abfe09-39d1-4ac0-a617-2c9641e49922.pdf | Exist
Mursyid | Yes | 147C2917-ADBA-4897-A871-B8F16904CA7A | BC148C77-24B2-4256-8E3E-5E43DC211695 | BAYAN-C313ST1 | 30413643-C61D-486C-BDF8-9C559A5DFF8D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-313 ST1 Final Well Report - Signed.pdf |  | No |  | Uploads\30413643-c61d-486c-bdf8-9c559a5dff8d.pdf | Exist
Mursyid | Yes | 15A9C7CA-348E-44D2-B3C9-FB2A78A6472A | 0CBD6EB2-F060-4D5D-B7E8-5EC1C331F8FC | MARJORAM-2 | 6BC24789-978A-465B-A474-C9552F473277 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Marjoram-2 Appraisal NOP.pdf | Marjoram-2 Appraisal NOP.pdf | Yes |  | Uploads\6bc24789-978a-465b-a474-c9552f473277.pdf | Exist
Mursyid | Yes | 789B05B5-EC30-4760-B42E-4231ED46EED1 | 0CBD6EB2-F060-4D5D-B7E8-5EC1C331F8FC | MARJORAM-2 | 228F58D9-1018-4D1C-B5A6-E7649ADBB26D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Marjoram-2 FWR.pdf | Marjoram-2 FWR.pdf | Yes |  | Uploads\228f58d9-1018-4d1c-b5a6-e7649adbb26d.pdf | Exist
Mursyid | Yes | D8480056-0361-4C0F-A1D2-17A2974DA1B8 | B498C70A-F204-4865-AD6A-5ED9E64E2F33 | MAK YONG-1 | C4516E23-E19E-42B2-8AA4-5F53F9DF1220 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mak_Yong-1_NOOP.docx.pdf | Mak_Yong-1_NOOP.docx.pdf | Yes |  | Uploads\c4516e23-e19e-42b2-8aa4-5f53f9df1220.pdf | Exist
Mursyid | Yes | BBA2185D-5AA3-4434-B760-716FB40F677A | B498C70A-F204-4865-AD6A-5ED9E64E2F33 | MAK YONG-1 | 2D171B09-3853-4A44-9108-35B457A49ADD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mak_Yong-1_Final_Well_Report_Official.pdf | Mak_Yong-1_Final_Well_Report_Official.pdf | Yes |  | Uploads\2d171b09-3853-4a44-9108-35b457a49add.pdf | Exist
Mursyid | Yes | 5F4B82A3-624A-437F-897E-ABA72BDA3656 | 13EC4008-DEEE-41E8-B575-5F050145BAFE | BOKOR DEEP WESTERN FLANK - 1 | CCE11B8C-DB33-464F-9E83-F93153F32ADF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BOKRWS1A_BOKOR DEEP WESTERN FLANK-1.pdf | SKO3BOKRWS1A_BOKOR DEEP WESTERN FLANK-1.pdf | Yes |  | Uploads\cce11b8c-db33-464f-9e83-f93153f32adf.pdf | Exist
Mursyid | Yes | CFD231ED-39F6-4BE7-BE2D-59A9A6A4318E | 13EC4008-DEEE-41E8-B575-5F050145BAFE | BOKOR DEEP WESTERN FLANK - 1 | B6951599-3042-45F1-AE66-0BE86BC8A11D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BOKRWS2X_BOKOR DEEP WESTERN FLANK-1.pdf | SKO3BOKRWS2X_BOKOR DEEP WESTERN FLANK-1.pdf | Yes |  | Uploads\b6951599-3042-45f1-ae66-0be86bc8a11d.pdf | Exist
Mursyid | Yes | 0112E9B0-D5CA-45D9-918A-2011AB83CF50 | 62B875DB-FBBF-4D61-A0F7-5F5607EB954E | GRK-101 | 1E26F66B-CC41-429A-85E5-E006634B0161 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gorek-101 FDCR_EOWR_Final_Rev0.0_S.pdf |  | No |  | Uploads\1e26f66b-cc41-429a-85e5-e006634b0161.pdf | Exist
Mursyid | Yes | BEEBC936-7F82-4621-8D4C-6A2BE08F215A | 62B875DB-FBBF-4D61-A0F7-5F5607EB954E | GRK-101 | 364B5162-96FB-4F1A-A89D-4B8F4833F858 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gorek-101 (SW) NOOP_Final_Rev2.pdf |  | No |  | Uploads\364b5162-96fb-4f1a-a89d-4b8f4833f858.pdf | Exist
Mursyid | Yes | 31F0C0DA-B404-46AE-8CCE-8C95D94EC3A2 | FFA51F27-1563-49BB-AC0B-5F73DDD4D3E5 | ANGSI-B19 | 059211CC-A2C4-40F4-80A4-48228EACE94F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ANGSI-B19ST1 FWR.pdf | ANGSI-B19ST1 FWR.pdf | Yes |  | Uploads\059211cc-a2c4-40f4-80a4-48228eace94f.pdf | Exist
Mursyid | Yes | 542712E1-FC03-4674-8713-EFC258F40FB0 | FFA51F27-1563-49BB-AC0B-5F73DDD4D3E5 | ANGSI-B19 | 3290295D-E582-4384-B47D-E5E76EF0A816 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ANGSI-B19ST1 NOOP.pdf | ANGSI-B19ST1 NOOP.pdf | Yes |  | Uploads\3290295d-e582-4384-b47d-e5e76ef0a816.pdf | Exist
Mursyid | Yes | 977CD560-8203-420D-8D0F-A45F40A7453E | 29044E73-834E-4E1E-A8BA-602BA019FAAA | EB A-29ST1 | AFE98A9E-B8C1-43A2-A79E-8DC499E12A60 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-29ST1 EOWR.pdf | EB A-29ST1 EOWR.pdf | Yes |  | Uploads\afe98a9e-b8c1-43a2-a79e-8dc499e12a60.pdf | Exist
Mursyid | Yes | 1E2CED76-4EB5-43A2-A4A5-89E4DE91BBD6 | 29044E73-834E-4E1E-A8BA-602BA019FAAA | EB A-29ST1 | 8B5F66D2-6222-419C-953C-849ABBDF2A11 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-29ST1.pdf | EB A-29ST1.pdf | Yes |  | Uploads\8b5f66d2-6222-419c-953c-849abbdf2a11.pdf | Exist
Mursyid | Yes | 6C7EBC75-1113-48B8-95E8-8C7DBDA1123B | 838C5203-2623-40DF-B590-60E9C61C7473 | TELOK-B4 | 3A868ED7-AF49-4C40-8FD4-50B179EBB06B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TELOWS57_TELOK-B4_EMEPMI_NOOP.pdf | PMO3TELOWS57_TELOK-B4_EMEPMI_NOOP.pdf | Yes |  | Uploads\3a868ed7-af49-4c40-8fd4-50b179ebb06b.pdf | Exist
Mursyid | Yes | 0D6E2C5E-C0F1-4899-8264-45A0AC1262A8 | 838C5203-2623-40DF-B590-60E9C61C7473 | TELOK-B4 | CE4ECDC9-4A12-4C63-8DD4-7EB5D8E6C4F7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Telok B4 Final Well Report (MPM Submission).pdf | Telok B4 Final Well Report (MPM Submission).pdf | Yes |  | Uploads\ce4ecdc9-4a12-4c63-8dd4-7eb5d8e6c4f7.pdf | Exist
Mursyid | Yes | 671AE308-506A-476B-861F-F3931C73D716 | CC56CA6C-D87E-4305-B808-61A45E053A96 | SUMANDAK SELATAN-B01ST1 | 5502894F-BB40-4D54-AE7B-FDDBC3E62E3D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan _B01_ST 2 FWR.pdf | Sumandak Selatan _B01_ST 2 FWR.pdf | Yes |  | Uploads\5502894f-bb40-4d54-ae7b-fddbc3e62e3d.pdf | Exist
Mursyid | Yes | DCD3953A-2903-47D1-92F6-EFE60EDBF6D6 | CC56CA6C-D87E-4305-B808-61A45E053A96 | SUMANDAK SELATAN-B01ST1 | 84B651BF-CD26-4176-B129-9F5C6573B797 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B01 ST1 NOOP (Final).pdf | Sumandak Selatan B01 ST1 NOOP (Final).pdf | Yes |  | Uploads\84b651bf-cd26-4176-b129-9f5c6573b797.pdf | Exist
Mursyid | Yes | 7FA58665-CB4C-4EFA-A6D9-F69BE4B81ECE | 820C2F21-6291-48F4-BBB2-61A4757ABCE0 | TABU-A11ST1 | 70786F3A-FC7D-47EB-9984-C23EF88C29D7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A11ST1 Slot 1 NOOP.pdf | Tabu A11ST1 Slot 1 NOOP.pdf | Yes |  | Uploads\70786f3a-fc7d-47eb-9984-c23ef88c29d7.pdf | Exist
Mursyid | Yes | 5E460D0B-FD3C-4702-8EA2-64A6B28C9DA2 | 820C2F21-6291-48F4-BBB2-61A4757ABCE0 | TABU-A11ST1 | 61D6F491-B2FD-483F-8355-A5F616260493 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TuA11ST1 Final Well Report.pdf | TuA11ST1 Final Well Report.pdf | Yes |  | Uploads\61d6f491-b2fd-483f-8355-a5f616260493.pdf | Exist
Mursyid | Yes | 9963C408-537C-4DDF-81C7-C6964DD3E011 | 89C7126D-7B05-4F78-AC76-61AC5B74A124 | WB A-02ST3 | 89D8A8ED-770F-47A1-B1C0-C5B69B35F239 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A-02ST3 Final.pdf | WB A-02ST3 Final.pdf | Yes |  | Uploads\89d8a8ed-770f-47a1-b1c0-c5b69b35f239.pdf | Exist
Mursyid | Yes | AE2C6DCE-2ABA-4E07-8D5B-D0939ECE631E | 89C7126D-7B05-4F78-AC76-61AC5B74A124 | WB A-02ST3 | D2CFE363-8B55-4469-9BB0-8C7ED9823795 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A-02ST3 EOWR.pdf | WB A-02ST3 EOWR.pdf | Yes |  | Uploads\d2cfe363-8b55-4469-9bb0-8c7ed9823795.pdf | Exist
Mursyid | Yes | F6C78EFB-FD6F-4FC8-AE1E-FFF447DB1781 | B01722BE-A584-423D-BF62-61C43B395427 | BUNGA TASBIH-1 (HARAPAN-1) | 18E89F28-9568-4DA1-B3B3-9A8FF863C026 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Tasbih-1 NOOP Final Rev03 Naga 8 Name.pdf |  | No |  | Uploads\18e89f28-9568-4da1-b3b3-9a8ff863c026.pdf | Exist
Mursyid | Yes | D875BE71-EB5E-4CB8-A6B7-057A829ED51A | B01722BE-A584-423D-BF62-61C43B395427 | BUNGA TASBIH-1 (HARAPAN-1) | D970337F-D4BC-4B2E-83E4-0CA06F64A0A9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Tasbeh-1 Approved FWR.pdf |  | No |  | Uploads\d970337f-d4bc-4b2e-83e4-0ca06f64a0a9.pdf | Exist
Mursyid | Yes | 3405E5C1-28EA-45A7-B61C-6AB9E0DE9FAB | 894E2281-50A3-4C5C-86F4-6269D4B6AA5E | KN-B4 | 4B942967-362D-4CBA-BB57-5A7BCFBA4CA8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS3X_KN_B4.pdf | SBO3KNBLWS3X_KN_B4.pdf | Yes |  | Uploads\4b942967-362d-4cba-bb57-5a7bcfba4ca8.pdf | Exist
Mursyid | Yes | 027D49F2-FF2B-4B3A-AA36-749DCC08C943 | 894E2281-50A3-4C5C-86F4-6269D4B6AA5E | KN-B4 | AEA4DFC5-766F-4E5A-874F-161E47BA7B0A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLGL65_KN_B4.pdf | SBO3KNBLGL65_KN_B4.pdf | Yes |  | Uploads\aea4dfc5-766f-4e5a-874f-161e47ba7b0a.pdf | Exist
Mursyid | Yes | BC87E3FE-BC81-4D6A-8D38-64B09B602AF2 | 412D7E7C-A850-4647-96E3-62E3139577A4 | BEKOK-AA14 | 65479C31-8F42-41E5-A538-CB18C36724B3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA14 Approved [Internal]2.pdf | NOOP Bekok AA14 Approved [Internal]2.pdf | Yes |  | Uploads\65479c31-8f42-41e5-a538-cb18c36724b3.pdf | Exist
Mursyid | Yes | AA7AE8F2-D5CB-4A29-81B8-9D54E9D61AF4 | 412D7E7C-A850-4647-96E3-62E3139577A4 | BEKOK-AA14 | F179100F-92C5-4FAC-8A93-338F09F75808 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bekok-AA14ST1 FWR.pdf | Bekok-AA14ST1 FWR.pdf | Yes |  | Uploads\f179100f-92c5-4fac-8a93-338f09f75808.pdf | Exist
Mursyid | Yes | 7C5CE6EB-C80D-44A4-9EF3-8E6C775DA6C6 | 0E890AA4-00B6-41FF-B426-62FBCC4D63A6 | SEPAT A-09 | 78CD1EF2-8191-4B08-84CE-A8A863C2492D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL31_SEPAT-A9.pdf |  | No |  | Uploads\78cd1ef2-8191-4b08-84ce-a8a863c2492d.pdf | Exist
Mursyid | Yes | 8119A690-954D-4A33-B3B0-3E0D93013EBC | 0E890AA4-00B6-41FF-B426-62FBCC4D63A6 | SEPAT A-09 | FDD27786-F08A-41F9-B0FB-55E890519571 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATWS69_SEPAT-A9.pdf |  | No |  | Uploads\fdd27786-f08a-41f9-b0fb-55e890519571.pdf | Exist
Mursyid |  | 5E32C5A2-4B44-4992-A0BE-181A1DF3EBCA | A7E25A29-A854-401F-A781-6304B56218DD | EW-119 ST2 | E3F459D8-FB7C-4831-86B6-A9DFDBE7B59C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NULL | EW-119 ST2_Rev3 Final Well Report.pdf | No |  | Uploads\e3f459d8-fb7c-4831-86b6-a9dfdbe7b59c.pdf | Exist
Mursyid |  | A9B20D6F-A596-4FC6-B3A5-A89B5138E487 | A7E25A29-A854-401F-A781-6304B56218DD | EW-119 ST2 | CBBA1B6F-D1B3-4C61-9F89-8DFE1C4E6B09 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NULL | 20190515_Erb West EW119 ST2 NOOP.pdf | No |  | Uploads\cbba1b6f-d1b3-4c61-9f89-8dfe1c4e6b09.pdf | Exist
Mursyid | Yes | 720ADAFB-D6DF-4082-9A2D-016913D48FF5 | E126E423-32C9-4F06-8D04-6319CD601299 | TT-A3 | 21B564F0-20A4-4522-BFCA-1F38F2AAAD77 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TUKTGL10_TT-A3_NOOP_PCSB.pdf | SKO3TUKTGL10_TT-A3_NOOP_PCSB.pdf | Yes |  | Uploads\21b564f0-20a4-4522-bfca-1f38f2aaad77.pdf | Exist
Mursyid | Yes | 67CA040C-A9A8-4A83-809A-B3FCC148F38E | E126E423-32C9-4F06-8D04-6319CD601299 | TT-A3 | 410F1A60-B660-42AB-80C8-2AC3089F7603 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3TUKTWS21_TT-A3_PCSB_FWR.pdf | FWR TT-A3 -Final to MPM.pdf | No |  | Uploads\410f1a60-b660-42ab-80c8-2ac3089f7603.pdf | Exist
Mursyid | Yes | 81823E36-6455-4BE3-816F-BB0BB635ED44 | E26D4F48-E345-4334-9EEB-63245038564C | HIKMAT-1 | 3579C443-E3C7-4DDB-BA6C-C866FADA661D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Block H Exploration Hikmat-1 End Of Well Report_(MY-H-10-DR-PR-0002-00).pdf | Block H Exploration Hikmat-1 End Of Well Report_(MY-H-10-DR-PR-0002-00).pdf | Yes |  | Uploads\3579c443-e3c7-4ddb-ba6c-c866fada661d.pdf | Exist
Mursyid | Yes | 6E44F1C3-1EA7-421E-9A3A-F2D317D0059C | E26D4F48-E345-4334-9EEB-63245038564C | HIKMAT-1 | 4722A2E9-27DA-4BA7-A51C-5747D382DC07 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hikmat -1 SB Block H NOOP (2023).pdf | Hikmat -1 SB Block H NOOP (2023).pdf | Yes |  | Uploads\4722a2e9-27da-4ba7-a51c-5747d382dc07.pdf | Exist
Mursyid | Yes | F5D4DECE-E7D5-4CEB-95B3-FFA182FA43B1 | FD8DE6F4-7B8B-41FB-A963-634A7303A12E | PGA-04 | DD82E4B2-D561-41F2-94F1-D00B6A7A089F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-04 End of Well Report.pdf | PGA-04 End of Well Report.pdf | Yes |  | Uploads\dd82e4b2-d561-41f2-94f1-d00b6a7a089f.pdf | Exist
Mursyid | Yes | 65E11F31-CF97-4424-AE09-36982F85CB41 | FD8DE6F4-7B8B-41FB-A963-634A7303A12E | PGA-04 | 23955425-DE3E-47C1-9048-F0C08CCB5297 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-04_NOOP 20th Apr 2020.pdf | PGA-04_NOOP 20th Apr 2020.pdf | Yes |  | Uploads\23955425-de3e-47c1-9048-f0c08ccb5297.pdf | Exist
Mursyid | Yes | 5C8FF211-176B-4786-B7C5-AB7483F722AC | 7F3C8901-78F9-4D12-B43F-63613C3253C8 | TUKAU TIMUR-A4 | AFB3DFEA-9FBD-4D9F-B601-A4ABE51AA7B0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A4 NOOP.pdf |  | No |  | Uploads\afb3dfea-9fbd-4d9f-b601-a4abe51aa7b0.pdf | Exist
Mursyid | Yes | 7D0F6ED0-E470-4A98-8F8A-6AEA02A539A5 | 7F3C8901-78F9-4D12-B43F-63613C3253C8 | TUKAU TIMUR-A4 | 6D296727-A1B0-4D05-A268-A2C25FAE7FD7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT A4 Petronas Final Well Report_A4-signed.pdf |  | No |  | Uploads\6d296727-a1b0-4d05-a268-a2c25fae7fd7.pdf | Exist
Mursyid | Yes | BC5A9D8C-1FCF-40D4-A1E3-34C11E1CDC3A | 1CF0B821-8B13-49B8-8691-6375C4FA42EA | DULANG-D02ST1 | 6272536B-CCD2-43DA-A027-D874B18F25E7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PCSB FWR D02ST1 OP4 Complete Attachment (1).pdf |  | No |  | Uploads\6272536b-ccd2-43da-a027-d874b18f25e7.pdf | Exist
Mursyid | Yes | 3C7A34CD-EA8A-4A1E-B67D-E37D14C68A34 | 1CF0B821-8B13-49B8-8691-6375C4FA42EA | DULANG-D02ST1 | 75470F24-3C1E-47E9-817E-C3993731EA77 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang D2ST1 OP4 - FINAL INTERNAL MPM.pdf |  | No |  | Uploads\75470f24-3c1e-47e9-817e-c3993731ea77.pdf | Exist
Mursyid | Yes | 853E8FBB-9774-48E3-9454-377A9F351C6E | A87B18C9-231D-4574-9902-642B62F44969 | KULINTANG-1 | E328C562-69F5-47EE-ADC3-7C249FAAD7AE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kulintang-1_Notice_of_Operations_(NOOP).pdf | Kulintang-1_Notice_of_Operations_(NOOP).pdf | Yes |  | Uploads\e328c562-69f5-47ee-adc3-7c249faad7ae.pdf | Exist
Mursyid | Yes | F9BC1AA0-6884-40BA-A6F1-2CFE16FF2689 | A87B18C9-231D-4574-9902-642B62F44969 | KULINTANG-1 | 0E103F6C-B430-4226-A274-BED39E0F94A3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kulintang-1 ST1 Final Well Report_Official_Revision.docx.pdf | Kulintang-1 ST1 Final Well Report_Official_Revision.docx.pdf | Yes |  | Uploads\0e103f6c-b430-4226-a274-bed39e0f94a3.pdf | Exist
Mursyid | Yes | 2C7F9B08-03EF-4DC1-ABD8-5FCBF4C101C7 | 90059BB6-CEF0-44B8-8DE9-643026D3108D | SM-115 | 709E7F81-2F1A-4BB9-B672-37C981569067 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL47_SM_115.pdf | SBO3SMRGGL47_SM_115.pdf | Yes |  | Uploads\709e7f81-2f1a-4bb9-b672-37c981569067.pdf | Exist
Mursyid | Yes | 741218D7-B2BA-4ED3-9CB9-F69BC9F213FE | 90059BB6-CEF0-44B8-8DE9-643026D3108D | SM-115 | 0BDC5A90-F268-4D2C-B83E-09D7E5D7F51D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSEY_SM_115.pdf | SBO3SMRGWSEY_SM_115.pdf | Yes |  | Uploads\0bdc5a90-f268-4d2c-b83e-09d7e5d7f51d.pdf | Exist
Mursyid | Yes | 2C885B4B-DE70-4570-AAF5-ED54B103DF10 | 117FF868-FA15-4F39-AABB-64394930A29B | BOKOR-E502 | 83884BEB-03AF-4A34-9767-9DF14D6BC124 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-502 SIGNED NOOP.pdf |  | No |  | Uploads\83884beb-03af-4a34-9767-9df14d6bc124.pdf | Exist
Mursyid | Yes | FC0AC419-D4DA-4566-BB79-5F1B3C08667E | 117FF868-FA15-4F39-AABB-64394930A29B | BOKOR-E502 | 9D2C4F05-47D7-4CA1-AF38-2EBD8121A5E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR-E502.pdf | FWR BOKOR-E502.pdf | Yes |  | Uploads\9d2c4f05-47d7-4ca1-af38-2ebd8121a5e8.pdf | Exist
Mursyid | Yes | 3A10E0FE-C453-4603-B12C-0A35A7B0C6AC | 22CB559B-B0EB-40D7-B6F3-645A102314A7 | E06-109 | E1D78A8F-53AC-4476-93E7-11D2C23AD39A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-109 End of Well Report.pdf | E06-109 End of Well Report.pdf | Yes |  | Uploads\e1d78a8f-53ac-4476-93e7-11d2c23ad39a.pdf | Missing
Mursyid | Yes | AEF8192A-B930-44CF-BD42-34E562062F8B | 22CB559B-B0EB-40D7-B6F3-645A102314A7 | E06-109 | 8F4A8294-C589-4EE6-B7D1-7D0A74F42929 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-109 (N3) NOOP R2 Final - signed.pdf | E06-109 (N3) NOOP R2 Final - signed.pdf | Yes |  | Uploads\8f4a8294-c589-4ee6-b7d1-7d0a74f42929.pdf | Missing
Mursyid | Yes | 5EBF6ED1-E8D0-42CC-8E3B-5EBE7805E923 | 764529C0-DA76-44AE-BA77-64705109B605 | AMRA-1 | A528B406-FE69-4BE6-87A1-C1C80556C7A9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3AMRAWS01_AMRA_1.pdf | SKO3AMRAWS01_AMRA_1.pdf | Yes |  | Uploads\a528b406-fe69-4be6-87a1-c1c80556c7a9.pdf | Exist
Mursyid | Yes | 6365300D-7CD1-4196-A2AC-D348334FBF1F | 764529C0-DA76-44AE-BA77-64705109B605 | AMRA-1 | 1D9DB6E8-2CCD-45B3-9509-0A946EDADC05 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3AMRAWS07_AMRA_1.pdf | SKO3AMRAWS07_AMRA_1.pdf | Yes |  | Uploads\1d9db6e8-2ccd-45b3-9509-0a946edadc05.pdf | Exist
Mursyid | Yes | 6412A000-10FF-439A-B2D3-5944FFF5DB66 | 83B9CC23-3643-4BF7-959C-649F294BBBC2 | KNDW-D10 | 76B52613-5989-4AA5-9997-79E51CA7373C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D10 NOOP_Signed.pdf | KNDW-D10 NOOP_Signed.pdf | Yes |  | Uploads\76b52613-5989-4aa5-9997-79e51ca7373c.pdf | Exist
Mursyid | Yes | 63E99FC3-131A-478A-AE14-181659C540E1 | 83B9CC23-3643-4BF7-959C-649F294BBBC2 | KNDW-D10 | C5BD66FE-1554-4908-A533-E4D59C772401 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW-D10.pdf | EOWR KNDW-D10.pdf | Yes |  | Uploads\c5bd66fe-1554-4908-a533-e4d59c772401.pdf | Exist
Mursyid | Yes | 984C4EFB-8D39-4E95-BB32-07A428B3D530 | 1CBF238E-077D-4E55-BFED-663BAADABBEA | SAMARANG-C110 | 9A3B078D-377C-4E52-A381-CF35FB6B2BCB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-C110 FWR.pdf | SM-C110 FWR.pdf | Yes |  | Uploads\9a3b078d-377c-4e52-a381-cf35fb6b2bcb.pdf | Exist
Mursyid | Yes | EEF765D1-F946-412C-9D0E-B539D37363B2 | 1CBF238E-077D-4E55-BFED-663BAADABBEA | SAMARANG-C110 | 51DFC938-D568-4723-839B-0D1DEDE52F8D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-C110 NOOP_FINAL.pdf | SM-C110 NOOP_FINAL.pdf | Yes |  | Uploads\51dfc938-d568-4723-839b-0d1dede52f8d.pdf | Exist
Mursyid | Yes | 68DAE644-E89A-431B-939F-D5BEDBABDC93 | C5A933CB-0553-4057-8811-66D1FFCE62C2 | ANGSI-D17 | 8576E0F8-3BBF-44E3-B71C-1487B256E6BF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWS8X_ANGSI-D17_FWR.pdf | PMO3ANSIWS8X_ANGSI-D17_FWR.pdf | Yes |  | Uploads\8576e0f8-3bbf-44e3-b71c-1487b256e6bf.pdf | Exist
Mursyid | Yes | 1970CA03-A74E-429B-822B-6A56B4EA9719 | C5A933CB-0553-4057-8811-66D1FFCE62C2 | ANGSI-D17 | FCD09FD6-1B5D-492C-BF98-A1DFB685F892 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWS9P_ANGSI-D17_PCSB_NOOP.pdf | PMO3ANSIWS9P_ANGSI-D17_PCSB_NOOP.pdf | Yes |  | Uploads\fcd09fd6-1b5d-492c-bf98-a1dfb685f892.pdf | Exist
Mursyid | Yes | 57E7260F-C487-44DB-AA9F-8903A9B6D6F7 | 3653CDD3-6956-444B-B64F-670AA51C7C57 | SAPA-15 | 90306071-92AB-4997-9625-EAE355682F0E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS67_SAPA-05-06-13-15_PTTEP.pdf | SKO3ACISWS1N_SAPA-15_PTTEP_NOOP.pdf | No |  | Uploads\90306071-92ab-4997-9625-eae355682f0e.pdf | Exist
Mursyid | Yes | BBDE0148-9225-440B-A817-2695346DD838 | 3653CDD3-6956-444B-B64F-670AA51C7C57 | SAPA-15 | F5ED95C4-E233-4937-A2A9-8C2F28E170C0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS87_SAPA-15_PTTEP_FWR.pdf | SKO3ACISWS86_SAPA-5,SAPA-13,SAPA-15,PCSB__FWR.pdf | No |  | Uploads\f5ed95c4-e233-4937-a2a9-8c2f28e170c0.pdf | Exist
Mursyid | Yes | 9C51E119-63FD-4232-AF27-3C029A45AAEA | 058D5D90-642D-425C-8CED-670B3C1DD8B4 | BO-401ST1 | 1E69E4CB-0DF2-4045-816B-3B0141518EA5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report BO-401ST.pdf |  | No |  | Uploads\1e69e4cb-0df2-4045-816b-3b0141518ea5.pdf | Exist
Mursyid | Yes | 9178049B-AD71-40E2-B75D-63A171085F52 | 058D5D90-642D-425C-8CED-670B3C1DD8B4 | BO-401ST1 | 32715BF4-3EC3-45EF-AED1-893E05987DEA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-401 NOOP SIGNED.pdf |  | No |  | Uploads\32715bf4-3ec3-45ef-aed1-893e05987dea.pdf | Exist
Mursyid | Yes | 17F33251-3429-4897-A0BA-5D2BC45E2B06 | 8114ABD4-862D-44D0-A8D6-6761315E74C6 | MEPA-11 | C0B5B8ED-00E9-47D2-90AA-9BA55C22B383 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MEPA-11 EOWR.pdf | MEPA-11 EOWR.pdf | Yes |  | Uploads\c0b5b8ed-00e9-47d2-90aa-9ba55c22b383.pdf | Missing
Mursyid | Yes | 001AE46C-EAE8-41B0-83D2-24346C1DA756 | 8114ABD4-862D-44D0-A8D6-6761315E74C6 | MEPA-11 | CFCC7FA0-6B48-4166-92FC-37C48138E9F3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MEPA-09 ST1and MEPA11 NOOP.pdf | MEPA-09 ST1and MEPA11 NOOP.pdf | Yes |  | Uploads\cfcc7fa0-6b48-4166-92fc-37c48138e9f3.pdf | Missing
Mursyid | Yes | 8CB9E002-C5FC-4C6F-B5E4-66EC5F44222C | 38A1B8E1-E3A0-44E9-9E34-67E30CAD76A3 | BUNGA ANGGERIK A-3(E) | 84A802FE-FC77-4A9F-AD16-63B780B67BC2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NMB-DRI-RPT-01173 BAA-3(E).pdf |  | No |  | Uploads\84a802fe-fc77-4a9f-ad16-63b780b67bc2.pdf | Exist
Mursyid | Yes | BBF16F5D-FA17-4779-9A2D-F76877B2F2DA | 38A1B8E1-E3A0-44E9-9E34-67E30CAD76A3 | BUNGA ANGGERIK A-3(E) | 7F25A82D-78ED-464F-BE25-A46D206A9C3D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BAA_4C and 3E_Rev0_Final.pdf |  | No |  | Uploads\7f25a82d-78ed-464f-be25-a46d206a9c3d.pdf | Exist
Mursyid | Yes | 54AA22F2-3C43-453A-8C83-9B09BE6B03A3 | A64ACF0B-A062-46CC-B24A-685D177C5FEF | BOD-25 | E815C9F9-30AA-4535-B80D-EFB5C9DDE6E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BOKDWS1O_BOD-25.pdf | BOD-25 and ST1 (1)EOWR .pdf | No |  | Uploads\e815c9f9-30aa-4535-b80d-efb5c9dde6e8.pdf | Exist
Mursyid | Yes | 662216A4-EB05-40EB-8BB8-57FA8985F7C6 | A64ACF0B-A062-46CC-B24A-685D177C5FEF | BOD-25 | F515EFC9-B7DA-4750-A7C7-C0D3E6F99A03 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BOKDGL73_BOD-25.pdf |  | No |  | Uploads\f515efc9-b7da-4750-a7c7-c0d3e6f99a03.pdf | Exist
Mursyid | Yes | A4AC3009-61ED-43B0-831B-44204760E5F7 | D01D20A9-1949-4561-AB5D-688934EEA870 | RAJAH SHALLOW-1 | 105C9C3B-4EA2-441E-A1C3-CCEA3BAB7308 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RJSHGL01_RAJAH SHALLOW-1_noop.pdf | PMO3RJSHGL01_RAJAH SHALLOW-1_noop.pdf | Yes |  | Uploads\105c9c3b-4ea2-441e-a1c3-ccea3bab7308.pdf | Exist
Mursyid | Yes | 21476401-E2E6-4C07-872A-33BCD79D540A | D01D20A9-1949-4561-AB5D-688934EEA870 | RAJAH SHALLOW-1 | DD614408-7C48-47F2-9CDD-83A1AE860CB7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RJSHWS02_RAJAH_SHALLOW-1_fwr.pdf |  | No |  | Uploads\dd614408-7c48-47f2-9cdd-83a1ae860cb7.pdf | Exist
Mursyid | Yes | 31639A46-A09A-4461-B7ED-71AE6079B91A | 86AEC735-015E-4CBA-9C02-6A5A3931049D | BESAR-A6 | E8DB5FE5-2320-4A26-A8A0-A8D36FD72E04 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar-A6 FWR.pdf | Besar-A6 FWR.pdf | Yes |  | Uploads\e8db5fe5-2320-4a26-a8a0-a8d36fd72e04.pdf | Exist
Mursyid | Yes | B7AD2824-BA13-4CC6-9E86-70BC60E784A5 | 86AEC735-015E-4CBA-9C02-6A5A3931049D | BESAR-A6 | 3DBEB58D-8614-4C87-A1A7-50527154A4EF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Besar A6 (Internal Copy).pdf | NOOP Besar A6 (Internal Copy).pdf | Yes |  | Uploads\3dbeb58d-8614-4c87-a1a7-50527154a4ef.pdf | Exist
Mursyid | Yes | 4622BE08-F23D-423B-A5D9-E3DE546CB8E2 | 165C0FD6-F6A2-4552-AFD0-6A90AD490C3D | S-NE1-P8 | 890E70BC-7147-4E7F-A025-9588E20EA498 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SBO-DR22_S-NE1-P8.pdf | SBO3SBO-DR22_S-NE1-P8.pdf | Yes |  | Uploads\890e70bc-7147-4e7f-a025-9588e20ea498.pdf | Exist
Mursyid | Yes | 33D4E597-184F-4697-B767-F9C680264E46 | 165C0FD6-F6A2-4552-AFD0-6A90AD490C3D | S-NE1-P8 | B1F33BDF-2C8E-4390-952C-44BDC6B69A4D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR15_S-NE1-P8.pdf | SBO3SKNPDR15_S-NE1-P8.pdf | Yes |  | Uploads\b1f33bdf-2c8e-4390-952c-44bdc6b69a4d.pdf | Exist
Mursyid | Yes | 8BF0C664-02B4-4757-8CD0-C0C15D02AC4F | 7DDF0CFF-8BA3-4CD3-BAD0-6B242470AFE2 | TBK-A1ST1 | CF23A361-33EF-4E0A-8888-8718821ABC75 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TBK-A1.pdf |  | No |  | Uploads\cf23a361-33ef-4e0a-8888-8718821abc75.pdf | Exist
Mursyid | Yes | 811DB2AF-1C2B-4CFB-A7EE-8FA9BC0B1981 | 7DDF0CFF-8BA3-4CD3-BAD0-6B242470AFE2 | TBK-A1ST1 | 223B6E62-CF79-4870-82B7-9ECAFB45AA75 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A1ST1 Final Well Report final.pdf | TBK-A1ST1 Final Well Report final.pdf | Yes |  | Uploads\223b6e62-cf79-4870-82b7-9ecafb45aa75.pdf | Exist
Mursyid | Yes | 9517F554-B0CD-4001-995A-532AC7AAF645 | 6C6BBCC1-A419-4BFD-8CE9-6B3F468F0EED | SASA-14 | 260EDF01-0B99-42B8-A504-4BC3047980D3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS2M_SASA-14_PTTEP_FWR.pdf | SASA-14_14ST1 EOWR.pdf | No |  | Uploads\260edf01-0b99-42b8-a504-4bc3047980d3.pdf | Exist
Wadi | Yes | 2EDF1513-DE83-47DE-B858-E21D1EEAFF44 | 6C6BBCC1-A419-4BFD-8CE9-6B3F468F0EED | SASA-14 | 2B6F9BA2-5560-49F3-AFB3-1AECCA02EEEF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Ph1_BATCH 2 NOOP.pdf |  | No |  | Uploads\2b6f9ba2-5560-49f3-afb3-1aecca02eeef.pdf | Exist
Mursyid | Yes | A7A8C658-FFB3-4B2D-B1DD-2EA235BF6954 | E8A41F63-9ACC-4C6E-AFB2-6BC0370CDA90 | WEST LUTONG-A06ST1 | 48C2C8A3-070E-4AC1-AA44-935CD3FC098F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP WL6ST1 Final_signed.pdf |  | No |  | Uploads\48c2c8a3-070e-4ac1-aa44-935cd3fc098f.pdf | Exist
Mursyid | Yes | 20EE9D77-4C8F-4224-9FAB-7DB9668E618E | E8A41F63-9ACC-4C6E-AFB2-6BC0370CDA90 | WEST LUTONG-A06ST1 | EE16D181-7B1B-4A8B-A426-5E2D5EF25A68 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report WL6ST1 - FINAL.pdf |  | No |  | Uploads\ee16d181-7b1b-4a8b-a426-5e2d5ef25a68.pdf | Exist
Mursyid | Yes | D0E4B4C1-662E-4C3A-9C08-6F40759451ED | D5C9BCA1-80C4-4D41-A79E-6BE4355DB724 | EC-A05 | 5597F079-8F1E-4C15-B669-7C1B3406FAC5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0003_Rev.00 NOOP WELL EC-A05 (Slot 3B ECW-A Platform) Rev 00_DS.pdf | ECN-GEN-D-0003_Rev.00 NOOP WELL EC-A05 (Slot 3B ECW-A Platform) Rev 00_DS.pdf | Yes |  | Uploads\5597f079-8f1e-4c15-b669-7c1b3406fac5.pdf | Exist
Mursyid | Yes | 921D6DD0-187D-4D9E-83FD-F5E150BAF183 | D5C9BCA1-80C4-4D41-A79E-6BE4355DB724 | EC-A05 | EE24ED00-FD65-4A12-A29B-BA4FB4CE52D2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A05 Final Well Report (Final).pdf | EC-A05 Final Well Report (Final).pdf | Yes |  | Uploads\ee24ed00-fd65-4a12-a29b-ba4fb4ce52d2.pdf | Exist
Mursyid | Yes | EF1B13BD-8E79-4A95-80F6-6A04FA3774B0 | 579299B9-681A-4026-B2D7-6C8DB1E5AF6C | WEST LUTONG-A15ST1 | DBE1D91D-408B-44E2-AA41-C56967B1508A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP WL15ST1 Final-Signed.pdf |  | No |  | Uploads\dbe1d91d-408b-44e2-aa41-c56967b1508a.pdf | Exist
Mursyid | Yes | 6AF61E08-17D2-4E16-96C6-4EA336D248D3 | 579299B9-681A-4026-B2D7-6C8DB1E5AF6C | WEST LUTONG-A15ST1 | 63F2123B-C42E-4B85-B58F-9AC9E72FCAD5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WL15ST1 Final Well Report (FWR)_signed.pdf |  | No |  | Uploads\63f2123b-c42e-4b85-b58f-9ac9e72fcad5.pdf | Exist
Mursyid | Yes | 1EA857F7-633E-4BE4-B841-1A8827B63C62 | A37AA0B3-497A-4530-9E0F-6CF9FE2EEC32 | PIMENTO-1 | D935173B-74CB-4710-87CF-70B278E70244 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3PMNTWS01_PIMENTO-1_PCSB_NOOP.pdf | SKO3PMNTWS01_PIMENTO-1_PCSB_NOOP.pdf | Yes |  | Uploads\d935173b-74cb-4710-87cf-70b278e70244.pdf | Exist
Mursyid | Yes | 3F1DA686-3FD6-4A61-8BB4-9F7025EE423A | A37AA0B3-497A-4530-9E0F-6CF9FE2EEC32 | PIMENTO-1 | F46B8FE7-06D5-4839-BCB9-184CFDE646FE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pimento-1 2013 FWR.pdf | Pimento-1 2013 FWR.pdf | Yes |  | Uploads\f46b8fe7-06d5-4839-bcb9-184cfde646fe.pdf | Exist
Mursyid | Yes | 246A1164-EB70-483B-A4E9-A3F30E7755FA | 26CF4EE5-A532-4DC4-8876-6D879F36E121 | KNDW-D17 | 88D169A8-0AD2-4583-BB8F-D70EF15E55B8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D17 NOOP_signed.pdf | KNDW-D17 NOOP_signed.pdf | Yes |  | Uploads\88d169a8-0ad2-4583-bb8f-d70ef15e55b8.pdf | Exist
Mursyid | Yes | A3780816-67FD-4FB1-AC7F-55EFC3686B28 | 26CF4EE5-A532-4DC4-8876-6D879F36E121 | KNDW-D17 | CC81B2EB-73E3-4455-A71C-4EE76BD8924A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D17 ST1 EOWR 20 Feb 2020.pdf | KNDW-D17 ST1 EOWR 20 Feb 2020.pdf | Yes |  | Uploads\cc81b2eb-73e3-4455-a71c-4ee76bd8924a.pdf | Exist
Mursyid | Yes | F831BD82-C2A6-4D29-9852-3A09645114E2 | 03B0B5A8-3A65-414D-B76A-6F29671025A5 | ANGSI-E15 | 05996AC6-5E65-410B-BD5C-F8AF6826F5DB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ANGSI E-15 NOOP Final Signed.pdf | ANGSI E-15 NOOP Final Signed.pdf | Yes |  | Uploads\05996ac6-5e65-410b-bd5c-f8af6826f5db.pdf | Exist
Mursyid | Yes | E5FF58E2-6E32-4565-8DC3-1E79EF999EBA | 03B0B5A8-3A65-414D-B76A-6F29671025A5 | ANGSI-E15 | 05277C55-75A8-42FB-AA61-FFDD4CD4234A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report ANGSI E-15 Complete Signed.pdf | Final Well Report ANGSI E-15 Complete Signed.pdf | Yes |  | Uploads\05277c55-75a8-42fb-aa61-ffdd4cd4234a.pdf | Exist
Mursyid | Yes | 5F8C1EFF-F4BA-4532-934D-13D4E99172C3 | EE346195-3DA8-4516-82AA-6F8AA9F53A61 | SASA-03 | D43AB4E1-3236-402D-9F48-9CE21F25F79A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf |  | No |  | Uploads\d43ab4e1-3236-402d-9f48-9ce21f25f79a.pdf | Exist
Mursyid | Yes | 53F7AB57-53BF-441E-90DB-3E98744C3814 | EE346195-3DA8-4516-82AA-6F8AA9F53A61 | SASA-03 | 19034768-7FC9-4607-9709-A03854840973 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf |  | No |  | Uploads\19034768-7fc9-4607-9709-a03854840973.pdf | Exist
Mursyid | Yes | 2485CCAC-0CA3-477D-B1CF-43EBC27DA3C2 | E59D61D3-AC0A-426A-B3E0-7000752E0E0B | BARAM-H15 | DF35B3FB-40D9-4628-B01A-EE77D194A606 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram-H15 Final Well Report_Approved.pdf | Baram-H15 Final Well Report_Approved.pdf | Yes |  | Uploads\df35b3fb-40d9-4628-b01a-ee77d194a606.pdf | Exist
Mursyid | Yes | B3A157B6-4318-4FF7-A537-B48C88ACDE02 | E59D61D3-AC0A-426A-B3E0-7000752E0E0B | BARAM-H15 | 661D6528-C51A-4D1D-A5B0-16C67DC89D8D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram South BARAM-H15 NOOP (Approved).pdf | Baram South BARAM-H15 NOOP (Approved).pdf | Yes |  | Uploads\661d6528-c51a-4d1d-a5b0-16c67dc89d8d.pdf | Exist
Mursyid | Yes | 2D6ACC80-FEFF-45EE-94ED-B5D3D8E4E912 | 03C26C8F-78E2-452B-899D-70420248ECD5 | MLK-124 | 98261076-77BA-44BB-987D-FC1640F6C6F5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL28_MLK-124_NOOP_SHELL.pdf | Malikai MLK-124 W405 NOOP_Final.pdf | No |  | Uploads\98261076-77ba-44bb-987d-fc1640f6c6f5.pdf | Exist
Mursyid | Yes | 9C27263D-3961-4C18-9EB5-2F96A956B282 | 03C26C8F-78E2-452B-899D-70420248ECD5 | MLK-124 | 3E07A9D7-3392-48E5-8DB6-059AA67C60F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-124.pdf | MLK-124.pdf | Yes |  | Uploads\3e07a9d7-3392-48e5-8db6-059aa67c60f4.pdf | Exist
Mursyid | Yes | 55269237-C14C-4B3E-9662-B9EA4667100E | B2A8D8F1-5D8F-42B9-80D1-714B7ADEEBD3 | D18-402 | BAE7FAC4-ED41-453A-9D69-F79F97CB4FFC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-402 NOOP.pdf | D18-402 NOOP.pdf | Yes |  | Uploads\bae7fac4-ed41-453a-9d69-f79f97cb4ffc.pdf | Exist
Mursyid | Yes | 7F97D11F-665F-4866-A135-DC3478F588B6 | B2A8D8F1-5D8F-42B9-80D1-714B7ADEEBD3 | D18-402 | B6BE78CF-62DA-4BAC-A37E-9DA76A155A15 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 402 FWR-signed.pdf | D18 402 FWR-signed.pdf | Yes |  | Uploads\b6be78cf-62da-4bac-a37e-9da76a155a15.pdf | Exist
Mursyid | Yes | 1907178E-B28C-439D-ACB9-A26E151769E5 | 5FE9DBC0-55A3-41DD-9242-7236FD8CC3B5 | KNDW-D08 | BEA71BD7-3625-435F-BD7D-BCF75A490C8B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS4G_KNDW_D08.pdf | KNDW-D08 EOWR.pdf | No |  | Uploads\bea71bd7-3625-435f-bd7d-bcf75a490c8b.pdf | Exist
Mursyid | Yes | 792A70DC-5E9B-445B-9B16-8BCD41B6F2B3 | 5FE9DBC0-55A3-41DD-9242-7236FD8CC3B5 | KNDW-D08 | AACA42DE-1DA4-49B8-A724-308321F9CFEF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLGL61_KNDW_D08.pdf | SBO3KNBLGL61_KNDW_D08.pdf | Yes |  | Uploads\aaca42de-1da4-49b8-a724-308321f9cfef.pdf | Exist
Mursyid | Yes | 18205A12-BF89-4BAC-8D9D-81665C2F7B0E | C24271A7-5922-4F8E-BD07-725E9506D344 | TNGB-A12 | BD264A4D-0D49-4CDF-851D-5B7BC56856B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS1E_1_TNGB_A12.pdf | PMO3TNGBWS1E_1_TNGB_A12.pdf | Yes |  | Uploads\bd264a4d-0d49-4cdf-851d-5b7bc56856b7.pdf | Exist
Mursyid | Yes | 2A2DADC7-3B30-40B3-9D00-578AEE223227 | C24271A7-5922-4F8E-BD07-725E9506D344 | TNGB-A12 | CDD16A9F-78A7-4ADC-BD98-57B9050B4320 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS43_TNGB_A12.pdf | PMO3TNGBWS43_TNGB_A12.pdf | Yes |  | Uploads\cdd16a9f-78a7-4adc-bd98-57b9050b4320.pdf | Exist
Mursyid | Yes | F027709F-5259-4868-BDAF-60612E3E80CE | 4BCD97FC-D2FE-40BC-95B9-729D0DA80147 | TT-A2 | FB58EA2B-81F3-4083-82CC-7398D61F6324 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A2 FWR 2016 FINAL - for MPM.pdf | TT-A2 FWR 2016 FINAL - for MPM.pdf | Yes |  | Uploads\fb58ea2b-81f3-4083-82cc-7398d61f6324.pdf | Exist
Mursyid | Yes | 84E85242-26D5-4363-9E7C-F86FECC1E128 | 4BCD97FC-D2FE-40BC-95B9-729D0DA80147 | TT-A2 | FF50E208-5046-4061-888F-5557B1A03CFA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A2 Final_Internal Distribution.pdf | TT-A2 Final_Internal Distribution.pdf | Yes |  | Uploads\ff50e208-5046-4061-888f-5557b1a03cfa.pdf | Exist
Mursyid | Yes | 34146C1B-078B-48FA-A1E8-53C0356DE15B | AA621514-94DB-4374-AE08-72A626B9D361 | BARAM-B43 | 22FB13A9-38B3-4310-8234-9209D8006007 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARAM-B43 FWR (WITH ATTACHMENTS).pdf | BARAM-B43 FWR (WITH ATTACHMENTS).pdf | Yes |  | Uploads\22fb13a9-38b3-4310-8234-9209d8006007.pdf | Exist
Mursyid | Yes | B3C9E607-69FC-410C-888E-44ADA376F302 | AA621514-94DB-4374-AE08-72A626B9D361 | BARAM-B43 | DB23E3A1-AE19-49C4-A5DE-ED93FA369484 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARAM-B43 NOOP.pdf | BARAM-B43 NOOP.pdf | Yes |  | Uploads\db23e3a1-ae19-49c4-a5de-ed93fa369484.pdf | Exist
Mursyid | Yes | 3F33185D-7929-4AAC-9A54-3B0F0BC8C65D | 87B79576-3E97-4588-B06D-72A910140A4F | BUNGA KANGSAR A-2 | EBAC6822-74F1-4B10-A960-520FD7A18F8B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A2 EOWR.pdf |  | No |  | Uploads\ebac6822-74f1-4b10-a960-520fd7a18f8b.pdf | Exist
Mursyid | Yes | 9E9266C9-DD2C-4D82-958F-DA68A9CEE025 | 87B79576-3E97-4588-B06D-72A910140A4F | BUNGA KANGSAR A-2 | 4F56C859-132A-4E74-9199-1A2ECD6AB72E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A2 NOOP - signed-off_signed.pdf |  | No |  | Uploads\4f56c859-132a-4e74-9199-1a2ecd6ab72e.pdf | Exist
Mursyid | Yes | 8F826A0D-49F2-40AA-8DB6-BF9BEEA3E0AF | 8677A3F0-C2CA-45FF-92E4-7318C6D9B395 | SAPA-06 | 5BD45BCA-7736-4594-9F94-85CA08968060 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-06 EOWR.pdf | SAPA-06 EOWR.pdf | Yes |  | Uploads\5bd45bca-7736-4594-9f94-85ca08968060.pdf | Exist
Mursyid | Yes | F3F6C9DF-379C-427C-AF80-FB539CF22D72 | 8677A3F0-C2CA-45FF-92E4-7318C6D9B395 | SAPA-06 | 612921E9-3DAB-443A-A357-1CCC3FADD23D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SK311 South Acis Revisit I Phase III.pdf |  | No |  | Uploads\612921e9-3dab-443a-a357-1ccc3fadd23d.pdf | Exist
Mursyid | Yes | 4A70399F-0E74-4C1F-967F-DE3112E594BD | CA64B3AB-3E4A-4B38-A226-736359C7FA1A | BUNGA ASTER -1 | 8ED93829-FF09-48A5-AE33-77C500A66995 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Aster-1 NOOP_signed.pdf | Bunga Aster-1 NOOP_signed.pdf | Yes |  | Uploads\8ed93829-ff09-48a5-ae33-77c500a66995.pdf | Exist
Mursyid | Yes | E8509381-211B-4E64-A476-2F894AC866A6 | CA64B3AB-3E4A-4B38-A226-736359C7FA1A | BUNGA ASTER -1 | BD3D5F5D-6BD9-4D4B-AEC8-F48BAD71178A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Aster-1 EOWR_ June 2024.pdf | Bunga Aster-1 EOWR_ June 2024.pdf | Yes |  | Uploads\bd3d5f5d-6bd9-4d4b-aec8-f48bad71178a.pdf | Exist
Mursyid | Yes | DF1FCB93-D335-40FB-9DBC-15A28A3D45CD | 31639B19-17C3-4064-A09A-737101A2D231 | BAYAN-221ST2 | 45C71C2D-F5E9-4332-80E3-427DF618169C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-221-ST2 Final Well Report_Bayan Redevelopment Project.pdf |  | No |  | Uploads\45c71c2d-f5e9-4332-80e3-427df618169c.pdf | Exist
Mursyid | Yes | 8A5B4352-6E49-4CB1-A405-467897111AF7 | 31639B19-17C3-4064-A09A-737101A2D231 | BAYAN-221ST2 | BEAFF3CC-D4A1-48BC-B874-AF0D22C3AD00 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-221 ST2 NOOP_PCSB.pdf |  | No |  | Uploads\beaff3cc-d4a1-48bc-b874-af0d22c3ad00.pdf | Exist
Mursyid | Yes | 2C78F470-80E7-4829-951A-246DD8FB2A7E | EA553245-B66C-40F4-B39F-73719C6311B9 | K5-4 | AC0966E4-1F09-4A4D-80B6-C20EE28711F9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3K5--WS25_K5_4.pdf | SKO3K5--WS25_K5_4.pdf | Yes |  | Uploads\ac0966e4-1f09-4a4d-80b6-c20ee28711f9.pdf | Exist
Mursyid | Yes | BB52EC91-7D4D-4446-BFBA-EA523A356D86 | EA553245-B66C-40F4-B39F-73719C6311B9 | K5-4 | 1E1D21E1-0CAC-41FE-A9DB-C5F23D88D568 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3K5--WS29_K5_4.pdf | SKO3K5--WS29_K5_4.pdf | Yes |  | Uploads\1e1d21e1-0cac-41fe-a9db-c5f23d88d568.pdf | Exist
Mursyid | Yes | 72844A94-10CF-45FF-BCA3-8DAAD45DCB8D | 8F60923F-0F73-4A40-8886-73BE9EED23DD | BESA-01 | 070E97BF-B3C6-4924-9009-3ABB6C308E5E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | SKO3BLUMWS16_BESA-01_BESA-02_BESA-03_BESA-11_BESA-12.pdf | No |  | Uploads\070e97bf-b3c6-4924-9009-3abb6c308e5e.pdf | Exist
Mursyid | Yes | 3146FF56-2277-4139-8F4A-8DBEB56D90B1 | 8F60923F-0F73-4A40-8886-73BE9EED23DD | BESA-01 | 2124C412-5AFD-419D-A499-6ED6FC7E6C8F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-69-DNC-RP-0001-00_BESA-01 EOWR.pdf | MOM-SK309-69-DNC-RP-0001-00_BESA-01 EOWR.pdf | Yes |  | Uploads\2124c412-5afd-419d-a499-6ed6fc7e6c8f.pdf | Exist
Mursyid | Yes | 582E259C-35E2-4794-9ED2-7142BD2D9DE2 | C3B2B961-EEF8-4380-B993-7427CFBD5B46 | LARUT-A01ST1 | A6847095-65CE-467D-B7CF-4B102CCEB924 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-1ST1 (OP10_NOOP) rev.2.pdf |  | No |  | Uploads\a6847095-65ce-467d-b7cf-4b102cceb924.pdf | Exist
Mursyid | Yes | BCAA1B96-DA39-46AF-AE31-303C58A75E4B | C3B2B961-EEF8-4380-B993-7427CFBD5B46 | LARUT-A01ST1 | 7F6D1993-B541-4756-81D2-6246B5269EDB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-01ST1 (OP10) Final Well Report_Rev0.pdf | LARUT A-01ST1 (OP10) Final Well Report_Rev0.pdf | Yes |  | Uploads\7f6d1993-b541-4756-81d2-6246b5269edb.pdf | Exist
Mursyid | Yes | D5FF33AB-C2F2-4795-AC7B-6494BDA61070 | 5E822AB5-CA0D-4812-83D0-74D27F64C2FA | MLK-120 | CA641889-CB91-4D77-89E3-7F4B7A58F6F1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-120 EOWR_Final.pdf | MLK-120 EOWR_Final.pdf | Yes |  | Uploads\ca641889-cb91-4d77-89e3-7f4b7a58f6f1.pdf | Exist
Mursyid | Yes | 28C9934A-301B-4F60-B83B-C4364E7EBE14 | 5E822AB5-CA0D-4812-83D0-74D27F64C2FA | MLK-120 | 6FB0E80C-3C6A-42C8-9701-3090E5F2063C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL23_MLK-120_SHELL.pdf | SBO3MKAIGL23_MLK-120_SHELL.pdf | Yes |  | Uploads\6fb0e80c-3c6a-42c8-9701-3090e5f2063c.pdf | Exist
Mursyid | Yes | 2CB25D82-6EF6-4B5D-BCE5-879DB54DC61C | 5C8CA992-A773-429B-BC03-74DBF053758F | LARUT-A09ST1 | 22D1B04B-DBA2-4535-B2D7-AEBEFD1D6683 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-09ST1 (OP4_NOOP) rev.2.pdf | LARUT A-09ST1 (OP4_NOOP) rev.2.pdf | Yes |  | Uploads\22d1b04b-dba2-4535-b2d7-aebefd1d6683.pdf | Exist
Mursyid | Yes | 0394A946-0369-47C4-9D53-206EF81C61A9 | 5C8CA992-A773-429B-BC03-74DBF053758F | LARUT-A09ST1 | 96001163-DAA0-4565-932C-3D8801474C36 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-09ST1 (OP4) Final Well Report_Rev0.pdf | LARUT A-09ST1 (OP4) Final Well Report_Rev0.pdf | Yes |  | Uploads\96001163-daa0-4565-932c-3d8801474c36.pdf | Exist
Mursyid | Yes | 328EA574-EAD9-4329-942A-970B090C0170 | 66895556-9AF5-49F8-AC19-74E1A0CDA23D | BOC-27 (3C) | 7D868546-AE95-429C-8F8F-EB9963E9B4F5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR BOC-27 (3C) Final_240622_Signed.pdf | EOWR BOC-27 (3C) Final_240622_Signed.pdf | Yes |  | Uploads\7d868546-ae95-429c-8f8f-eb9963e9b4f5.pdf | Exist
Mursyid | Yes | 91C58681-9C3B-4653-B81C-BB5653A6BBA6 | 66895556-9AF5-49F8-AC19-74E1A0CDA23D | BOC-27 (3C) | 979A7E68-D82D-4F34-A97B-D0CEA0E88164 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-27 (3C) NOOP-signed.pdf | BOC-27 (3C) NOOP-signed.pdf | Yes |  | Uploads\979a7e68-d82d-4f34-a97b-d0cea0e88164.pdf | Exist
Mursyid | Yes | B70D2FDC-EB72-499B-9746-0BCE3C8DB46F | A937C8B3-65CA-4657-A4BD-75816A3903A3 | KIKEH_PX03(136) | E0661217-BB07-4204-9120-152C660596D9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KIKHWS1J_KIKEH_PX03.pdf |  | No |  | Uploads\e0661217-bb07-4204-9120-152c660596d9.pdf | Exist
Mursyid | Yes | C32DF420-72B0-4C9F-8C95-4023D337E3B6 | A937C8B3-65CA-4657-A4BD-75816A3903A3 | KIKEH_PX03(136) | A271919E-F110-4564-83D4-4FEB0D5042EF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KIKHDR1B_KIKEH_PX03.pdf |  | No |  | Uploads\a271919e-f110-4564-83d4-4feb0d5042ef.pdf | Exist
Mursyid | Yes | 1E90955D-578C-4675-ACCB-27A56FA7F40D | 2462E1B8-F1B6-4388-B02F-7585A44E66AA | LANG LEBAH-1RDL2 | 7710B559-19DF-43C8-9C3E-AEEBB95C3B7B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_LANG LEBAH-1RDL2 RDR2 ST1 Main Body.pdf | EOWR_LANG LEBAH-1RDL2 RDR2 ST1 Main Body.pdf | Yes |  | Uploads\7710b559-19df-43c8-9c3e-aeebb95c3b7b.pdf | Exist
Mursyid | Yes | 0D5BDBE1-9F8A-4725-9CE1-FE49A6D5836A | 2462E1B8-F1B6-4388-B02F-7585A44E66AA | LANG LEBAH-1RDL2 | 90F6A4C9-9241-4E11-8A5A-237C456C0DE6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LLB1 RDL2 NOOP Final.pdf |  | No |  | Uploads\90f6a4c9-9241-4e11-8a5a-237c456c0de6.pdf | Exist
Mursyid | Yes | 2E1E2434-25A8-4B72-A544-C38AD44DCF92 | BB62C63D-A164-431A-8658-758D45E35E4B | BESAR-A2 | 171AA64D-F2E3-4C05-83B7-64D832841DA6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar-A2_Final.pdf | Besar-A2_Final.pdf | Yes |  | Uploads\171aa64d-f2e3-4c05-83b7-64d832841da6.pdf | Exist
Mursyid | Yes | 282E23A8-575D-4EEE-B963-1229F0EE42C3 | BB62C63D-A164-431A-8658-758D45E35E4B | BESAR-A2 | B68A4B62-1B4A-43B3-B830-6DFB7293284D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Besar-A2.pdf | FWR Besar-A2.pdf | Yes |  | Uploads\b68a4b62-1b4a-43b3-b830-6dfb7293284d.pdf | Exist
Mursyid | Yes | 4AE52EEE-94EE-4DF0-AD12-86CA4C8884C2 | 02064B50-5AEE-48AD-AA04-75ACC8D9BB9E | TIMI-103 | 17190C98-DE1C-4882-9292-CF5F10DCB740 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR TIMI103.pdf | EOWR TIMI103.pdf | Yes |  | Uploads\17190c98-de1c-4882-9292-cf5f10dcb740.pdf | Exist
Mursyid | Yes | F1B89ABB-CCB0-433F-8DA2-C5B2A20024D5 | 02064B50-5AEE-48AD-AA04-75ACC8D9BB9E | TIMI-103 | 064E480F-37E3-4DCB-915C-BDF62A76B748 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Timi-103 NOOP_Rev1_Signed.pdf | Timi-103 NOOP_Rev1_Signed.pdf | Yes |  | Uploads\064e480f-37e3-4dcb-915c-bdf62a76b748.pdf | Exist
Mursyid | Yes | 2A98FB02-599F-498B-B945-E2C508A16BF8 | 8857EB5C-5F68-44CA-8BBE-75C1FD63238B | BN-80 | C700C4D2-1938-4BF2-B4C6-37AE990661B6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-80 FWR Final.pdf | BN-80 FWR Final.pdf | Yes |  | Uploads\c700c4d2-1938-4bf2-b4c6-37ae990661b6.pdf | Exist
Mursyid | Yes | 150BB11F-10B7-4828-8582-04BA6025AA6F | 8857EB5C-5F68-44CA-8BBE-75C1FD63238B | BN-80 | A26F4270-CCD4-43B5-820B-CA4AEBD76C87 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-80 Final (Internal) (1).pdf | NOOP BN-80 Final (Internal) (1).pdf | Yes |  | Uploads\a26f4270-ccd4-43b5-820b-ca4aebd76c87.pdf | Exist
Mursyid | Yes | 77FEF01D-2CDD-45B9-86C5-46CF75909833 | 056DF1F9-F6F0-4669-BAA2-75D179FEC940 | JTG-A2 | BA66952F-597D-4FB8-A622-35EC44558D67 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP JTG-A2.pdf | NOOP JTG-A2.pdf | Yes |  | Uploads\ba66952f-597d-4fb8-a622-35ec44558d67.pdf | Exist
Mursyid | Yes | D9216577-3651-41B1-ABC4-FD0BE96CEBED | 056DF1F9-F6F0-4669-BAA2-75D179FEC940 | JTG-A2 | 4A455B3C-972D-4AB3-86B9-7809179B2851 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JTG-A2 Final Well Report_2020_01_23.pdf | JTG-A2 Final Well Report_2020_01_23.pdf | Yes |  | Uploads\4a455b3c-972d-4ab3-86b9-7809179b2851.pdf | Exist
Mursyid | Yes | 78E2C4D9-1C09-44C1-8259-FC6A326E3E44 | 005F0B50-E0AC-493A-8DDF-760DEEDE3E1D | SALAM-2 | 8FF15FC1-E308-4D69-AF64-7DEBAD8BFE43 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Salam-2_NOOP.pdf |  | No |  | Uploads\8ff15fc1-e308-4d69-af64-7debad8bfe43.pdf | Exist
Mursyid | Yes | D1A5EBAB-D765-4041-8C86-A000A39D95D6 | 005F0B50-E0AC-493A-8DDF-760DEEDE3E1D | SALAM-2 | 8D639F64-71A8-4814-819E-7AF2842139E3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Salam-2 End of Well Report Drilling.pdf | Salam-2 End of Well Report Drilling.pdf | Yes |  | Uploads\8d639f64-71a8-4814-819e-7af2842139e3.pdf | Exist
Mursyid | Yes | 99589CE7-9818-4B6B-A3F4-30330440980B | 20EE3377-77E4-40CA-B3F5-76368AD18E85 | BN-75 | 8A8B3CCD-35DC-4FA6-9589-79B5050C276D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BRNAWS5B_BARONIA-75.pdf |  | No |  | Uploads\8a8b3ccd-35dc-4fa6-9589-79b5050c276d.pdf | Exist
Mursyid | Yes | B3CEB553-23B1-45EA-BB26-13BD2A03865A | 20EE3377-77E4-40CA-B3F5-76368AD18E85 | BN-75 | 161350E3-90EC-484B-8D5F-B6E1B350B3F6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-75_signed.pdf | BN-75_signed.pdf | Yes |  | Uploads\161350e3-90ec-484b-8d5f-b6e1b350b3f6.pdf | Exist
Mursyid | Yes | C47112D7-CB40-464F-A560-7376224D3C11 | 90163AE5-AF2F-4CB4-ABA6-76B32B922CD4 | LARUT-A29ST2 | D380C728-EF92-4F90-ACE3-048DA3E580AC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-23ST1 (OP5) Final Well Report_Rev0.pdf | LARUT A-29ST2 (OP9) Final Well Report_Rev0.pdf | No |  | Uploads\d380c728-ef92-4f90-ace3-048da3e580ac.pdf | Exist
Mursyid | Yes | 79D7E4BF-3A03-45CB-A840-C7FBBDF12042 | 90163AE5-AF2F-4CB4-ABA6-76B32B922CD4 | LARUT-A29ST2 | B527C4CA-893A-4BAB-BFBD-11F654154808 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-23ST1 (OP5_NOOP) rev.3.pdf | LARUT A-29ST2 (OP9_NOOP) rev.2.pdf | No |  | Uploads\b527c4ca-893a-4bab-bfbd-11f654154808.pdf | Exist
Mursyid | Yes | F1C81771-95E4-4256-8ABF-2ED7797A4324 | 5FE67FA2-BB2A-4CE7-B2A2-76E536FAEFB2 | KNDW-D16 | 1C4AF6E8-46DD-44AD-8166-4B29F47425DC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D16 EOWR.pdf | KNDW-D16 EOWR.pdf | Yes |  | Uploads\1c4af6e8-46dd-44ad-8166-4b29f47425dc.pdf | Exist
Mursyid | Yes | 2C0F7C19-720E-4770-B7A4-3D86CB03BD92 | 5FE67FA2-BB2A-4CE7-B2A2-76E536FAEFB2 | KNDW-D16 | E128974F-64F9-4C0B-B7E9-B179BE23AC09 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-16 NOOP.pdf | KNDW D-16 NOOP.pdf | Yes |  | Uploads\e128974f-64f9-4c0b-b7e9-b179be23ac09.pdf | Exist
Mursyid | Yes | 1DF62BA4-7849-4AC6-B8C3-0CBFF69F274B | D221210E-24AB-4D66-B16A-77C728CECAD3 | F9-A7 | 3478767A-B01D-48A4-92FC-378B678BBFE6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F9 Redev 2.0 A7 NOOP Final Addendum signed.pdf |  | No |  | Uploads\3478767a-b01d-48a4-92fc-378b678bbfe6.pdf | Exist
Mursyid | Yes | E79B160D-F7C1-441F-924F-F88BAF8DC0C1 | D221210E-24AB-4D66-B16A-77C728CECAD3 | F9-A7 | A6D7058F-DC84-4E06-86A1-16A9B16A78D1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F9-A7 Final Well Report signed.pdf | F9-A7 Final Well Report signed.pdf | Yes |  | Uploads\a6d7058f-dc84-4e06-86a1-16a9b16a78d1.pdf | Exist
Mursyid | Yes | 62FCD80B-B259-4FBF-8916-4333BABDC8A8 | CAA357F6-B747-4E5A-B4F3-7807BD6C3956 | TIMI-101 | 3133AF7E-1BF3-46B4-8137-399573A6659A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR TIMI101.pdf | EOWR TIMI101.pdf | Yes |  | Uploads\3133af7e-1bf3-46b4-8137-399573a6659a.pdf | Exist
Mursyid | Yes | 8A8A840C-6C6F-4A15-BDA3-A423EBE630DC | CAA357F6-B747-4E5A-B4F3-7807BD6C3956 | TIMI-101 | 5BFF0227-4001-472A-8D4C-1D9B1D49B66E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Timi-101 NOOP_Rev1_Signed.pdf | Timi-101 NOOP_Rev1_Signed.pdf | Yes |  | Uploads\5bff0227-4001-472a-8d4c-1d9b1d49b66e.pdf | Exist
Mursyid | Yes | 8D6F2446-DDF5-4AEE-BDAA-70EF668F0476 | C201BAAF-596E-4EA7-8635-784103C728A3 | KNDW-D07 | 46506ECF-B9D6-4378-AFF9-2B62AC4D3A6C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-07 NOOP.pdf | KNDW D-07 NOOP.pdf | Yes |  | Uploads\46506ecf-b9d6-4378-aff9-2b62ac4d3a6c.pdf | Exist
Mursyid | Yes | 52E7606A-151E-43F0-9B9D-C9171DDFD96A | C201BAAF-596E-4EA7-8635-784103C728A3 | KNDW-D07 | 0853FDDD-1315-4714-9CE3-A98F815D0F78 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D07 EOWR.pdf | KNDW-D07 EOWR.pdf | Yes |  | Uploads\0853fddd-1315-4714-9ce3-a98f815d0f78.pdf | Exist
Mursyid | Yes | AAF22F98-4BED-40AF-BE81-AACCE17CF420 | 0EBFB842-FBE9-49A3-81AB-78561F33577E | PE-1 | 1FE1C66A-A41F-460D-8E32-CB412E0D762F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Puding Emas-1 FWR.pdf |  | No |  | Uploads\1fe1c66a-a41f-460d-8e32-cb412e0d762f.pdf | Exist
Mursyid | Yes | 3294B2FF-8F98-4853-9441-32C8D0B801CA | 0EBFB842-FBE9-49A3-81AB-78561F33577E | PE-1 | 4BB18D88-2046-41F1-AD15-4405BF02C01A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Puding Emas rev.01.pdf |  | No |  | Uploads\4bb18d88-2046-41f1-ad15-4405bf02c01a.pdf | Exist
Mursyid | Yes | EE6F81D2-F0AF-4042-AA7A-3C8E0BE3281B | 9241B7C7-155B-4B5D-BC3F-7860C2570E4B | BO-404 | 6F1284B2-C6F0-460F-B010-CCE66A15F476 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report BO-404.pdf | Final Well Report BO-404.pdf | Yes |  | Uploads\6f1284b2-c6f0-460f-b010-cce66a15f476.pdf | Exist
Mursyid | Yes | 522946A4-70A6-4AF7-B889-278BBA4B1C0F | 9241B7C7-155B-4B5D-BC3F-7860C2570E4B | BO-404 | F24A920B-7E13-4F34-A75F-7E4BD094C064 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-404 NOOP SIGNED.pdf | BO-404 NOOP SIGNED.pdf | Yes |  | Uploads\f24a920b-7e13-4f34-a75f-7e4bd094c064.pdf | Exist
Mursyid | Yes | EF26121B-8018-4535-A360-8CCAF9F21605 | 70B46DF2-B86A-467C-A045-78648177133E | DULANG-C29 | B1BAE3BC-128C-4109-A0BA-0EAC6CEC2D6D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXK_DULANG-C29.pdf | PMO3DULGWSXK_DULANG-C29.pdf | Yes |  | Uploads\b1bae3bc-128c-4109-a0ba-0eac6cec2d6d.pdf | Exist
Mursyid | Yes | 8119E9D8-FE20-447C-B0C6-EEFF053C258C | 70B46DF2-B86A-467C-A045-78648177133E | DULANG-C29 | B43E5270-01A8-45E4-872C-40781E1DFBA6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYC_DULANG-C29.pdf | PMO3DULGWSYC_DULANG-C29.pdf | Yes |  | Uploads\b43e5270-01a8-45e4-872c-40781e1dfba6.pdf | Exist
Mursyid | Yes | D4CA4B78-70CA-48C7-9FD6-FB52CC4A5D8F | A4CB7D52-71FD-4B7D-9FF1-78889655B16A | ENAU-1 | DB3707D5-7B85-4DE3-B0B1-D8D8F7511056 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ENAUWS07_ENAU_1.pdf | PMO3ENAUWS07_ENAU_1.pdf | Yes |  | Uploads\db3707d5-7b85-4de3-b0b1-d8d8f7511056.pdf | Exist
Mursyid | Yes | C4B5A999-4390-42B9-BF0D-4ABEBAAD0DF4 | A4CB7D52-71FD-4B7D-9FF1-78889655B16A | ENAU-1 | DC5D63A4-EA43-4268-A0F2-75EC9B31DA67 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ENAUGL01_ENAU_1.pdf | PMO3ENAUGL01_ENAU_1.pdf | Yes |  | Uploads\dc5d63a4-ea43-4268-a0f2-75ec9b31da67.pdf | Exist
Mursyid | Yes | 1D507AEB-320A-4198-BC09-F5AEBA1DE737 | CE4249C5-F049-4375-ACF8-790478E7C6CB | CHENDA-1 | 0FC583F6-5DAF-4C78-9EED-CAD92C1CD93F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Chenda-1_SK405B_NOOP (2023).pdf | Chenda-1_SK405B_NOOP (2023).pdf | Yes |  | Uploads\0fc583f6-5daf-4c78-9eed-cad92c1cd93f.pdf | Exist
Mursyid | Yes | 7D91D814-2DE3-4E17-9465-CA7A3BAF884C | CE4249C5-F049-4375-ACF8-790478E7C6CB | CHENDA-1 | 08A8AA24-6553-49CA-971F-BDEE03770B10 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3CNDAGL6526_CHENDA-1_PTTEP_FWR.pdf | SKO3CNDAGL6526_CHENDA-1_PTTEP_FWR.pdf | Yes |  | Uploads\08a8aa24-6553-49ca-971f-bdee03770b10.pdf | Exist
Mursyid | Yes | E797F6F8-5A29-4E97-AC89-2AD870735067 | 017548A9-4B36-44FD-B21E-79084A5CB1E0 | DANUM-2 | 7F064B6C-7626-497D-B337-0CD0C7C3D61A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3DNUMWS11_DANUM-2.pdf | SBO3DNUMWS11_DANUM-2.pdf | Yes |  | Uploads\7f064b6c-7626-497d-b337-0cd0c7c3d61a.pdf | Exist
Mursyid | Yes | 6D5AA6EC-46A6-432C-95F7-AC704DF7CA76 | 017548A9-4B36-44FD-B21E-79084A5CB1E0 | DANUM-2 | D40C7C24-1B88-4059-8394-DD6A309AFFF3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3DNUMWS05_DANUM-2.pdf | SBO3DNUMWS05_DANUM-2.pdf | Yes |  | Uploads\d40c7c24-1b88-4059-8394-dd6a309afff3.pdf | Exist
Mursyid | Yes | 9E39E54B-EE8F-48DA-9E6E-04F4F7525B09 | A2EF61B9-5D70-4E3B-A327-7911C325FE84 | BOKOR-E501 | BA42D68E-1B63-450B-80D1-0BD597711455 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR-E501.pdf | FWR BOKOR-E501.pdf | Yes |  | Uploads\ba42d68e-1b63-450b-80d1-0bd597711455.pdf | Exist
Mursyid | Yes | 4CE5EFDB-4BA2-476E-9ACB-FFA0DE0C7742 | A2EF61B9-5D70-4E3B-A327-7911C325FE84 | BOKOR-E501 | 8FC3076F-8810-4EA9-8173-3D38C69CB165 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BO-501 FINAL.pdf |  | No |  | Uploads\8fc3076f-8810-4ea9-8173-3d38c69cb165.pdf | Exist
Mursyid | Yes | 57501A83-982A-4C08-B90C-F2FF0AFD625E | 0EBD6665-F428-422D-A37C-7A5B8DCC6005 | D18-404 | 179F9DDD-1DD7-4FF4-AD81-FDABB02A8229 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 404 FWR-signed.pdf | D18 404 FWR-signed.pdf | Yes |  | Uploads\179f9ddd-1dd7-4ff4-ad81-fdabb02a8229.pdf | Exist
Mursyid | Yes | 4EA77F4C-D53F-4161-AE36-8F0138C6368B | 0EBD6665-F428-422D-A37C-7A5B8DCC6005 | D18-404 | A909BD73-E79E-478E-8F86-7CC4F64A0D47 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-404 NOOP.pdf | D18-404 NOOP.pdf | Yes |  | Uploads\a909bd73-e79e-478e-8f86-7cc4f64a0d47.pdf | Exist
Mursyid | Yes | 047F09E1-38CC-4776-B2F3-0B1E65B2C892 | 6BF4D919-A247-48BF-8734-7A83535DC7C1 | LAKUM-1 | C94794A1-0FBB-42AF-BD3F-376F95C04FD8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lakum-1 NOOP Final 14.06.2016.pdf | Lakum-1 NOOP Final 14.06.2016.pdf | Yes |  | Uploads\c94794a1-0fbb-42af-bd3f-376f95c04fd8.pdf | Exist
Mursyid | Yes | 1C995820-24DF-452D-B3A7-2DD950A7C662 | 6BF4D919-A247-48BF-8734-7A83535DC7C1 | LAKUM-1 | 9E9EB890-150A-46E2-A91D-620B1A6326BC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAKUM-1 FWR.pdf | LAKUM-1 FWR.pdf | Yes |  | Uploads\9e9eb890-150a-46e2-a91d-620b1a6326bc.pdf | Exist
Mursyid | Yes | E53CB5CC-CBDA-4E1A-B1D1-5B4CE90E83AA | 357D87E8-0EAB-4EC1-97AA-7B6550791328 | D21-A11 | CF969A6A-4709-4970-9226-9C94755970CA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A11 End of Well Report Final.pdf | D21-A11 End of Well Report Final.pdf | Yes |  | Uploads\cf969a6a-4709-4970-9226-9c94755970ca.pdf | Exist
Mursyid | Yes | DA816EB0-CEB7-4740-9007-31383948B9B1 | 357D87E8-0EAB-4EC1-97AA-7B6550791328 | D21-A11 | 8A6589BA-5897-4F31-BC8C-09D2C8B81FB0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A11 NOOP_FINAL.pdf | D21-A11 NOOP_FINAL.pdf | Yes |  | Uploads\8a6589ba-5897-4f31-bc8c-09d2c8b81fb0.pdf | Exist
Mursyid | Yes | 65D43374-8A2A-4B71-B006-235EC2467C52 | E3693002-1483-4062-9B8F-7B7BF2C6627E | DAMAR-A05 | 8CD341A3-8850-483C-8559-4EAF04912512 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DAMAR-A5 EOWR.pdf |  | No |  | Uploads\8cd341a3-8850-483c-8559-4eaf04912512.pdf | Exist
Mursyid | Yes | 53D3E196-4095-48F9-BD25-7E4E7C4CFE44 | E3693002-1483-4062-9B8F-7B7BF2C6627E | DAMAR-A05 | 312155AC-D05D-4B8D-A54E-081C41CB3409 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARWS30_DAMAR-A05_JULY_2014.pdf |  | No |  | Uploads\312155ac-d05d-4b8d-a54e-081c41cb3409.pdf | Exist
Mursyid | Yes | F4930544-16A4-4E95-B3DC-5D22EB7F46C9 | F6EB7456-A450-4115-AE43-7BA785FA71B4 | WAKID-3 | 9E015E74-677A-424F-A7AA-A0844F88F7B2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 8 WAKID-3_FWR.pdf |  | No |  | Uploads\9e015e74-677a-424f-a7aa-a0844f88f7b2.pdf | Exist
Mursyid | Yes | D293C1E7-62EE-4B5C-9F2F-B45C4D47E3ED | F6EB7456-A450-4115-AE43-7BA785FA71B4 | WAKID-3 | D4761FC0-EF2C-4A81-B5B9-260CD65CE17C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 3 WAKID-3 NOOP.pdf |  | No |  | Uploads\d4761fc0-ef2c-4a81-b5b9-260cd65ce17c.pdf | Exist
Mursyid | Yes | 3F77D7EC-FB49-4D40-9406-A628B084CD9C | CE64DF8F-C4B8-492D-AE9F-7BD2867272E4 | DULANG A-26 ST1 | C1B5B6C7-CE32-474A-A223-AFBED7767D15 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG A-26 ST1 EOWR.pdf | DULANG A-26 ST1 EOWR.pdf | Yes |  | Uploads\c1b5b6c7-ce32-474a-a223-afbed7767d15.pdf | Exist
Mursyid | Yes | 603C2142-E6FB-4171-BB8C-27463304A75F | CE64DF8F-C4B8-492D-AE9F-7BD2867272E4 | DULANG A-26 ST1 | 0952CB6A-7067-4D0B-BB61-4B584C61AA6C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG-A26ST1 NOOP.pdf | DULANG-A26ST1 NOOP.pdf | Yes |  | Uploads\0952cb6a-7067-4d0b-bb61-4b584c61aa6c.pdf | Exist
Mursyid | Yes | 9ED4BCBE-9B63-4038-896D-47CA486EC6FA | 4147A7ED-4187-442C-B79E-7BEDAA6CB77F | EC-A03 | AF227D11-B943-4EAF-91BC-F7B7A8756C1A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A03 Final Well Report (Final).pdf | EC-A03 Final Well Report (Final).pdf | Yes |  | Uploads\af227d11-b943-4eaf-91bc-f7b7a8756c1a.pdf | Exist
Mursyid | Yes | 2DBB12E2-FB0E-4A09-81E8-6BFF30FDBBE7 | 4147A7ED-4187-442C-B79E-7BEDAA6CB77F | EC-A03 | 9028D4F6-92D3-4540-855D-54CA41C0D362 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0001_Rev.00 NOOP WELL EC-A03 (Slot 2A ECW-A Platform)_DS.pdf | ECN-GEN-D-0001_Rev.00 NOOP WELL EC-A03 (Slot 2A ECW-A Platform)_DS.pdf | Yes |  | Uploads\9028d4f6-92d3-4540-855d-54ca41c0d362.pdf | Exist
Mursyid | Yes | 13E7C182-B5EB-4524-A561-6CF790591D47 | 289A6112-0B98-4190-876B-7C8718B7B785 | BESAR-A9 | 8ADEC0D6-E5A3-4B75-B275-AE7681E3720F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar A9 FWR.pdf | Besar A9 FWR.pdf | Yes |  | Uploads\8adec0d6-e5a3-4b75-b275-ae7681e3720f.pdf | Exist
Mursyid | Yes | 9A2F24BD-8FD3-41E1-92F6-2183F22E1EB6 | 289A6112-0B98-4190-876B-7C8718B7B785 | BESAR-A9 | 853C2D7D-9D01-4AD3-AE06-41BE6E682A3A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar A9 NOOP Internal.pdf | Besar A9 NOOP Internal.pdf | Yes |  | Uploads\853c2d7d-9d01-4ad3-ae06-41be6e682a3a.pdf | Exist
Mursyid | Yes | E8C2DDC2-CC5B-4630-BF1A-879A754B56CE | 1328370F-8982-48F9-97BA-7D40891EA536 | BERTAM A-18 | 03052592-7648-4673-A6A1-3CECB0F1B6C1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-18 NOOP.pdf | Bertam A-18 NOOP.pdf | Yes |  | Uploads\03052592-7648-4673-a6a1-3cecb0f1b6c1.pdf | Exist
Mursyid | Yes | 9BB77A98-73D6-44DD-B6D8-E78E4BDC325B | 1328370F-8982-48F9-97BA-7D40891EA536 | BERTAM A-18 | 157174B2-7DE0-4958-B863-B6AF5C839D71 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-18 EOWR.pdf | Bertam A-18 EOWR.pdf | Yes |  | Uploads\157174b2-7de0-4958-b863-b6af5c839d71.pdf | Exist
Mursyid | Yes | 81915025-095E-4FE1-9163-CE781BEEAC55 | B1F5BCE7-F56F-4848-93D6-7E2ADFC27E84 | F14-108 | 23CA1A3E-64E0-4376-8D2D-5583DA16EBAA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-108 End of Well Report - Final.pdf | F14-108 End of Well Report - Final.pdf | Yes |  | Uploads\23ca1a3e-64e0-4376-8d2d-5583da16ebaa.pdf | Exist
Mursyid | Yes | 1B0F450F-AAB3-47CC-B9FE-3FC942774401 | B1F5BCE7-F56F-4848-93D6-7E2ADFC27E84 | F14-108 | 186A85E6-B0DB-41E2-AF0A-282AD01C9B82 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-108 NOOP - Final - Signed.pdf | F14-108 NOOP - Final - Signed.pdf | Yes |  | Uploads\186a85e6-b0db-41e2-af0a-282ad01c9b82.pdf | Exist
Mursyid | Yes | 3C6A4EC4-DB16-4929-9279-28CE2C83D64B | 7B2437EE-EF3F-4053-A0AC-7E4A9F25562D | LA-103 | 2970E66E-A9A3-49A4-9C1E-5756D9BF8482 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LAILWS18_LA-103_SHELL FWR.pdf | SKO3LAILWS18_LA-103_SHELL FWR.pdf | Yes |  | Uploads\2970e66e-a9a3-49a4-9c1e-5756d9bf8482.pdf | Exist
Mursyid | Yes | 97718631-B3A4-4042-88F1-BE1CDAA99256 | 7B2437EE-EF3F-4053-A0AC-7E4A9F25562D | LA-103 | 62C524D2-D7C4-4B54-B28A-6A220396F09D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LAILWS11_LA-103_SHELL_NOOP.pdf | SKO3LAILWS11_LA-103_SHELL_NOOP.pdf | Yes |  | Uploads\62c524d2-d7c4-4b54-b28a-6a220396f09d.pdf | Exist
Mursyid | Yes | DE77BDA0-F68A-4DA0-8FCF-492DA542A44D | 8C726572-51ED-41FB-A468-7ED1069CA69F | TABU-A05 ST1 | 835B3CEA-9487-4CA2-A94D-3E61C3639DF4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A5ST1 Slot 3 NOOP.pdf | Tabu A5ST1 Slot 3 NOOP.pdf | Yes |  | Uploads\835b3cea-9487-4ca2-a94d-3e61c3639df4.pdf | Exist
Mursyid | Yes | 4C5E1A5A-52ED-45CD-B623-73AAFFD7277F | 8C726572-51ED-41FB-A468-7ED1069CA69F | TABU-A05 ST1 | 65EA4261-793D-47DA-940F-80C32D0320D1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A5ST1 Final Well Report.pdf | Tabu A5ST1 Final Well Report.pdf | Yes |  | Uploads\65ea4261-793d-47da-940f-80c32d0320d1.pdf | Exist
Mursyid | Yes | B9669448-D659-4064-91FB-9C1DF8932DD6 | E9800FB4-6A47-4D28-8BA1-7F1724256B77 | SAMARANG-C23S2 | 7D7F5FF0-19E4-440A-8189-67AD0594C8E9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-C23S2 NOOP.pdf | SM-C23S2 NOOP.pdf | Yes |  | Uploads\7d7f5ff0-19e4-440a-8189-67ad0594c8e9.pdf | Exist
Mursyid | Yes | CB2EEB4D-A400-4597-A59B-0E95F53AE936 | E9800FB4-6A47-4D28-8BA1-7F1724256B77 | SAMARANG-C23S2 | E8A3C40E-DA44-433A-B233-D45E06148921 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-C23S2 FWR.pdf | SM-C23S2 FWR.pdf | Yes |  | Uploads\e8a3c40e-da44-433a-b233-d45e06148921.pdf | Exist
Mursyid | Yes | 7B3565CC-9DEF-422E-AD50-4DD3DD42B894 | 2F9C7963-F704-4372-BCD2-7F1B2C10F774 | TELOK-B3 | 6D406448-1FA8-4B6A-ADF3-5940B95CA0D5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Telok B3 - FWR.pdf | Telok B3 - FWR.pdf | Yes |  | Uploads\6d406448-1fa8-4b6a-adf3-5940b95ca0d5.pdf | Exist
Mursyid | Yes | B16CF0EA-CB67-44D4-8760-AB1E057C27D3 | 2F9C7963-F704-4372-BCD2-7F1B2C10F774 | TELOK-B3 | C7812049-988F-4E7D-B7B2-4FD9E535A0A4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TELOWS41_TELOK-B3_EMEPMI_NOOP.pdf | PMO3TELOWS41_TELOK-B3_EMEPMI_NOOP.pdf | Yes |  | Uploads\c7812049-988f-4e7d-b7b2-4fd9e535a0a4.pdf | Exist
Mursyid | Yes | 93398F16-9314-41E0-A1C1-7CA886972A02 | 81CA614D-51B0-40AD-9086-7F1DB98FBB86 | NC3-A4 | 57EE7E0A-7A08-41D2-AC08-DDB9646214C6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NC3-A4 NOOP for PMU.pdf | NC3-A4 NOOP for PMU.pdf | Yes |  | Uploads\57ee7e0a-7a08-41d2-ac08-ddb9646214c6.pdf | Exist
Mursyid | Yes | 27D4E60F-B644-403D-8036-149650B9484C | 81CA614D-51B0-40AD-9086-7F1DB98FBB86 | NC3-A4 | 63ADD7CB-96F5-4E7E-BA0E-7268CFBC54C9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NC3-A4 FWR.pdf | NC3-A4 FWR.pdf | Yes |  | Uploads\63add7cb-96f5-4e7e-ba0e-7268cfbc54c9.pdf | Exist
Mursyid | Yes | 83B9D976-5180-4C20-9881-4AEBBED10FB5 | 3B977326-B096-4A3E-A6F8-7F2E083E9F70 | NAIM-1 | 7974C7CE-513A-4D53-BA58-52496177DA4C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3NAIMGL02_NAIM-1.pdf | SKO3NAIMGL02_NAIM-1.pdf | Yes |  | Uploads\7974c7ce-513a-4d53-ba58-52496177da4c.pdf | Exist
Mursyid | Yes | 5712412F-C88B-4C27-BD0F-A9C4D3DE95D5 | 3B977326-B096-4A3E-A6F8-7F2E083E9F70 | NAIM-1 | 3879CE67-71B9-465A-9EB9-8F4F3D75F81B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3NAIMWS03_NAIM-1_FWR.pdf | SKO3NAIMWS03_NAIM-1_FWR.pdf | Yes |  | Uploads\3879ce67-71b9-465a-9eb9-8f4f3d75f81b.pdf | Exist
Mursyid | Yes | 80271092-C85F-45C8-AD94-4EA32BAB6839 | BBF8F1F7-9A0D-4E3C-AAAC-7F82BB45AF89 | CENGKIH-1 | EADB8D68-8150-4D41-99AC-8510A87B3840 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Cengkih-1 MP_EOWR_FINAL_Rev5_30 September 2022.pdf | Cengkih-1 MP_EOWR_FINAL_Rev5_30 September 2022.pdf | Yes |  | Uploads\eadb8d68-8150-4d41-99ac-8510a87b3840.pdf | Exist
Mursyid | Yes | 0E621B33-0CF0-49DA-9FFE-EC0B951FEF2A | BBF8F1F7-9A0D-4E3C-AAAC-7F82BB45AF89 | CENGKIH-1 | 58082420-FCC5-43F0-8B18-4725F15BA866 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CENGKIH-1 NOOP Final Version 1.pdf | CENGKIH-1 NOOP Final Version 1.pdf | Yes |  | Uploads\58082420-fcc5-43f0-8b18-4725f15ba866.pdf | Exist
Mursyid | Yes | 9A5A7765-E8E7-41C6-87F9-FF97B226ABEE | B434A350-AB25-4832-A216-802D0533E483 | BESTARI-2 | EFF3F225-6F88-44C5-8E4B-0DDC514C780A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bestari-2_FWR.pdf | Bestari-2_FWR.pdf | Yes |  | Uploads\eff3f225-6f88-44c5-8e4b-0ddc514c780a.pdf | Exist
Mursyid | Yes | 0EE8DAF5-42C1-4F1E-8583-DB2011CFAF93 | B434A350-AB25-4832-A216-802D0533E483 | BESTARI-2 | AAC4DEB9-DBBF-45D1-9CFE-A7C76CA02A38 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bestari-2 NOOP_Signed.pdf | Bestari-2 NOOP_Signed | No |  | Uploads\aac4deb9-dbbf-45d1-9cfe-a7c76ca02a38.pdf | Exist
Mursyid | Yes | 9C9ED6D3-76EB-4C54-861A-DD096C13FEB6 | 925FE9B5-7FEC-4E16-B9D7-8048CAC5BB1C | BUJANG-6 | 15249486-00F5-4B5B-8393-079A0B48CD51 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BUJGWS53_BUJANG_6.pdf | PMO3BUJGWS53_BUJANG_6.pdf | Yes |  | Uploads\15249486-00f5-4b5b-8393-079a0b48cd51.pdf | Exist
Mursyid | Yes | FA2FB30C-4560-4C05-B8FD-CCE1D4552C1C | 925FE9B5-7FEC-4E16-B9D7-8048CAC5BB1C | BUJANG-6 | C084BC36-F0A8-4D20-A47F-1A6F1F9FE592 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BUJGGL06_BUJANG_6.pdf | PMO3BUJGGL06_BUJANG_6.pdf | Yes |  | Uploads\c084bc36-f0a8-4d20-a47f-1a6f1f9fe592.pdf | Exist
Mursyid | Yes | DBB4737C-3ACE-474C-AD3E-365826BEE346 | FAD7B2D4-98FE-48C9-9D93-807485EA20F9 | BOB-9(J) | B56B66C2-2E7B-4320-867B-F160D29F27B2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOB-9J NOOP.pdf | BOB-9J NOOP.pdf | Yes |  | Uploads\b56b66c2-2e7b-4320-867b-f160d29f27b2.pdf | Exist
Mursyid | Yes | B73793D6-0022-4CE2-A51B-02FCB1BC66A7 | FAD7B2D4-98FE-48C9-9D93-807485EA20F9 | BOB-9(J) | E75F6685-0A1A-4EDB-A7DB-0478969B1BD1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOB-9J EOWR.pdf | BOB-9J EOWR.pdf | Yes |  | Uploads\e75f6685-0a1a-4edb-a7db-0478969b1bd1.pdf | Exist
Mursyid | Yes | 6CDFED80-E53C-43A0-8490-1F597C3C827F | 230F1AB1-1E91-4A23-B6C1-811ADA0290A3 | BEKOK-AA13 | 064B6238-D904-4543-B7E5-FF2FB6AF8505 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA13 Approved.pdf | NOOP Bekok AA13 Approved.pdf | Yes |  | Uploads\064b6238-d904-4543-b7e5-ff2fb6af8505.pdf | Exist
Mursyid | Yes | C585147E-4845-4179-8319-D845A4F29DCF | 230F1AB1-1E91-4A23-B6C1-811ADA0290A3 | BEKOK-AA13 | E7541021-D7E2-4D58-BC38-C61219E1F918 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report_Bekok-AA13ST1_FINAL.pdf | Final Well Report_Bekok-AA13ST1_FINAL.pdf | Yes |  | Uploads\e7541021-d7e2-4d58-bc38-c61219e1f918.pdf | Exist
Mursyid | Yes | 7CEAB5DE-CFF6-4216-966C-88E9E62CC630 | B3D29AAB-67BD-4923-9BB7-813315648317 | TAWAKAL-1 | 988A7262-3F39-45F1-99C7-02EDCB976A1E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tawakal-1 MPM.pdf | Tawakal-1 MPM.pdf | Yes |  | Uploads\988a7262-3f39-45f1-99c7-02edcb976a1e.pdf | Exist
Mursyid | Yes | C5BE15BA-D515-4976-953F-642C15FDB25F | B3D29AAB-67BD-4923-9BB7-813315648317 | TAWAKAL-1 | 7E90EE28-1CDF-488E-9CE0-1D65D68DFB59 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tawakal-1 Final Well Report with Attachment.pdf | Tawakal-1 Final Well Report with Attachment.pdf | Yes |  | Uploads\7e90ee28-1cdf-488e-9ce0-1d65d68dfb59.pdf | Exist
Mursyid | Yes | 491431F5-23F0-4A70-A99C-17956BF4B441 | E926986E-9E22-4137-BA8F-81726890F4CB | S-SW1-P2 | 528CC9B0-5739-4A3B-A58C-808A2E6046CF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPWS20_S-SW1-P2_PTTEP_NOOP.pdf | SBO3SKNPWS20_S-SW1-P2_PTTEP_NOOP.pdf | Yes |  | Uploads\528cc9b0-5739-4a3b-a58c-808a2e6046cf.pdf | Exist
Mursyid | Yes | 100A702E-9A0F-49BE-8B56-CC8FDCF93D28 | E926986E-9E22-4137-BA8F-81726890F4CB | S-SW1-P2 | C41BE8F2-C8B3-4187-99DB-549A8505D9A7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR11_S-SW1-P2_PTTEP_FWR.pdf | SBO3SKNPDR11_S-SW1-P2_PTTEP_FWR.pdf | Yes |  | Uploads\c41be8f2-c8b3-4187-99db-549a8505d9a7.pdf | Exist
Mursyid | Yes | 045B39CA-E6DB-42C0-92E0-DC04829A2138 | F223D67A-87AC-49AA-9465-8190A85785AD | TABU-B23 ST1 | 72464EF7-AC37-40B6-9808-373E606987EC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B23ST1 Final Well Report.pdf | Tabu B23ST1 Final Well Report.pdf | Yes |  | Uploads\72464ef7-ac37-40b6-9808-373e606987ec.pdf | Exist
Mursyid | Yes | D0DACBCB-94C5-4D6A-A904-EBF1DE13B370 | F223D67A-87AC-49AA-9465-8190A85785AD | TABU-B23 ST1 | C87521C7-629F-4D86-A569-CDD489B51467 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B23ST1 Slot 5 NOOP v0.pdf | Tabu B23ST1 Slot 5 NOOP v0.pdf | Yes |  | Uploads\c87521c7-629f-4d86-a569-cdd489b51467.pdf | Exist
Mursyid | Yes | E0EFA394-9E57-4219-B283-DA10D0DE4FE5 | 2AD68670-B408-4DEE-B140-81ABA06F2A4E | KMSE-A03 | B2D9F0B7-BE42-4357-A220-90FEB01A4A2B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE-A03 Final Well Report.pdf | KMSE-A03 Final Well Report.pdf | Yes |  | Uploads\b2d9f0b7-be42-4357-a220-90feb01a4a2b.pdf | Exist
Mursyid | Yes | D3FEBFD2-0A46-4D9B-9349-71200B0E1918 | 2AD68670-B408-4DEE-B140-81ABA06F2A4E | KMSE-A03 | BB6C8194-AA2A-4622-B3EF-66A1E6B7E9F7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE-A03 (NOOP) Rev.0.pdf | KMSE-A03 (NOOP) Rev.0.pdf | Yes |  | Uploads\bb6c8194-aa2a-4622-b3ef-66a1e6b7e9f7.pdf | Exist
Mursyid | Yes | D2966566-4EA7-4472-B9B2-9A1B27F323AA | FBAB7659-907F-4E45-87A2-81C085726D40 | BY-415 | 216B1D51-B823-4112-96F2-625734AA56F9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-415 Notice of Operations APPROVED_INTERNAL CIRCULATION.pdf | BY-415 Notice of Operations APPROVED_INTERNAL CIRCULATION.pdf | Yes |  | Uploads\216b1d51-b823-4112-96f2-625734aa56f9.pdf | Exist
Mursyid | Yes | 1A63C583-5DC8-4D12-B02A-456CABC35D67 | FBAB7659-907F-4E45-87A2-81C085726D40 | BY-415 | 4C9476C0-5CCC-49B5-A4F4-ACBE836C2EDB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-415 Final Well Report_Bayan Redevelopment Project.pdf | BY-415 Final Well Report_Bayan Redevelopment Project.pdf | Yes |  | Uploads\4c9476c0-5ccc-49b5-a4f4-acbe836c2edb.pdf | Exist
Mursyid | Yes | E4A287B7-4383-4086-946F-9F0B2F976D66 | 7DB9804A-559C-4B93-BA2B-820252A41818 | J4-A02ST1 | 9FC4A617-FE38-430B-A8CE-8D783A96FD0F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4 A02ST2 (WI-1) EOWR_Rev6.pdf | J4 A02ST2 (WI-1) EOWR_Rev6.pdf | Yes |  | Uploads\9fc4a617-fe38-430b-a8ce-8d783a96fd0f.pdf | Exist
Mursyid | Yes | E0DB9E99-7B4B-4AB5-B4F6-666A484C9814 | 7DB9804A-559C-4B93-BA2B-820252A41818 | J4-A02ST1 | 129C7125-5AC3-434C-865B-CA06528A1E77 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4-A02ST1 (WI-1) Well.pdf | J4-A02ST1 (WI-1) Well.pdf | Yes |  | Uploads\129c7125-5ac3-434c-865b-ca06528a1e77.pdf | Exist
Mursyid | Yes | 2A7D7986-F55A-4481-A3A0-6FF3F78FED3C | 92681605-BBC7-4B7E-8521-8233625DA013 | UMBAI-1 | 48972337-23BD-4F73-9B6F-F62289492555 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Umbai-1 NOOP Final Signed.pdf | Umbai-1 NOOP Final Signed.pdf | Yes |  | Uploads\48972337-23bd-4f73-9b6f-f62289492555.pdf | Exist
Mursyid | Yes | 70B42FBE-987E-40FE-924A-0B188DA34002 | 92681605-BBC7-4B7E-8521-8233625DA013 | UMBAI-1 | 7B412BE9-F623-4DBD-BFA3-1350CA055866 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Umbai-1 Final Well Report Rev.1.pdf | Umbai-1 Final Well Report Rev.1.pdf | Yes |  | Uploads\7b412be9-f623-4dbd-bfa3-1350ca055866.pdf | Exist
Mursyid | Yes | 8A550E34-9487-4B81-9918-613C3D3D7D31 | 2841AA89-F59C-4F3F-B727-82993513C8FB | D21-A12 | 5338EBD5-B050-4043-8001-1CDDB6D79973 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A12 NOOP_signed.pdf | D21-A12 NOOP_signed.pdf | Yes |  | Uploads\5338ebd5-b050-4043-8001-1cddb6d79973.pdf | Exist
Mursyid | Yes | 6FE0232A-43D5-4F12-A99E-DDBB59F4467F | 2841AA89-F59C-4F3F-B727-82993513C8FB | D21-A12 | 43157C69-D26D-4506-9796-DD105272A7D1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A12 and A12ST1 End of Well Report.pdf | D21-A12 and A12ST1 End of Well Report.pdf | Yes |  | Uploads\43157c69-d26d-4506-9796-dd105272a7d1.pdf | Exist
Mursyid | Yes | DD36518B-3E94-41D1-9D49-A2E229C8D6B6 | 54F0EA5E-2EE5-4656-AC18-82DA178CDB17 | SRI AMAN-1 RDR-1 | 8A74F908-7782-4ED2-83EC-398309F93CE4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRMNWS04_SRI AMAN-1 RDR-1.pdf | SKO3SRMNWS04_SRI AMAN-1 RDR-1.pdf | Yes |  | Uploads\8a74f908-7782-4ed2-83ec-398309f93ce4.pdf | Exist
Mursyid | Yes | 0490ADFB-4D08-448B-8227-3C22ED560756 | 54F0EA5E-2EE5-4656-AC18-82DA178CDB17 | SRI AMAN-1 RDR-1 | 95DAA37E-2906-40BA-A791-EC07DE56B379 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRMNWS09_SRI AMAN-1 RDR-1.pdf | SKO3SRMNWS09_SRI AMAN-1 RDR-1.pdf | Yes |  | Uploads\95daa37e-2906-40ba-a791-ec07de56b379.pdf | Exist
Mursyid | Yes | 5E645CEC-2FCC-483D-A0DE-1A34168A7B2E | 8BA9223F-986D-4D1A-A0C0-82E8E6D88AA9 | D35C-301ST1 | 6142C9BB-CD61-4A81-80DF-E149329E58BA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-301ST1 Well NOOP_Final.pdf | D35C-301ST1 Well NOOP_Final.pdf | Yes |  | Uploads\6142c9bb-cd61-4a81-80df-e149329e58ba.pdf | Exist
Mursyid | Yes | 70FD3C22-D27F-4BB6-8C5D-A68E9F88637C | 8BA9223F-986D-4D1A-A0C0-82E8E6D88AA9 | D35C-301ST1 | A22E64C4-AC68-4548-A814-0D2BAE271A1E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-301ST1 End Of Well Report.pdf | D35C-301ST1 End Of Well Report.pdf | Yes |  | Uploads\a22e64c4-ac68-4548-a814-0d2bae271a1e.pdf | Exist
Mursyid | Yes | E18294FF-B9AD-443B-ABDA-8A052F59A4A9 | 791C9D9F-CC29-4BF3-A214-832545F0FE36 | TABU-A17ST1 | 7EE9EE57-06F3-4FB5-A655-C5C56529A462 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A17ST1 Final Well Report.pdf | Tabu A17ST1 Final Well Report.pdf | Yes |  | Uploads\7ee9ee57-06f3-4fb5-a655-c5c56529a462.pdf | Exist
Mursyid | Yes | 3E20079D-548A-4C0E-B1FB-7EF4385FB7EC | 791C9D9F-CC29-4BF3-A214-832545F0FE36 | TABU-A17ST1 | FD59788A-9BB2-4060-B847-2D30C2573277 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A17ST1 Slot 4 NOOP.pdf | Tabu A17ST1 Slot 4 NOOP.pdf | Yes |  | Uploads\fd59788a-9bb2-4060-b847-2d30c2573277.pdf | Exist
Mursyid | Yes | D03D9FEE-845F-4F09-A676-7FE6BB5F8FA6 | E614CF30-94FD-4EA3-ADF8-8355B9CC2118 | SUMANDAK SELATAN B04 ST1 | 71B102D5-F364-46A4-A8E4-9956DC2FE01D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B04 ST2 FWR 7 Nov 2018.pdf | Sumandak Selatan B04 ST2 FWR 7 Nov 2018.pdf | Yes |  | Uploads\71b102d5-f364-46a4-a8e4-9956dc2fe01d.pdf | Exist
Mursyid | Yes | 621C9A12-4E72-49E0-9F27-4EDFD596F885 | E614CF30-94FD-4EA3-ADF8-8355B9CC2118 | SUMANDAK SELATAN B04 ST1 | 4594D944-1C19-4C5C-8102-7A9E1B11ED90 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B04ST1 NOOP (Final).pdf | Sumandak Selatan B04ST1 NOOP (Final).pdf | Yes |  | Uploads\4594d944-1c19-4c5c-8102-7a9e1b11ed90.pdf | Exist
Mursyid | Yes | 8D74098B-9E0C-4ED4-A8C9-7E9123C0656C | ABE2D23E-64E1-4EC4-B301-8355EE1DEB14 | BKC-03 | 2CF75481-271B-4C56-B24F-7DAB5F19D07E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKWAGL72_REPSOL_BKC-03ST2_NOOP.pdf | PMO3BKWAGL72_REPSOL_BKC-03ST2_NOOP.pdf | Yes |  | Uploads\2cf75481-271b-4c56-b24f-7dab5f19d07e.pdf | Exist
Mursyid | Yes | 1A2C0242-6DCF-41A4-8E40-BB2CD889958C | ABE2D23E-64E1-4EC4-B301-8355EE1DEB14 | BKC-03 | 6237CA1B-3819-4418-8496-E770758B3626 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKC-3ST2 (D) EOWR.pdf | BKC-3ST2 (D) EOWR.pdf | Yes |  | Uploads\6237ca1b-3819-4418-8496-e770758b3626.pdf | Exist
Mursyid | Yes | D97A88FE-686C-4C05-9447-E5B852DBD81C | CD3A5F6E-E8EB-47DB-92AB-8365CE81B175 | BANANG-B1 | F2F90E2A-C611-4AFC-B438-4F208CA668C5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS05_BANANG-B1.pdf | PMO3BANGWS05_BANANG-B1.pdf | Yes |  | Uploads\f2f90e2a-c611-4afc-b438-4f208ca668c5.pdf | Exist
Mursyid | Yes | E6C2C002-207E-4AC2-B7F8-471DBC4528F9 | CD3A5F6E-E8EB-47DB-92AB-8365CE81B175 | BANANG-B1 | 428C8961-12E1-47A0-B419-BBC375E9AA47 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS07_BANANG_B1.pdf | PMO3BANGWS07_BANANG_B1.pdf | Yes |  | Uploads\428c8961-12e1-47a0-b419-bbc375e9aa47.pdf | Exist
Mursyid | Yes | 13B6819F-F409-4674-B21B-09A31B2A62D2 | D2F3DE86-AE2E-421F-94A5-83CA69C03D90 | JERUN-A5 | E39AA16A-EB31-4096-8E5A-8787C5B5F346 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\e39aa16a-eb31-4096-8e5a-8787c5b5f346.pdf | Exist
Mursyid | Yes | C0CC67B9-4E30-4CD5-B643-0F23481BE2AB | D2F3DE86-AE2E-421F-94A5-83CA69C03D90 | JERUN-A5 | BA790C0E-6F70-4CED-A887-CC342CC02704 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun-A5 Final Well Report.pdf | SapuraOMV SK408 Jerun-A5 Final Well Report.pdf | Yes |  | Uploads\ba790c0e-6f70-4ced-a887-cc342cc02704.pdf | Exist
Mursyid | Yes | 7FCBDA93-4C8D-4687-B242-3A71DF377636 | 30929C62-26F4-46B1-9CD4-83E0828CDE13 | BUNGA TERATAI C-3 | D040D16A-9EF1-4521-AA54-EF1EB1BA1073 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BTR-C3 NOOP (DWP).pdf | BTR-C3 NOOP (DWP).pdf | Yes |  | Uploads\d040d16a-9ef1-4521-aa54-ef1eb1ba1073.pdf | Exist
Mursyid | Yes | D4642E6D-6730-4EAE-8C85-FDB668B2D775 | 30929C62-26F4-46B1-9CD4-83E0828CDE13 | BUNGA TERATAI C-3 | AEA278FD-E306-47F9-BA5D-7182249FAEB6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BTR-C3_29_July_2024.pdf | EOWR_BTR-C3_29_July_2024.pdf | Yes |  | Uploads\aea278fd-e306-47f9-ba5d-7182249faeb6.pdf | Exist
Mursyid | Yes | 4D291124-4DF0-40A6-8F98-F7BD05683D2A | D00567E0-F467-4915-AAC4-83EF045A986B | SAMARANG-B122 | E32ABEA0-5402-439A-87DF-8C95E6BC54E6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B122 NOOP.pdf | SAMARANG-B122 NOOP.pdf | Yes |  | Uploads\e32abea0-5402-439a-87df-8c95e6bc54e6.pdf | Exist
Mursyid | Yes | 3BD13518-09A2-4DC5-914E-0BF5638F93BF | D00567E0-F467-4915-AAC4-83EF045A986B | SAMARANG-B122 | 9C249552-9E3B-4089-BEBC-AB2B5D127CAF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B122 FWR.pdf | SAMARANG-B122 FWR.pdf | Yes |  | Uploads\9c249552-9e3b-4089-bebc-ab2b5d127caf.pdf | Exist
Mursyid | Yes | 9F6ECAD5-69D7-4D29-8071-F0D0B76F3A29 | 141B73DF-EC78-40D5-B0DF-842862D6594E | BAKAU-A08 | 3626B618-E48D-4D6D-8975-F18052CC7E91 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAKAU-A08 NOOP.pdf | BAKAU-A08 NOOP.pdf | Yes |  | Uploads\3626b618-e48d-4d6d-8975-f18052cc7e91.pdf | Exist
Mursyid | Yes | 1B6BE4F3-E100-40E4-B215-C37FF570C89D | 141B73DF-EC78-40D5-B0DF-842862D6594E | BAKAU-A08 | 5224FF07-8224-4E74-ABB5-AB3A708CCB92 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BK-A08 FWR Final V1.pdf | BK-A08 FWR Final V1.pdf | Yes |  | Uploads\5224ff07-8224-4e74-abb5-ab3a708ccb92.pdf | Exist
Mursyid | Yes | 99B45B56-DC32-451E-A18E-B9F686A64E66 | 0D0D3337-D543-4333-A338-8474D276B4D2 | J4-A06ST1 | 49D1B87A-ADD2-4848-9A3C-BC0081358753 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4 A06ST1 (U) EOWR_Rev6.pdf | J4 A06ST1 (U) EOWR_Rev6.pdf | Yes |  | Uploads\49d1b87a-add2-4848-9a3c-bc0081358753.pdf | Exist
Mursyid | Yes | BC21FF75-91B4-44DC-8258-2B0B712BAD83 | 0D0D3337-D543-4333-A338-8474D276B4D2 | J4-A06ST1 | 9D91B514-9EB5-49F9-87BB-DEB4503967D2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4-A06ST1 (U) Well.pdf | J4-A06ST1 (U) Well.pdf | Yes |  | Uploads\9d91b514-9eb5-49f9-87bb-deb4503967d2.pdf | Exist
Atikah | Yes | 0DEA1C76-6564-49EE-B428-30178729959F | B0F8F05E-2CAF-4E66-8CF0-847C8833512E | SED-03 | 9619F9FE-676E-4E7D-8030-2D01744A07C2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SeD-03ST1 Notice of Operation (NOOP) C1 Signed.pdf | SeD-03ST1 Notice of Operation (NOOP) C1 Signed.pdf | Yes |  | Uploads\9619f9fe-676e-4e7d-8030-2d01744a07c2.pdf | Exist
Atikah | Yes | 5C77A251-1F30-4222-AA06-C814C5F7F759 | B0F8F05E-2CAF-4E66-8CF0-847C8833512E | SED-03 | 7B8D49B1-E8FA-4299-9B21-F25F0E886948 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeD-03ST_1_2_3 Development Well Final (1).pdf | Final Well Report SeD-03ST_1_2_3 Development Well Final (1).pdf | Yes |  | Uploads\7b8d49b1-e8fa-4299-9b21-f25f0e886948.pdf | Exist
Atikah | Yes | 02566EA0-EF8F-4860-B5AE-3CDA17A3AD95 | 2DEA387B-F291-44FA-BBCC-850BFEE48CC8 | GK-P516A | E0E93FA6-26CC-4E6C-8E27-74955D450C3B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK P516A EOWR rev1.pdf | GK P516A EOWR rev1.pdf | Yes |  | Uploads\e0e93fa6-26cc-4e6c-8e27-74955d450c3b.pdf | Missing
Atikah | Yes | 10AD0A37-DAD4-4A5E-895E-8F81CDDC5565 | 2DEA387B-F291-44FA-BBCC-850BFEE48CC8 | GK-P516A | 4571B383-0F8A-4A7E-9BEF-AC329B3548AA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-P516A NOOP.pdf | GK-P516A NOOP.pdf | Yes |  | Uploads\4571b383-0f8a-4a7e-9bef-ac329b3548aa.pdf | Missing
Atikah | Yes | 2C5112DA-61CC-4368-89A1-9AA2E3BCB6C4 | 2399ACD5-908C-40A6-BC43-852E8445E651 | DULANG-C03 | EBC5C3F3-12EE-4BB2-B594-F512CF39FC58 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang C03 ST1 FWR.pdf | Dulang C03 ST1 FWR.pdf | Yes |  | Uploads\ebc5c3f3-12ee-4bb2-b594-f512cf39fc58.pdf | Exist
Atikah | Yes | B1FF9FA5-F902-4BA3-B7C8-2F01F4ED62AD | 2399ACD5-908C-40A6-BC43-852E8445E651 | DULANG-C03 | B6C876AD-4385-446D-AC0E-BEF10828306F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGGL81_DULANG_C03.pdf | PMO3DULGGL81_DULANG_C03.pdf | Yes |  | Uploads\b6c876ad-4385-446d-ac0e-bef10828306f.pdf | Exist
Atikah | Yes | 502D60C4-166D-4E0A-9A7B-1E32287C0890 | A1B852F1-E069-411A-A488-8618A31BC6AB | BUNGA KANGSAR A-1 | 185920F9-5E99-4EA5-9D3A-1B4CDEDD65EF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A1 EOWR.pdf | BKG-A1 EOWR.pdf | Yes |  | Uploads\185920f9-5e99-4ea5-9d3a-1b4cdedd65ef.pdf | Exist
Atikah | Yes | 5DF9F214-0A1C-4F64-8B72-0E9D2621C77D | A1B852F1-E069-411A-A488-8618A31BC6AB | BUNGA KANGSAR A-1 | 476E4A0C-F36A-496A-9543-CB925DDB603F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A1 NOOP.pdf | BKG-A1 NOOP.pdf | Yes |  | Uploads\476e4a0c-f36a-496a-9543-cb925ddb603f.pdf | Exist
Atikah | Yes | 06DED216-B6BB-4447-88A4-88E9AE1FA9D3 | 197FFF5B-4F99-43B7-97E9-8645BD0A70B4 | BRWA-19 | ED78D0D9-7785-4100-9FD2-4D611041BBD9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRWA-19 (NOOP) _final_to MPM.pdf | BRWA-19 (NOOP) _final_to MPM.pdf | Yes |  | Uploads\ed78d0d9-7785-4100-9fd2-4d611041bbd9.pdf | Exist
Atikah | Yes | 4E8DC3C0-9028-4A92-B347-F4BA3B28620E | 197FFF5B-4F99-43B7-97E9-8645BD0A70B4 | BRWA-19 | 0290BBDC-563D-4F41-B5FA-700F91742E24 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRWA-19 End of Well Report_RevB signed by FA.pdf | BRWA-19 End of Well Report_RevB signed by FA.pdf | Yes |  | Uploads\0290bbdc-563d-4f41-b5fa-700f91742e24.pdf | Exist
Atikah | Yes | 7DD768AD-7881-4086-8B81-72B3BC9D3EC1 | 4F9E2A11-9A48-435E-9A82-8688AA6E0AD5 | E11SC-5ST1 | 0F28A0DA-E3DF-4AFB-8A02-142FBA74F9CB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | [INTERNAL] Notice of Operations (NOOP)_Shallow Clastics E11SC-5ST1.pdf | [INTERNAL] Notice of Operations (NOOP)_Shallow Clastics E11SC-5ST1.pdf | Yes |  | Uploads\0f28a0da-e3df-4afb-8a02-142fba74f9cb.pdf | Exist
Atikah | Yes | 07739407-853A-4C55-AE86-8C2348AECEC7 | 4F9E2A11-9A48-435E-9A82-8688AA6E0AD5 | E11SC-5ST1 | 2349E127-E9A1-4C62-9955-F2EC0CBDF6A9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR E11SC-5ST1 (MAIN BODY).pdf | FWR E11SC-5ST1 (MAIN BODY).pdf | Yes |  | Uploads\2349e127-e9a1-4c62-9955-f2ec0cbdf6a9.pdf | Exist
Atikah | Yes | 20FCFF81-3646-4FE5-80ED-A5F6FCB2D292 | 0ABE868B-262F-4FF4-8159-86EAFDC05A31 | BUNGA KAMANJU-1 RDR1 | C7ED9A16-1648-4280-A4F2-918C4DD7ADB6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Kamanju-1RDR1_NOOP_Rev2.pdf | Bunga Kamanju-1RDR1_NOOP_Rev2.pdf | Yes |  | Uploads\c7ed9a16-1648-4280-a4f2-918c4dd7adb6.pdf | Exist
Atikah | Yes | 808208C5-BADA-45C2-9B33-D430B41D3EA5 | 0ABE868B-262F-4FF4-8159-86EAFDC05A31 | BUNGA KAMANJU-1 RDR1 | 5FA5AFD2-444C-421E-A084-41C211634DB8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BKMJDR04_BUNGA_KAMANJU_1_RDR1.pdf | PMO3BKMJDR04_BUNGA_KAMANJU_1_RDR1.pdf | Yes |  | Uploads\5fa5afd2-444c-421e-a084-41c211634db8.pdf | Exist
Atikah | Yes | 35A22AF6-ECBC-4BA6-9CAB-BFAA477D2517 | 9AFA6546-492F-4AFA-90EF-874D545E4786 | BO-402 | CB945502-80C6-4F2D-9EED-314A9220D57A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-402 NOOP SIGNED (1).pdf | BO-402 NOOP SIGNED (1).pdf | Yes |  | Uploads\cb945502-80c6-4f2d-9eed-314a9220d57a.pdf | Exist
Atikah | Yes | C0C858B7-B737-4D76-937C-7E9B78C15B53 | 9AFA6546-492F-4AFA-90EF-874D545E4786 | BO-402 | 06DBD3C6-BBD4-4F2A-ADAC-33CC07255656 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report BO-402.pdf | Final Well Report BO-402.pdf | Yes |  | Uploads\06dbd3c6-bbd4-4f2a-adac-33cc07255656.pdf | Exist
Atikah | Yes | 78765E4A-982D-48BD-8D00-F0E99B02A18B | C14648FF-A417-415A-8364-879A33190C9C | MLK-118 | ADE2146D-D62D-4565-90AD-6F7A3D476778 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-118 Pink East OP - NOOP v2.pdf | MLK-118 Pink East OP - NOOP v2.pdf | Yes |  | Uploads\ade2146d-d62d-4565-90ad-6f7a3d476778.pdf | Exist
Atikah | Yes | 6E9C409E-69F4-4A4D-93E7-EE21F9938924 | C14648FF-A417-415A-8364-879A33190C9C | MLK-118 | 8CD9A5C3-21FD-4683-A7FB-1AC92C6390B6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-118 FINAL.pdf | EOWR Malikai-118 FINAL.pdf | Yes |  | Uploads\8cd9a5c3-21fd-4683-a7fb-1ac92c6390b6.pdf | Exist
Atikah | Yes | 46EA4FB5-0C5C-4B8C-BB38-B95EE8F9ECB2 | 8AD6428C-B59C-4989-BA66-87AD503205DC | WD-A09-ST1 | B70510C3-5E83-46A7-9D45-F5966AB6DDFA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WD1-REP-D-0003_WD-A09ST1 Final Well Report.pdf | WD1-REP-D-0003_WD-A09ST1 Final Well Report.pdf | Yes |  | Uploads\b70510c3-5e83-46a7-9d45-f5966ab6ddfa.pdf | Exist
Atikah | Yes | B35D0967-1F94-470F-B629-0EA09176A94F | 8AD6428C-B59C-4989-BA66-87AD503205DC | WD-A09-ST1 | 7222E56C-0549-4863-9CEB-039757EF9C40 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 211127_WD1-GEN-D-0012 NOOP WELL WD-A09ST1_rev00-SFR-Signed_DS.pdf | 211127_WD1-GEN-D-0012 NOOP WELL WD-A09ST1_rev00-SFR-Signed_DS.pdf | Yes |  | Uploads\7222e56c-0549-4863-9ceb-039757ef9c40.pdf | Exist
Atikah | Yes | 3DFBDF81-C423-4097-AC9F-8C88197DB853 | B2C180B9-31FB-4931-8020-88AB333A57C8 | KN-B3 | C8551F40-094B-4C44-A631-019E4C27E88A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLGL64_KN_B3.pdf | SBO3KNBLGL64_KN_B3.pdf | Yes |  | Uploads\c8551f40-094b-4c44-a631-019e4c27e88a.pdf | Exist
Atikah | Yes | 0F81990A-8BE5-4C05-821E-9242F33A384F | B2C180B9-31FB-4931-8020-88AB333A57C8 | KN-B3 | D8FA1946-2D79-44CA-A44E-179FFD1B0102 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS3W_KN_B3.pdf | SBO3KNBLWS3W_KN_B3.pdf | Yes |  | Uploads\d8fa1946-2d79-44ca-a44e-179ffd1b0102.pdf | Exist
Atikah | Yes | 2E3EF6E2-DE70-430F-B55E-79810F538E6D | CC942116-E8F1-43AE-A8DD-895CB63D4E38 | BEKOK A-01 | 75C7505A-AB45-4D48-9FD2-FCDDD9F7176F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK A-01 ST2 EOWR.pdf | BEKOK A-01 ST2 EOWR.pdf | Yes |  | Uploads\75c7505a-ab45-4d48-9fd2-fcddd9f7176f.pdf | Exist
Atikah | Yes | 1CD14CA0-DCB6-44CB-9A67-6C014C485CD6 | CC942116-E8F1-43AE-A8DD-895CB63D4E38 | BEKOK A-01 | FC58ED80-81EA-44BD-8DDC-0C3998722F83 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK-A01ST2 NOOP.pdf | BEKOK-A01ST2 NOOP.pdf | Yes |  | Uploads\fc58ed80-81ea-44bd-8ddc-0c3998722f83.pdf | Exist
Atikah | Yes | 5B52EC13-A474-414D-B60B-6A8E6DD7C316 | 5F99113F-DD29-40C4-A750-8990C590D1B2 | TNGB-A4 | 6298578F-2A4F-4F2B-B445-DC2BD72E675F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBGL13_TNGB-A4_PCSB_NOOP.pdf | PMO3TNGBGL13_TNGB-A4_PCSB_NOOP.pdf | Yes |  | Uploads\6298578f-2a4f-4f2b-b445-dc2bd72e675f.pdf | Exist
Atikah | Yes | E2500904-9045-4655-85EB-196DB7D330D8 | 5F99113F-DD29-40C4-A750-8990C590D1B2 | TNGB-A4 | F3F9E098-6D35-49B8-9E77-6F547A9D1EBF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TANGGA BARAT-A04ST1 FWR.pdf | TANGGA BARAT-A04ST1 FWR.pdf | Yes |  | Uploads\f3f9e098-6d35-49b8-9e77-6f547a9d1ebf.pdf | Exist
Atikah | Yes | B72241C6-2B15-479B-94B2-91C135EAF06D | 934A2765-3A3B-42A8-BB00-899C6A714D05 | CERI-1 | 10046216-7D58-43BE-A6C8-C1FDCDBF9061 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3CERIWS02_CERI_1.pdf | SKO3CERIWS02_CERI_1.pdf | Yes |  | Uploads\10046216-7d58-43be-a6c8-c1fdcdbf9061.pdf | Exist
Atikah | Yes | FDAF9640-AC0C-4468-BF5C-B396AFF808EB | 934A2765-3A3B-42A8-BB00-899C6A714D05 | CERI-1 | 2E7D60B8-E51B-47B2-BCA8-9E8ED85E48E9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CERI-1 FWR-rev 1.0e.pdf | CERI-1 FWR-rev 1.0e.pdf | Yes |  | Uploads\2e7d60b8-e51b-47b2-bca8-9e8ed85e48e9.pdf | Exist
Atikah | Yes | 29B3D807-B5DF-48E9-AB98-6F75B4E6D754 | 424BAD9F-1FE9-4669-BAB3-89C9D3FDA034 | PEPULUT-01 | 4AFDED44-E757-4F45-AC10-808C934367F7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pepulut-1_NOOP FINAL.pdf | Pepulut-1_NOOP FINAL.pdf | Yes |  | Uploads\4afded44-e757-4f45-ac10-808c934367f7.pdf | Exist
Atikah | Yes | D5D2B689-6962-4C06-A03F-3354DF6A9C3E | 424BAD9F-1FE9-4669-BAB3-89C9D3FDA034 | PEPULUT-01 | E10F46B6-59BE-4F03-BB1D-84EF92D8D114 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pepulut 1 End of Well Report.pdf | Pepulut 1 End of Well Report.pdf | Yes |  | Uploads\e10f46b6-59be-4f03-bb1d-84ef92d8d114.pdf | Exist
Atikah | Yes | 7D30EF25-D336-4060-9056-6D429AB7A54E | A4126F47-96E4-4A4F-BE47-89DB2E41F32B | PRPA-03 | 2C6134ED-EB6A-4E3A-BB3B-5738537CA8DD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | Yes |  | Uploads\2c6134ed-eb6a-4e3a-bb3b-5738537ca8dd.pdf | Exist
Atikah | Yes | C92CC3AD-83E6-4AD3-9F7F-C891A8E53C22 | A4126F47-96E4-4A4F-BE47-89DB2E41F32B | PRPA-03 | D87E6D62-3D9E-43A6-887E-43F493543FE6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-03 EOWR.pdf | PRPA-03 EOWR.pdf | Yes |  | Uploads\d87e6d62-3d9e-43a6-887e-43f493543fe6.pdf | Exist
Atikah | Yes | D4D0D806-5FD2-4415-AA53-A54BE8148D64 | A0261E31-EB1E-4E75-945D-8A1CD64A5CB9 | BO-F605 | 267AD0BA-F0D0-4351-8E1F-D8767561A67D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOKOR-F605 FINAL rev2.0 SIGNED NOOP.pdf | BOKOR-F605 FINAL rev2.0 SIGNED NOOP.pdf | Yes |  | Uploads\267ad0ba-f0d0-4351-8e1f-d8767561a67d.pdf | Exist
Atikah | Yes | A44D1372-D77C-491A-A740-22DB489CD106 | A0261E31-EB1E-4E75-945D-8A1CD64A5CB9 | BO-F605 | DFDE8CA7-7EA4-4472-AC90-C149FF837F75 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report (FWR) BOKOR-F605ST1 FINAL APPROVED.pdf | Final Well Report (FWR) BOKOR-F605ST1 FINAL APPROVED.pdf | Yes |  | Uploads\dfde8ca7-7ea4-4472-ac90-c149ff837f75.pdf | Exist
Atikah | Yes | 4E8DB63C-C6A4-47A0-9FEF-8F0A830315E6 | 994CF932-A135-4751-9CF7-8AB3E4B6A570 | BUNGA ANDONG-1 | 2A2B5F84-CE14-4A26-922D-6093C44A5E0F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Andong-1 NOOP.pdf | Bunga Andong-1 NOOP.pdf | Yes |  | Uploads\2a2b5f84-ce14-4a26-922d-6093c44a5e0f.pdf | Exist
Atikah | Yes | 374EA8AA-DAD4-4947-988F-FC009DB4685F | 994CF932-A135-4751-9CF7-8AB3E4B6A570 | BUNGA ANDONG-1 | 9DBAEA26-7B05-4003-8574-A2C97F0C1D27 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Andong-1 n ST1 EoWR.pdf | Bunga Andong-1 n ST1 EoWR.pdf | Yes |  | Uploads\9dbaea26-7b05-4003-8574-a2c97f0c1d27.pdf | Exist
Atikah | Yes | 5EDF19FA-F420-4A3F-BF1C-B7FF416CF198 | F67379D4-8F74-44B2-9456-8BA46FC49F73 | BY-414 | BB2E4629-ED70-4B8F-B2A5-58606E451219 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-414 Final Well Report_Bayan Redevelopment Project.pdf | BY-414 Final Well Report_Bayan Redevelopment Project.pdf | Yes |  | Uploads\bb2e4629-ed70-4b8f-b2a5-58606e451219.pdf | Exist
Atikah | Yes | FC3CBDB0-FA50-4839-97DC-A795B204D44C | F67379D4-8F74-44B2-9456-8BA46FC49F73 | BY-414 | 8722C501-593F-47A4-8259-2D2FC1875563 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-414 Notice of Operations APPROVED_INTERNAL COPY.pdf | BY-414 Notice of Operations APPROVED_INTERNAL COPY.pdf | Yes |  | Uploads\8722c501-593f-47a4-8259-2d2fc1875563.pdf | Exist
Atikah | Yes | 5CCAC90F-0807-4F59-AAC5-B298493ACB87 | 5F76C581-8DD3-4AEA-B931-8BE3065D2DA3 | WD-A17ST1 | 022CD0BD-AB7D-43F7-B786-F39160B4A712 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WD-A17ST1 - PML-PR-D-0002 NOOP.pdf | WD-A17ST1 - PML-PR-D-0002 NOOP.pdf | Yes |  | Uploads\022cd0bd-ab7d-43f7-b786-f39160b4a712.pdf | Exist
Atikah | Yes | C06F713D-58BF-4BA2-9DA5-B913B3DC2B57 | 5F76C581-8DD3-4AEA-B931-8BE3065D2DA3 | WD-A17ST1 | 69F3CD60-D2D1-4B0C-B540-861DAA402183 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WD-A17ST1 Final Well Report.pdf | WD-A17ST1 Final Well Report.pdf | Yes |  | Uploads\69f3cd60-d2d1-4b0c-b540-861daa402183.pdf | Exist
Atikah | Yes | C5EF6262-310B-4626-A9B2-6DF67B75F491 | 6F0A97BB-690A-4D90-A1D9-8C4109A0E5C3 | BEKOK A-10 | B3E48504-0A1E-4952-9E95-A995972EFBE7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK A10SR1 EOWR Signed.pdf | BEKOK A10SR1 EOWR Signed.pdf | Yes |  | Uploads\b3e48504-0a1e-4952-9e95-a995972efbe7.pdf | Exist
Atikah | Yes | 93C21189-335B-4D61-BD6F-39111DE5362F | 6F0A97BB-690A-4D90-A1D9-8C4109A0E5C3 | BEKOK A-10 | 214E2FAF-B13E-4197-976C-A8F337451CB7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BEKOK-A10SR1 NOOP.pdf | BEKOK-A10SR1 NOOP.pdf | Yes |  | Uploads\214e2faf-b13e-4197-976c-a8f337451cb7.pdf | Exist
Atikah | Yes | F3B2FE73-2AC4-4648-B603-20E0B02B2E2A | CB8BB571-BC29-460D-998F-8D003909A3C4 | ZOISIT-1 | C553FB2C-258A-415F-B703-7B54040B4E4A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Zoisit-1 End of Well Report.pdf | Zoisit-1 End of Well Report.pdf | Yes |  | Uploads\c553fb2c-258a-415f-b703-7b54040b4e4a.pdf | Exist
Atikah | Yes | 3BB14718-7F3C-48F1-963F-8DE68F8C4954 | CB8BB571-BC29-460D-998F-8D003909A3C4 | ZOISIT-1 | F278BB32-5BDE-472B-BD4C-FC42CB798214 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ZOISIT-1 NOOP rev 0.0.pdf | ZOISIT-1 NOOP rev 0.0.pdf | Yes |  | Uploads\f278bb32-5bde-472b-bd4c-fc42cb798214.pdf | Exist
Atikah | Yes | 8C142B3C-A8CC-4147-A30A-3260A76CB836 | A570A8A1-A852-4A6B-8DC6-8D0B918E713D | TAMPARULI-1 | F0C95A14-686B-4407-890E-03F5E0B8E298 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMPRWS06_TAMPARULI_1.pdf | SBO3TMPRWS06_TAMPARULI_1.pdf | Yes |  | Uploads\f0c95a14-686b-4407-890e-03f5e0b8e298.pdf | Exist
Atikah | Yes | E7EF539F-3716-4D15-86C6-46DDB52062E3 | A570A8A1-A852-4A6B-8DC6-8D0B918E713D | TAMPARULI-1 | 5309EEA4-6279-4F7A-8E5F-40B5A65694D6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMPRWS04_TAMPARULI_1.pdf | SBO3TMPRWS04_TAMPARULI_1.pdf | Yes |  | Uploads\5309eea4-6279-4f7a-8e5f-40b5a65694d6.pdf | Exist
Atikah | Yes | AC820C42-B3AC-4480-B669-12FA60F4105D | 6AED283B-835B-4A6E-8ED4-8E103B48B4E9 | AZURIT-1 | CF3F5364-D5EA-4C1B-B3A8-76A4961D5FDB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3AZITWS01_AZURIT-1_COP_NOOP.pdf | SBO3AZITWS01_AZURIT-1_COP_NOOP.pdf | Yes |  | Uploads\cf3f5364-d5ea-4c1b-b3a8-76a4961d5fdb.pdf | Exist
Atikah | Yes | D60A2F9A-66EC-439F-9FAC-0400FDF20301 | 6AED283B-835B-4A6E-8ED4-8E103B48B4E9 | AZURIT-1 | 29B4E11C-4D14-4B8D-94EA-AEDEEF70037E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3AZITWS03_AZURIT-1_COP.pdf | SBO3AZITWS03_AZURIT-1_COP.pdf | Yes |  | Uploads\29b4e11c-4d14-4b8d-94ea-aedeef70037e.pdf | Exist
Atikah | Yes | 60D50F94-F3CC-45A9-810F-0B0D42945D17 | EE37C929-38A0-4208-AFE2-8E65B50456F1 | WD-A12 | 88B2173A-68CD-4493-A9E6-D3BBB0F4B451 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3WDESWS45_WD-A12.pdf | PMO3WDESWS45_WD-A12.pdf | Yes |  | Uploads\88b2173a-68cd-4493-a9e6-d3bbb0f4b451.pdf | Exist
Atikah | Yes | 059BC72F-6CD9-437C-AD95-544BD5AC258D | EE37C929-38A0-4208-AFE2-8E65B50456F1 | WD-A12 | 492F0A59-B135-447E-A9FD-8ABAEABC6353 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 3. WD-A12 NOOP.pdf | 3. WD-A12 NOOP.pdf | Yes |  | Uploads\492f0a59-b135-447e-a9fd-8abaeabc6353.pdf | Exist
Atikah | Yes | EE0BA6A6-C881-4585-A09C-099F48C782AE | 33F7CF62-4DE0-4C70-9740-8ED197254823 | OPHIR-A2 | 27DC28A4-C79A-479E-AEE8-B9FFCC2CD137 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | OPHIR-A2 EOWR [FINAL].pdf | OPHIR-A2 EOWR [FINAL].pdf | Yes |  | Uploads\27dc28a4-c79a-479e-aee8-b9ffcc2cd137.pdf | Exist
Atikah | Yes | F5DB94D3-67CC-4A58-9043-1DBE056776F2 | 33F7CF62-4DE0-4C70-9740-8ED197254823 | OPHIR-A2 | 576FD841-A8B2-40A7-9737-DE9B7C5BAF5D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Ophir-A2 well.pdf | NOOP Ophir-A2 well.pdf | Yes |  | Uploads\576fd841-a8b2-40a7-9737-de9b7c5baf5d.pdf | Exist
Atikah | Yes | AD49411C-BDBB-4339-BC3B-03756064C082 | DD41D6B0-347E-4520-B415-8ED200BD2F78 | KNDW-D08ST1 | 53264BB0-99F2-4BC4-AEFA-CC49F3BFF962 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNDWWS6073_KNDW_D08ST1.pdf | SBO3KNDWWS6073_KNDW_D08ST1.pdf | Yes |  | Uploads\53264bb0-99f2-4bc4-aefa-cc49f3bff962.pdf | Exist
Atikah | Yes | BCE6BA40-442E-469D-BFDA-84D51EB084AD | DD41D6B0-347E-4520-B415-8ED200BD2F78 | KNDW-D08ST1 | FEDAD9CC-27A4-47B9-9D01-BD3B20F1E473 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR D08ST1_Final.pdf | EOWR D08ST1_Final.pdf | Yes |  | Uploads\fedad9cc-27a4-47b9-9d01-bd3b20f1e473.pdf | Exist
Atikah | Yes | 20000A64-0B4D-4593-B9F8-5010FD5F0DDD | 8337AC09-A7E6-4353-A0DB-8F1CFCEBB9B7 | SED-22ST1 | 24969DB0-4198-43B5-BCAE-D1B8AF3FA27F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeD-22ST_1 Development Well Final_Signed (1).pdf | Final Well Report SeD-22ST_1 Development Well Final_Signed (1).pdf | Yes |  | Uploads\24969db0-4198-43b5-bcae-d1b8af3fa27f.pdf | Exist
Atikah | Yes | 26FEB1FF-B453-4196-9BAC-C4A58DCCE865 | 8337AC09-A7E6-4353-A0DB-8F1CFCEBB9B7 | SED-22ST1 | 3964C79A-4961-401E-A579-44A945B13434 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SeD-22ST1&2 Notice of Operation (NOOP) C1 Signed.pdf | SeD-22ST1&2 Notice of Operation (NOOP) C1 Signed.pdf | Yes |  | Uploads\3964c79a-4961-401e-a579-44a945b13434.pdf | Exist
Atikah | Yes | 9ED94ADC-01D2-40E6-9FD6-EF211B19CCA7 | E4F3091D-B498-4676-A486-8FB06721810E | MEMALI-1 | 0A3E2618-C148-46C1-94B4-06231327009F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Memali-1_Final_NOOP_MLNG Ph1 Expl_.pdf | Memali-1_Final_NOOP_MLNG Ph1 Expl_.pdf | Yes |  | Uploads\0a3e2618-c148-46c1-94b4-06231327009f.pdf | Exist
Atikah | Yes | 216EB0DD-527E-4C09-A8C4-8F836468F9C8 | E4F3091D-B498-4676-A486-8FB06721810E | MEMALI-1 | 1F3D7795-1918-40C6-A7A0-1D616C907FDB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Memali-1-Shell MLNG Exploration_EOWR.pdf | Memali-1-Shell MLNG Exploration_EOWR.pdf | Yes |  | Uploads\1f3d7795-1918-40c6-a7a0-1d616c907fdb.pdf | Exist
Atikah | Yes | F838EE55-D98E-414D-A994-8D93454442DF | FB7D8E0F-C0DA-4E1A-AA64-9008ACB27CA2 | BY-312 | 5B54D29C-9142-4F82-8E48-762EFB7FC66D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-312 Notice of Operations_APPROVED.pdf | BY-312 Notice of Operations_APPROVED.pdf | Yes |  | Uploads\5b54d29c-9142-4f82-8e48-762efb7fc66d.pdf | Exist
Atikah | Yes | 968B8197-3AB7-4D23-8FBE-A1A4CCFC25F4 | FB7D8E0F-C0DA-4E1A-AA64-9008ACB27CA2 | BY-312 | 1F968833-0982-4E56-8DA2-7BE21E15AF26 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-312 Final Well Report - Signed.pdf | BY-312 Final Well Report - Signed.pdf | Yes |  | Uploads\1f968833-0982-4e56-8da2-7be21e15af26.pdf | Exist
Atikah | Yes | 9A3FA029-0206-48FC-8A13-7AC06CDF8428 | 1AC4FFB4-A3C7-4756-9190-9017D33CE30D | EW-119 ST2 | 70089811-7D1E-4268-BAF0-53972302DB2E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EW-119 ST2_Rev3 Final Well Report.pdf | EW-119 ST2_Rev3 Final Well Report.pdf | Yes |  | Uploads\70089811-7d1e-4268-baf0-53972302db2e.pdf | Exist
Atikah | Yes | 3DE0C39D-18DE-4E31-96CD-591FB0A6F620 | 1AC4FFB4-A3C7-4756-9190-9017D33CE30D | EW-119 ST2 | A34875AC-FBE9-446D-9607-FA5CC61A5E4B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20190515_Erb West EW119 ST2 NOOP.pdf | 20190515_Erb West EW119 ST2 NOOP.pdf | Yes |  | Uploads\a34875ac-fbe9-446d-9607-fa5cc61a5e4b.pdf | Exist
Atikah | Yes | 57DA2471-4782-459D-8B34-779E1E0DBE68 | AD674FF7-D260-46E1-9F8C-902F251D21D6 | LANG LEBAH-3 | 561F8ECF-6A4A-4EDB-BC37-AFAC999F5590 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK410B_Lang_Lebah-3_EOWR (2 May 2024).pdf | SK410B_Lang_Lebah-3_EOWR (2 May 2024).pdf | Yes |  | Uploads\561f8ecf-6a4a-4edb-bc37-afac999f5590.pdf | Exist
Atikah | Yes | 30240E11-8C74-43EB-AB68-D5BAF3497F9B | AD674FF7-D260-46E1-9F8C-902F251D21D6 | LANG LEBAH-3 | 65F05B8D-F245-447E-A125-8C00A1EBE521 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lang Lebah-3 NOOP (FINAL Rev)_21Aug23.pdf | Lang Lebah-3 NOOP (FINAL Rev)_21Aug23.pdf | Yes |  | Uploads\65f05b8d-f245-447e-a125-8c00a1ebe521.pdf | Exist
Atikah | Yes | FF7AEB2B-867D-47DF-BFA4-278AD8EF7356 | B3A213C2-7B96-446B-B3E8-90606ECBB497 | MLK-122 | CF29365B-5A10-4EB9-9136-F53B17871D7B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-122.pdf | MLK-122.pdf | Yes |  | Uploads\cf29365b-5a10-4eb9-9136-f53b17871d7b.pdf | Exist
Atikah | Yes | A33794F3-CD72-49B6-B25B-2FBD0C817FB9 | B3A213C2-7B96-446B-B3E8-90606ECBB497 | MLK-122 | 71E6679F-5A22-497A-B860-F79B541A0BC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-122 P414 NOOP_Rev2.pdf | MLK-122 P414 NOOP_Rev2.pdf | Yes |  | Uploads\71e6679f-5a22-497a-b860-f79b541a0bc6.pdf | Exist
Atikah | Yes | D7C4137D-0339-48A4-8883-7CFF3A7119A5 | A857C69D-809A-448B-B75D-91DF12B2D86C | SEROK-7 | 717E3FC1-D78B-4041-91C7-3F54F929007F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SROKWS29_SEROK_7.pdf | PMO3SROKWS29_SEROK_7.pdf | Yes |  | Uploads\717e3fc1-d78b-4041-91c7-3f54f929007f.pdf | Exist
Atikah | Yes | 2373B4AB-E32B-4601-9719-EC151C1563F1 | A857C69D-809A-448B-B75D-91DF12B2D86C | SEROK-7 | 207742E1-3FDC-484A-98D1-EECD9A70BD19 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Serok-7 NOOP final.pdf | Serok-7 NOOP final.pdf | Yes |  | Uploads\207742e1-3fdc-484a-98d1-eecd9a70bd19.pdf | Exist
Atikah | Yes | AC738824-5728-4AE5-B31B-954281753B48 | 65FB0E8A-53F0-4D08-A38D-91EE6E0280A0 | REMAYONG-1 | 62DCDA09-629F-4FFB-8183-53B76ADC0C19 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3RMYGGL02_REMAYONG_1.pdf | SKO3RMYGGL02_REMAYONG_1.pdf | Yes |  | Uploads\62dcda09-629f-4ffb-8183-53b76adc0c19.pdf | Exist
Atikah | Yes | 44CE22CF-7D6C-40CB-BDD9-48DD860E448C | 65FB0E8A-53F0-4D08-A38D-91EE6E0280A0 | REMAYONG-1 | 1542E162-66ED-47A1-B7CD-F454AFB1C753 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 REMAYONG-1 FINAL WELL REPORT FINAL.pdf | SK408 REMAYONG-1 FINAL WELL REPORT FINAL.pdf | Yes |  | Uploads\1542e162-66ed-47a1-b7cd-f454afb1c753.pdf | Exist
Atikah | Yes | E778D488-D19D-46CA-B582-1BD71EDCE12B | 97C443C8-C959-481D-B66D-92211C740406 | DULANG-C22ST2 | AA1CC689-BF31-4410-B063-3778772AC1CE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG-C22ST2 NOOP.pdf | DULANG-C22ST2 NOOP.pdf | Yes |  | Uploads\aa1cc689-bf31-4410-b063-3778772ac1ce.pdf | Exist
Atikah | Yes | 606E17D2-197C-47A0-929F-FEE1B923CA55 | 97C443C8-C959-481D-B66D-92211C740406 | DULANG-C22ST2 | D46A240A-8928-4812-A079-6CF9068AE0A4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang C22 FWR.pdf | Dulang C22 FWR.pdf | Yes |  | Uploads\d46a240a-8928-4812-a079-6cf9068ae0a4.pdf | Exist
Atikah | Yes | E1EEB8D8-37A5-4484-B51C-957A76980FBC | 256118F1-14EF-4399-AB12-92580FCC1FC8 | GANSAR-2 | E570EA25-6350-40CE-9060-181F3BDC922C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3GNSRGL03_GANSAR-2_PCSB_NOOP.pdf | PMO3GNSRGL03_GANSAR-2_PCSB_NOOP.pdf | Yes |  | Uploads\e570ea25-6350-40ce-9060-181f3bdc922c.pdf | Exist
Atikah | Yes | F92FA06B-4D78-4819-B8BA-9C06F44DFABE | 256118F1-14EF-4399-AB12-92580FCC1FC8 | GANSAR-2 | 5F340BFC-820B-46BF-B2CD-92834ACEB66C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gansar-2 FWR (Signed with attachments).pdf | Gansar-2 FWR (Signed with attachments).pdf | Yes |  | Uploads\5f340bfc-820b-46bf-b2cd-92834aceb66c.pdf | Exist
Atikah | Yes | 5C6F458D-437D-43CB-AD5F-722050707AF9 | D955FC45-8AF1-4D0C-A121-9282E4959D91 | BOD-26 | CD7F2824-B3D3-4ABB-BBCB-B5652DFB9AE7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BOKDGL79_BOD-26.pdf | PMO3BOKDGL79_BOD-26.pdf | Yes |  | Uploads\cd7f2824-b3d3-4abb-bbcb-b5652dfb9ae7.pdf | Exist
Atikah | Yes | 0CA61980-D80A-4E5B-A450-0F2DBCDBBCB3 | D955FC45-8AF1-4D0C-A121-9282E4959D91 | BOD-26 | A7B1E058-2CE2-45CB-A09E-EA5F75768390 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BOKDWS1N_BOD-26.pdf | PMO3BOKDWS1N_BOD-26.pdf | Yes |  | Uploads\a7b1e058-2ce2-45cb-a09e-ea5f75768390.pdf | Exist
Atikah | Yes | 33157E4D-0810-4244-A714-4FF49DC42E79 | EACFF3C9-6481-408D-907C-928CC7702A11 | ARENGA-1 | 6F039B5D-1FC6-4D88-AE1C-155D260FEE56 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ARGAWS04_ARENGA-1.pdf | PMO3ARGAWS04_ARENGA-1.pdf | Yes |  | Uploads\6f039b5d-1fc6-4d88-ae1c-155d260fee56.pdf | Exist
Atikah | Yes | 617F046D-B8BC-4228-BA8C-CE1C41750DC7 | EACFF3C9-6481-408D-907C-928CC7702A11 | ARENGA-1 | E39398DB-DB36-4A9A-93CC-FAF37B0E7ADB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ARGAGL03_ARENGA-1.pdf | PMO3ARGAGL03_ARENGA-1.pdf | Yes |  | Uploads\e39398db-db36-4a9a-93cc-faf37b0e7adb.pdf | Exist
Atikah | Yes | AB46B689-D32C-4520-BF9C-58E43F34661C | 63968968-46C8-4FCE-955E-92F51946FE9E | ANGSI-D16 | 09D73BFA-4169-4152-B1CA-1E7C7FAE15FF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWS8W_ANGSI-D16.pdf | PMO3ANSIWS8W_ANGSI-D16.pdf | Yes |  | Uploads\09d73bfa-4169-4152-b1ca-1e7c7fae15ff.pdf | Exist
Atikah | Yes | BC732704-DD2D-4B62-8AE2-679295710A0E | 63968968-46C8-4FCE-955E-92F51946FE9E | ANGSI-D16 | 5F84826B-A2FF-468B-BA40-FAF582950C77 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWS9O_ANGSI-D16.pdf | PMO3ANSIWS9O_ANGSI-D16.pdf | Yes |  | Uploads\5f84826b-a2ff-468b-ba40-faf582950c77.pdf | Exist
Atikah | Yes | C11C4DB2-8C91-44AF-A566-92DACC5B7855 | 89209E7E-223E-472D-ADCD-93773A033805 | TABU-B08ST2 | D97CB91A-DDED-42A2-941C-35D0246947E3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B8ST2 Final Well Report Part 1.pdf | Tabu B8ST2 Final Well Report Part 1.pdf | Yes |  | Uploads\d97cb91a-dded-42a2-941c-35d0246947e3.pdf | Exist
Atikah | Yes | B6BFA427-9B8C-4D5B-98AE-B7901D368D7D | 89209E7E-223E-472D-ADCD-93773A033805 | TABU-B08ST2 | 11137A0B-40F2-492A-A414-81698BE32B50 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B8ST2 Slot 6 NOOP v0.pdf | Tabu B8ST2 Slot 6 NOOP v0.pdf | Yes |  | Uploads\11137a0b-40f2-492a-a414-81698be32b50.pdf | Exist
Atikah | Yes | 670EBBBF-E7A4-4D4C-88CB-98C41AA4DF83 | 4928164D-2BB0-406E-B95E-938148B5F259 | BARAM D2-1 | 61D6F5C1-8753-4A0F-A4F4-9CA841299427 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BD2-1 FWR with Attachment_SIGNED.pdf | BD2-1 FWR with Attachment_SIGNED.pdf | Yes |  | Uploads\61d6f5c1-8753-4a0f-a4f4-9ca841299427.pdf | Exist
Atikah | Yes | EF8B3BA6-F0A3-4DE2-80D7-8293870D1CED | 4928164D-2BB0-406E-B95E-938148B5F259 | BARAM D2-1 | C0BE5579-A121-4202-862A-80BF6DB05226 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram D2-1_INTERNAL.pdf | Baram D2-1_INTERNAL.pdf | Yes |  | Uploads\c0be5579-a121-4202-862a-80bf6db05226.pdf | Exist
Atikah | Yes | 8EC666DE-175E-4773-A108-406F7F4A2D3E | BD6AEB07-CC46-4D25-A0BA-93ADDDB6A5D9 | BN-87 | 6422BC6E-05E3-4329-972F-BC3727F54CDC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN87 Petronas Final Well Report.pdf | BN87 Petronas Final Well Report.pdf | Yes |  | Uploads\6422bc6e-05e3-4329-972f-bc3727f54cdc.pdf | Exist
Atikah | Yes | 2C15D839-787F-4F36-89D1-414D9D4BAE69 | BD6AEB07-CC46-4D25-A0BA-93ADDDB6A5D9 | BN-87 | 76226A34-466C-461D-B0B4-80C3DE9171AF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-87-FINAL.pdf | NOOP BN-87-FINAL.pdf | Yes |  | Uploads\76226a34-466c-461d-b0b4-80c3de9171af.pdf | Exist
Atikah | Yes | DE3D7407-9ADA-4B16-BD1D-B6D262DA7B53 | 31C7645D-65F8-4145-A386-93F2ECD606C8 | PESA-03 | 97560BCB-4CD3-4084-936E-1F5D0B8C4437 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PESA-3 EOWR FINAL (APPROVED).pdf | PESA-3 EOWR FINAL (APPROVED).pdf | Yes |  | Uploads\97560bcb-4cd3-4084-936e-1f5d0b8c4437.pdf | Missing
Atikah | Yes | 1BF34DD6-1C86-46AE-971B-DFF87C111B86 | 31C7645D-65F8-4145-A386-93F2ECD606C8 | PESA-03 | BCA11C8A-8989-461E-B238-C9E96E439C90 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pemanis PESA-1, PESA-2, PESA-3 and PESA-4 NOOP.pdf | Pemanis PESA-1, PESA-2, PESA-3 and PESA-4 NOOP.pdf | Yes |  | Uploads\bca11c8a-8989-461e-b238-c9e96e439c90.pdf | Missing
Atikah | Yes | 5D8AD1A6-FD3E-4AB5-80A1-FA87BEA6E5DD | 950253F9-0CC2-4C1E-B49D-9404523730CE | EMPURAU-1 | 4A35B19D-9BBA-4432-8FE9-B558AA43B893 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EMPURAU-1 FWR FINAL.pdf | EMPURAU-1 FWR FINAL.pdf | Yes |  | Uploads\4a35b19d-9bba-4432-8fe9-b558aa43b893.pdf | Exist
Atikah | Yes | 507472D7-DFA1-4824-A60E-44D1BB3CC84E | 950253F9-0CC2-4C1E-B49D-9404523730CE | EMPURAU-1 | 7E4BF2EA-A30F-4B22-B38E-5D7712217902 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EMPURAU-1 NOOP Final doc.pdf | EMPURAU-1 NOOP Final doc.pdf | Yes |  | Uploads\7e4bf2ea-a30f-4b22-b38e-5d7712217902.pdf | Exist
Atikah | Yes | 9AAD7767-DD26-4741-84E2-686F17EF8C35 | 0A69FDDA-64A2-4460-B736-94E36BABE479 | BAYAN-220 | A9E83A08-A607-4270-AF8D-85F20EA0ADE4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BYANWS2T_BAYAN-220_FWR_PCSB.pdf | SKO3BYANWS2T_BAYAN-220_FWR_PCSB.pdf | Yes |  | Uploads\a9e83a08-a607-4270-af8d-85f20ea0ade4.pdf | Exist
Atikah | Yes | FF932EA3-ACBC-47CC-8C4E-68F4C919EBE9 | 0A69FDDA-64A2-4460-B736-94E36BABE479 | BAYAN-220 | 2A578FAA-DDB7-4FCF-BEA6-6D468979C04F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BYANGL10_BAYAN-220_PCSB_NOOP.pdf | SKO3BYANGL10_BAYAN-220_PCSB_NOOP.pdf | Yes |  | Uploads\2a578faa-ddb7-4fcf-bea6-6d468979c04f.pdf | Exist
Atikah | Yes | 2099C817-B7D4-4E1A-B701-05293A27E9C0 | B8277C3E-3ED6-4BD1-9A4F-951615FB08A2 | LALA-1 | 25A89CF8-D04C-42DF-A904-FFE3C8A78119 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lala-1RDR2 Final Well Report (without attachment).pdf | Lala-1RDR2 Final Well Report (without attachment).pdf | Yes |  | Uploads\25a89cf8-d04c-42df-a904-ffe3c8a78119.pdf | Exist
Atikah | Yes | 4D0631A1-9AA9-4241-A37F-B6E8D4C2BC4D | B8277C3E-3ED6-4BD1-9A4F-951615FB08A2 | LALA-1 | 3DFB3737-5D36-45E7-8570-B81E472094C7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lala-1RDR2 Internal_MPM.pdf | Lala-1RDR2 Internal_MPM.pdf | Yes |  | Uploads\3dfb3737-5d36-45e7-8570-b81e472094c7.pdf | Exist
Atikah | Yes | A36BF5C2-3296-4A3D-BD6B-C622225C781B | 9F34DB30-751E-4EFA-9512-954639286F44 | PGA-03ST1 | E8814CD5-5F3B-4CAE-A02F-669195D4441B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-03_NOOP 20th Apr 2020.pdf | PGA-03_NOOP 20th Apr 2020.pdf | Yes |  | Uploads\e8814cd5-5f3b-4cae-a02f-669195d4441b.pdf | Exist
Atikah | Yes | 5FBA45D2-A8CC-4FF3-8C99-3028EF75D9C3 | 9F34DB30-751E-4EFA-9512-954639286F44 | PGA-03ST1 | 58D4F4B8-0ADE-46A1-9C08-6F56BAAB774F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-03ST1 End of Well Report_signed.pdf | PGA-03ST1 End of Well Report_signed.pdf | Yes |  | Uploads\58d4f4b8-0ade-46a1-9c08-6f56baab774f.pdf | Exist
Atikah | Yes | AB158373-CE8B-4E2F-AF48-149B3D56F692 | 6EF0BEEB-6920-4E31-BB39-95518A36459A | TUKAU-E41ST1 | 2D499FB2-8B31-476F-980A-7CBB69B74320 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TK-41 ST2 FWR.pdf |  | No |  | Uploads\2d499fb2-8b31-476f-980a-7cbb69b74320.pdf | Exist
Atikah | Yes | 7C4FBCB0-6DB0-4C11-941E-8F45A03A6E47 | 6EF0BEEB-6920-4E31-BB39-95518A36459A | TUKAU-E41ST1 | B49D8E39-44AD-4C87-9B8C-9AF5F743C99C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TK41ST1 (Rev1).pdf | NOOP TK41ST1 (Rev1)_Approved1.pdf | No |  | Uploads\b49d8e39-44ad-4c87-9b8c-9af5f743c99c.pdf | Exist
Atikah | Yes | 62CCBCD7-5896-4A36-9E56-690348BB8E9D | A60345B7-7D78-46E5-B344-9561AB38743C | BOKOR-E504 | E094B53F-679E-4D8F-9869-CC36082990F3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR_E504.pdf | FWR BOKOR_E504.pdf | Yes |  | Uploads\e094b53f-679e-4d8f-9869-cc36082990f3.pdf | Exist
Atikah | Yes | E0CB1455-6B22-4B8E-86B7-62C61EC02F9F | A60345B7-7D78-46E5-B344-9561AB38743C | BOKOR-E504 | D9D509D2-5F4D-476E-A4E4-D127B6A102BA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BOKOR-E504 signed MSD (1).pdf | NOOP BOKOR-E504 signed MSD (1).pdf | Yes |  | Uploads\d9d509d2-5f4d-476e-a4e4-d127b6a102ba.pdf | Exist
Atikah | Yes | 1424BC3F-A5A1-4792-AE7F-74A3028BE2B1 | 08EC62EA-B101-4D68-A101-95DA8C39ADD7 | SEPAT-A08ST1 | 1A5C6930-8FBB-47CB-874B-ED90C62688E5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Approved NOOP Sepat A08ST.pdf | Approved NOOP Sepat A08ST.pdf | Yes |  | Uploads\1a5c6930-8fbb-47cb-874b-ed90c62688e5.pdf | Exist
Atikah | Yes | 23A6C7DF-F861-4622-8D6D-CD57919B64BF | 08EC62EA-B101-4D68-A101-95DA8C39ADD7 | SEPAT-A08ST1 | F69D27F2-AAB6-4423-8185-9C96DB35477B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR A08ST1 2020 June 20-signed-signed.pdf | FWR A08ST1 2020 June 20-signed-signed.pdf | Yes |  | Uploads\f69d27f2-aab6-4423-8185-9c96db35477b.pdf | Exist
Atikah | Yes | 1A0D95C9-2768-48BA-8265-8408A0EA2F22 | 6F8EAB12-FD8B-4944-8DFE-9623E1A21017 | HELANG DEEP-1 | FB6BDF93-32F3-482A-8F9F-65208A8070C6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Helang Deep D1-1 ST1 EOWR_Rev0.1.pdf | Helang Deep D1-1 ST1 EOWR_Rev0.1.pdf | Yes |  | Uploads\fb6bdf93-32f3-482a-8f9f-65208a8070c6.pdf | Exist
Atikah | Yes | 393835D7-A529-4319-80DE-2C645C72EE44 | 6F8EAB12-FD8B-4944-8DFE-9623E1A21017 | HELANG DEEP-1 | 38FDEC82-E1AD-469E-BF6C-AD149FD5AAB1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20210301 Supplementary of NOOP HELANG D1-1 R0.0.pdf | 20210301 Supplementary of NOOP HELANG D1-1 R0.0.pdf | Yes |  | Uploads\38fdec82-e1ad-469e-bf6c-ad149fd5aab1.pdf | Exist
Atikah | Yes | 8F30C366-4B92-4DAF-99D6-67FCB5A95DEB | 2A2EDCD8-61E2-4C96-9455-9628C6942407 | TBG-B5ST1 | 99507A86-CA5C-4C60-A2D5-A4558AD47A76 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS8N_TBG-B5ST1_PCSB_NOOP.pdf | SBO3TMBGWS8N_TBG-B5ST1_PCSB_NOOP.pdf | Yes |  | Uploads\99507a86-ca5c-4c60-a2d5-a4558ad47a76.pdf | Exist
Atikah | Yes | F4E09F69-D4EB-4BC1-87D4-AA1AED716767 | 2A2EDCD8-61E2-4C96-9455-9628C6942407 | TBG-B5ST1 | EEF74ACC-EF04-4579-9CE0-5D4FF0AE0AAD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3TMBGWS8U_TBG-B5ST1_PCSB_FWR.pdf | SBO3TMBGWS8U_TBG-B5ST1_PCSB_FWR.pdf | Yes |  | Uploads\eef74acc-ef04-4579-9ce0-5d4ff0ae0aad.pdf | Exist
Atikah | Yes | 00AAD50A-D570-4097-899D-B452AAD901B5 | C447CC56-2DB4-44BA-8783-969D62BA1555 | DULANG-D32 | 921DE3BF-7FE0-421A-98D9-0C66ACE357BF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGGL85_DULANG_D32.pdf | PMO3DULGGL85_DULANG_D32.pdf | Yes |  | Uploads\921de3bf-7fe0-421a-98d9-0c66ace357bf.pdf | Exist
Atikah | Yes | 8F44D585-4113-4E14-AA36-EC318E21176F | C447CC56-2DB4-44BA-8783-969D62BA1555 | DULANG-D32 | 6A34AB0E-2A1D-456B-A0A7-0AB920BDBE08 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYJ_DULANG_D32.pdf | PMO3DULGWSYJ_DULANG_D32.pdf | Yes |  | Uploads\6a34ab0e-2a1d-456b-a0a7-0ab920bdbe08.pdf | Exist
Atikah | Yes | C7AE8206-AE07-4793-909D-8B4F923586BD | 4B56642E-3D74-4285-AE0D-9772FF7AF7B7 | PRPA-05 | 21AB8E14-B159-4B88-9963-EE5ED56995B5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | Yes |  | Uploads\21ab8e14-b159-4b88-9963-ee5ed56995b5.pdf | Exist
Atikah | Yes | AE3A1F6E-194E-4689-A22B-335F88616AB0 | 4B56642E-3D74-4285-AE0D-9772FF7AF7B7 | PRPA-05 | CC97FB5E-409D-4D61-88E4-E709C7A0EE5F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-05 EOWR.pdf | PRPA-05 EOWR.pdf | Yes |  | Uploads\cc97fb5e-409d-4d61-88e4-e709c7a0ee5f.pdf | Exist
Atikah | Yes | 165BB5E7-8B00-4D52-B29B-0C57FF6E4F17 | 21D9D1A7-E98D-4FE6-BFAC-97B6B9EC6C97 | JANGAS-3 | 39A1A704-9657-45D1-9484-35334F59C6B8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JANGAS-3 FWR without attachment.pdf | JANGAS-3 FWR without attachment.pdf | Yes |  | Uploads\39a1a704-9657-45d1-9484-35334f59c6b8.pdf | Exist
Atikah | Yes | 4CB5C63C-EBEC-42C2-93D7-613A85AFF19E | 21D9D1A7-E98D-4FE6-BFAC-97B6B9EC6C97 | JANGAS-3 | BBA6D64F-F1C9-486D-B9A1-3FE04747B6EC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - JANGAS-3_Internal.pdf | NOOP - JANGAS-3_Internal.pdf | Yes |  | Uploads\bba6d64f-f1c9-486d-b9a1-3fe04747b6ec.pdf | Exist
Atikah | Yes | BC70C864-4077-40DE-B96E-8D639C1F4591 | 79D09570-D77F-4BAB-B080-97F197697E08 | BERGADING-A9(M) | 16F4EE38-AC18-4519-A8F9-306E5E529755 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRG A-9(M).pdf | BRG A-9(M).pdf | Yes |  | Uploads\16f4ee38-ac18-4519-a8f9-306e5e529755.pdf | Exist
Atikah | Yes | 2002EFC1-02D6-474C-B0F2-D04BB612B476 | 79D09570-D77F-4BAB-B080-97F197697E08 | BERGADING-A9(M) | 69A49996-7A85-46ED-B915-7D42ECD54BD8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading A-9_ Rev0.pdf | EOWR_Bergading A-9_ Rev0.pdf | Yes |  | Uploads\69a49996-7a85-46ed-b915-7d42ecd54bd8.pdf | Exist
Atikah | Yes | 41936909-DF23-47E7-809C-AABF066B659C | 4568FFCD-280E-4226-BC2C-97F2D1E3DD08 | CD-C11 | B1386E92-A040-4D80-8F64-2046458D1684 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-C11 CP2-GEN-D-0003_Rev.01 NOTICE OF OPERATIONS - WELL (Slot 9b, CDW-C Platform).pdf | CD-C11 CP2-GEN-D-0003_Rev.01 NOTICE OF OPERATIONS - WELL (Slot 9b, CDW-C Platform).pdf | Yes |  | Uploads\b1386e92-a040-4d80-8f64-2046458d1684.pdf | Exist
Atikah | Yes | 0A42534F-E272-4404-9F49-73A2575B2593 | 4568FFCD-280E-4226-BC2C-97F2D1E3DD08 | CD-C11 | 3D4B43F0-B8C6-4CB4-86AD-9017C24D68DD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-C11 Final Well Report.pdf | CD-C11 Final Well Report.pdf | Yes |  | Uploads\3d4b43f0-b8c6-4cb4-86ad-9017c24d68dd.pdf | Exist
Atikah | Yes | F7E8D098-FDA9-4C0E-BD44-9047DCC13225 | 168441E4-CBA2-4DDD-B26B-980845AEB5A3 | BAMBAZON SH1-1 | 7E29DFA2-6AF8-44B0-BB80-946D3F15CDDD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAMBAZON SH1-1 EOWR.pdf | BAMBAZON SH1-1 EOWR.pdf | Yes |  | Uploads\7e29dfa2-6af8-44b0-bb80-946d3f15cddd.pdf | Exist
Atikah | Yes | D8A7CF43-3114-4A26-B2B7-B3EC194E38E6 | 168441E4-CBA2-4DDD-B26B-980845AEB5A3 | BAMBAZON SH1-1 | CF41F760-C3B4-4F6C-BA2B-B03B990C387B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bambazon SH1-1 NOOP.pdf | Bambazon SH1-1 NOOP.pdf | Yes |  | Uploads\cf41f760-c3b4-4f6c-ba2b-b03b990c387b.pdf | Exist
Atikah | Yes | A054B45D-C16F-437B-8079-CDBCF4A166E7 | 99C24B06-AB30-4F10-A726-982748AD020D | KELAPA BALI-1 | C89E96AC-8F91-4ACB-86FA-28DAFA266C2C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | kelapa Bali-1_fwr.pdf | kelapa Bali-1_fwr.pdf | Yes |  | Uploads\c89e96ac-8f91-4acb-86fa-28dafa266c2c.pdf | Exist
Atikah | Yes | 8869CBC3-760F-4940-8EB1-E34CBCBF30A0 | 99C24B06-AB30-4F10-A726-982748AD020D | KELAPA BALI-1 | B1AF29AB-69BC-42B0-8626-F747EC975FA0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kelapa Bali-1 NOOP MPM Submission.pdf | Kelapa Bali-1 NOOP MPM Submission.pdf | Yes |  | Uploads\b1af29ab-69bc-42b0-8626-f747ec975fa0.pdf | Exist
Atikah | Yes | 4546E91A-0E10-4516-B607-B12D56957688 | ED44A4AB-67D8-4A13-85DA-9845D9A18A15 | TELOK-B2 | 20C2D149-1EEE-46E3-81F8-D4F56B84FDB4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TELOWS40_TELOK-B2_EMEPMI_NOOP.pdf | PMO3TELOWS40_TELOK-B2_EMEPMI_NOOP.pdf | Yes |  | Uploads\20c2d149-1eee-46e3-81f8-d4f56b84fdb4.pdf | Exist
Atikah | Yes | 696F7266-F54A-44A3-A836-B0E6A1612298 | ED44A4AB-67D8-4A13-85DA-9845D9A18A15 | TELOK-B2 | CF9B71DC-AFE0-4D39-96EC-1CB0E7D6A6EC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Telok B2 - FWR.pdf | Telok B2 - FWR.pdf | Yes |  | Uploads\cf9b71dc-afe0-4d39-96ec-1cb0e7d6a6ec.pdf | Exist
Atikah | Yes | 24AAEEBE-FCED-453E-A83B-751C47E6AADC | E1597A63-361A-405C-9CB4-99BEB5F00E73 | EC-A08 | 25D6AA92-B713-4FD6-B8A8-FE6D29768D00 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A08 Final Well ReportDS.pdf | EC-A08 Final Well ReportDS.pdf | Yes |  | Uploads\25d6aa92-b713-4fd6-b8a8-fe6d29768d00.pdf | Exist
Atikah | Yes | 7097EFF6-722A-4AD2-9651-15A902529390 | E1597A63-361A-405C-9CB4-99BEB5F00E73 | EC-A08 | 30897D8E-3AFD-42CF-9D11-95563F202AB7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0006_Rev.00 NOTICE OF OPERATIONS - WELL EC-A08 (Slot 4B ECW-A Platform) signed AAMZY_SFR_DS.pdf | ECN-GEN-D-0006_Rev.00 NOTICE OF OPERATIONS - WELL EC-A08 (Slot 4B ECW-A Platform) signed AAMZY_SFR_DS.pdf | Yes |  | Uploads\30897d8e-3afd-42cf-9d11-95563f202ab7.pdf | Exist
Atikah | Yes | 3B454087-EC8F-4173-8E3F-73D21F109641 | 1AA1C9B0-6846-44F0-A1FE-99D95A3A5F22 | DULANG-A17ST2 | 25FEEC2F-984F-4130-B5F5-8BC471F04ED8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_A17ST2(OP5) Signed_Internal Copy.pdf | NOOP_A17ST2(OP5) Signed_Internal Copy.pdf | Yes |  | Uploads\25feec2f-984f-4130-b5f5-8bc471f04ed8.pdf | Exist
Atikah | Yes | CC6D544D-7D8E-4C3F-AD59-C2F7F72B42DD | 1AA1C9B0-6846-44F0-A1FE-99D95A3A5F22 | DULANG-A17ST2 | 8D3C4BB5-CBEE-477B-9499-40ECD3861505 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Dulang A17ST2_Submission to MPM.pdf | FWR Dulang A17ST2_Submission to MPM.pdf | Yes |  | Uploads\8d3c4bb5-cbee-477b-9499-40ecd3861505.pdf | Exist
Atikah | Yes | 26EA77FC-71E3-4EB6-BC8E-10FF42A26AD8 | 62A3CDDD-910F-4AF6-814E-99E47970AF0F | MLK-112 | DA116386-4481-4655-9E58-AEDD195C4839 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-112 EOWR (2 Nov) for Petronas (Final).pdf | MLK-112 EOWR (2 Nov) for Petronas (Final).pdf | Yes |  | Uploads\da116386-4481-4655-9e58-aedd195c4839.pdf | Missing
Atikah | Yes | 083B5C11-8CB7-487A-9E85-50A785F4BEF6 | 62A3CDDD-910F-4AF6-814E-99E47970AF0F | MLK-112 | D1515778-50B0-41AA-91CB-F782DBB0748B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MKAIGL20_MLK_112.pdf | SBO3MKAIGL20_MLK_112.pdf | Yes |  | Uploads\d1515778-50b0-41aa-91cb-f782dbb0748b.pdf | Missing
Atikah | Yes | 05BB5C31-F8D2-4C5D-AB3B-75A6310585D4 | 0B1D4FEE-744F-4419-A027-99FFD20FB7B2 | RERAMA-1 | 1592552C-11C0-460F-9E01-81F1747BE741 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Rerama-1 End of Well Report (FINAL).pdf | Rerama-1 End of Well Report (FINAL).pdf | Yes |  | Uploads\1592552c-11c0-460f-9e01-81f1747be741.pdf | Exist
Atikah | Yes | 54F148A2-3001-4B4F-A03B-EBBD1E20DCF8 | 0B1D4FEE-744F-4419-A027-99FFD20FB7B2 | RERAMA-1 | 034E72FB-2F07-4EAA-9676-DA9DBE4AD904 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Rerama-1 NOOP rev1.pdf | Rerama-1 NOOP rev1.pdf | Yes |  | Uploads\034e72fb-2f07-4eaa-9676-da9dbe4ad904.pdf | Exist
Atikah | Yes | 8B1E99DF-A2EE-4464-82B9-CFE27B07C43B | EB8BD2E4-4E51-4A64-B2B1-9A27F62B46FB | D18-108 | 0D2126AA-ABFF-4F10-A5FA-72734552F871 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS73_D18-108_PCSB.pdf | SKO3D18-WS73_D18-108_PCSB.pdf | Yes |  | Uploads\0d2126aa-abff-4f10-a5fa-72734552f871.pdf | Exist
Atikah | Yes | 06F08F16-2778-4E8C-99BA-6FFF6BDE087F | EB8BD2E4-4E51-4A64-B2B1-9A27F62B46FB | D18-108 | 543DB4E1-04B1-4521-9CB9-21ABDE6E92CA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS2I_D18-108_PCSB.pdf | SKO3D18-WS2I_D18-108_PCSB.pdf | Yes |  | Uploads\543db4e1-04b1-4521-9cb9-21abde6e92ca.pdf | Exist
Atikah | Yes | 4962DAD0-EF28-4B1A-8068-1AEE7DFBF523 | 6D342B18-73AD-4A21-8CD9-9A5C913CFF90 | BERGADING-A1(A) | A446AA6A-063F-4E50-B6A6-E8F54D03747C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERGADING-A1 NOOP - FINAL_Signed.pdf | BERGADING-A1 NOOP - FINAL_Signed.pdf | Yes |  | Uploads\a446aa6a-063f-4e50-b6a6-e8f54d03747c.pdf | Exist
Atikah | Yes | 4DDBA557-EE08-46F1-AF59-F7D37FC70452 | 6D342B18-73AD-4A21-8CD9-9A5C913CFF90 | BERGADING-A1(A) | 67EB6874-73CA-4A7E-A8BD-CDBC81B45408 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BGDGWS38_BERGADING-A1.pdf | PMO3BGDGWS38_BERGADING-A1.PDF | Yes |  | Uploads\67eb6874-73ca-4a7e-a8bd-cdbc81b45408.pdf | Exist
Atikah | Yes | 1A61AD0F-08F8-4AA1-8F8E-36778FB5F03A | 4B678E01-461C-4C44-826F-9A63D2AD6B5B | BOLAI-1 | 3197DDD4-B2A0-4283-A00E-03AECE10CBEE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bolai-1 End of Well Report_Finalsdpdf.pdf | Bolai-1 End of Well Report_Finalsdpdf.pdf | Yes |  | Uploads\3197ddd4-b2a0-4283-a00e-03aece10cbee.pdf | Exist
Atikah | Yes | 0D6DACC7-5C61-43A3-A9E3-95C0E990FCCC | 4B678E01-461C-4C44-826F-9A63D2AD6B5B | BOLAI-1 | 86B7332F-C945-4843-8254-69CE2AA20D34 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bolai-1 NOOP_FINAL.pdf | Bolai-1 NOOP_FINAL.pdf | Yes |  | Uploads\86b7332f-c945-4843-8254-69ce2aa20d34.pdf | Exist
Atikah | Yes | C08D525D-AFE8-4EC0-9E7E-8753298400B9 | 8903431B-DDEE-4B18-B0A4-9A8EB9068D34 | S-SW1-P1 | F6A1AB4C-FCE9-4131-AA55-A19803F9C3E2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SBO-WS6S_S_SW1_P1.pdf | SBO3SBO-WS6S_S_SW1_P1.pdf | Yes |  | Uploads\f6a1ab4c-fce9-4131-aa55-a19803f9c3e2.pdf | Exist
Atikah | Yes | 8B7E374A-50C7-488F-9FC0-4F8B85219677 | 8903431B-DDEE-4B18-B0A4-9A8EB9068D34 | S-SW1-P1 | 2AF4217D-D566-4A64-B6EC-A5742230030E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR06_S_SW1_P1.pdf | SBO3SKNPDR06_S_SW1_P1.pdf | Yes |  | Uploads\2af4217d-d566-4a64-b6ec-a5742230030e.pdf | Exist
Atikah | Yes | 8AC70A56-B86B-4116-917C-747DA4DB6BDE | B2F45F7B-A055-46CA-AD4A-9B00573AA8D5 | SF UNGU-1 | 743756AC-EE40-456B-B4AB-85E0A618929A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SOUTH FURIOUS UNGU-1 and ST1 NOOP_FINAL - Rev.11.pdf | SOUTH FURIOUS UNGU-1 and ST1 NOOP_FINAL - Rev.11.pdf | Yes |  | Uploads\743756ac-ee40-456b-b4ab-85e0a618929a.pdf | Exist
Atikah | Yes | 4D1AF285-D46B-485E-BC8B-DA646C9109AF | B2F45F7B-A055-46CA-AD4A-9B00573AA8D5 | SF UNGU-1 | F2CB2114-1720-490B-94AC-282555970493 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEAH_EOWR_SF Ungu-1 and S1 (MPM - Well Management).pdf | SEAH_EOWR_SF Ungu-1 and S1 (MPM - Well Management).pdf | Yes |  | Uploads\f2cb2114-1720-490b-94ac-282555970493.pdf | Exist
Atikah | Yes | EACA8A70-FB69-4CBD-8617-F8A19EEA297D | 8EE43412-31BE-4C7B-86FC-9B8CE55D1FCA | BENUM-2 | 7F9008DC-E739-40FB-B18B-5392FC68301A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Benum-2_May2022_signed.pdf | Benum-2_May2022_signed.pdf | Yes |  | Uploads\7f9008dc-e739-40fb-b18b-5392fc68301a.pdf | Exist
Atikah | Yes | 688AC8DD-ACBD-4008-8073-9D9C4A6DE52B | 8EE43412-31BE-4C7B-86FC-9B8CE55D1FCA | BENUM-2 | E7BC78CD-C67B-4586-9071-BE1535B4AFBC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Benum-2ST1_End of Well_Report.pdf | Benum-2ST1_End of Well_Report.pdf | Yes |  | Uploads\e7bc78cd-c67b-4586-9071-be1535b4afbc.pdf | Exist
Atikah | Yes | 40247B3D-3CBC-4BEA-91C7-25E0BB7170A1 | 47358100-3D16-4190-8A22-9BDB0D836E73 | TT-A6 | A5287523-13EE-4F7C-8ACE-55056BF49DA4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR TT-A6 Final to MPM.pdf | FWR TT-A6 Final to MPM.pdf | Yes |  | Uploads\a5287523-13ee-4f7c-8ace-55056bf49da4.pdf | Exist
Atikah | Yes | 37D8AF2F-0116-439A-9AEA-BB571C2723F6 | 47358100-3D16-4190-8A22-9BDB0D836E73 | TT-A6 | 165194DD-3901-40FC-8766-4A2689FC4685 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A6 Final Internal Distribution.pdf | TT-A6 Final Internal Distribution.pdf | Yes |  | Uploads\165194dd-3901-40fc-8766-4a2689fc4685.pdf | Exist
Atikah | Yes | 01F87ED4-E7B1-4D62-ABF0-7207946A7846 | 9CB3D687-03DF-41E7-94E6-9BEB7BB6282F | MERANTI M1 | BEF3A0A9-DF1C-4FC7-BAB6-9401DAF9667F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MRNTWS17_MERANTI M1_M2_M3.pdf | PMO3MRNTWS17_MERANTI M1_M2_M3.pdf | Yes |  | Uploads\bef3a0a9-df1c-4fc7-bab6-9401daf9667f.pdf | Exist
Atikah | Yes | E1B34C7B-DFCB-49F4-97AB-88A061DE4677 | 9CB3D687-03DF-41E7-94E6-9BEB7BB6282F | MERANTI M1 | A445A6EE-36ED-45C2-9F79-E8099ECFFAD2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MRNTWS12_MERANTI M1.pdf | PMO3MRNTWS12_MERANTI M1.pdf | Yes |  | Uploads\a445a6ee-36ed-45c2-9f79-e8099ecffad2.pdf | Exist
Atikah | Yes | 8993E4FC-DFC6-4846-99EC-91EBDD592EE9 | C91838B9-CE9B-451C-A3A0-9C769280EB80 | MLK-119 | 0A13F9EC-E816-4AC7-8429-634BA2C5600D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-119 KNR South WI - NOOP v2.pdf | MLK-119 KNR South WI - NOOP v2.pdf | Yes |  | Uploads\0a13f9ec-e816-4ac7-8429-634ba2c5600d.pdf | Exist
Atikah | Yes | 7FA282C0-D8BD-4175-A59E-0AF2D4421DBA | C91838B9-CE9B-451C-A3A0-9C769280EB80 | MLK-119 | C482EDE0-D7C5-4A8F-88C4-09B6270AB856 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20210712 - EOWR Malikai-119S1 FINAL.pdf | 20210712 - EOWR Malikai-119S1 FINAL.pdf | Yes |  | Uploads\c482ede0-d7c5-4a8f-88c4-09b6270ab856.pdf | Exist
Atikah | Yes | FA00D18C-2AD0-45FF-A7D2-4063EF265F3C | BBFAD6CB-DB51-454C-8A31-9E0F24353A1D | LAWA-1 | 190A7BB0-BDFC-49CB-959D-BE5AC42748D8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3LAWAWS06_LAWA-1.pdf | SBO3LAWAWS06_LAWA-1.pdf | Yes |  | Uploads\190a7bb0-bdfc-49cb-959d-be5ac42748d8.pdf | Exist
Atikah | Yes | 7C573873-20BD-4ABA-AAED-DA7B7FB95301 | BBFAD6CB-DB51-454C-8A31-9E0F24353A1D | LAWA-1 | C43E4F76-2DF6-4531-A914-D5BA6B4A9C94 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3LAWAWS01_LAWA-1.pdf | SBO3LAWAWS01_LAWA-1.pdf | Yes |  | Uploads\c43e4f76-2df6-4531-a914-d5ba6b4a9c94.pdf | Exist
Atikah | Yes | 434C4631-405E-48AE-B007-CAC21D789D33 | 359DC7E7-991D-4E39-B20C-9E81E9E7CB40 | S-CN1-P11 | 0DE11EE9-20B4-4AE2-90AD-473E7DD8F37F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-K-56-DNC-RP-0002-00_S-CNI-P11 EOWR.pdf | MY-K-56-DNC-RP-0002-00_S-CNI-P11 EOWR.pdf | Yes |  | Uploads\0de11ee9-20b4-4ae2-90ad-473e7dd8f37f.pdf | Exist
Atikah | Yes | 658D1AEF-7098-4DF8-A69E-217D3A2A5D24 | 359DC7E7-991D-4E39-B20C-9E81E9E7CB40 | S-CN1-P11 | 08BF25C5-2F4B-4D96-BBB7-88046362124B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf | Yes |  | Uploads\08bf25c5-2f4b-4d96-bbb7-88046362124b.pdf | Exist
Atikah | Yes | 8C31A32D-F091-4EFF-A387-B07B191A36C1 | C8EC4463-E6A7-42A3-AB65-9EA8F40F0ECA | BN-83 | 8980DC6D-7882-4AF2-91BA-01C88BCBBC2C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BN83 Suspended for Re-Entry.pdf | FWR BN83 Suspended for Re-Entry.pdf | Yes |  | Uploads\8980dc6d-7882-4af2-91ba-01c88bcbbc2c.pdf | Exist
Atikah | Yes | DFA8EB96-C0B6-4B90-868C-E802479E70C7 | C8EC4463-E6A7-42A3-AB65-9EA8F40F0ECA | BN-83 | 3F7B7EC5-CFDE-45F1-81E3-E8BB6B920BE7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-83_Internal- New revisedf.pdf | NOOP BN-83_Internal- New revisedf.pdf | Yes |  | Uploads\3f7b7ec5-cfde-45f1-81e3-e8bb6b920be7.pdf | Exist
Atikah | Yes | 67E925D1-D715-4EB0-947A-CFABF3D953D4 | F48CDBC8-5E99-46AA-A0C3-9ED5835273BC | BAYAN-C315 | 0686AB94-B02A-4212-8931-83CB1185F94B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-315 Final Well Report - Signed.pdf | BY-315 Final Well Report - Signed.pdf | Yes |  | Uploads\0686ab94-b02a-4212-8931-83cb1185f94b.pdf | Exist
Atikah | Yes | 16A3036E-02DC-46B5-925E-2F5DE39173A5 | F48CDBC8-5E99-46AA-A0C3-9ED5835273BC | BAYAN-C315 | 576B1D87-D888-4DE8-AA50-D6A3F2466C2F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-315 R-1 Notice of Operations_APPROVED.pdf | BY-315 R-1 Notice of Operations_APPROVED.pdf | Yes |  | Uploads\576b1d87-d888-4de8-aa50-d6a3f2466c2f.pdf | Exist
Atikah | Yes | 9E5DD0DA-4475-4BAE-B8EE-937E3CB47C09 | 11B7262E-0B3E-4CC6-99D3-9EFA9877E358 | BUNGA KESUMBA A-3(C) | 838DB85D-92C8-4718-9E5B-C6FE4551CD15 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Kesumba A-3 (C)_Final.pdf | NOOP Kesumba A-3 (C)_Final.pdf | Yes |  | Uploads\838db85d-92c8-4718-9e5b-c6fe4551cd15.pdf | Exist
Atikah | Yes | 3BCB2376-ECBE-4BBC-A6FD-C88A4155C5CD | 11B7262E-0B3E-4CC6-99D3-9EFA9877E358 | BUNGA KESUMBA A-3(C) | DFDCB917-4016-4524-863C-D4FCA653275D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | B.Kesumba A-3_ Rev0_05072017 - PETRONAS SUBMISSION_FINAL.pdf | B.Kesumba A-3_ Rev0_05072017 - PETRONAS SUBMISSION_FINAL.pdf | Yes |  | Uploads\dfdcb917-4016-4524-863c-d4fca653275d.pdf | Exist
Atikah | Yes | 0D102821-1524-42E1-B43C-9A3E358F5586 | D03EEDED-4346-45D2-904A-9F3D21B0ADDE | TE-82 | 7302DFD1-8F0D-4F53-B179-A1D5F337F870 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TE-82 FWR Compiled.pdf | TE-82 FWR Compiled.pdf | Yes |  | Uploads\7302dfd1-8f0d-4f53-b179-a1d5f337f870.pdf | Exist
Atikah | Yes | 0D15708E-DCA7-497E-885B-281FA47D4A33 | D03EEDED-4346-45D2-904A-9F3D21B0ADDE | TE-82 | 760C7D10-A4DA-43DA-A824-5524C36BFEAB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temana EMP 1.0 TE-82 NOOP Final (1).pdf | Temana EMP 1.0 TE-82 NOOP Final (1).pdf | Yes |  | Uploads\760c7d10-a4da-43da-a824-5524c36bfeab.pdf | Exist
Atikah | Yes | F2E68BB7-34D4-4064-BDCC-42A29A7A2C5C | 94F9EA1C-3F37-48CC-A9F3-9F5CA9C58AB1 | SF30-4 | B2E67C0B-1602-4E8C-9091-C33209F52656 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-4 EOWR_FINAL - MPM Drilling.pdf | SF30-4 EOWR_FINAL - MPM Drilling.pdf | Yes |  | Uploads\b2e67c0b-1602-4e8c-9091-c33209f52656.pdf | Exist
Atikah | Yes | 46002732-15F5-4C09-B2A9-35980BCD3BB3 | 94F9EA1C-3F37-48CC-A9F3-9F5CA9C58AB1 | SF30-4 | A4BBE05D-EB05-4710-9298-4A1CE5D9CACD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-4 NOOP - MPM Well Management.pdf | SF30-4 NOOP - MPM Well Management.pdf | Yes |  | Uploads\a4bbe05d-eb05-4710-9298-4a1ce5d9cacd.pdf | Exist
Atikah | Yes | FFEEFAB0-458B-40D3-A469-AA5B805FE979 | 64DE40E1-E945-4B29-A1F0-9FA16D55EEC6 | PRPA-04 | 6DDEAEB5-EEBD-41C3-AA0F-24542F855B93 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-04 EOWR.pdf | PRPA-04 EOWR.pdf | Yes |  | Uploads\6ddeaeb5-eebd-41c3-aa0f-24542f855b93.pdf | Exist
Atikah | Yes | 5CFDC385-D702-4AF2-8A4D-FD2F4FCF6E7F | 64DE40E1-E945-4B29-A1F0-9FA16D55EEC6 | PRPA-04 | 8AE58DE7-234F-4207-B54B-3491A15342A7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf | Yes |  | Uploads\8ae58de7-234f-4207-b54b-3491a15342a7.pdf | Exist
Atikah | Yes | 99120D01-68D5-4BBE-9F3D-FDDCF9F158DC | DF900C03-1E4F-419D-8847-9FCFF83D3EC4 | D35A-107ST1 | E01FC9F8-82C0-4650-9678-3D5976B21D6F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPA-107ST1 End Of Well Report Final.pdf | D35DPA-107ST1 End Of Well Report Final.pdf | Yes |  | Uploads\e01fc9f8-82c0-4650-9678-3d5976b21d6f.pdf | Exist
Atikah | Yes | B50FD610-AF0E-463F-9C08-D0DBBAA7E10C | DF900C03-1E4F-419D-8847-9FCFF83D3EC4 | D35A-107ST1 | D7BE2B20-4497-4FE3-A073-801984EA24D8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35A-107ST1 NOOP_Rev1.pdf | D35A-107ST1 NOOP_Rev1.pdf | Yes |  | Uploads\d7be2b20-4497-4fe3-a073-801984ea24d8.pdf | Exist
Atikah | Yes | 5E811928-ED5E-44AE-B9FC-71C3B7F06AE8 | 6AC131B8-4FD3-4575-AFC3-9FE98FB9D617 | BESAR-A3 | F2A4A06F-A77E-4A2A-B084-E1A68ADEFF04 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Besar-A3.pdf | FWR Besar-A3.pdf | Yes |  | Uploads\f2a4a06f-a77e-4a2a-b084-e1a68adeff04.pdf | Exist
Atikah | Yes | D9891721-2E21-493C-8BBF-4DFD76823A53 | 6AC131B8-4FD3-4575-AFC3-9FE98FB9D617 | BESAR-A3 | A13C97C0-21ED-49CA-88B0-1E296EA15557 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Besar-A3.pdf | NOOP Besar-A3.pdf | Yes |  | Uploads\a13c97c0-21ed-49ca-88b0-1e296ea15557.pdf | Exist
Atikah | Yes | A216CE17-E3BE-44B4-987D-18A61EBD1615 | CC99ECE0-94D3-488D-B2D6-A039721490B9 | SEPAT A-02 | E991968C-2681-4BC1-AB14-F2A3593A221D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL34_SEPAT A-02_PCSB_NOOP.pdf | PMO3SPATGL34_SEPAT A-02_PCSB_NOOP.pdf | Yes |  | Uploads\e991968c-2681-4bc1-ab14-f2a3593a221d.pdf | Exist
Atikah | Yes | 234CF6AA-135B-4A32-9118-B3C48799117E | CC99ECE0-94D3-488D-B2D6-A039721490B9 | SEPAT A-02 | 0ED54C39-8D5A-4EA3-BD01-F06DC14AF21A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATWS74_SEPAT-A02_PCSB_FWR.pdf | PMO3SPATWS74_SEPAT-A02_PCSB_FWR.pdf | Yes |  | Uploads\0ed54c39-8d5a-4ea3-bd01-f06dc14af21a.pdf | Exist
Atikah | Yes | 19A59577-CD7C-4DD9-AB39-90B5254A50B8 | C93E097E-31C2-4777-A301-A050EF021781 | PRPA-12 | 3AE8EDCE-1179-46E7-9A3F-CA63AF29F872 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PERMAS Revisit 1 PHASE 1 NOOP_Rev 1 (1)_PRPA-10-11-12.pdf | PERMAS Revisit 1 PHASE 1 NOOP_Rev 1 (1).pdf | No |  | Uploads\3ae8edce-1179-46e7-9a3f-ca63af29f872.pdf | Exist
Atikah | Yes | 27B22E77-C442-44EB-964C-8658006737F5 | C93E097E-31C2-4777-A301-A050EF021781 | PRPA-12 | 2A64EBB6-E4AF-43C7-8297-D14BA1B84FFF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-12 EOWR.pdf | PRPA-12 EOWR.pdf | Yes |  | Uploads\2a64ebb6-e4af-43c7-8297-d14ba1b84fff.pdf | Exist
Atikah | Yes | 8B7F0949-69CC-4003-93BA-7B8B0B076683 | C76F9619-41FC-4C7A-9FE2-A087E8AB9F60 | BAKAU-A09 | 8C5BEA5F-349D-449D-A246-407DEC5691A9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAKAU-A09 NOOP.pdf | BAKAU-A09 NOOP.pdf | Yes |  | Uploads\8c5bea5f-349d-449d-a246-407dec5691a9.pdf | Exist
Atikah | Yes | FC535454-47F8-49C6-8872-0CEBB57A4237 | C76F9619-41FC-4C7A-9FE2-A087E8AB9F60 | BAKAU-A09 | 9866B132-E61B-45A3-A637-C22B8CF41669 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAKAU-A09 FINAL WELL REPORT (Split).pdf | BAKAU-A09 FINAL WELL REPORT (Split).pdf | Yes |  | Uploads\9866b132-e61b-45a3-a637-c22b8cf41669.pdf | Exist
Atikah | Yes | BA7410BB-0D41-46D5-8F1D-4D5B561D2DFE | 7755418F-ACC3-45AD-AD8B-A0C188F2DE9A | SASA-01 | 79065E7A-9AC9-4165-A18B-373733C6C961 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf | Yes |  | Uploads\79065e7a-9ac9-4165-a18b-373733c6c961.pdf | Exist
Atikah | Yes | F6765781-D578-473A-8DC1-AC4CED686A1E | 7755418F-ACC3-45AD-AD8B-A0C188F2DE9A | SASA-01 | 9F417255-B814-45DE-89C0-A6E6116D81F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf | SASA Infill Campaign EOWR.pdf | Yes |  | Uploads\9f417255-b814-45de-89c0-a6e6116d81f4.pdf | Exist
Atikah | Yes | 22510B12-FC74-47BB-8181-0FA16BF7C5A5 | D075466C-2F9B-45F1-920F-A0C4BF5DB1F8 | BAYAN-B224 | 61DE8416-A5A9-4EFE-B625-822973F946BB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-224 Final Well Report_Bayan Redevelopment Project.pdf | BY-224 Final Well Report_Bayan Redevelopment Project.pdf | Yes |  | Uploads\61de8416-a5a9-4efe-b625-822973f946bb.pdf | Exist
Atikah | Yes | AC01D799-551D-42E0-BA6B-2137F1220C73 | D075466C-2F9B-45F1-920F-A0C4BF5DB1F8 | BAYAN-B224 | 176F8501-CA92-4FCE-A3EE-CFB056F04DE5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-224 Notice of Operations_APPROVED (controlled copy).pdf | BY-224 Notice of Operations_APPROVED (controlled copy).pdf | Yes |  | Uploads\176f8501-ca92-4fce-a3ee-cfb056f04de5.pdf | Exist
Atikah | Yes | CB593792-90DB-47F1-8CBE-996CE74C372A | E4B3672E-B181-408A-B3F8-A0D36044946D | BRWA-16ST1 | EA17367B-B5F5-40F2-B932-A3A9B1AB7DC5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BRWA16ST1.pdf | NOOP BRWA16ST1.pdf | Yes |  | Uploads\ea17367b-b5f5-40f2-b932-a3a9b1ab7dc5.pdf | Exist
Atikah | Yes | 54FA8C3A-67A2-462D-AA87-E210D5F3A752 | E4B3672E-B181-408A-B3F8-A0D36044946D | BRWA-16ST1 | 289DA23A-B424-4DF7-AD72-12C7784EEED3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | VPSB-BEF3-DRL-WWR-0001 BRWA-16ST1 Final Well Report Rev.1.pdf | VPSB-BEF3-DRL-WWR-0001 BRWA-16ST1 Final Well Report Rev.1.pdf | Yes |  | Uploads\289da23a-b424-4df7-ad72-12c7784eeed3.pdf | Exist
Atikah | Yes | BE48070E-E6DC-4E7A-9465-F80F7F8B430A | AC5D920A-9E8A-4AD3-A575-A0DB93D9FB5A | TABU-B11 ST1 | 66630785-BD88-4EFC-B8C8-D4B02B615496 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B11ST1 Final Well Report 1 of 2.pdf | Tabu B11ST1 Final Well Report 1 of 2.pdf | Yes |  | Uploads\66630785-bd88-4efc-b8c8-d4b02b615496.pdf | Exist
Atikah | Yes | 05311DCB-6F26-488D-BA49-F58BCED58EA8 | AC5D920A-9E8A-4AD3-A575-A0DB93D9FB5A | TABU-B11 ST1 | B9CEF52F-71C7-41BD-82DF-ED885F868B51 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B11ST1 Slot 4 NOOP v0.pdf | Tabu B11ST1 Slot 4 NOOP v0.pdf | Yes |  | Uploads\b9cef52f-71c7-41bd-82df-ed885f868b51.pdf | Exist
Atikah | Yes | 60DFA87B-E7B7-4CBE-897F-F5780726DC7B | 8EA0961E-2F25-4F28-B177-A12B67418237 | JERUN-A4 | 86524255-BBFD-448B-8CF9-8DD6C5CA4D83 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Jerun-A4 Final Well Report_Final.pdf | SK408 Jerun-A4 Final Well Report_Final.pdf | Yes |  | Uploads\86524255-bbfd-448b-8cf9-8dd6c5ca4d83.pdf | Exist
Atikah | Yes | EEFF8588-A841-42D5-9BA1-91D52050D4FB | 8EA0961E-2F25-4F28-B177-A12B67418237 | JERUN-A4 | 3DDF4B38-1B4D-4435-A194-39E31B09E9D0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\3ddf4b38-1b4d-4435-a194-39e31b09e9d0.pdf | Exist
Atikah | Yes | 9E28ACE6-DF73-41F5-841A-A740414F0B47 | 63A758C6-5695-4EE4-BD82-A1BD36B6A411 | KN-B2 | D8BBB7F9-5326-476C-90A9-C2029DE9E0BF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS2X_KN-B2_PCSB_FWR.pdf | SBO3KNBLWS2X_KN-B2_PCSB_FWR.pdf | Yes |  | Uploads\d8bbb7f9-5326-476c-90a9-c2029de9e0bf.pdf | Exist
Atikah | Yes | 2AB94D93-4748-482E-A2FF-3A3F73CD9195 | 63A758C6-5695-4EE4-BD82-A1BD36B6A411 | KN-B2 | C910BF5A-40AD-43EC-BF58-4DE834DDAF52 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLGL51_KN-B2_PCSB_NOOP.pdf | SBO3KNBLGL51_KN-B2_PCSB_NOOP.pdf | Yes |  | Uploads\c910bf5a-40ad-43ec-bf58-4de834ddaf52.pdf | Exist
Atikah | Yes | 6D0B2520-3CFE-440C-8630-30E4EB50C063 | C98184A8-1319-4625-886D-A259B1C299E7 | BUNGA ANGGERIK A-5(B)ST1 | 2C6904B2-3F15-4029-86E3-3772F5A88D22 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BAA5B_FINAL.pdf | NOOP - BAA5B_FINAL.pdf | Yes |  | Uploads\2c6904b2-3f15-4029-86e3-3772f5a88d22.pdf | Exist
Atikah | Yes | 5901713F-4867-4EF4-B77E-060AE7064DD3 | C98184A8-1319-4625-886D-A259B1C299E7 | BUNGA ANGGERIK A-5(B)ST1 | 78FF02F6-2954-4B75-899D-D59A19992353 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Anggerik A-5B.pdf | EOWR_Bunga Anggerik A-5B.pdf | Yes |  | Uploads\78ff02f6-2954-4b75-899d-d59a19992353.pdf | Exist
Atikah | Yes | 64B9E74D-93B7-4F7A-B241-496F846B75BC | 6F555321-F19F-4B11-92F0-A271DC65FBC5 | MLK-111 | F6A759A0-3E52-4248-8953-2B60EF3E2EAF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-111 Pink West OP - NOOP v2.pdf | MLK-111 Pink West OP - NOOP v2.pdf | Yes |  | Uploads\f6a759a0-3e52-4248-8953-2b60ef3e2eaf.pdf | Missing
Atikah | Yes | 18EDCE1B-25E0-4AA0-92C9-7FEAC3E69533 | 6F555321-F19F-4B11-92F0-A271DC65FBC5 | MLK-111 | B5076675-9392-4057-985B-4C82DC509B60 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-111 FINAL.pdf | EOWR Malikai-111 FINAL.pdf | Yes |  | Uploads\b5076675-9392-4057-985b-4c82dc509b60.pdf | Missing
Atikah | Yes | 5CAF6DC9-364B-40FC-BB9B-4CA3F5FADA26 | A5C63C75-97B0-407F-90A7-A2830A7F5F57 | IRONG-7 | 8725204A-E9D2-40F1-8CBB-57E921915D89 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Irong-7 Appraisal to MPM.pdf | EOWR Irong-7 Appraisal to MPM.pdf | Yes |  | Uploads\8725204a-e9d2-40f1-8cbb-57e921915d89.pdf | Exist
Atikah | Yes | C1FD9296-FAB0-40D3-A2EC-B881CB72AB38 | A5C63C75-97B0-407F-90A7-A2830A7F5F57 | IRONG-7 | AB46E887-1581-441B-ABAC-4237F549290F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Irong-7 Appraisal.pdf | NOOP Irong-7 Appraisal.pdf | Yes |  | Uploads\ab46e887-1581-441b-abac-4237f549290f.pdf | Exist
Atikah | Yes | 1433E505-2203-490A-9EA6-053EA80C436D | A0D52006-C35C-4A00-8E51-A2997253C54F | KUANG NORTH-3 | CCC5007B-A41B-42D4-9522-E28117687671 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KN-3 NOOP INTERNAL_130115_rev1.pdf | KN-3 NOOP INTERNAL_130115_rev1.pdf | Yes |  | Uploads\ccc5007b-a41b-42d4-9522-e28117687671.pdf | Exist
Atikah | Yes | A15FD1FF-E7CD-47DB-814C-7027853984AD | A0D52006-C35C-4A00-8E51-A2997253C54F | KUANG NORTH-3 | 8CDF98F0-A8F4-4F01-AF92-81E46534513B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KNGNWS18_KUANG NORTH-3_FWR_PCSB.pdf | SKO3KNGNWS18_KUANG NORTH-3_FWR_PCSB.pdf | Yes |  | Uploads\8cdf98f0-a8f4-4f01-af92-81e46534513b.pdf | Exist
Atikah | Yes | 30D4F5F1-6D38-49C4-BA7D-6F34C69518A5 | 174B4235-EFF0-4265-A3D5-A3108CC92F65 | MENGKUANG-1 | A18647AA-6E45-4B9D-BCE1-090202F37E57 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MKUAGL02_MENGKUANG_1_2016.pdf | PMO3MKUAGL02_MENGKUANG_1_2016.pdf | Yes |  | Uploads\a18647aa-6e45-4b9d-bce1-090202f37e57.pdf | Exist
Atikah | Yes | 5A057F70-CA38-4A74-B903-E5C0B27FDFFD | 174B4235-EFF0-4265-A3D5-A3108CC92F65 | MENGKUANG-1 | 08FCF022-0D60-45CB-A88A-E83BD9681F7E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mengkuang-1_NOOP.pdf | Mengkuang-1_NOOP.pdf | Yes |  | Uploads\08fcf022-0d60-45cb-a88a-e83bd9681f7e.pdf | Exist
Atikah | Yes | 40125A67-46C3-4858-8EF7-FD87BB408AF6 | E21A796B-A0B9-4E74-8AF7-A39A739FD9F7 | DOKONG-1 | FBBD737F-E12E-4528-86D8-CBA489156A4D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dokong-1 End of Well Report.pdf | Dokong-1 End of Well Report.pdf | Yes |  | Uploads\fbbd737f-e12e-4528-86d8-cba489156a4d.pdf | Exist
Atikah | Yes | 60BD1E9D-33BE-493C-AC8F-BBEBDAE24864 | E21A796B-A0B9-4E74-8AF7-A39A739FD9F7 | DOKONG-1 | D7ADAB6C-7953-4E5A-8B92-F741751EB4A4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DOKONG-1_NOOP.pdf | DOKONG-1_NOOP.pdf | Yes |  | Uploads\d7adab6c-7953-4e5a-8b92-f741751eb4a4.pdf | Exist
Atikah | Yes | 71D52B66-956B-4F97-944F-C5D0DD375DEC | F5C90137-0E5A-4835-898C-A3C6907EFE0D | TABU-B19 ST1 | A4B8C552-9506-4852-8282-C50617F06AEF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B-19ST1 FWR - Final PETRONAS_opt.pdf | Tabu B-19ST1 FWR - Final PETRONAS_opt.pdf | Yes |  | Uploads\a4b8c552-9506-4852-8282-c50617f06aef.pdf | Exist
Atikah | Yes | F7B8C9FB-22D0-4367-B7BF-31BE6F157519 | F5C90137-0E5A-4835-898C-A3C6907EFE0D | TABU-B19 ST1 | 9418DE7D-C70B-4DAC-B325-84622C892869 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu B19ST1 Slot 27 NOOP v0.pdf | Tabu B19ST1 Slot 27 NOOP v0.pdf | Yes |  | Uploads\9418de7d-c70b-4dac-b325-84622c892869.pdf | Exist
Atikah | Yes | C567DCD1-B4D3-4518-B21D-81D96320C91D | 93CC83FF-8396-4F68-AC70-A3E6CA19C755 | KNDW-D03 | 7008124B-ABE0-450C-BB53-CC4212324E49 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW-D03 ST1.pdf | EOWR KNDW-D03 ST1.pdf | Yes |  | Uploads\7008124b-abe0-450c-bb53-cc4212324e49.pdf | Exist
Atikah | Yes | C7BD9C88-2EBD-456E-9B30-75147E33E9EA | 93CC83FF-8396-4F68-AC70-A3E6CA19C755 | KNDW-D03 | BDCA0379-0196-4DBE-9D36-00790A16CF74 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D03 ST1 NOOP_REV1_Signed.pdf | KNDW-D03 ST1 NOOP_REV1_Signed.pdf | Yes |  | Uploads\bdca0379-0196-4dbe-9d36-00790a16cf74.pdf | Exist
Atikah | Yes | D018E44D-E3DC-43A3-84ED-7F45CE73DFD5 | CDE8F4B3-2EB9-4F3F-A262-A44B5277AB33 | S-CN1-W4 | AFA22D10-8DB3-426C-A73B-FA1074328C12 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR13_S_CN1_W4.pdf | SBO3SKNPDR13_S_CN1_W4.pdf | Yes |  | Uploads\afa22d10-8db3-426c-a73b-fa1074328c12.pdf | Exist
Atikah | Yes | 7DCECAAF-357D-4E3B-9886-64413F08722F | CDE8F4B3-2EB9-4F3F-A262-A44B5277AB33 | S-CN1-W4 | 1EED9F27-F755-40F9-B767-24A2F7AEA3FA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPWSA4_S_CN1_W4.pdf | SBO3SKNPWSA4_S_CN1_W4.pdf | Yes |  | Uploads\1eed9f27-f755-40f9-b767-24a2f7aea3fa.pdf | Exist
Atikah | Yes | EDD0DAB4-5395-4DC9-A691-A101C3AED1B2 | B2F74EAA-36FF-4AD1-96EF-A4D57DB1AB1E | KACAK-1 | 3FA50EA1-BE88-4D48-91BC-DE65F9509066 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kacak-1 Final Well Report Final.pdf | Kacak-1 Final Well Report Final.pdf | Yes |  | Uploads\3fa50ea1-be88-4d48-91bc-de65f9509066.pdf | Exist
Atikah | Yes | 6E9D301F-B62F-4C67-8593-5A78E5FFC1CE | B2F74EAA-36FF-4AD1-96EF-A4D57DB1AB1E | KACAK-1 | 37519D98-F840-4804-9E77-5F407BB2A7A1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Kacak-1 Internal.pdf | NOOP - Kacak-1 Internal.pdf | Yes |  | Uploads\37519d98-f840-4804-9e77-5f407bb2a7a1.pdf | Exist
Atikah | Yes | 168618BC-563C-473E-B5D9-4E4127275550 | E7C4EA89-BC82-4F73-A30C-A5123D6407A9 | JERANGAU-1 | 729C73EC-AD2F-43B4-9C02-7A43065FFBF2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jerangau-1 NOOP_FINAL.pdf | Jerangau-1 NOOP_FINAL.pdf | Yes |  | Uploads\729c73ec-ad2f-43b4-9c02-7a43065ffbf2.pdf | Exist
Atikah | Yes | 59D4C086-A25F-4781-B1F1-BC5F80C4C131 | E7C4EA89-BC82-4F73-A30C-A5123D6407A9 | JERANGAU-1 | 1F36FB5F-393B-4010-80E8-E89D15F32930 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jerangau-1 End of Well Report (FINAL).pdf | Jerangau-1 End of Well Report (FINAL).pdf | Yes |  | Uploads\1f36fb5f-393b-4010-80e8-e89d15f32930.pdf | Exist
Atikah | Yes | 5DF60444-EA59-413D-BAD9-475B373A86D0 | F735AAB8-6392-49AB-AC8B-A5181A5D9A71 | BUNGA ZETUNG A-2 (B) | D4003DA8-5E2B-4376-9A5B-F3DD0BF3088D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BZA_Rev0_Final.pdf | NOOP - BZA_Rev0_Final.pdf | Yes |  | Uploads\d4003da8-5e2b-4376-9a5b-f3dd0bf3088d.pdf | Exist
Atikah | Yes | CB3D16C4-D22C-4522-8BC0-69FDFCF28D8C | F735AAB8-6392-49AB-AC8B-A5181A5D9A71 | BUNGA ZETUNG A-2 (B) | 761DDB84-258A-4BC2-88BD-71CD73D24A25 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NMB-DRI-RPT-01167.pdf | NMB-DRI-RPT-01167.pdf | Yes |  | Uploads\761ddb84-258a-4bc2-88bd-71cd73d24a25.pdf | Exist
Atikah | Yes | 154AFACE-532D-4180-A3E2-3BFD41929524 | FBBE77AF-2E0C-4109-A8A2-A53D684A6017 | LIMBAYONG-3 | D8DDF09F-A356-4715-B712-CA61CC09EE66 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LIMBAYONG 3 NOOP .pdf | LIMBAYONG 3 NOOP .pdf | Yes |  | Uploads\d8ddf09f-a356-4715-b712-ca61cc09ee66.pdf | Exist
Atikah | Yes | 9181B892-37E1-4E08-AE02-19995721DDC9 | FBBE77AF-2E0C-4109-A8A2-A53D684A6017 | LIMBAYONG-3 | 47BF3CC5-E92D-4F4E-95BA-A9FC3C3445E4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3LIBYWS09_LIMBAYONG-3_PCSB_FWR.pdf | SBO3LIBYWS09_LIMBAYONG-3_PCSB_FWR.pdf | Yes |  | Uploads\47bf3cc5-e92d-4f4e-95ba-a9fc3c3445e4.pdf | Exist
Atikah | Yes | C5ACE51B-0F82-4724-A22D-2A68A4A7C080 | 587B2FD8-2F9E-427C-9494-A5481693811B | SASA-07 | E6662A4A-DEDB-49FD-9EA6-F52FBA497F0F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf | Yes |  | Uploads\e6662a4a-dedb-49fd-9ea6-f52fba497f0f.pdf | Exist
Atikah | Yes | 4933B097-7B22-40D6-B0E8-91D396627888 | 587B2FD8-2F9E-427C-9494-A5481693811B | SASA-07 | 747E045C-0683-46C0-9A89-C38BFDF385B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf | SASA Infill Campaign EOWR.pdf | Yes |  | Uploads\747e045c-0683-46c0-9a89-c38bfdf385b7.pdf | Exist
Atikah | Yes | 4E59D674-DDB1-4245-A570-2351AAE61759 | 6C9C6125-E5E8-4355-9A9D-A56828AFF396 | S-CN1-P14 | B831EC08-BFCB-4B51-8C7C-FD3D5326A3A9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf |  | No |  | Uploads\b831ec08-bfcb-4b51-8c7c-fd3d5326a3a9.pdf | Exist
Atikah | Yes | 2409723A-BACF-484A-BCCF-3CCD6F340295 | 6C9C6125-E5E8-4355-9A9D-A56828AFF396 | S-CN1-P14 | E0B4FB7C-ED37-4A64-B383-ACE7FEA3AC1A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-K-56-DNC-RP-0003-00_S-CNI-P14ST1 EOWR.pdf | MY-K-56-DNC-RP-0003-00_S-CNI-P14ST1 EOWR.pdf | Yes |  | Uploads\e0b4fb7c-ed37-4a64-b383-ace7fea3ac1a.pdf | Exist
Atikah | Yes | 3F212245-C153-40F4-97E8-4239C8AF2A32 | 09D798EC-A3C4-462A-B22F-A5C2A6338797 | BUNGA ANGGERIK A-1(D) | 7E4DD32D-E030-4B62-A916-BC7BD6F58237 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Anggerik A-1D FINAL.pdf | EOWR_Bunga Anggerik A-1D FINAL.pdf | Yes |  | Uploads\7e4dd32d-e030-4b62-a916-bc7bd6f58237.pdf | Exist
Atikah | Yes | E93C7913-5342-401D-8E98-9E134AB7C030 | 09D798EC-A3C4-462A-B22F-A5C2A6338797 | BUNGA ANGGERIK A-1(D) | C63EBBB0-4ADF-472F-B168-4D92CB8DFD08 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BAA_SxS_Rev0.pdf | NOOP - BAA_SxS_Rev0.pdf | Yes |  | Uploads\c63ebbb0-4adf-472f-b168-4d92cb8dfd08.pdf | Exist
Atikah | Yes | 8CFFC9B2-03CE-4B2B-9776-967B36B4D9C7 | 5FE9C3DA-D9F0-47E6-8736-A6B61F4D641B | ANGSI-B20ST1 | A4486D27-4182-4EC3-9DAB-8A8B66A332EA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWSA4_ANGSI-B20ST1.pdf | PMO3ANSIWSA4_ANGSI-B20ST1.pdf | Yes |  | Uploads\a4486d27-4182-4ec3-9dab-8a8b66a332ea.pdf | Exist
Atikah | Yes | 993CB17E-DFD2-45E1-A345-BE497B329730 | 5FE9C3DA-D9F0-47E6-8736-A6B61F4D641B | ANGSI-B20ST1 | 4B9B11A0-D518-4529-A08C-3AA17E1A0A6B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ANGSI-B20ST1 FWR.pdf | ANGSI-B20ST1 FWR.pdf | Yes |  | Uploads\4b9b11a0-d518-4529-a08c-3aa17e1a0a6b.pdf | Exist
Atikah | Yes | 8ABED109-9E1A-4CEE-99D3-F88088CF6D05 | 247CB815-E3A6-44D7-80D0-A6C5B4293B21 | D18-403 | 256D13EA-6253-40BA-94C2-FF43BED904DD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 403 ST1 FWR.pdf | D18 403 ST1 FWR.pdf | Yes |  | Uploads\256d13ea-6253-40ba-94c2-ff43bed904dd.pdf | Exist
Atikah | Yes | A1D9F5AF-D48E-4915-A70F-0BA56FFE73CC | 247CB815-E3A6-44D7-80D0-A6C5B4293B21 | D18-403 | FD005F2C-8010-4472-B254-C203C43220DA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-403 NOOP.pdf | D18-403 NOOP.pdf | Yes |  | Uploads\fd005f2c-8010-4472-b254-c203c43220da.pdf | Exist
Atikah | Yes | 0DF08265-8FCB-4889-A389-5A9C3371798E | D4405BE2-5C19-4C5C-89B2-A74470309E31 | SF MERAH-1 | 5DC0FB0F-CC2E-41E2-9259-F25086274D39 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF Merah-1 EOWR_MPM_Drilling.pdf | SF Merah-1 EOWR_MPM_Drilling.pdf | Yes |  | Uploads\5dc0fb0f-cc2e-41e2-9259-f25086274d39.pdf | Exist
Atikah | Yes | C7DD9794-A445-492B-BBB5-F543C9BED618 | D4405BE2-5C19-4C5C-89B2-A74470309E31 | SF MERAH-1 | 7BD1A351-BC30-4631-AFC8-3AE7D876E0C9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF MERAH NOOP_FINAL.pdf | SF MERAH NOOP_FINAL.pdf | Yes |  | Uploads\7bd1a351-bc30-4631-afc8-3ae7d876e0c9.pdf | Exist
Atikah | Yes | 64BC1B4D-8332-45FF-83A5-D680B663CB52 | 1C6647FE-51C0-4947-935D-A764F1E8CDBD | SAPA-11 | 6F3588ED-3857-485F-AB27-A33D42564457 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-11 EOWR.pdf | SAPA-11 EOWR.pdf | Yes |  | Uploads\6f3588ed-3857-485f-ab27-a33d42564457.pdf | Exist
Atikah | Yes | 8AEFB70E-31BE-4D25-8D5E-15DA0BA8C0AF | 1C6647FE-51C0-4947-935D-A764F1E8CDBD | SAPA-11 | 4DBC9459-5B9A-477D-85A6-D89448F59D89 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SK311 South Acis (SAPA) Revisit I Phase II.pdf | NOOP SK311 South Acis (SAPA) Revisit I Phase II.pdf | Yes |  | Uploads\4dbc9459-5b9a-477d-85a6-d89448f59d89.pdf | Exist
Atikah | Yes | 08DF3197-2B88-4FB2-94F0-1A4AEE1C82D6 | 7ACBF05D-0119-404C-9653-A7F67F084246 | BOKOR-E505 | 525BF7BA-DFFB-4D2D-97CC-3E3060B3CD3E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR-E505.pdf | FWR BOKOR-E505.pdf | Yes |  | Uploads\525bf7ba-dffb-4d2d-97cc-3e3060b3cd3e.pdf | Exist
Atikah | Yes | B67E3D0F-9A4D-4BEF-8CB5-7409D0DE7EFE | 7ACBF05D-0119-404C-9653-A7F67F084246 | BOKOR-E505 | 1944E624-0FDC-443F-A22F-3C64DA516380 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BO-505 FINAL_Rev_04_MSD_approved by AAR.pdf | NOOP BO-505 FINAL_Rev_04_MSD_approved by AAR.pdf | Yes |  | Uploads\1944e624-0fdc-443f-a22f-3c64da516380.pdf | Exist
Atikah | Yes | 1849D3F9-D930-4491-A164-8C65CFA75693 | 9B5F5311-03FC-42DF-8F68-A8116FCA616A | CD-B02ST2 | 1CB90EFC-213E-41F0-B30F-3B6D00C3695D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-B02ST2 Final Drilling and Completion Report .pdf | CD-B02ST2 Final Drilling and Completion Report .pdf | Yes |  | Uploads\1cb90efc-213e-41f0-b30f-3b6d00c3695d.pdf | Exist
Atikah | Yes | 7DCED1FB-7D65-46ED-AAF2-AA963373F0F8 | 9B5F5311-03FC-42DF-8F68-A8116FCA616A | CD-B02ST2 | 1B1A9FA3-53B7-435C-B2EE-B67AD8A759B8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-B02ST2 (Slot 8a CDW-B Platform) Rev.00 CP2-GEN-D-0003_ NOOP - WELL rev.00.pdf | CD-B02ST2 (Slot 8a CDW-B Platform) Rev.00 CP2-GEN-D-0003_ NOOP - WELL rev.00.pdf | Yes |  | Uploads\1b1a9fa3-53b7-435c-b2ee-b67ad8a759b8.pdf | Exist
Atikah | Yes | C9A8C732-09DB-4862-A242-A55BE999F33D | 017BAB10-0B5D-4229-B6E0-A823032231EC | BAYAN-223 | 1097D068-D291-4691-8D8B-8E17EECDB452 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAYAN-223ST1 FWR.pdf | BAYAN-223ST1 FWR.pdf | Yes |  | Uploads\1097d068-d291-4691-8d8b-8e17eecdb452.pdf | Exist
Atikah | Yes | 444E0983-A214-4967-A04D-4357A00AF4E9 | 017BAB10-0B5D-4229-B6E0-A823032231EC | BAYAN-223 | DA574FB7-A9A9-4DBA-9A92-6F5F86D9363A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BYANWSH2_BAYAN-223_PCSB_NOOP.pdf | SKO3BYANWSH2_BAYAN-223_PCSB_NOOP.pdf | Yes |  | Uploads\da574fb7-a9a9-4dba-9a92-6f5f86d9363a.pdf | Exist
Atikah | Yes | 14D2381E-B42C-40FA-84FC-9BD47EBBB102 | FA55664B-204E-4297-B3DA-A85646DCC33D | F14-104 | D246C75C-A17A-4A76-AF11-1F5EC7A50324 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-104 FDCR (EOWR).pdf | F14-104 FDCR (EOWR).pdf | Yes |  | Uploads\d246c75c-a17a-4a76-af11-1f5ec7a50324.pdf | Missing
Atikah | Yes | 7CB9E183-3E77-4529-A117-6B1C5B30A70A | FA55664B-204E-4297-B3DA-A85646DCC33D | F14-104 | 28A9415A-43BD-4192-87C7-3164AEE0FE23 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F14-GL02_F14-A104, F14-A105, F14-A107_SHELL_NOOP.pdf | SKO3F14-GL02_F14-A104, F14-A105, F14-A107_SHELL_NOOP.pdf | Yes |  | Uploads\28a9415a-43bd-4192-87c7-3164aee0fe23.pdf | Missing
Atikah | Yes | 0B442371-736D-4694-ABC2-A827CD628416 | 907B380E-A8D3-4DF8-8745-A864A79CB2EF | E06-104 | 81C7352B-8C11-40D6-9571-E5327EDD1B99 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-104 End of Well Report_Final.pdf | E06-104 End of Well Report_Final.pdf | Yes |  | Uploads\81c7352b-8c11-40d6-9571-e5327edd1b99.pdf | Missing
Atikah | Yes | 2959588F-DFA5-4B09-86BA-F7752A33266F | 907B380E-A8D3-4DF8-8745-A864A79CB2EF | E06-104 | F2771EF0-2D46-4D68-9D79-11EB976C267F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-104 (S7) NOOP.pdf | E06-104 (S7) NOOP.pdf | Yes |  | Uploads\f2771ef0-2d46-4d68-9d79-11eb976c267f.pdf | Missing
Atikah | Yes | 662560BB-7B0B-4CEA-B594-8F9D611F4D72 | 3DE5C65B-35F0-4523-A7C3-A86A1E7AB69B | BIDARA-1 | C3C64865-96D9-4D30-8DD0-7C38116A29E6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BDRAWS04_BIDARA_1.pdf | SKO3BDRAWS04_BIDARA_1.pdf | Yes |  | Uploads\c3c64865-96d9-4d30-8dd0-7c38116a29e6.pdf | Exist
Atikah | Yes | C4E3351F-A3B7-465F-88FD-7F27FE7AF994 | 3DE5C65B-35F0-4523-A7C3-A86A1E7AB69B | BIDARA-1 | E3B89CCF-AEF2-40E6-A2B4-9DB7F90B1976 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BDRAWS02_BIDARA_1.pdf | SKO3BDRAWS02_BIDARA_1.pdf | Yes |  | Uploads\e3b89ccf-aef2-40e6-a2b4-9db7f90b1976.pdf | Exist
Atikah | Yes | EB67BA5B-0842-4BE4-AABD-1EA18E10681A | 455E2192-70F8-496D-BF70-A8813F9DC244 | CHRA-03 ST1 | 156FBDC5-2FCF-4B56-A3C7-31ECAED9D18C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CRMGWS26_CHRA-03 ST1_SAPURA OMV_FWR.pdf | PMO3CRMGWS26_CHRA-03 ST1_SAPURA OMV_FWR.pdf | Yes |  | Uploads\156fbdc5-2fcf-4b56-a3c7-31ecaed9d18c.pdf | Exist
Atikah | Yes | 9E4C286C-48CE-4D09-B685-B6581F75CD7A | 455E2192-70F8-496D-BF70-A8813F9DC244 | CHRA-03 ST1 | 21FF7BAD-7FFE-4207-BAA6-B31EF59D37CF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CRMGWS25_CHRA-03 ST1_SAPURA OMV_nOOP.pdf | PMO3CRMGWS25_CHRA-03 ST1_SAPURA OMV_nOOP.pdf | Yes |  | Uploads\21ff7bad-7ffe-4207-baa6-b31ef59d37cf.pdf | Exist
Atikah | Yes | CF59D603-4051-498D-B830-FC3B064A6891 | 2D746E94-3E95-4B1E-A299-A8970F830C99 | F12-A3 | 2201AC32-D020-44DF-AE29-E16FDFD30D5F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP F12-A3 FINAL.pdf | NOOP F12-A3 FINAL.pdf | Yes |  | Uploads\2201ac32-d020-44df-ae29-e16fdfd30d5f.pdf | Exist
Atikah | Yes | 8AE10D0B-E020-4765-9B7E-AC8D10D2D178 | 2D746E94-3E95-4B1E-A299-A8970F830C99 | F12-A3 | 834C622F-756B-4664-BC2C-46AF54731D88 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR F12-A3 (1).pdf | FWR F12-A3 (1).pdf | Yes |  | Uploads\834c622f-756b-4664-bc2c-46af54731d88.pdf | Exist
Atikah | Yes | 4414565C-AE34-49F7-A082-AA0909D28EB3 | 42357450-FA87-4715-B0C0-A8B3FAE466F5 | BUNGA TERATAI C-4 | 21183E7C-B975-4FB8-84CC-B723B22A394F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BTR-C4_Final_signed.pdf | EOWR_BTR-C4_Final_signed.pdf | Yes |  | Uploads\21183e7c-b975-4fb8-84cc-b723b22a394f.pdf | Exist
Atikah | Yes | 9EB49853-A210-40CB-8960-024E64922E4B | 42357450-FA87-4715-B0C0-A8B3FAE466F5 | BUNGA TERATAI C-4 | D926C446-2801-4FCC-A97E-081E7805AF21 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BTR-C4 NOOP (DWP).pdf | BTR-C4 NOOP (DWP).pdf | Yes |  | Uploads\d926c446-2801-4fcc-a97e-081e7805af21.pdf | Exist
Atikah | Yes | 67A46AD7-E625-4C72-B344-053DA5AE6A1C | 7A93F16B-83DA-4CF3-97EE-A8DE82E907C8 | BU-2 | 6BDC2C7D-6FC3-4BDF-B764-D73E851094F5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU-2 DRILLING EOWR.pdf | BU-2 DRILLING EOWR.pdf | Yes |  | Uploads\6bdc2c7d-6fc3-4bdf-b764-d73e851094f5.pdf | Exist
Atikah | Yes | 987318AE-0A64-4A6D-865B-8CA6F8B5AB92 | 7A93F16B-83DA-4CF3-97EE-A8DE82E907C8 | BU-2 | 3EA52A13-9C13-44CB-8A7D-AF8A12E15E7C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU2 NOOPR1.0.pdf | BU2 NOOP.pdf | No |  | Uploads\3ea52a13-9c13-44cb-8a7d-af8a12e15e7c.pdf | Exist
Atikah | Yes | C6E95B52-358B-451B-BFB9-9AC7F6E87C6C | 7FE0C3E1-231E-4882-8FC7-A91BB365621C | BEBOLI-1 | 094596B4-6074-4C73-8125-584617638E23 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Beboli-1 - Shell MLNG Exploration - EOWR.pdf | Beboli-1 - Shell MLNG Exploration - EOWR.pdf | Yes |  | Uploads\094596b4-6074-4c73-8125-584617638e23.pdf | Exist
Atikah | Yes | B3378795-7A10-405A-84D7-16F30B0420CB | 7FE0C3E1-231E-4882-8FC7-A91BB365621C | BEBOLI-1 | 617BCEB7-79F4-4042-9877-C4683B022265 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Beboli-1_Final MLNG Ph1 Expl NOOP.pdf | Beboli-1_Final MLNG Ph1 Expl NOOP.pdf | Yes |  | Uploads\617bceb7-79f4-4042-9877-c4683b022265.pdf | Exist
Atikah | Yes | 639BE75F-5BB7-44D9-BC8E-58AC999548AA | 9587F8C1-3856-4FF1-83C9-A99D51BACA6A | KEDIDI-1 | 9DB9EABA-819D-4FDE-9454-CE3073F1F82E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KDDIWS05_KEDIDI_1.pdf | SKO3KDDIWS05_KEDIDI_1.pdf | Yes |  | Uploads\9db9eaba-819d-4fde-9454-ce3073f1f82e.pdf | Exist
Atikah | Yes | ED94EC5C-A241-4E87-B34A-E0BEB10883BE | 9587F8C1-3856-4FF1-83C9-A99D51BACA6A | KEDIDI-1 | 37360B54-2E0A-47E9-9D5F-77B924B4D6E3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KDDIGL01_KEDIDI_1.pdf | SKO3KDDIGL01_KEDIDI_1.pdf | Yes |  | Uploads\37360b54-2e0a-47e9-9d5f-77b924b4d6e3.pdf | Exist
Atikah | Yes | 1ADDFC4C-B67E-40BB-BE00-9A2B21F2C0E2 | 9DBE013B-93A6-408C-BDF4-A9D2078781F4 | SM-105 | 233E1380-0AE5-493C-813E-6136E72423CF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL30_SM-105.pdf | SBO3SMRGGL30_SM-105.pdf | Yes |  | Uploads\233e1380-0ae5-493c-813e-6136e72423cf.pdf | Exist
Atikah | Yes | CA7FF1AE-A71F-4CAB-925D-9CF5BFD97149 | 9DBE013B-93A6-408C-BDF4-A9D2078781F4 | SM-105 | 7829B22D-ECDC-4FA1-943F-3928A6C4687C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSBR_SM-105.pdf | SBO3SMRGWSBR_SM-105.pdf | Yes |  | Uploads\7829b22d-ecdc-4fa1-943f-3928a6c4687c.pdf | Exist
Atikah | Yes | 638C9272-0AAB-4E85-B425-A5B04F1B0A52 | 92E78905-AC5B-49A1-911B-A9DBA5E4D750 | TE-83 | 3F513781-3335-410E-BE4B-49EE7AF622AF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TE-83 Petronas Final Well Report Compiled (1).pdf | TE-83 Petronas Final Well Report Compiled (1).pdf | Yes |  | Uploads\3f513781-3335-410e-be4b-49ee7af622af.pdf | Exist
Atikah | Yes | C49008E6-DF35-499F-858A-1C2CADBDF88A | 92E78905-AC5B-49A1-911B-A9DBA5E4D750 | TE-83 | 76E62C18-2DB6-4E50-B609-3A0110C70AC0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temana EMP 1.0 TE-83 NOOP Final.pdf | Temana EMP 1.0 TE-83 NOOP Final.pdf | Yes |  | Uploads\76e62c18-2db6-4e50-b609-3a0110c70ac0.pdf | Exist
Atikah | Yes | F2D70371-F8AD-40B5-AFF1-772BA5709905 | 62E4F0A9-3E99-4FCB-AEE6-A9EDA44D7C63 | BAYAN-B225 | AC1C133B-3182-4CF9-9E0D-C1EDF2B56764 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-225 Final Well Report_Bayan Redevelopment Project.pdf |  | No |  | Uploads\ac1c133b-3182-4cf9-9e0d-c1edf2b56764.pdf | Exist
Atikah | Yes | 7315D388-B91F-4EEC-8C0B-6F897B607365 | 62E4F0A9-3E99-4FCB-AEE6-A9EDA44D7C63 | BAYAN-B225 | 95CA054A-5958-48C7-8BAC-76684692C362 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-225 Notice of Operations_APPROVED_Controlled Copy.pdf |  | No |  | Uploads\95ca054a-5958-48c7-8bac-76684692c362.pdf | Exist
Atikah | Yes | F5ECB423-D9B0-48A5-98A3-6F21D5BA75CF | 8C655535-7BD8-40FF-A860-AA2B40C7ACC8 | MACHINCANG-1 | 54D20536-1143-4842-A00F-2BDA9E5CD3BC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Machincang-1 Final Well Report rev03.pdf | Machincang-1 Final Well Report rev03.pdf | Yes |  | Uploads\54d20536-1143-4842-a00f-2bda9e5cd3bc.pdf | Exist
Atikah | Yes | 3BB9AB58-824C-4F3E-A5F2-C9451A7F5034 | 8C655535-7BD8-40FF-A860-AA2B40C7ACC8 | MACHINCANG-1 | 31B83607-966C-4B9E-B4A7-477A460CF1C5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Machincang-1 NOOP (2023).pdf | Machincang-1 NOOP (2023).pdf | Yes |  | Uploads\31b83607-966c-4b9e-b4a7-477a460cf1c5.pdf | Exist
Atikah | Yes | BD169B67-55C5-402F-BF0C-EF970178A31F | 8A786E7A-C452-4D43-A957-AA5101D6082E | PADANG-A02 | F7054D76-6F30-4761-A977-5E5418CB348C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Padang A02 Final (Internal).pdf | NOOP Padang A02 Final (Internal).pdf | Yes |  | Uploads\f7054d76-6f30-4761-a977-5e5418cb348c.pdf | Exist
Atikah | Yes | 371D9174-EC8C-47C5-BF1D-9C30A3E6DC6E | 8A786E7A-C452-4D43-A957-AA5101D6082E | PADANG-A02 | 6151B10F-8D44-405E-9B6D-9496273945FF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Padang A02 Final Well Report.pdf | Padang A02 Final Well Report.pdf | Yes |  | Uploads\6151b10f-8d44-405e-9b6d-9496273945ff.pdf | Exist
Atikah | Yes | F04DB014-7739-48B6-B520-B273F7BA907C | E78B1943-41E5-49D8-B4AB-AA5A9D2F3136 | BERTAM A-3 | 60DE9174-52F0-497E-850A-FD079A3D9633 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A3 EOWR.pdf |  | No |  | Uploads\60de9174-52f0-497e-850a-fd079a3d9633.pdf | Exist
Atikah | Yes | 3B0C4140-9DDA-4FF5-A7DF-2C5111653C9F | E78B1943-41E5-49D8-B4AB-AA5A9D2F3136 | BERTAM A-3 | 02FF2079-EBBA-4ACE-8B60-A5071429CD56 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A3 NOOP.pdf |  | No |  | Uploads\02ff2079-ebba-4ace-8b60-a5071429cd56.pdf | Exist
Atikah | Yes | 9C91A675-03D7-4B05-941C-2861D1915685 | 46890E33-0A54-44CC-9BE0-AA5BEB88A425 | KERDAS-1 | 1082CE75-624A-4F87-B897-A71B198D4446 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kerdas-1 Final Well Report.pdf | Kerdas-1 Final Well Report.pdf | Yes |  | Uploads\1082ce75-624a-4f87-b897-a71b198d4446.pdf | Exist
Atikah | Yes | 76EFD9E0-E957-4316-88AD-5CA7A06EE403 | 46890E33-0A54-44CC-9BE0-AA5BEB88A425 | KERDAS-1 | A2021F85-7060-490A-BE82-EF671557A7B4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Kerdas-1.pdf | NOOP - Kerdas-1.pdf | Yes |  | Uploads\a2021f85-7060-490a-be82-ef671557a7b4.pdf | Exist
Atikah | Yes | 03561B92-8945-4F44-8C1C-9A9B8DC04DDD | 5DD868FE-93F4-4DCF-A868-AA84115F5B51 | LAYANG-LAYANG-1 | E49BDCD4-0B0F-4F2B-8558-2B627B9E76F9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3LLYGGL6130_LAYANG-LAYANG-1.pdf | SBO3LLYGGL6130_LAYANG-LAYANG-1.pdf | Yes |  | Uploads\e49bdcd4-0b0f-4f2b-8558-2b627b9e76f9.pdf | Exist
Atikah | Yes | CBD909F7-B519-4686-9E05-C654DDC72BA7 | 5DD868FE-93F4-4DCF-A868-AA84115F5B51 | LAYANG-LAYANG-1 | 2A03BF44-4AA1-474A-8F37-98D085B81183 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Layang-Layang-1 - NOOP (2023).pdf | Layang-Layang-1 - NOOP (2023).pdf | Yes |  | Uploads\2a03bf44-4aa1-474a-8f37-98d085b81183.pdf | Exist
Atikah | Yes | C7B22B26-1A18-4270-90BF-5B7C4060FE07 | FBD9BDDF-69D3-4F85-AF17-AAD8FE54E553 | BERTAM-4 | 3EF8B0CF-B820-42E0-B7B6-40E8E7A9C37C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam-4 NOOP.pdf | Bertam-4 NOOP.pdf | Yes |  | Uploads\3ef8b0cf-b820-42e0-b7b6-40e8e7a9c37c.pdf | Exist
Atikah | Yes | 5EB67C66-5136-4C63-8850-3F2D89CA1ACC | FBD9BDDF-69D3-4F85-AF17-AAD8FE54E553 | BERTAM-4 | C8FFCCF6-18BD-4C35-B093-E2961EFB606C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam-4 EOWR_Final_complete (1).pdf | Bertam-4 EOWR_Final_complete (1).pdf | Yes |  | Uploads\c8ffccf6-18bd-4c35-b093-e2961efb606c.pdf | Exist
Atikah | Yes | F5D41956-C96B-4D29-A90B-D317476AB392 | 7D7E6AD9-7C71-4BDF-A3BF-AAE152CEB9D0 | DULANG-D29 | 026ABA36-2A8A-4DEE-A7BB-787CB1517E95 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXL_DULANG-D29_PCSB_NOOP.pdf | PMO3DULGWSXL_DULANG-D29_PCSB_NOOP.pdf | Yes |  | Uploads\026aba36-2a8a-4dee-a7bb-787cb1517e95.pdf | Exist
Atikah | Yes | ED79F4C2-2F0E-4354-BDA7-D48E4EF02B58 | 7D7E6AD9-7C71-4BDF-A3BF-AAE152CEB9D0 | DULANG-D29 | E14BA50E-C644-406A-827F-8C219941CD76 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYG_DULANG-D29_PCSB_FWR.pdf | PMO3DULGWSYG_DULANG-D29_PCSB_FWR.pdf | Yes |  | Uploads\e14ba50e-c644-406a-827f-8c219941cd76.pdf | Exist
Atikah | Yes | 5A484D13-F690-4F12-BEEF-DA2EC822D55F | B621AE03-FC7A-4C5A-9011-AB5C0E0B2DFB | BENTARA-A3 | BFD8AC65-8B73-48D0-BA9C-9EBB5369A577 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bentara-A3 Final Well Report_.pdf | Bentara-A3 Final Well Report_.pdf | Yes |  | Uploads\bfd8ac65-8b73-48d0-ba9c-9ebb5369a577.pdf | Exist
Atikah | Yes | E6036D9F-CE27-44CA-B072-98CBE60BA045 | B621AE03-FC7A-4C5A-9011-AB5C0E0B2DFB | BENTARA-A3 | B7CA5035-A868-4CE6-BB46-5BCD99CEBB00 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bentara-A3_Signed_rev01.pdf | NOOP Bentara-A3_Signed_rev01.pdf | Yes |  | Uploads\b7ca5035-a868-4ce6-bb46-5bcd99cebb00.pdf | Exist
Atikah | Yes | C6370918-500B-46EA-B97E-439FA9A2E605 | 4BA5E439-F6BC-4483-AD3C-AC1AC19F9430 | D28-OP1 | C2A454E6-41DE-4AA3-8067-51A899EE32AE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D28 OP1 FWR Signed.pdf | D28 OP1 FWR Signed.pdf | Yes |  | Uploads\c2a454e6-41de-4aa3-8067-51a899ee32ae.pdf | Exist
Atikah | Yes | 9CD2A6E9-17DB-45B6-9D50-434BE4DFCBE3 | 4BA5E439-F6BC-4483-AD3C-AC1AC19F9430 | D28-OP1 | 2D4AA0A7-E019-4CA8-80DE-01FCD4EF4DC8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D28 NOOP OP1 Final Signed.pdf |  | No |  | Uploads\2d4aa0a7-e019-4ca8-80de-01fcd4ef4dc8.pdf | Exist
Atikah | Yes | 06EA31E7-7A94-470F-B80D-A70230FC914E | 4E9A64F2-0F90-4B85-9A16-AC7411229A86 | D35B-221 | 8CC9320E-0E00-44EE-9149-2CA325FDFF3E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-221 NOOP_signed.pdf | D35B-221 NOOP_signed.pdf | Yes |  | Uploads\8cc9320e-0e00-44ee-9149-2ca325fdff3e.pdf | Exist
Atikah | Yes | 8E0BCEC9-FAE1-4BCF-B693-BA1E8039EA1F | 4E9A64F2-0F90-4B85-9A16-AC7411229A86 | D35B-221 | 8946B500-2C31-4F68-889D-972B7371AA75 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-221 EOWR (1 of 3).pdf | D35B-221 EOWR (1 of 3).pdf | Yes |  | Uploads\8946b500-2c31-4f68-889d-972b7371aa75.pdf | Exist
Atikah | Yes | D11A8559-B4F8-4259-8503-6634392B1C7C | 8B7D622F-7BAD-4147-891E-AC7FDE2EE376 | D18-301ST1 | 697ABAAE-4C5C-4643-AB80-E17FE3FEC446 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 301 ST1_EOWR Rev1.pdf | D18 301 ST1_EOWR Rev1.pdf | Yes |  | Uploads\697abaae-4c5c-4643-ab80-e17fe3fec446.pdf | Exist
Atikah | Yes | D806339A-D69D-42B5-B767-1ABDF7AD888D | 8B7D622F-7BAD-4147-891E-AC7FDE2EE376 | D18-301ST1 | 5550B0A7-B6D5-490C-AF20-DBD6CD6D05DE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-301 ST1 (OP-1A) NOOP.pdf | D18-301 ST1 (OP-1A) NOOP.pdf | Yes |  | Uploads\5550b0a7-b6d5-490c-af20-dbd6cd6d05de.pdf | Exist
Atikah | Yes | 9C4D1ACE-F317-4EE5-8D96-39F2824731B4 | E8C85471-CAC2-4308-8BE3-ACE642D04327 | BERGADING-D5 (D_1_10) | 2F291B86-1309-463D-8211-31D275F73156 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BRGD-5 (D_1_10).pdf |  | No |  | Uploads\2f291b86-1309-463d-8211-31d275f73156.pdf | Exist
Atikah | Yes | C2760AD0-6295-4926-82F2-BFA881389E15 | E8C85471-CAC2-4308-8BE3-ACE642D04327 | BERGADING-D5 (D_1_10) | A9BAF282-A39D-42BB-A215-283AEF0DCD71 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRGD-5(D_1_10) Rev0.pdf |  | No |  | Uploads\a9baf282-a39d-42bb-a215-283aef0dcd71.pdf | Exist
Atikah | Yes | B761617D-8719-464A-8F85-F45F12BC756C | 5F61351D-B2B2-4D7E-8407-AD27B5C01E7B | PGA-01ST1 | 542F3C5E-F6E3-4BF7-8625-4CC58EE6E97D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-01ST-1Rev3.0_SZ Signed.pdf | PGA-01ST-1Rev3.0_SZ Signed.pdf | Yes |  | Uploads\542f3c5e-f6e3-4bf7-8625-4cc58ee6e97d.pdf | Exist
Atikah | Yes | 4819C120-BCB1-4642-A7FE-9455B8F7E7D9 | 5F61351D-B2B2-4D7E-8407-AD27B5C01E7B | PGA-01ST1 | E7961D9D-1AB5-4A64-8F2F-8FC21266A8B5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-01ST1 EOW_25th January 2021.pdf | PGA-01ST1 EOW_25th January 2021.pdf | Yes |  | Uploads\e7961d9d-1ab5-4a64-8f2f-8fc21266a8b5.pdf | Exist
Atikah | Yes | 2CA82A59-D5B6-4AA4-BE66-9176E51C8FBB | 23AB17E6-EA40-4E68-A4A1-AD3EE7D9FB7C | DULANG-A04 ST1 | 410A4BC2-A01C-4598-8203-11E323C94D6C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_DULANG-A04ST1(OP4)_Final.pdf | NOOP_DULANG-A04ST1(OP4)_Final.pdf | Yes |  | Uploads\410a4bc2-a01c-4598-8203-11e323c94d6c.pdf | Exist
Atikah | Yes | 5BADAB8F-ECE0-4813-A90B-FB1069AB111B | 23AB17E6-EA40-4E68-A4A1-AD3EE7D9FB7C | DULANG-A04 ST1 | 384410A1-04A4-4B04-80F2-44EC4A5B030F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report_Dulang-A04ST1.pdf | Final Well Report_Dulang-A04ST1.pdf | Yes |  | Uploads\384410a1-04a4-4b04-80f2-44ec4a5b030f.pdf | Exist
Atikah | Yes | F9260A7E-07F3-4E3F-9E7C-77C9915226AE | 89B0069F-C22E-469D-84C4-ADBFCE7C620A | BY-311 | 6653FB9D-1594-4777-A4C1-D19389169498 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-311 Notice of Operations_APPROVED.pdf | BY-311 Notice of Operations_APPROVED.pdf | Yes |  | Uploads\6653fb9d-1594-4777-a4c1-d19389169498.pdf | Exist
Atikah | Yes | B2B86A3F-CF35-4446-9349-30C74A64A6FF | 89B0069F-C22E-469D-84C4-ADBFCE7C620A | BY-311 | A6BD5534-3B28-4E7F-9DB6-290F1B869AF4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-311 Final Well Report - Signed.pdf | BY-311 Final Well Report - Signed.pdf | Yes |  | Uploads\a6bd5534-3b28-4e7f-9db6-290f1b869af4.pdf | Exist
Atikah | Yes | DCC20138-8CCA-4DBE-BD27-7ACC2EF69679 | FBC4BF25-8389-4C47-B7CD-ADF1BAE011A6 | NAHARA-1 | 2628A9AA-249D-48AA-A0D3-6F9C07D237DA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Nahara-1 NOOP - signed.pdf | Nahara-1 NOOP - signed.pdf | Yes |  | Uploads\2628a9aa-249d-48aa-a0d3-6f9c07d237da.pdf | Exist
Atikah | Yes | 9DE8CF97-1E51-41E4-BD16-811FB7E16C6F | FBC4BF25-8389-4C47-B7CD-ADF1BAE011A6 | NAHARA-1 | 387BA852-45E1-456A-B98F-532AD82ED53E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Nahara-1 -Approved Final Well Report (FWR) without Attachment .pdf | Nahara-1 -Approved Final Well Report (FWR) without Attachment .pdf | Yes |  | Uploads\387ba852-45e1-456a-b98f-532ad82ed53e.pdf | Exist
Atikah | Yes | 078D4049-F361-48D8-A7C4-2EFE0E7F7498 | FC0276FB-41E8-4264-A33E-AE0243A23989 | TT-A8 | D1B7328F-FAC8-4AD3-98AF-157B672203A5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A8_FWR - Final to MPM.pdf | TT-A8_FWR - Final to MPM.pdf | Yes |  | Uploads\d1b7328f-fac8-4ad3-98af-157b672203a5.pdf | Exist
Atikah | Yes | AA4D6635-E98B-4644-8666-DB03C63AFF10 | FC0276FB-41E8-4264-A33E-AE0243A23989 | TT-A8 | 7CA097F7-54CD-4B09-ACD7-1F5C9B4D65B0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A8_Internal Copy.pdf | TT-A8_Internal Copy.pdf | Yes |  | Uploads\7ca097f7-54cd-4b09-acd7-1f5c9b4d65b0.pdf | Exist
Atikah | Yes | 6825EE1B-5196-4C59-AAB2-7F5E3E41B4E9 | CCE63AE9-0DBF-451E-A1BB-AE53F1CD9133 | LARUT A-26ST2 | 4DEDD076-93E3-4932-ACE3-956140BB0C60 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-26ST2 (GP1_NOOP) rev.2.pdf | LARUT A-26ST2 (GP1_NOOP) rev.2.pdf | Yes |  | Uploads\4dedd076-93e3-4932-ace3-956140bb0c60.pdf | Exist
Atikah | Yes | 86F3B814-6999-47F1-AE13-630074E6B8F1 | CCE63AE9-0DBF-451E-A1BB-AE53F1CD9133 | LARUT A-26ST2 | 2E808B84-2D0F-4E67-81AE-EA72B166369B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-26ST2 (GP1) Final Well Report_Rev0.pdf | LARUT A-26ST2 (GP1) Final Well Report_Rev0.pdf | Yes |  | Uploads\2e808b84-2d0f-4e67-81ae-ea72b166369b.pdf | Exist
Atikah | Yes | 5CFD306D-A27C-4BB7-8710-40B2C8E00605 | 074566EF-7D37-46AA-9EB2-AEDB8E578AB7 | SEPAT A-05 | A1E1771A-B64A-4566-9054-5AC761DAD8A3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL29_SEPAT-A05_PCSB_NOOP.pdf | PMO3SPATGL29_SEPAT-A05_PCSB_NOOP.pdf | Yes |  | Uploads\a1e1771a-b64a-4566-9054-5ac761dad8a3.pdf | Exist
Atikah | Yes | EEF8BCC5-90D6-403F-8134-DA6FCC78092C | 074566EF-7D37-46AA-9EB2-AEDB8E578AB7 | SEPAT A-05 | AA050AF0-DC95-47BB-8530-1D25095A2FB0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATWS68_SEPAT-A05_PCSB_FWR.pdf | PMO3SPATWS68_SEPAT-A05_PCSB_FWR.pdf | Yes |  | Uploads\aa050af0-dc95-47bb-8530-1d25095a2fb0.pdf | Exist
Atikah | Yes | 88AF57E7-084A-4405-9EBB-5E1B7F4A97EB | 00FC4FD6-82DD-431A-AF3F-AEE9B45B8446 | GUNTONG-C14ST1 | 8A54366B-287E-40D3-965C-A2CB13331F75 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GUNTONG-C14ST1 (C36) NOOP - PCSB.pdf |  | No |  | Uploads\8a54366b-287e-40d3-965c-a2cb13331f75.pdf | Exist
Atikah | Yes | D4B7B61B-D4B6-44A7-952F-7DA220F91444 | 00FC4FD6-82DD-431A-AF3F-AEE9B45B8446 | GUNTONG-C14ST1 | 069CD61E-6F6D-4414-A4FF-A8AE9056C4A2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Guntong C-14.pdf |  | No |  | Uploads\069cd61e-6f6d-4414-a4ff-a8ae9056c4a2.pdf | Exist
Atikah | Yes | F7162633-8C68-41E6-96FD-8A677D720080 | 58424E94-4711-4181-8115-AF1CE05AE953 | PUTAT-1 | FDDA66CF-1398-4D96-8CA6-9AF2F7CD872B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Putat-1 Final Well Report Rev.1.pdf | Putat-1 Final Well Report Rev.1.pdf | Yes |  | Uploads\fdda66cf-1398-4d96-8ca6-9af2f7cd872b.pdf | Exist
Atikah | Yes | 5C26F8BE-26A3-4479-934F-C3B8124DD6B6 | 58424E94-4711-4181-8115-AF1CE05AE953 | PUTAT-1 | F8AA3FE8-7765-4433-8C75-03EC27B87EF5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Putat-1 NOOP - rev 1.1 copy.pdf | Putat-1 NOOP - rev 1.1 copy.pdf | Yes |  | Uploads\f8aa3fe8-7765-4433-8c75-03ec27b87ef5.pdf | Exist
Atikah | Yes | E4F1FE32-B2F5-458C-9673-C84FCF2E01F9 | 705CA9A8-2E20-4AD0-9A72-AF3AF4A30036 | F14-102 | FA902FB0-D88E-41E9-9D16-8D26DC01F9F3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-102 NOOP-160718 Final Signed.pdf | F14-102 NOOP-160718 Final Signed.pdf | Yes |  | Uploads\fa902fb0-d88e-41e9-9d16-8d26dc01f9f3.pdf | Exist
Atikah | Yes | 396F992D-0C47-4702-8069-DE843141ED9C | 705CA9A8-2E20-4AD0-9A72-AF3AF4A30036 | F14-102 | AEBEBB01-3830-4AF8-B007-43B0CCA3A863 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-102 EOWR (19 DEC)_FINAL_SIGNED.pdf | F14-102 EOWR (19 DEC)_FINAL_SIGNED.PDF | Yes |  | Uploads\aebebb01-3830-4af8-b007-43b0cca3a863.pdf | Exist
Atikah | Yes | 5E1E923B-8D2C-47CD-A34A-C91BBE3F99EB | BF27A3E2-B219-4055-B059-AF8DFB52F92D | SJ-609C | E0011CE8-D940-4A46-95C9-BDE482F12230 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609C EOWR_FINAL_MPM WM.pdf | SJ-609C EOWR_FINAL_MPM WM.pdf | Yes |  | Uploads\e0011ce8-d940-4a46-95c9-bde482f12230.pdf | Exist
Atikah | Yes | 680DBC42-346D-4A3A-8D10-79E55CC26A21 | BF27A3E2-B219-4055-B059-AF8DFB52F92D | SJ-609C | 28A97D9E-E2E2-4949-99FC-3EB163EE0E5C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609C NOOP - MPM Drilling.pdf | SJ-609C NOOP - MPM Drilling.pdf | Yes |  | Uploads\28a97d9e-e2e2-4949-99fc-3eb163ee0e5c.pdf | Exist
Atikah | Yes | 9F06156B-0018-42CC-A2A1-D748AEF5E1CF | DCFBDDB8-091C-4BCB-B09E-AF8E58412A91 | NBO-4 | DFC440AA-9FF1-4FAC-8CCF-744E3F484CF2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NBO-4_End of Well Drilling Operation Report_FINAL.pdf | NBO-4_End of Well Drilling Operation Report_FINAL.pdf | Yes |  | Uploads\dfc440aa-9ff1-4fac-8ccf-744e3f484cf2.pdf | Exist
Atikah | Yes | 6CFAD5FF-E359-4FA6-93EE-D461233ED348 | DCFBDDB8-091C-4BCB-B09E-AF8E58412A91 | NBO-4 | 5B265C48-BE5B-40F5-8305-5F151B8D634B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NBO-4 NOOP_Final_Rev0.pdf | NBO-4 NOOP_Final_Rev0.pdf | Yes |  | Uploads\5b265c48-be5b-40f5-8305-5f151b8d634b.pdf | Exist
Atikah | Yes | 3CDA18D6-C3A5-40A0-A9EF-AA5C6A760D4F | 6506DCE9-C1F3-4068-80F6-B1043FFF3570 | BAIDURI-1 | 7FCDE7C3-C6CA-4E42-AC51-6F538AB847CB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAIDURI-1 NOOP rev 0.0.pdf | BAIDURI-1 NOOP rev 0.0.pdf | Yes |  | Uploads\7fcde7c3-c6ca-4e42-ac51-6f538ab847cb.pdf | Exist
Atikah | Yes | 6DFE3D42-690F-4AAE-A5A4-201988AD029D | 6506DCE9-C1F3-4068-80F6-B1043FFF3570 | BAIDURI-1 | EAB9DBC4-DAEC-4887-BB0E-8C29A7B679A0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SB310 Baiduri-1 End of Well Report.pdf | SB310 Baiduri-1 End of Well Report.pdf | Yes |  | Uploads\eab9dbc4-daec-4887-bb0e-8c29a7b679a0.pdf | Exist
Atikah | Yes | 4B14B886-8C2E-4AE8-836F-5BDD64827D56 | B48376DE-3BD3-49D5-8D51-B286FD55D131 | BN-72 | D8D95ED7-15FF-4539-8247-F21B98046D6C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARONIA-J72 NOOP.pdf |  | No |  | Uploads\d8d95ed7-15ff-4539-8247-f21b98046d6c.pdf | Exist
Atikah | Yes | 8962CD02-30D6-4229-B44A-4D58FCB5FBD9 | B48376DE-3BD3-49D5-8D51-B286FD55D131 | BN-72 | 20D117EC-6FF1-4B1D-8F31-683CE1040885 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARONIA-BN 72 FWR.pdf | BARONIA-BN 72 FWR.pdf | Yes |  | Uploads\20d117ec-6ff1-4b1d-8f31-683ce1040885.pdf | Exist
Atikah | Yes | 8745AE0D-1656-4965-996C-15A26C3543FA | BAAC85E2-1E34-4C26-9109-B29D524205AD | PENARA NW-1 | 53B1CBB5-A607-4279-A717-0DEE2F562DCF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3PRNWWS04_PENARA_NW1.pdf | PMO3PRNWWS04_PENARA_NW1.pdf | Yes |  | Uploads\53b1cbb5-a607-4279-a717-0dee2f562dcf.pdf | Exist
Atikah | Yes | 0EBB24F6-52DA-4A72-9DB8-D9FD36E0C5A1 | BAAC85E2-1E34-4C26-9109-B29D524205AD | PENARA NW-1 | 74E953D3-F9DD-446A-ADA5-1212707A0D94 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3PNARWS47_PENARA_NW1.pdf | PMO3PNARWS47_PENARA_NW1.pdf | Yes |  | Uploads\74e953d3-f9dd-446a-ada5-1212707a0d94.pdf | Exist
Atikah | Yes | F92A7651-2259-4A48-B4FD-C970AD3C733C | B9E936CA-BE70-4AFC-9899-B2E7962A0B0E | SIRUNG-1 | 5F51DE5D-4613-4AFA-AA2C-A3805CE3AC42 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sirung-1 EOWR Rev0 (FINAL).pdf | Sirung-1 EOWR Rev0 (FINAL).pdf | Yes |  | Uploads\5f51de5d-4613-4afa-aa2c-a3805ce3ac42.pdf | Exist
Atikah | Yes | D9F01981-FBC1-46E2-BE2D-50E06D8ABEA2 | B9E936CA-BE70-4AFC-9899-B2E7962A0B0E | SIRUNG-1 | E7C785CF-601C-42BB-AE7C-A8B46B584798 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sirung-1 Rev1.pdf | Sirung-1 Rev1.pdf | Yes |  | Uploads\e7c785cf-601c-42bb-ae7c-a8b46b584798.pdf | Exist
Atikah | Yes | E26C1AC2-E4C7-4859-A8D5-3846079068F0 | 462BBEC8-853D-4E08-8CA5-B31715A6FB25 | F13ESC-A5 | CA627595-D5B8-467B-8A32-8D60EDFED4F6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PETRONAS Final Well Report F13ESC-5_signed.pdf |  | No |  | Uploads\ca627595-d5b8-467b-8a32-8d60edfed4f6.pdf | Exist
Atikah | Yes | 0F8E7E89-6C79-4190-92E3-E1A3468EAC60 | 462BBEC8-853D-4E08-8CA5-B31715A6FB25 | F13ESC-A5 | 3B65C012-152B-40BC-8285-7A43175EC6DB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F13CWS6243_F13ESC-A5.pdf | SKO3F13CWS6243_F13ESC-A5.pdf | Yes |  | Uploads\3b65c012-152b-40bc-8285-7a43175ec6db.pdf | Exist
Atikah | Yes | B717B5C2-A13C-411C-8065-B2DAB2FFEC3C | 813F5BEC-CE77-496E-840C-B398FB9DDCA4 | PGA-06 | 134744FA-9D20-4B59-AD55-6BED966D7470 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-06 NOOP Update Rev 1.0_8th February 2021.pdf | PGA-06 NOOP Update Rev 1.0_8th February 2021.pdf | Yes |  | Uploads\134744fa-9d20-4b59-ad55-6bed966d7470.pdf | Exist
Atikah | Yes | 4D250622-697E-4108-8213-632C9703162C | 813F5BEC-CE77-496E-840C-B398FB9DDCA4 | PGA-06 | 4EE60996-72A8-4F41-AA74-63EB3624A900 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-06 EOWR_13Aug21.pdf | PGA-06 EOWR_13Aug21.pdf | Yes |  | Uploads\4ee60996-72a8-4f41-aa74-63eb3624a900.pdf | Exist
Atikah | Yes | FB3E908E-68BE-4D50-85C0-5FB09A95AE69 | 52862D37-8D2C-46FD-8D0B-B3A93EA8AA79 | BERGADING-B1(H) | 3A6A2332-8BD5-4885-BD78-AF3342E61669 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRGB-1(H), Bergading B-1(H).pdf | NOOP - BRGB-1(H), Bergading B-1(H).pdf | Yes |  | Uploads\3a6a2332-8bd5-4885-bd78-af3342e61669.pdf | Exist
Atikah | Yes | CAFFE5F6-115F-448B-BA92-D0E3A4A246D6 | 52862D37-8D2C-46FD-8D0B-B3A93EA8AA79 | BERGADING-B1(H) | 44AA8A32-9B68-4F2B-A606-F2909884E251 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading B-1(H).pdf | EOWR_Bergading B-1(H).pdf | Yes |  | Uploads\44aa8a32-9b68-4f2b-a606-f2909884e251.pdf | Exist
Atikah | Yes | 0C1BF97A-5582-4112-93A7-72EE85D25ABA | 5A559FE7-0AF2-40F9-AA3C-B3B276AF6AB1 | LARUT-A30ST1 | 4853B9C2-140E-4F68-A642-8AC20B6DAAFA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-30ST1 (OP3_NOOP) rev.2.pdf | LARUT A-30ST1 (OP3_NOOP) rev.2.pdf | Yes |  | Uploads\4853b9c2-140e-4f68-a642-8ac20b6daafa.pdf | Exist
Atikah | Yes | 2B858269-FCC2-4CA1-BBF7-45F3508430B4 | 5A559FE7-0AF2-40F9-AA3C-B3B276AF6AB1 | LARUT-A30ST1 | DC2E789C-28AE-4206-B6C5-9F3CF3FC69D5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-30ST1 (OP3) Final Well Report_Rev0.pdf | LARUT A-30ST1 (OP3) Final Well Report_Rev0.pdf | Yes |  | Uploads\dc2e789c-28ae-4206-b6c5-9f3cf3fc69d5.pdf | Exist
Atikah | Yes | C77E3B7A-EB97-4275-9011-4EA0E18974BB | 7C623E66-A3E2-4186-A083-B3EFE7A3BA31 | PRPA-01 | B7397902-05EF-4695-86BE-7F537C9F1C4D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-01 EOWR.pdf | PRPA-01 EOWR.pdf | Yes |  | Uploads\b7397902-05ef-4695-86be-7f537c9f1c4d.pdf | Exist
Atikah | Yes | 32ECC08A-BD06-47F4-A7E8-33ABD55590A3 | 7C623E66-A3E2-4186-A083-B3EFE7A3BA31 | PRPA-01 | 2F50D820-4ABF-4259-A7D9-CE861CA045E1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf |  | No |  | Uploads\2f50d820-4abf-4259-a7d9-ce861ca045e1.pdf | Exist
Atikah | Yes | A8D344B1-289A-48CF-BC65-B15B262C3D4E | F193F455-D23B-4FE1-A4DC-B42E50E5813C | BERGADING-C2(B) | E1DC82E5-EAFD-4EB5-8273-C4A4497D1E22 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading C-2 (B) R0_Final.pdf | Bergading C-2 (B) R0_Final.pdf | Yes |  | Uploads\e1dc82e5-eafd-4eb5-8273-c4a4497d1e22.pdf | Exist
Atikah | Yes | 68C57A38-C631-4E1B-9F38-F975A545C636 | F193F455-D23B-4FE1-A4DC-B42E50E5813C | BERGADING-C2(B) | 7DF78CEC-90A6-46D9-9798-D7263193B1E6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading C-2_ Rev2_28082017 - PETRONAS SUBMISSION.pdf |  | No |  | Uploads\7df78cec-90a6-46d9-9798-d7263193b1e6.pdf | Exist
Atikah | Yes | ED90F1A2-ADE9-4F49-9F8C-EE90151CDEBF | 94599DE7-EA76-4B1E-A98D-B46A2A8AC331 | PERMAI-1 | 51D14378-BEB6-4012-BE55-27898BDDDDCF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Permai-1_EOWR.pdf | Permai-1 Petronas and Carigali_EOWR.pdf | No |  | Uploads\51d14378-beb6-4012-be55-27898bddddcf.pdf | Exist
Atikah | Yes | 1D07AE69-94A4-4A3E-BECE-E05AB16C2804 | 94599DE7-EA76-4B1E-A98D-B46A2A8AC331 | PERMAI-1 | D3F36DE8-E2CB-4D80-9191-B6D21249CC63 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Permai-1 Petronas and Carigali_Drilling NOOP.pdf | Permai-1 Petronas and Carigali_Drilling NOOP.pdf | Yes |  | Uploads\d3f36de8-e2cb-4d80-9191-b6d21249cc63.pdf | Exist
Atikah | Yes | 636E0AC8-A30E-458D-909E-F70FF0FD1C74 | 492CF62F-1B50-470F-BFF5-B4EA4B4EDD5B | BUNGA KESUMBA A-4 | 07173F21-AC9E-4FCE-B173-161927BD05FE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Kesumba A-4.pdf | EOWR_Bunga Kesumba A-4.pdf | Yes |  | Uploads\07173f21-ac9e-4fce-b173-161927bd05fe.pdf | Exist
Atikah | Yes | D2FE07B2-4AE4-4C93-AF32-26224C7ED27E | 492CF62F-1B50-470F-BFF5-B4EA4B4EDD5B | BUNGA KESUMBA A-4 | 6B13273E-22BE-4A2C-A848-4E30D867C195 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NMB-DRI-RPT-01180_BKsA-4 NOOP.pdf |  | No |  | Uploads\6b13273e-22be-4a2c-a848-4e30d867c195.pdf | Exist
Atikah | Yes | 7ED1F57E-CE8E-4CB7-92D1-3C553DFC3513 | 401FCB52-A186-443B-9A9E-B5988CFE3C74 | D21-A13 | 8683F3A6-F6C5-4105-BBAC-85F9E899D13F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A13 End of Well Report.pdf | D21-A13 End of Well Report.pdf | Yes |  | Uploads\8683f3a6-f6c5-4105-bbac-85f9e899d13f.pdf | Exist
Atikah | Yes | 4644DED0-C179-48B6-9227-FF742C2E3ACF | 401FCB52-A186-443B-9A9E-B5988CFE3C74 | D21-A13 | 7DF6664C-68AF-4C6F-A483-F4B882267571 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A13 NOOP_FINAL_.pdf | D21-A13 NOOP_FINAL_.pdf | Yes |  | Uploads\7df6664c-68af-4c6f-a483-f4b882267571.pdf | Exist
Atikah | Yes | C9AD0916-4966-4B1C-ADFD-5A3F28F83520 | AA29826C-B432-4206-BB4F-B5E6DD6BF96F | LOKIO-1 | BA405AFF-E0F1-4C4F-99A6-E1CF458D81FF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LOKIO-1 EOWR_Final.pdf | LOKIO-1 EOWR_Final.pdf | Yes |  | Uploads\ba405aff-e0f1-4c4f-99a6-e1cf458d81ff.pdf | Exist
Atikah | Yes | A39A8F4A-A1D1-416F-B0B7-7B626BDCFBE5 | AA29826C-B432-4206-BB4F-B5E6DD6BF96F | LOKIO-1 | 5574FB3D-6973-4B88-8D57-9D90BB147C0F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lokio-1_NOOP_Nov2017_final_signed.pdf | Lokio-1_NOOP_Nov2017_final_signed.pdf | Yes |  | Uploads\5574fb3d-6973-4b88-8d57-9d90bb147c0f.pdf | Exist
Atikah | Yes | FC6DA927-B8D6-4E56-89C4-735991EDFAA2 | A586A140-446A-4A4D-A62F-B6738FC798D4 | BANANG-B2 | D6867B00-AEE6-4F6D-8378-66582EBFB73C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS08_BANANG_B2.pdf | PMO3BANGWS08_BANANG_B2.pdf | Yes |  | Uploads\d6867b00-aee6-4f6d-8378-66582ebfb73c.pdf | Exist
Atikah | Yes | 864364FE-D942-4558-9847-C6EC98156AC8 | A586A140-446A-4A4D-A62F-B6738FC798D4 | BANANG-B2 | 29ADCE76-49A5-4D74-9404-199C01ADF667 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BANGWS10_BANANG_B2.pdf | PMO3BANGWS10_BANANG_B2.pdf | Yes |  | Uploads\29adce76-49a5-4d74-9404-199c01adf667.pdf | Exist
Atikah | Yes | 85B5BAA6-41CC-4DA9-9F7F-A06286E107CB | 755C9F02-47D9-433C-8B44-B68E27F704AE | SF30-2 | 799C1738-387B-48A5-85FB-D4AE89DCB54E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-2 NOOP - MPM Well Management.pdf | SF30-2 NOOP - MPM Well Management.pdf | Yes |  | Uploads\799c1738-387b-48a5-85fb-d4ae89dcb54e.pdf | Exist
Atikah | Yes | D2B2598B-50CF-4647-92A2-243BFAAE1175 | 755C9F02-47D9-433C-8B44-B68E27F704AE | SF30-2 | B48EBE1B-2CBD-4EBC-ACCC-2273F35F4353 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-2 EOWR_FINAL - MPM Drilling.pdf | SF30-2 EOWR_FINAL - MPM Drilling.pdf | Yes |  | Uploads\b48ebe1b-2cbd-4ebc-accc-2273f35f4353.pdf | Exist
Atikah | Yes | A43C398C-75A6-4C38-8F6C-51FBEB36CD8A | 0B350C2A-E5EA-4E99-8A93-B6B6A9AC4F8A | PGA-02ST2 | 7E18E367-7B26-4D69-9920-BAC11F3607B4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-02ST2 NOOP_12th July 21_update.pdf | PGA-02ST2 NOOP_12th July 21_update.pdf | Yes |  | Uploads\7e18e367-7b26-4d69-9920-bac11f3607b4.pdf | Exist
Atikah | Yes | 4627C20F-9FBC-49D8-B35E-8187FFE82667 | 0B350C2A-E5EA-4E99-8A93-B6B6A9AC4F8A | PGA-02ST2 | 53A3BC08-D291-4553-9AC3-E6834E531230 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PGA-02ST2 EOWR (2).pdf | PGA-02ST2 EOWR (2).pdf | Yes |  | Uploads\53a3bc08-d291-4553-9ac3-e6834e531230.pdf | Exist
Atikah | Yes | 19A183D4-5023-435C-ABE9-605AC5EE451C | 4314EA77-9204-48DF-8ECB-B79EBC026408 | JTG-A4 | 909C8C77-14FA-4F0C-ABC9-CA308184379D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JTG-A4 Final Well Report_2020_01_23.pdf | JTG-A4 Final Well Report_2020_01_23.pdf | Yes |  | Uploads\909c8c77-14fa-4f0c-abc9-ca308184379d.pdf | Exist
Atikah | Yes | 5C8BDBBF-F2FD-41C1-9C02-EC9E2B83DBAA | 4314EA77-9204-48DF-8ECB-B79EBC026408 | JTG-A4 | 2B833F34-C59A-4604-A01E-D2EB9769FE01 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP JTG-A4.pdf | NOOP JTG-A4.pdf | Yes |  | Uploads\2b833f34-c59a-4604-a01e-d2eb9769fe01.pdf | Exist
Atikah | Yes | 12902868-B6AA-4908-84D0-9F471E06CE4C | 21781E00-5F54-4CFA-8C2F-B7C950DAC242 | KNDW-D14 | F567AD9F-D838-4740-9504-F2BC4195E04D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-14 NOOP.pdf | KNDW D-14 NOOP.pdf | Yes |  | Uploads\f567ad9f-d838-4740-9504-f2bc4195e04d.pdf | Exist
Atikah | Yes | C33BE285-4FD0-4DFB-B838-41D984E3D0F5 | 21781E00-5F54-4CFA-8C2F-B7C950DAC242 | KNDW-D14 | A28B9FC4-8168-40A1-A88E-F089FC29A324 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D14_End of Well Report Rev 2.pdf | KNDW-D14_End of Well Report Rev 2.pdf | Yes |  | Uploads\a28b9fc4-8168-40a1-a88e-f089fc29a324.pdf | Exist
Atikah | Yes | B671675A-0EBF-418E-A3B4-27DDAD463D24 | 89E4C9D1-2B7F-4F10-9F2F-B7E79256D738 | RT-P1 | F0BD7DAE-E907-48DE-94A5-331D1787D43B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_Block H Phase 1A Development Notice of Operation Rev0.pdf |  | No |  | Uploads\f0bd7dae-e907-48de-94a5-331d1787d43b.pdf | Exist
Atikah | Yes | 8918E1CD-3DC4-4017-83D1-B3BC7FC5A6C7 | 89E4C9D1-2B7F-4F10-9F2F-B7E79256D738 | RT-P1 | 6359BEB9-6386-436B-9AB3-A16F73BD5D3C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | RT-P1 EOWR.pdf | RT-P1 EOWR.pdf | Yes |  | Uploads\6359beb9-6386-436b-9ab3-a16f73bd5d3c.pdf | Exist
Atikah | Yes | 0A6436FA-8613-4A56-A15D-B54C6A70A3CE | A3E97666-081D-4FFE-9E6B-B8126EE33096 | BESA-03 | C8CCA07B-B417-4C02-9FBC-C26569B9C1E3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-69-DNC-RP-0003-00_BESA-03 EOWR.pdf | MOM-SK309-69-DNC-RP-0003-00_BESA-03 EOWR.pdf | Yes |  | Uploads\c8cca07b-b417-4c02-9fbc-c26569b9c1e3.pdf | Exist
Atikah | Yes | FC7EB25D-21AE-4E9D-82F0-98CA954CDCD1 | A3E97666-081D-4FFE-9E6B-B8126EE33096 | BESA-03 | 3C3146A1-F6A8-4D6D-806B-D62D0A5F0DD9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | SKO3BLUMWS16_BESA-01_BESA-02_BESA-03_BESA-11_BESA-12.pdf | No |  | Uploads\3c3146a1-f6a8-4d6d-806b-d62d0a5f0dd9.pdf | Exist
Atikah | Yes | 681B9364-52F1-466A-95CB-A3C022D9BD59 | 903F4E3F-7A5A-4611-A593-B91B63E8591B | BERGADING-C4 (D) | C9280A1C-6946-41BE-BF47-78B47B713C28 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading C-4 (D) R0_Final.pdf | Bergading C-4 (D) R0_Final.pdf | Yes |  | Uploads\c9280a1c-6946-41be-bf47-78b47b713c28.pdf | Exist
Atikah | Yes | 2CA1F17A-CDE2-4982-BD34-CC30DB59099D | 903F4E3F-7A5A-4611-A593-B91B63E8591B | BERGADING-C4 (D) | FD98628D-FE47-4E99-A66A-DC41A5FB298E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BGDGWS44_BERGADING_C4.pdf |  | No |  | Uploads\fd98628d-fe47-4e99-a66a-dc41a5fb298e.pdf | Exist
Atikah | Yes | 789BE6B9-A0AD-4195-925A-A5E20B434EBF | 1D73CF38-8474-4B9B-A2AC-B94E6E9D3E48 | SM-117 | 3A7CDB34-ACD1-4162-B331-2FE3076BE201 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-117ST1 FWR.pdf |  | No |  | Uploads\3a7cdb34-acd1-4162-b331-2fe3076be201.pdf | Exist
Atikah | Yes | 07DD63E4-3B05-4196-9666-3C00EB5FC073 | 1D73CF38-8474-4B9B-A2AC-B94E6E9D3E48 | SM-117 | F0F168EE-FB23-48B7-B902-7297C362D149 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM 117.pdf | SM 117.pdf | Yes |  | Uploads\f0f168ee-fb23-48b7-b902-7297c362d149.pdf | Exist
Atikah | Yes | DD749711-CD72-4813-B7A3-6F74DF528E67 | D5F89637-88D2-4A38-B540-B962C03FBC7A | BEKOK-BB18ST1 | 2FD01A61-EE1B-4358-A039-89C1E13C62BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BB18_Final Well Report_Final_021222.pdf |  | No |  | Uploads\2fd01a61-ee1b-4358-a039-89c1e13c62be.pdf | Exist
Atikah | Yes | A15D47B3-76FA-4CC3-AF0B-DE7BF58DD4AE | D5F89637-88D2-4A38-B540-B962C03FBC7A | BEKOK-BB18ST1 | 239E3494-46CE-4971-825D-2B7E6149F679 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 1. NOOP Bekok BB18.pdf |  | No |  | Uploads\239e3494-46ce-4971-825d-2b7e6149f679.pdf | Exist
Atikah | Yes | 4991F4F6-CAF7-40CE-83BA-0F26563C3B7C | 3EC88A08-60E4-4533-8DEB-B97016BCCBDE | D35-211 | 6397170C-5458-44A1-8D68-AB9EEED04170 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-211 S1 NOOP_FINAL - Signed.pdf | D35-211 S1 NOOP_FINAL - Signed.pdf | Yes |  | Uploads\6397170c-5458-44a1-8d68-ab9eeed04170.pdf | Exist
Atikah | Yes | 70E4D551-E3C6-4B8E-9016-0ECDAEFD891B | 3EC88A08-60E4-4533-8DEB-B97016BCCBDE | D35-211 | 23A7AB7B-E5D6-455A-ADCC-6276BFD94F60 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35 -211S1 Final Well Report -Final.pdf | D35 -211S1 Final Well Report -Final.pdf | Yes |  | Uploads\23a7ab7b-e5d6-455a-adcc-6276bfd94f60.pdf | Exist
Atikah | Yes | 59660520-AC6A-48C7-9593-5CD22C5E6DE0 | 89959F19-098A-4061-BC4F-B99C94D256D4 | BY-416 | 1957E5A9-8577-4162-9B8E-34CBB101CA53 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-416 Notice of Operations APPROVED_INTERNAL COPY.pdf | BY-416 Notice of Operations APPROVED_INTERNAL COPY.pdf | Yes |  | Uploads\1957e5a9-8577-4162-9b8e-34cbb101ca53.pdf | Exist
Atikah | Yes | 45AAA868-1957-4DDD-85BB-D031D7237644 | 89959F19-098A-4061-BC4F-B99C94D256D4 | BY-416 | F06E70A4-F536-4467-B5F1-32B93E68CF77 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-416 Final Well Report_Bayan Redevelopment Project.pdf | BY-416 Final Well Report_Bayan Redevelopment Project.pdf | Yes |  | Uploads\f06e70a4-f536-4467-b5f1-32b93e68cf77.pdf | Exist
Atikah | Yes | 5D7096C5-12D7-4953-81A2-A7A5029B6E61 | D00F90A1-CB97-4137-B55E-BA2E35C36018 | EBA-06ST2 | B0F7F45D-22DA-48F9-B877-D0738B10DAD4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-06ST2 FWR.pdf | EBA-06ST2 FWR.pdf | Yes |  | Uploads\b0f7f45d-22da-48f9-b877-d0738b10dad4.pdf | Exist
Atikah | Yes | AF98B1AB-668F-4862-946E-1755DD8D8185 | D00F90A1-CB97-4137-B55E-BA2E35C36018 | EBA-06ST2 | 050F8AFD-D69D-473B-9D53-4BEDD61CE3CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-06ST2 NOOP FINAL APPROVED.pdf |  | No |  | Uploads\050f8afd-d69d-473b-9d53-4bedd61ce3cd.pdf | Exist
Atikah | Yes | 5684C3AF-57F4-4512-9B87-A161BD2F7D4A | 411B4E79-8191-4B16-B782-BAECABB6C524 | BUNGA KESUMBA A-1(A) | 171461C1-4FFD-41CD-8D02-21D5B71C657D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Kesumba A-1 (A)_Final.pdf |  | No |  | Uploads\171461c1-4ffd-41cd-8d02-21d5b71c657d.pdf | Exist
Atikah | Yes | 44AD7CF5-73DC-48B5-BB30-E81E83C1F3A9 | 411B4E79-8191-4B16-B782-BAECABB6C524 | BUNGA KESUMBA A-1(A) | FC43D161-D53A-418B-8F6B-187E75667712 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | B.Kesumba A-1_ Rev0_22062017 - PETRONAS SUBMISSION_FINAL.pdf |  | No |  | Uploads\fc43d161-d53a-418b-8f6b-187e75667712.pdf | Exist
Atikah | Yes | 09798A97-BAEB-4A7F-B6D8-0FBEB36FE34C | F2535EF1-E4F6-408F-9144-BAF447AED9B4 | ANGSI-B27 ST3 | BC7F2056-8CE7-44DE-AA7C-D0BAA70626DB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Angsi B27ST3 Final Well Report.pdf | Angsi B27ST3 Final Well Report.pdf | Yes |  | Uploads\bc7f2056-8ce7-44de-aa7c-d0baa70626db.pdf | Exist
Atikah | Yes | 697F13EF-6484-4591-8207-07D7962C4C4C | F2535EF1-E4F6-408F-9144-BAF447AED9B4 | ANGSI-B27 ST3 | 13A1FD65-DA62-4B3F-A81C-E28B7DE69762 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWSA8_ANGSI-B27ST3_PCSB_NOOP.pdf | PMO3ANSIWSA8_ANGSI-B27ST3_PCSB_NOOP.pdf | Yes |  | Uploads\13a1fd65-da62-4b3f-a81c-e28b7de69762.pdf | Exist
Atikah | Yes | 4BC02E19-37F6-4C32-A83D-3BDB39D34E25 | E8548F32-7BB5-4ECE-80FF-BAFC63D951F9 | GOREK-1 | BE5E83A0-FDBC-4F06-B41A-4632B1DEE42A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gorek-1 Final Well Report 3rd July 2014.pdf | Gorek-1 Final Well Report 3rd July 2014.pdf | Yes |  | Uploads\be5e83a0-fdbc-4f06-b41a-4632b1dee42a.pdf | Exist
Atikah | Yes | 774F0C92-B111-49E2-BBA9-875B8DC115D8 | E8548F32-7BB5-4ECE-80FF-BAFC63D951F9 | GOREK-1 | 5CA3642D-0E60-45C2-B60C-5EE5A0BC8FB6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3GREKWS04_GOREK-1.pdf | SKO3GREKWS04_GOREK-1.pdf | Yes |  | Uploads\5ca3642d-0e60-45c2-b60c-5ee5a0bc8fb6.pdf | Exist
Atikah | Yes | CA54A476-355E-4B8A-BF56-622329BD097C | A1583F55-2FBE-427E-A13B-BB7E891275C0 | SM-103 | 0BD08A0E-95A7-4F09-B804-4B368881F473 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL36_SM-103_PCSB_NOOP.pdf | SBO3SMRGGL36_SM-103_PCSB_NOOP.pdf | Yes |  | Uploads\0bd08a0e-95a7-4f09-b804-4b368881f473.pdf | Exist
Atikah | Yes | 24CEE87D-AE21-4931-A026-A53A7D27AF06 | A1583F55-2FBE-427E-A13B-BB7E891275C0 | SM-103 | 72F05EC1-A699-4926-A157-F9818F4C3160 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSER_SM-103_PCSB_FWR.pdf | SBO3SMRGWSDY_SM-103_PCSB_FWR.pdf | No |  | Uploads\72f05ec1-a699-4926-a157-f9818f4c3160.pdf | Exist
Atikah | Yes | 96784BBA-1DB3-4D85-B450-815CF654057B | 1CE3D497-F6DB-4FE7-85FE-BC01D550B225 | AJK-A1 | 0DF0BADF-29BB-4765-B30D-42EA5C91E8CB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ANJKWS04_AJK_A1.pdf | SKO3ANJKWS04_AJK_A1.pdf | Yes |  | Uploads\0df0badf-29bb-4765-b30d-42ea5c91e8cb.pdf | Exist
Atikah | Yes | 5E9692C3-D6F8-403A-A74E-7799F618B626 | 1CE3D497-F6DB-4FE7-85FE-BC01D550B225 | AJK-A1 | 909CAD64-E0BB-4E9D-A409-290581FDBB89 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ANJKWS06_AJK_A1.pdf | SKO3ANJKWS06_AJK_A1.pdf | Yes |  | Uploads\909cad64-e0bb-4e9d-a409-290581fdbb89.pdf | Exist
Atikah | Yes | BB85BFD0-2EB7-424A-AA62-5C24B61DA4CB | 098FD75F-C1B3-48F9-9470-BC8C5BA0168F | BN-73 | 2F816A7A-AB8A-4472-B944-3E87BD40F642 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-73 BN14Z1 - NOOP.pdf | BN-73 BN14Z1 - NOOP.pdf | Yes |  | Uploads\2f816a7a-ab8a-4472-b944-3e87bd40f642.pdf | Exist
Atikah | Yes | BA28A39C-01A9-4589-8967-CBBC7B3779B3 | 098FD75F-C1B3-48F9-9470-BC8C5BA0168F | BN-73 | FC113794-80EF-46D7-BA9D-1010A835BB63 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARONIA-J73 FWR.pdf | BARONIA-BN-73 FWR.pdf | No |  | Uploads\fc113794-80ef-46d7-ba9d-1010a835bb63.pdf | Exist
Atikah | Yes | 3340EBF5-2F3C-4F98-AE5B-B6548A41C065 | 180B92FB-EB71-41E9-B0A3-BCBC14E82EB9 | SEPAT-9 | 0349773B-6ABB-4DA2-8789-3AB3B631A1AB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sepat 9 FWR - finalized.pdf | Sepat 9 FWR - finalized.pdf | Yes |  | Uploads\0349773b-6abb-4da2-8789-3ab3b631a1ab.pdf | Exist
Atikah | Yes | D9888169-3ADB-4C0B-9887-0CD99D3923F2 | 180B92FB-EB71-41E9-B0A3-BCBC14E82EB9 | SEPAT-9 | 53A5E7BE-EC5C-484F-B4ED-2D38B25E7B9D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Sepat-9 (approved).pdf | NOOP Sepat-9 (approved).pdf | Yes |  | Uploads\53a5e7be-ec5c-484f-b4ed-2d38b25e7b9d.pdf | Exist
Atikah | Yes | 63B9B159-0609-4566-95F8-73D0190D9A77 | 01E92C88-2507-48E8-8537-BD5FF4DA0AA4 | GOPA-12 | 37DE5D0E-21F2-4AC4-9A40-702C2EA399CE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GOPA-12 NOOP Rev0.pdf | GOPA-12 NOOP Rev0.pdf | Yes |  | Uploads\37de5d0e-21f2-4ac4-9a40-702c2ea399ce.pdf | Missing
Atikah | Yes | 8A379375-0C4C-4B72-8467-B93D551DAC90 | 01E92C88-2507-48E8-8537-BD5FF4DA0AA4 | GOPA-12 | 58DF4905-1102-434D-95A7-522A3D41188C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GOPA-12 EOWR FINAL.pdf | GOPA-12 EOWR FINAL.pdf | Yes |  | Uploads\58df4905-1102-434d-95a7-522a3d41188c.pdf | Missing
Atikah | Yes | 63FC3D1F-6162-4841-AD9D-DC10C3719C0B | 26D14DBC-2740-45D2-BBBD-BD83816EEFE9 | BY-417 | 772BF715-7C8F-4D07-A046-07C570EE6687 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-417 Notice of Operation APPROVED_INTERNAL CIRCULATION.pdf | BY-417 Notice of Operation APPROVED_INTERNAL CIRCULATION.pdf | Yes |  | Uploads\772bf715-7c8f-4d07-a046-07c570ee6687.pdf | Exist
Atikah | Yes | AC35F687-1728-4F6C-8B03-EE290B567C30 | 26D14DBC-2740-45D2-BBBD-BD83816EEFE9 | BY-417 | E3EE87D7-06C6-4220-B05A-ECB0D02D205A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-417 Final Well Report_Bayan Redevelopment Project.pdf | BY-417 Final Well Report_Bayan Redevelopment Project.pdf | Yes |  | Uploads\e3ee87d7-06c6-4220-b05a-ecb0d02d205a.pdf | Exist
Atikah | Yes | 8F81BCB3-FBFC-4EC7-9776-B31196988FB2 | CC2F2D7F-F12B-4BA0-A76E-BDF69B5A8CFC | JEREMIN-1 | D4A9D14F-DED9-415F-AA75-EC5A77B7F536 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jeremin-1 NOOP - rev 1.1 copy.pdf | Jeremin-1 NOOP - rev 1.1 copy.pdf | Yes |  | Uploads\d4a9d14f-ded9-415f-aa75-ec5a77b7f536.pdf | Exist
Atikah | Yes | 8E82D669-02CA-4D4B-8C4B-104916EB5C00 | CC2F2D7F-F12B-4BA0-A76E-BDF69B5A8CFC | JEREMIN-1 | 0BF1C07F-6269-4932-9207-6E0D8B525B7B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3JRMNWS02_JEREMIN_1.pdf |  | No |  | Uploads\0bf1c07f-6269-4932-9207-6e0d8b525b7b.pdf | Exist
Atikah | Yes | 0AD029D4-31D1-4F7C-AB03-40756014E645 | 5AD3B1B7-EAFF-4781-AEF9-BE5751701C39 | TT-A1 | 09F29ABF-2C65-43F6-9989-1C6B74904BB3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TT-A1.pdf | NOOP TT-A1.pdf | Yes |  | Uploads\09f29abf-2c65-43f6-9989-1c6b74904bb3.pdf | Exist
Atikah | Yes | BFD29822-EDA5-4F1D-9FC0-43F4FBC82140 | 5AD3B1B7-EAFF-4781-AEF9-BE5751701C39 | TT-A1 | D75C54DE-F2A7-4252-98CA-D8C311A80720 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TT-A1 FWR Phase 1B 2019.pdf | TT-A1 FWR Phase 1B 2019.pdf | Yes |  | Uploads\d75c54de-f2a7-4252-98ca-d8c311a80720.pdf | Exist
Atikah | Yes | 49C9074F-FC91-4BBC-B2AD-49F6C4646572 | 9A4F2C90-1525-478B-8B29-BE5D2CF31487 | BN-77 | 4324E7D5-C0CA-4358-A6AF-C0362B7C3695 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-77 Final (Internal) Rev1.pdf | NOOP BN-77 Final (Internal) Rev1.pdf | Yes |  | Uploads\4324e7d5-c0ca-4358-a6af-c0362b7c3695.pdf | Exist
Atikah | Yes | 2B5AFCE8-85B2-46C9-94EA-66C8C7C66178 | 9A4F2C90-1525-478B-8B29-BE5D2CF31487 | BN-77 | 59DD06F1-633B-4D62-94B8-E83A6A202F98 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARONIA-BN77 FWR.pdf | BARONIA-BN77 FWR.pdf | Yes |  | Uploads\59dd06f1-633b-4d62-94b8-e83a6a202f98.pdf | Exist
Atikah | Yes | B0D6F99D-19A1-438E-83E6-92D39C940F55 | 4B7E1080-9E04-42C8-B7C2-BE71266C7417 | BOKOR-E506 | FB4C469A-D1D8-4969-A1C4-949D32D7006B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BO-506 FINAL_Rev_MSD_approved by AAR.pdf |  | No |  | Uploads\fb4c469a-d1d8-4969-a1c4-949d32d7006b.pdf | Exist
Atikah | Yes | A0D3D887-571A-48EB-8347-136F2BB48336 | 4B7E1080-9E04-42C8-B7C2-BE71266C7417 | BOKOR-E506 | C93FDA5B-7F2A-4AB2-8074-DB3E706A8BDB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR-E506.pdf | FWR BOKOR-E506.pdf | Yes |  | Uploads\c93fda5b-7f2a-4ab2-8074-db3e706a8bdb.pdf | Exist
Atikah | Yes | AE57929D-01FB-4CD3-B4B4-2368D7C60679 | 6327AE56-3A0B-41B2-9381-BED60E78C283 | S-NE1-P10 | 18948BF6-D842-4F32-9CC9-4400E1ED7BDC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-K-56-DNC-RP-0001-00_S-CNI-P10ST1 EOWR.pdf |  | No |  | Uploads\18948bf6-d842-4f32-9cc9-4400e1ed7bdc.pdf | Exist
Atikah | Yes | F0E393C3-EC38-41D8-8BD3-F813030D3CAF | 6327AE56-3A0B-41B2-9381-BED60E78C283 | S-NE1-P10 | 1CA772E9-918A-4D80-8B82-4E86D6FFF230 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf |  | No |  | Uploads\1ca772e9-918a-4d80-8b82-4e86d6fff230.pdf | Exist
Atikah | Yes | 20231CD8-425B-4566-A0D0-CA3E70B832BD | 8AE15DE3-7D77-4CDC-9BA3-BED953DCACA8 | F9-A6 | B84B692A-24B3-451A-A5A8-B75A15C8A9BE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F9A6 FWR (without attachment)_Final.pdf | F9A6 FWR (without attachment)_Final.pdf | Yes |  | Uploads\b84b692a-24b3-451a-a5a8-b75a15c8a9be.pdf | Exist
Atikah | Yes | B16D8B49-3CFC-409F-8589-B9634C74C8F6 | 8AE15DE3-7D77-4CDC-9BA3-BED953DCACA8 | F9-A6 | A008877F-059B-4D7F-91D9-612AD41EBB7B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 1. F9 Redev 2.0_A6 NOOP Signed RL TR.pdf |  | No |  | Uploads\a008877f-059b-4d7f-91d9-612ad41ebb7b.pdf | Exist
Atikah | Yes | C64181CB-26DE-4BF6-9638-DC7995CE6DD7 | F3F395E0-621B-46C9-805F-BF0574D82277 | S-SW1-P17 | 151F31A8-616C-4957-B145-79952BFAD23A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-K-56-DNC-RP-0004-00_S-SW1-P17 EOWR.pdf | MY-K-56-DNC-RP-0004-00_S-SW1-P17 EOWR.pdf | Yes |  | Uploads\151f31a8-616c-4957-b145-79952bfad23a.pdf | Exist
Atikah | Yes | 600AD254-2C6C-4C63-9E09-0D62DE53911E | F3F395E0-621B-46C9-805F-BF0574D82277 | S-SW1-P17 | C6C06AD7-E6A6-4B84-ACC1-08545C0B09CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf |  | No |  | Uploads\c6c06ad7-e6a6-4b84-acc1-08545c0b09cd.pdf | Exist
Wadi | Yes | C8C7DB0E-99E8-4E10-AF6D-77AE8ED33E3B | D3E14C0C-8124-48BD-87FE-BF88669FF287 | BERGADING-D4 (A) | 2564519C-6D77-4244-B560-95B811574B62 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading D-4_ Rev0_21062017 - PETRONAS SUBMISSION_FINAL.pdf |  | No |  | Uploads\2564519c-6d77-4244-b560-95b811574b62.pdf | Exist
Atikah | Yes | 8C8EC7AF-1221-43E3-929A-C57CFDC6A7D0 | D3E14C0C-8124-48BD-87FE-BF88669FF287 | BERGADING-D4 (A) | 3F4FEE1D-1053-4C97-83B5-833C7EBC1389 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading D-4 (A) R0_FINAL.pdf | Bergading D-4 (A) R0_FINAL.pdf | Yes |  | Uploads\3f4fee1d-1053-4c97-83b5-833c7ebc1389.pdf | Exist
Atikah | Yes | C9FBF1AC-693F-41AA-8073-DBB342DE99F0 | D3474DDD-E303-4431-82AD-BFBF31521381 | ANDING UTARA-3 | A62E2796-BF65-4D56-B007-E35F22852901 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANDUWS28_ANDING UTARA-3_PCSB_FWR.pdf | PMO3ANDUWS28_ANDING UTARA-3_PCSB_FWR.pdf | Yes |  | Uploads\a62e2796-bf65-4d56-b007-e35f22852901.pdf | Exist
Atikah | Yes | 2C692BBB-4E62-49B3-9AFD-8D281BD914CA | D3474DDD-E303-4431-82AD-BFBF31521381 | ANDING UTARA-3 | 822CBFBE-1DC1-4C61-A9CB-27A32F967CF9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANDUWS22_ANDING UTARA-3_PCSB_NOOP.pdf | PMO3ANDUWS22_ANDING UTARA-3_PCSB_NOOP.pdf | Yes |  | Uploads\822cbfbe-1dc1-4c61-a9cb-27a32f967cf9.pdf | Exist
Atikah | Yes | 3D61E53D-4FE7-4B66-BE18-60B191DA753B | FCB0E752-E4C3-4DC1-8834-BFD90F7C0F16 | TANGGU-1 | 6A44DFE6-0EC7-4B0E-90AB-D66FDF443ECF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tanggu-1 ST1 Final Well Report (1).pdf | Tanggu-1 ST1 Final Well Report (1).pdf | Yes |  | Uploads\6a44dfe6-0ec7-4b0e-90ab-d66fdf443ecf.pdf | Exist
Atikah | Yes | 6647B0CD-C52F-4882-AF26-E390CD912CAB | FCB0E752-E4C3-4DC1-8834-BFD90F7C0F16 | TANGGU-1 | 6AD8D893-463B-42E3-AE82-35E7FD7F7EAA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Tanggu-1 Final.pdf | NOOP - Tanggu-1 Final.pdf | Yes |  | Uploads\6ad8d893-463b-42e3-ae82-35e7fd7f7eaa.pdf | Exist
Atikah | Yes | 821DD827-7091-4A7D-A8DF-0752DE5C41F1 | 17A1A48D-09ED-4BC8-A73C-BFFD43CEEBFE | GEDOMBAK-1 | 5F4A9C76-8182-410D-976C-8DE12B412AA4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gedombak-1 Final Well Report with attachments.pdf | Gedombak-1 Final Well Report with attachments.pdf | Yes |  | Uploads\5f4a9c76-8182-410d-976c-8de12b412aa4.pdf | Exist
Atikah | Yes | CA6594D5-C3D1-4731-BD6E-267139F3349F | 17A1A48D-09ED-4BC8-A73C-BFFD43CEEBFE | GEDOMBAK-1 | 2C825E66-B75B-4AD1-88D1-5D132EDAC512 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gedombak-1 NOOP 2022.pdf | Gedombak-1 NOOP 2022.pdf | Yes |  | Uploads\2c825e66-b75b-4ad1-88d1-5d132edac512.pdf | Exist
Atikah | Yes | 08B797C9-5B60-4C23-9314-6A5A56AE88E2 | 10E60ECA-ED65-46DA-BC3C-C009C181D220 | SEPAT A-03 | 0D3B79BB-7591-4D8A-9515-1385AD7B8AFA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATWS76_SEPAT-A3.pdf |  | No |  | Uploads\0d3b79bb-7591-4d8a-9515-1385ad7b8afa.pdf | Exist
Atikah | Yes | 7D3E2455-A603-4EB6-917B-A174BE0FFDCF | 10E60ECA-ED65-46DA-BC3C-C009C181D220 | SEPAT A-03 | 09225A47-7F97-4C33-B2DA-042E80031EA5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL25_SEPAT-A3.pdf |  | No |  | Uploads\09225a47-7f97-4c33-b2da-042e80031ea5.pdf | Exist
Atikah | Yes | 4D0B6C05-1E29-4481-A4FD-6C86AAD7E115 | 11FEE9FA-754C-4A67-89A4-C08BDDBB4B3B | BUNGA ZETUNG A-3 (F) | 108CC537-601B-414F-B671-998358FEB07D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Zetung A-3F_Final.pdf | EOWR_Bunga Zetung A-3F_Final.pdf | Yes |  | Uploads\108cc537-601b-414f-b671-998358feb07d.pdf | Exist
Atikah | Yes | 89C56197-9314-400C-9A09-70F80CE6ECDB | 11FEE9FA-754C-4A67-89A4-C08BDDBB4B3B | BUNGA ZETUNG A-3 (F) | FE003213-0EFC-4DF5-A633-0080FA9561CC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BZA_Rev0_Final.pdf |  | No |  | Uploads\fe003213-0efc-4df5-a633-0080fa9561cc.pdf | Exist
Atikah | Yes | 5AFC4FC7-62F7-4E26-A582-015341B6B564 | 6BDB68B5-EEA3-4566-A996-C0DB281073AD | EB A-22ST2 | 666C11B5-1E5D-4A33-8FFD-A4794BA13078 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-22ST2 End of Well Report FINAL.pdf | EB A-22ST2 End of Well Report FINAL.pdf | Yes |  | Uploads\666c11b5-1e5d-4a33-8ffd-a4794ba13078.pdf | Exist
Atikah | Yes | F97C08F6-11C7-40D3-8B4C-3EB89A8E512E | 6BDB68B5-EEA3-4566-A996-C0DB281073AD | EB A-22ST2 | 26874728-D7AD-420C-8A4D-2027D8BB69AF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-22ST2.pdf | EB A-22ST2.pdf | Yes |  | Uploads\26874728-d7ad-420c-8a4d-2027d8bb69af.pdf | Exist
Atikah | Yes | 312050BB-867E-4271-83C7-1CF4A165CF03 | C851F993-ADFF-4BCA-BFDD-C0E4E6A7A467 | TBK-A3ST1 | 00715876-DBC0-4F59-8970-AE79D89F7746 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TBK-A3.pdf |  | No |  | Uploads\00715876-dbc0-4f59-8970-ae79d89f7746.pdf | Exist
Atikah | Yes | 7A23CF8F-6753-44BC-BA06-E18C5ABE0A6F | C851F993-ADFF-4BCA-BFDD-C0E4E6A7A467 | TBK-A3ST1 | 9A284B95-ED04-4A3E-B115-A6951771420F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A3ST1ST2 Final Well Report.pdf | TBK-A3ST1ST2 Final Well Report.pdf | Yes |  | Uploads\9a284b95-ed04-4a3e-b115-a6951771420f.pdf | Exist
Atikah | Yes | C06B0FA0-B1D5-4EB6-8E2D-3165397AF0BD | 4D3CBCB9-34AC-467A-BC92-C14C3A68EE25 | TABU-A09 ST1 | 333720B6-9784-4915-AE90-9730A6960786 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TuA9ST1 Final Well Report.pdf | TuA9ST1 Final Well Report.pdf | Yes |  | Uploads\333720b6-9784-4915-ae90-9730a6960786.pdf | Exist
Atikah | Yes | 818D368F-D014-4404-AC33-AC271A06EB39 | 4D3CBCB9-34AC-467A-BC92-C14C3A68EE25 | TABU-A09 ST1 | CC6DA60D-ED82-4DAF-BF38-C10C589F05E8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Tabu A9ST1 Slot 24 NOOP.pdf | Tabu A9ST1 Slot 24 NOOP.pdf | Yes |  | Uploads\cc6da60d-ed82-4daf-bf38-c10c589f05e8.pdf | Exist
Atikah | Yes | C8F3674C-3BBE-468D-841A-2FD082EB52B3 | 3A2DEB54-FF26-4795-AA6E-C18042B6D8C4 | BEKOK-AA17 | 12CB801D-3989-4560-956B-1CC5AA0E0773 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA17 Rev 1.pdf | NOOP Bekok AA17 Approved [Internal}.pdf | No |  | Uploads\12cb801d-3989-4560-956b-1cc5aa0e0773.pdf | Exist
Atikah | Yes | DF054125-A4CC-4E00-8C9A-E6B7DA4D19E9 | 3A2DEB54-FF26-4795-AA6E-C18042B6D8C4 | BEKOK-AA17 | 4EBB33C0-F7CD-4D4D-9251-E243325579A7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report Bekok-AA17ST1_FINAL.pdf | Petronas Final Well Report Bekok-AA17ST1_FINAL.pdf | Yes |  | Uploads\4ebb33c0-f7cd-4d4d-9251-e243325579a7.pdf | Exist
Atikah | Yes | 581C767E-926C-427A-BC81-0F9E0B67BAEB | 5C2DA3B9-B12D-4414-91B1-C2058115978F | KEBAYA-1 | C41E35DF-CEDE-4A20-AA20-23E54C8B140B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3KBYAWS02_KEBAYA-1.pdf | PMO3KBYAWS02_KEBAYA-1.pdf | Yes |  | Uploads\c41e35df-cede-4a20-aa20-23e54c8b140b.pdf | Exist
Atikah | Yes | 43A6C56A-77DD-4508-8593-5762C02402FD | 5C2DA3B9-B12D-4414-91B1-C2058115978F | KEBAYA-1 | 7C43F183-4A27-43B6-9566-7A039A693C9B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3KBYAWS04_KEBAYA-1.pdf | PMO3KBYAWS04_KEBAYA-1.pdf | Yes |  | Uploads\7c43f183-4a27-43b6-9566-7a039a693c9b.pdf | Exist
Atikah | Yes | F83339F6-8347-40DA-A592-9291191FBB23 | A8615D7D-0352-4259-9E62-C208E09D7E7B | BERGADING-A6(G) | 429FB99F-F0F7-47C5-A31B-33288E25C645 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRG A-6(G) - FINAL Signed.pdf |  | No |  | Uploads\429fb99f-f0f7-47c5-a31b-33288e25c645.pdf | Exist
Atikah | Yes | 72E67A80-A929-464B-991A-FBBC11482929 | A8615D7D-0352-4259-9E62-C208E09D7E7B | BERGADING-A6(G) | 0083B0D9-3CE6-414A-89FE-04A4F0DDF96D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading A-6_ EoWR Final.pdf |  | No |  | Uploads\0083b0d9-3ce6-414a-89fe-04a4f0ddf96d.pdf | Exist
Atikah | Yes | 37BA1603-48A1-4BDA-8ABE-FED933C7F82C | 6630C0BB-55F0-4C64-99AF-C242A3916A9B | BU-3 | 2D373F92-217C-44E3-B036-D977965AF783 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU-3 EOWR Final.pdf | BU-3 EOWR Final.pdf | Yes |  | Uploads\2d373f92-217c-44e3-b036-d977965af783.pdf | Exist
Atikah | Yes | 52275E43-865F-4A47-BD29-7A893CB555F6 | 6630C0BB-55F0-4C64-99AF-C242A3916A9B | BU-3 | 4ED79A4B-AB3C-45B6-A4F1-6859FB8E947B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BU3 NOOP R1.0.pdf | BU3 NOOP R1.0.pdf | Yes |  | Uploads\4ed79a4b-ab3c-45b6-a4f1-6859fb8e947b.pdf | Exist
Atikah | Yes | 11EC311B-79FD-499B-A83F-89BE697A8568 | 2321E445-23A2-405F-A693-C248BEA4C4A1 | PRPA-11 | 86D28974-FCB1-4B6C-BD1D-C06E4E93BF54 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-11ST1 EOWR.pdf | PRPA-11ST1 EOWR.pdf | Yes |  | Uploads\86d28974-fcb1-4b6c-bd1d-c06e4e93bf54.pdf | Exist
Atikah | Yes | E0718050-CDF9-4036-A68C-B7D16930537F | 2321E445-23A2-405F-A693-C248BEA4C4A1 | PRPA-11 | EA0EAE45-C162-4C38-BF7B-85EB305E6F91 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PERMAS Revisit 1 PHASE 1 NOOP_Rev 1 (1)_PRPA-10-11-12.pdf |  | No |  | Uploads\ea0eae45-c162-4c38-bf7b-85eb305e6f91.pdf | Exist
Atikah | Yes | C0C01B0B-3501-4F4B-9709-B876FB5F1FFA | 2ACB5AD1-AD5D-4BC2-AE67-C24C90D82D95 | S-CN2-W2 | 52CE4C7B-3EAF-44B3-8F2C-9C34503D3F84 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPWSA3_S_CN2_W2.pdf | SBO3SKNPWSA3_S_CN2_W2.pdf | Yes |  | Uploads\52ce4c7b-3eaf-44b3-8f2c-9c34503d3f84.pdf | Exist
Atikah | Yes | DA956005-A56C-474E-B7D9-13B040E2D9E1 | 2ACB5AD1-AD5D-4BC2-AE67-C24C90D82D95 | S-CN2-W2 | 16DCE693-368E-4D5C-A84A-5C51047ED3D2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPWS25_S_CN2_W2.pdf | SBO3SKNPWS25_S_CN2_W2.pdf | Yes |  | Uploads\16dce693-368e-4d5c-a84a-5c51047ed3d2.pdf | Exist
Atikah | Yes | E1620E45-18C4-473D-9C2E-C776F4A8558E | 762D6D3C-F3E6-4737-92E8-C2AEF1A5D897 | SF30-6 ST1 | 39C8C978-CCB8-4CC4-9541-5E6F37779E83 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-6ST1 NOOP (MPM Drilling).pdf | SF30-6ST1 NOOP (MPM Drilling).pdf | Yes |  | Uploads\39c8c978-ccb8-4cc4-9541-5e6f37779e83.pdf | Exist
Atikah | Yes | 49EC3564-B992-4D1E-8AD1-CFFBD1C5EFC3 | 762D6D3C-F3E6-4737-92E8-C2AEF1A5D897 | SF30-6 ST1 | 28AAE4B3-A72E-46D9-92E9-2F4F7CEEEB20 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-6ST EOWR (MPM Drilling).pdf |  | No |  | Uploads\28aae4b3-a72e-46d9-92e9-2f4f7ceeeb20.pdf | Exist
Atikah | Yes | 9BBF22C4-7E96-48C8-82E2-13CB01A3A356 | 03ACC1BF-03C5-467F-B6EB-C2AF71808F7A | MERSING-1 | B2ED1B6B-4C19-46D0-844C-015CCB53D0E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mersing-1 Drilling EOWR.pdf | Mersing-1 Drilling EOWR.pdf | Yes |  | Uploads\b2ed1b6b-4c19-46d0-844c-015ccb53d0e8.pdf | Exist
Atikah | Yes | 7CC5D270-DE11-4F3E-BB3C-7046D199EFE4 | 03ACC1BF-03C5-467F-B6EB-C2AF71808F7A | MERSING-1 | E50FE94F-1D9A-45AA-9904-577FD453C81B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mersing-1_Signed.pdf | Mersing-1_Signed.pdf | Yes |  | Uploads\e50fe94f-1d9a-45aa-9904-577fd453c81b.pdf | Exist
Atikah | Yes | E200A903-2925-49A1-A840-90522C63CB55 | 98E0C4B4-C43F-47E5-85A1-C2D89C3EA723 | ROTAN-2 | 45012B3A-40C4-41D6-88E1-042B684F6169 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SB_Block_H_Rotan-2_NOOP_MY-H-58-DR-RP-0003-00.pdf | SB_Block_H_Rotan-2_NOOP_MY-H-58-DR-RP-0003-00.pdf | Yes |  | Uploads\45012b3a-40c4-41d6-88e1-042b684f6169.pdf | Exist
Atikah | Yes | 1EFE6056-9C43-4CD2-A947-102E72110090 | 98E0C4B4-C43F-47E5-85A1-C2D89C3EA723 | ROTAN-2 | CF67EFC9-D224-486F-8DC3-3D6052BA0FD1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Block_H_Appraisal__Rotan-2_End_Of_Well_Report_(MY-H-58-DR-RP-0005-00).pdf | Block_H_Appraisal__Rotan-2_End_Of_Well_Report_(MY-H-58-DR-RP-0005-00).pdf | Yes |  | Uploads\cf67efc9-d224-486f-8dc3-3d6052ba0fd1.pdf | Exist
Atikah | Yes | 794EB8BD-6442-4B02-800F-3491F1DCC094 | E4C8E368-F247-4051-94A5-C3394122BCF1 | SALAM-3 | D1981037-2B7A-42A7-941A-07807A96D0FB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Salam-3 RevA_2022_signed.pdf | Salam-3 RevA_2022_signed.pdf | Yes |  | Uploads\d1981037-2b7a-42a7-941a-07807a96d0fb.pdf | Exist
Atikah | Yes | 06F9937B-5F85-4790-8A9A-665560342321 | E4C8E368-F247-4051-94A5-C3394122BCF1 | SALAM-3 | C80CAF8A-6538-435E-A444-2D0F4C9B6BEB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Salam-3_EndofWell_Report_FINAL.pdf | Salam-3_EndofWell_Report_FINAL.pdf | Yes |  | Uploads\c80caf8a-6538-435e-a444-2d0f4c9b6beb.pdf | Exist
Atikah | Yes | 6FEEF126-B2CA-47C9-9E7F-69623740B7CB | FF1C85E5-D6A0-45D4-A251-C33FFA8B6A3A | EC-A04 | F3F2CAD3-BE33-44E3-8B57-95B8AFF0A88E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0002_REV.00 NOOP WELL EC-A04 (Slot 1A ECW-A Platform)_DS.pdf | ECN-GEN-D-0002_REV.00 NOOP WELL EC-A04 (Slot 1A ECW-A Platform)_DS.pdf | Yes |  | Uploads\f3f2cad3-be33-44e3-8b57-95b8aff0a88e.pdf | Exist
Atikah | Yes | F8036907-2BA2-49D7-AEA0-EB6BAB0DEAC1 | FF1C85E5-D6A0-45D4-A251-C33FFA8B6A3A | EC-A04 | 67996B2F-A8DA-49A8-A62B-D80A734F45E4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A04 Final Well Report DS.pdf | EC-A04 Final Well Report DS.pdf | Yes |  | Uploads\67996b2f-a8da-49a8-a62b-d80a734f45e4.pdf | Exist
Atikah | Yes | BCDAFCCB-380D-4E61-B3A5-E417D0368176 | D89D1620-45C5-47E2-9612-C34E9B35B44A | MONG MERAH-1 | AF29DD66-86DC-46A0-B74C-479AFB4AD889 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Mong Merah-1 NOOP_signed 2022.pdf | Mong Merah-1 NOOP_signed 2022.pdf | Yes |  | Uploads\af29dd66-86dc-46a0-b74c-479afb4ad889.pdf | Exist
Atikah | Yes | E7C12483-0DD3-4322-8362-D64AECA29963 | D89D1620-45C5-47E2-9612-C34E9B35B44A | MONG MERAH-1 | 7EB0EC6F-BFD5-494E-912C-5B5E47F299EB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3MMRHGL6505_MONG MERAH-1_PTTEP_FWR.pdf | SKO3MMRHGL6505_MONG MERAH-1_PTTEP_FWR.pdf | Yes |  | Uploads\7eb0ec6f-bfd5-494e-912c-5b5e47f299eb.pdf | Exist
Atikah | Yes | AA8111DD-1ACB-4858-9375-38D88AEE07AB | 8BCB2D48-4AE7-42A4-95C5-C40CAF84AA3D | RAMUNIA-1 | 13A58C23-D479-4288-896B-28036FC564B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RMNAWS06_RAMUNIA-1_PCSB_FWR.pdf | PMO3RMNAWS06_RAMUNIA-1_PCSB_FWR.pdf | Yes |  | Uploads\13a58c23-d479-4288-896b-28036fc564b7.pdf | Exist
Atikah | Yes | 77F2E796-0535-44AD-800F-0CB9870CECD5 | 8BCB2D48-4AE7-42A4-95C5-C40CAF84AA3D | RAMUNIA-1 | 6D90EFB2-8DED-4700-A37E-1234765EC169 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3RMNAWS05_RAMUNIA-1_PCSB_NOOP.pdf | PMO3RMNAWS05_RAMUNIA-1_PCSB_NOOP.pdf | Yes |  | Uploads\6d90efb2-8ded-4700-a37e-1234765ec169.pdf | Exist
Atikah | Yes | 8E93665A-F846-4EEF-BF03-13CD16C36DA0 | 44FF5E90-379B-430F-B0D7-C4A5C4BAEA99 | DULANG-D30 | 13810DD6-0C29-48BF-B71A-5F7995BA773B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYH_DULANG_D30.pdf | PMO3DULGWSYH_DULANG_D30.pdf | Yes |  | Uploads\13810dd6-0c29-48bf-b71a-5f7995ba773b.pdf | Exist
Atikah | Yes | 6BF6D567-8824-4842-8F98-57DC2CD61705 | 44FF5E90-379B-430F-B0D7-C4A5C4BAEA99 | DULANG-D30 | B2988736-A896-44D7-9AD8-B9913E9277BC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGGL84_DULANG_D30.pdf | PMO3DULGGL84_DULANG_D30.pdf | Yes |  | Uploads\b2988736-a896-44d7-9ad8-b9913e9277bc.pdf | Exist
Atikah | Yes | 9058940B-0BDD-4031-9621-3921A033DA5F | 9AB6DF12-A9B2-4835-81AE-C4FAAB6473D1 | D18-209A | FC5127ED-8B6D-413B-8816-4AD20E67B146 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS77_D18-209A_PCSB_NOOP.pdf | SKO3D18-WS77_D18-209A_PCSB_NOOP.pdf | Yes |  | Uploads\fc5127ed-8b6d-413b-8816-4ad20e67b146.pdf | Exist
Atikah | Yes | 2D795303-2013-48EC-BDD5-F798AE16CF35 | 9AB6DF12-A9B2-4835-81AE-C4FAAB6473D1 | D18-209A | 6E19816D-2E99-4F72-8CAB-112BF2B3D47E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D-18 209 A Final Well Report 209A (Signed).pdf | D-18 209 A Final Well Report 209A (Signed).pdf | Yes |  | Uploads\6e19816d-2e99-4f72-8cab-112bf2b3d47e.pdf | Exist
Atikah | Yes | EF5B78E5-3091-44D4-8E04-85F4F05F041D | AC4B883A-5272-43F3-A090-C50E23273A1E | TBK-B4 | E48E3122-B65B-4799-8720-21AA01206DE5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B4 Final Well Report.pdf |  | No |  | Uploads\e48e3122-b65b-4799-8720-21aa01206de5.pdf | Exist
Atikah | Yes | 1A7EB716-4582-4631-A1A2-A3302D6EDF88 | AC4B883A-5272-43F3-A090-C50E23273A1E | TBK-B4 | D45E5A8C-7661-4E5E-B7F3-0DE734A388A0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B4.pdf | TBK-B4.pdf | Yes |  | Uploads\d45e5a8c-7661-4e5e-b7f3-0de734a388a0.pdf | Exist
Atikah | Yes | 79DB033D-0FAD-4DC6-B955-4BDFCDCD9980 | 4E35DB5F-60F8-4EC6-856D-C580D3BDEC7D | SEPAT-A10 | 49B18CC6-FC29-4FCE-B73B-B8DE2003B52B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATGL32_SEPAT-A10_PCSB_NOOP.pdf | PMO3SPATGL32_SEPAT-A10_PCSB_NOOP.pdf | Yes |  | Uploads\49b18cc6-fc29-4fce-b73b-b8de2003b52b.pdf | Exist
Atikah | Yes | B9DE89AA-B0B9-4A14-99B0-CB74F0B469FF | 4E35DB5F-60F8-4EC6-856D-C580D3BDEC7D | SEPAT-A10 | 32DBF43C-FED5-4D54-B16A-3EB4D6E507AD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3SPATWS67_SEPAT-A10_PCSB_FWR.pdf | PMO3SPATWS67_SEPAT-A10_PCSB_FWR.pdf | Yes |  | Uploads\32dbf43c-fed5-4d54-b16a-3eb4d6e507ad.pdf | Exist
Atikah | Yes | 5BD764EA-2860-476C-B996-B462D718B50C | 73C3498B-804A-4138-A787-C5F19FD8074E | D21-A6 | DD515812-58E9-46D6-B9E0-2975F7B26ACB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-C2A-FB5 (P2) (D-21-A6) NOOP.pdf | D21-C2A-FB5 (P2) (D-21-A6) NOOP.pdf | Yes |  | Uploads\dd515812-58e9-46d6-b9e0-2975f7b26acb.pdf | Exist
Atikah | Yes | FE3DB93C-04C9-46CA-A1AB-F68C7B9AD04E | 73C3498B-804A-4138-A787-C5F19FD8074E | D21-A6 | A6FFB3B0-9821-4ABE-8C16-63B817734304 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21 P2 (A6) EOWR .pdf |  | No |  | Uploads\a6ffb3b0-9821-4abe-8c16-63b817734304.pdf | Exist
Atikah | Yes | FCD107B2-A494-4076-88B5-30E0988D1094 | AFCBE44E-A76E-41B8-AFFC-C65A9A731265 | D35-213 | CAE4EE94-B2DF-4C78-894E-966934AF8BFB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-213-ST1 FINAL WELL REPORT.pdf | D35-213-ST1 FINAL WELL REPORT.pdf | Yes |  | Uploads\cae4ee94-b2df-4c78-894e-966934af8bfb.pdf | Exist
Atikah | Yes | 14948053-5166-43BE-9318-97226FC5472C | AFCBE44E-A76E-41B8-AFFC-C65A9A731265 | D35-213 | 5F1AABB8-F09D-4379-B2AB-CEFDF9E706AC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-213 NOOP_Rev1 (Signed).pdf | D35-213 NOOP_Rev1 (Signed).pdf | Yes |  | Uploads\5f1aabb8-f09d-4379-b2ab-cefdf9e706ac.pdf | Exist
Atikah | Yes | AAE08B5C-0FF8-454A-A1B9-63C4C1C0BEDE | FD543C65-4B3E-404D-B209-C69BDF6CBDE3 | SEC-40 | 4207AC64-CF78-47A1-9D0E-F18F5359E00F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeC-40 Appraisal cum Development Well Final.pdf | Final Well Report SeC-40 Appraisal cum Development Well Final.pdf | Yes |  | Uploads\4207ac64-cf78-47a1-9d0e-f18f5359e00f.pdf | Exist
Atikah | Yes | 1702D12F-34FD-4626-BEB9-FFEAD6148CC9 | FD543C65-4B3E-404D-B209-C69BDF6CBDE3 | SEC-40 | 28631FBE-D053-4DA4-A628-2C03E168517A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SeC-40 Notice Of Operation (NOOP) Seligi Appraisal Cum Development Well _Final.pdf | SeC-40 Notice Of Operation (NOOP) Seligi Appraisal Cum Development Well _Final.pdf | Yes |  | Uploads\28631fbe-d053-4da4-a628-2c03e168517a.pdf | Exist
Atikah | Yes | 5CB24353-9766-4A88-9DC9-8EE5B6367F7A | C3445C5D-B056-4DA1-B610-C73C33325176 | BERGADING-C3 (C) | A374FFE2-A399-48CE-91E2-DA755C0DA19C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading C-3 (C) R0_Final.pdf | Bergading C-3 (C) R0_Final.pdf | Yes |  | Uploads\a374ffe2-a399-48ce-91e2-da755c0da19c.pdf | Exist
Atikah | Yes | D6588C49-3FB1-45DD-BC91-0A265BA812AA | C3445C5D-B056-4DA1-B610-C73C33325176 | BERGADING-C3 (C) | 564D3138-0789-41AA-B447-7BFDCF40C16E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BGDGWS43_BERGADING_C3.pdf |  | No |  | Uploads\564d3138-0789-41aa-b447-7bfdcf40c16e.pdf | Exist
Atikah | Yes | 871E7CBB-922F-48D2-B1DC-88531DC282A6 | 259C3DE0-AC75-427F-90EE-C73C5D971A22 | BPA-5 | 34967814-CDDA-4526-853F-210FED04FE77 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-5 NOOP.pdf | BPA-5 NOOP.pdf | Yes |  | Uploads\34967814-cdda-4526-853f-210fed04fe77.pdf | Exist
Atikah | Yes | 763792F6-8BBA-4E19-B18B-73ED5C635CCD | 259C3DE0-AC75-427F-90EE-C73C5D971A22 | BPA-5 | 1F5DC8CF-585E-45FC-8D68-B30B706F0515 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-5 EOWR.pdf | BPA-5 EOWR.pdf | Yes |  | Uploads\1f5dc8cf-585e-45fc-8d68-b30b706f0515.pdf | Exist
Atikah | Yes | A8CD040B-6810-4448-9280-0F56043615C6 | 17C6E3D3-9517-4AB2-BEEF-C76FEFC789FB | D35-209-ST2 | F741A4D5-2FBE-4625-9D5C-C58F31F7D31F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-209S2 NOOP_Rev1.pdf |  | No |  | Uploads\f741a4d5-2fbe-4625-9d5c-c58f31f7d31f.pdf | Exist
Atikah | Yes | F920012E-DA6D-4A16-938A-3526D632DAFC | 17C6E3D3-9517-4AB2-BEEF-C76FEFC789FB | D35-209-ST2 | 22E2A39F-7026-40D1-9089-F7B1D1F98AD1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-209S2 FINAL WELL REPORT.pdf |  | No |  | Uploads\22e2a39f-7026-40d1-9089-f7b1d1f98ad1.pdf | Exist
Atikah | Yes | 02D10F9E-21C0-4006-B0CD-8D9F51C4117F | F26C63F1-5C5D-4000-B861-C84D3088B6A9 | BO-602 | 71C4B9CB-3BA5-4500-8CEF-484F9EBC4B35 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-F602 FWR Final.pdf |  | No |  | Uploads\71c4b9cb-3ba5-4500-8cef-484f9ebc4b35.pdf | Exist
Atikah | Yes | BB637510-FE5B-4F79-BE19-E45717FD9894 | F26C63F1-5C5D-4000-B861-C84D3088B6A9 | BO-602 | D6264BB0-EE67-47FE-B782-CF568B0960E6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-602 SIGNED NOOP.pdf | BO-602 SIGNED NOOP.pdf | Yes |  | Uploads\d6264bb0-ee67-47fe-b782-cf568b0960e6.pdf | Exist
Atikah | Yes | 9DA270CA-1AF4-433B-90AB-90C064FD991E | 754594EB-59E8-4D58-ABEA-C88D1A9D580C | SINSING-1 | F6B0B75F-DE41-462A-BF9D-1DEB6DEE133D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sinsing-1_Internal NOOP.pdf | Sinsing-1_Internal NOOP.pdf | Yes |  | Uploads\f6b0b75f-de41-462a-bf9d-1deb6dee133d.pdf | Exist
Atikah | Yes | 06090B97-13A3-4AB5-994B-8164C15DE93D | 754594EB-59E8-4D58-ABEA-C88D1A9D580C | SINSING-1 | 17FEBC54-B927-4C15-BC61-DACA22498AF3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sinsing-1 FWR_w attachment.pdf | Sinsing-1 FWR_w attachment.pdf | Yes |  | Uploads\17febc54-b927-4c15-bc61-daca22498af3.pdf | Exist
Atikah | Yes | 2E67BD7A-47A0-4D89-9BE9-3D7F08911900 | 3FAF461F-144F-4A10-95CA-C8AF87C6082A | SAPA-13 | AE6DEA35-FA09-4B80-BC65-3F355F811268 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-13 EOWR.pdf | SKO3ACISWS86_SAPA-5,SAPA-13,SAPA-15,PCSB__FWR.pdf | No |  | Uploads\ae6dea35-fa09-4b80-bc65-3f355f811268.pdf | Exist
Atikah | Yes | 5BD5A78C-9C67-44B7-8737-C6F6E9DB0423 | 3FAF461F-144F-4A10-95CA-C8AF87C6082A | SAPA-13 | F7F0847B-FDC8-423F-AE57-DE03FED459D4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISWS67_SAPA-05-06-13-15_PTTEP.pdf | SKO3ACISWS67_SAPA-5,SAPA-6,SAPA-13,SAPA-15,PCSB_NOOP.pdf | No |  | Uploads\f7f0847b-fdc8-423f-ae57-de03fed459d4.pdf | Exist
Atikah | Yes | D89D9C47-B43E-4FA1-BCB1-C729C9311C7F | 69269D5C-5972-45B6-B462-C8BBB1EE9E9A | BERTAM A-11 | FF88C567-4F46-49AA-882F-D1A746B2611B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAMDR13_BERTAM-A11_IPC_FWR.pdf | PMO3BTAMDR13_BERTAM-A11_IPC_FWR.pdf | Yes |  | Uploads\ff88c567-4f46-49aa-882f-d1a746b2611b.pdf | Exist
Atikah | Yes | 987ED5D1-5A6C-412C-8DDA-20A0AFBDB6B3 | 69269D5C-5972-45B6-B462-C8BBB1EE9E9A | BERTAM A-11 | EC55126F-FCA6-419F-B41B-1D1C5CA54091 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAMWS26_BERTAM-A11-A11ST1_IPC.pdf | PMO3BTAMWS26_BERTAM-A11-A11ST1_IPC.pdf | Yes |  | Uploads\ec55126f-fca6-419f-b41b-1d1c5ca54091.pdf | Exist
Atikah | Yes | 13EB56F9-585D-4E29-97FB-B3FC690576CE | 953C1EA1-C02B-43EF-B728-C8C98A2EF357 | SASA-16 | BBC76549-7DD5-4BA7-89F6-E4F70130A3C6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf |  | No |  | Uploads\bbc76549-7dd5-4ba7-89f6-e4f70130a3c6.pdf | Exist
Atikah | Yes | 3A17E78B-AA53-4671-B1D5-F7DC39925E04 | 953C1EA1-C02B-43EF-B728-C8C98A2EF357 | SASA-16 | 6E5FFE04-DA91-45F1-9138-2990C21B50E7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf |  | No |  | Uploads\6e5ffe04-da91-45f1-9138-2990c21b50e7.pdf | Exist
Atikah | Yes | B0D9F11E-9465-4295-A899-FD3C5E88978F | D8CC1ED4-B384-4CD4-BE0F-C8EC8B595DD8 | SELUANG-1 | 10339177-4CAC-4B41-8DD7-0F390A869811 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SELUANG-1RDR1 FWR without Appendix_signed.pdf |  | No |  | Uploads\10339177-4cac-4b41-8dd7-0f390a869811.pdf | Exist
Atikah | Yes | 1E9DA129-D8C4-4D4C-AE7C-42D2EDBB52DB | D8CC1ED4-B384-4CD4-BE0F-C8EC8B595DD8 | SELUANG-1 | 2F5760F7-4E38-4CE3-8B03-26079D416206 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Seluang-1 NOOP Internal.pdf | Seluang-1 NOOP Internal.pdf | Yes |  | Uploads\2f5760f7-4e38-4ce3-8b03-26079d416206.pdf | Exist
Atikah | Yes | 1CC36211-B9C0-48A5-B673-2A1EBA7586D4 | FCB17AC4-3498-4605-9CFB-C9211656BD48 | BUNGA DAHLIA A-2 | 8212FF9A-1458-4E1A-AA1D-EFE6241D4D54 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_BDL-A2 - signed.pdf |  | No |  | Uploads\8212ff9a-1458-4e1a-aa1d-efe6241d4d54.pdf | Exist
Atikah | Yes | F31974C7-2239-4772-AD8D-8A21B9191447 | FCB17AC4-3498-4605-9CFB-C9211656BD48 | BUNGA DAHLIA A-2 | 2688A917-1DD6-432C-A171-2F9F64E51A93 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Bunga Dahlia-A2_ BDL-A2.pdf | NOOP_Bunga Dahlia-A2_ BDL-A2.pdf | Yes |  | Uploads\2688a917-1dd6-432c-a171-2f9f64e51a93.pdf | Exist
Atikah | Yes | 50CE1165-DA68-4C4F-B1AD-8B61A812F1D4 | F8DDEF00-F5EA-4962-893E-C923A1B71878 | NILAM-1 | FFA0C1A5-E166-4475-B1A5-E5EC2DF7B75F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3NILMWS08_NILAM_1.pdf | SBO3NILMWS08_NILAM_1.pdf | Yes |  | Uploads\ffa0c1a5-e166-4475-b1a5-e5ec2df7b75f.pdf | Exist
Atikah | Yes | 4172AD8D-3375-49D5-AC79-073517631BE4 | F8DDEF00-F5EA-4962-893E-C923A1B71878 | NILAM-1 | 186A9947-6217-43BF-A430-168890E64C93 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3NILMWS01_NILAM_1.pdf | SBO3NILMWS01_NILAM_1.pdf | Yes |  | Uploads\186a9947-6217-43bf-a430-168890e64c93.pdf | Exist
Atikah | Yes | 7CE3B8A8-8B94-4AA7-9AE3-2B1542B840D7 | 74983E62-22B7-4AEC-AD39-C944E0806EC7 | S-NE1-W5 | D6ABEC58-C1E8-4044-BE6D-E8F67CE0C208 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SBO-WS7H_S-NE1-W5_PTTEP_NOOP.pdf |  | No |  | Uploads\d6abec58-c1e8-4044-be6d-e8f67ce0c208.pdf | Exist
Atikah | Yes | 11A45F35-88E4-484E-A8A4-71872DC9329A | 74983E62-22B7-4AEC-AD39-C944E0806EC7 | S-NE1-W5 | 62316165-B845-4503-8A5A-9B21B48CB759 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR16_S-NE1-W5_PTTEP_FWR.pdf |  | No |  | Uploads\62316165-b845-4503-8a5a-9b21b48cb759.pdf | Exist
Atikah | Yes | BE0913F3-80EF-4848-B378-224091A1FE84 | 4385C239-D4FF-44BF-8D4A-C950B36B5920 | SEPAT BARAT-3 | 7E0125CE-40AF-4152-AE23-3DA1E464C265 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEPAT BARAT-3_NOOP_2013_PM.pdf |  | No |  | Uploads\7e0125ce-40af-4152-ae23-3da1e464c265.pdf | Exist
Atikah | Yes | B9BAE849-BA75-4EEF-97AC-D41DCBFCDFC9 | 4385C239-D4FF-44BF-8D4A-C950B36B5920 | SEPAT BARAT-3 | 1AB448A7-75CC-4641-86D0-2C49B7634A56 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEPAT BARAT-3 FWR.pdf |  | No |  | Uploads\1ab448a7-75cc-4641-86d0-2c49b7634a56.pdf | Exist
Atikah | Yes | CB2DEADB-626B-4C24-A753-C6703CEEE0EC | 1AC0FD70-83B4-4431-8362-C9D43C963E84 | DERMAWAN-1 | FF087259-BE20-45B5-B4CA-4053FAC4345F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DERMAWAN-1 SB Block H NOOP (2023).pdf | DERMAWAN-1 SB Block H NOOP (2023).pdf | Yes |  | Uploads\ff087259-be20-45b5-b4ca-4053fac4345f.pdf | Exist
Atikah | Yes | 2A24ADAD-2966-42C4-85D0-213D0094318E | 1AC0FD70-83B4-4431-8362-C9D43C963E84 | DERMAWAN-1 | 83F23653-0C83-4646-B576-2E1EEB92AFC3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Block H Exploration Dermawan-1 End Of Well Report (MY-H-10-DR-PR-0003-00).pdf | Block H Exploration Dermawan-1 End Of Well Report (MY-H-10-DR-PR-0003-00).pdf | Yes |  | Uploads\83f23653-0c83-4646-b576-2e1eeb92afc3.pdf | Exist
Atikah | Yes | 89A989E6-580B-4403-BBAB-F11611527C0A | DA5ABBE4-177D-4113-AF56-CA2A718B9AB0 | NUANG-1 | 2016096B-2C94-42A1-9A1E-A87EB5B40B87 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3NUANWS01_NUANG-1_PCSB_NOOP.pdf | SKO3NUANWS01_NUANG-1_PCSB_NOOP.pdf | Yes |  | Uploads\2016096b-2c94-42a1-9a1e-a87eb5b40b87.pdf | Exist
Atikah | Yes | 4383C575-550D-432D-8C6E-E5E3D5DC9634 | DA5ABBE4-177D-4113-AF56-CA2A718B9AB0 | NUANG-1 | F0F7FD3B-9DFE-48B4-8240-5B9D3CCB3233 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3NUANWS05_NUANG-1_PCSB_FWR.pdf | SKO3NUANWS05_NUANG-1_PCSB_FWR.pdf | Yes |  | Uploads\f0f7fd3b-9dfe-48b4-8240-5b9d3ccb3233.pdf | Exist
Atikah | Yes | DA6D7CA7-82B4-4C62-811F-F3AE771E77C9 | A53DCF80-B61C-48FB-B5D0-CA440555ACC5 | LANG LEBAH-2 | 733C8B8E-9569-4DB9-8878-CCFE2F7FDB67 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Lang Lebah-2 NOOP (Final) Rev 14 Sept 2020.pdf | Lang Lebah-2 NOOP (Final) Rev 14 Sept 2020.pdf | Yes |  | Uploads\733c8b8e-9569-4db9-8878-ccfe2f7fdb67.pdf | Exist
Atikah | Yes | F12F7C4F-3543-4DBC-A923-46C6EB2D8FAE | A53DCF80-B61C-48FB-B5D0-CA440555ACC5 | LANG LEBAH-2 | AC38EB6C-E164-4B90-A9DA-E516CCCEB201 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK410B_Lang_Lebah-2_EOWR_(Final) 25 March 2021-Signed.pdf | SK410B_Lang_Lebah-2_EOWR_(Final) 25 March 2021-Signed.pdf | Yes |  | Uploads\ac38eb6c-e164-4b90-a9da-e516ccceb201.pdf | Exist
Atikah | Yes | 6F6FCFB4-4267-4D0E-A925-7EE971D581A9 | 750A0444-070D-4CC0-B01C-CA6F06F9C35C | EC-A01 | C444D149-4FC3-4DCD-BEA1-1488F3C36956 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A01ST1 Final Well Report signedDS.pdf | EC-A01ST1 Final Well Report signedDS.pdf | Yes |  | Uploads\c444d149-4fc3-4dcd-bea1-1488f3c36956.pdf | Exist
Atikah | Yes | 06CA2E1C-4553-468D-9329-BAE5C17DAE2D | 750A0444-070D-4CC0-B01C-CA6F06F9C35C | EC-A01 | 921661E5-FC10-4269-9F75-B4951C3C75F0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOTICE OF OPERATIONS - WELL EC-A01 (Slot 1B ECW-A Platform) Signed.pdf | NOTICE OF OPERATIONS - WELL EC-A01 (Slot 1B ECW-A Platform) Signed.pdf | Yes |  | Uploads\921661e5-fc10-4269-9f75-b4951c3c75f0.pdf | Exist
Atikah | Yes | 576B1D8F-B07D-4581-8A8F-DF973CFD48A7 | BBC30033-5C36-4F47-AEE1-CA8AA40E0CBC | ANGSI-B32 | E87C4815-239A-4586-9588-77A9ACD24DC3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWSB3_ANGSI-B32_PCSB_NOOP.pdf | PMO3ANSIWSB3_ANGSI-B32_PCSB_NOOP.pdf | Yes |  | Uploads\e87c4815-239a-4586-9588-77a9acd24dc3.pdf | Exist
Atikah | Yes | 76D50A9D-A2CF-4D36-BC7B-7764A0B18644 | BBC30033-5C36-4F47-AEE1-CA8AA40E0CBC | ANGSI-B32 | 57DE56C5-9264-4931-8BB4-1F5401187663 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3ANSIWSB2_ANGSI-B32_PCSB_FWR.pdf | Angsi B32 FWR.pdf | No |  | Uploads\57de56c5-9264-4931-8bb4-1f5401187663.pdf | Exist
Atikah | Yes | 5D35CBC2-B7E2-412D-81A1-966EC1ADA0F7 | 7AEA341D-42E8-4BE3-A2B5-CAC477C0BBEB | D21-A2 | ECA3029C-2A9A-4EE4-A223-CC1B59EB7D32 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS49_D21-A2.pdf | SKO3D21-WS49_D21-A2.pdf | Yes |  | Uploads\eca3029c-2a9a-4ee4-a223-cc1b59eb7d32.pdf | Exist
Atikah | Yes | 15B3E7D7-F24B-4466-955A-1B390F962285 | 7AEA341D-42E8-4BE3-A2B5-CAC477C0BBEB | D21-A2 | 4CA0612E-29DD-4D66-90BB-312A2A6D8579 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D21-WS44_d21-a2.pdf | SKO3D21-WS44_d21-a2.pdf | Yes |  | Uploads\4ca0612e-29dd-4d66-90bb-312a2a6d8579.pdf | Exist
Atikah | Yes | 073863D1-8280-4F78-83F2-7022CF63FB21 | 05FB5405-9C1A-4601-91E7-CB32578EB25D | BOKOR-E503 | 12A25156-509F-4D8F-ADA7-7DBF347F6C28 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BOKOR-E503 Final.pdf | FWR BOKOR-E503 Final.pdf | Yes |  | Uploads\12a25156-509f-4d8f-ada7-7dbf347f6c28.pdf | Exist
Atikah | Yes | 37171BC8-2BCE-49C3-A896-BFFC8509D111 | 05FB5405-9C1A-4601-91E7-CB32578EB25D | BOKOR-E503 | 8CA9924F-B9D1-457B-8F64-11A72F96A605 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BO-503 FINAL NOOP.pdf | NOOP BOKOR-E503 FINAL signed by AAR.pdf | No |  | Uploads\8ca9924f-b9d1-457b-8f64-11a72f96a605.pdf | Exist
Atikah | Yes | 42B3FAB0-3EBA-400D-B11E-0F45B473A756 | 40DDC904-4699-4844-B416-CB3DA0A9E147 | ZE-B | D1EB1F86-99ED-4936-973A-9B8F477EECEB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ZUHAL EAST-B_NOOP_2013_SB.pdf |  | No |  | Uploads\d1eb1f86-99ed-4936-973a-9b8f477eeceb.pdf | Exist
Atikah | Yes | 900503F1-F923-49AA-ADA3-38FBD78422D1 | 40DDC904-4699-4844-B416-CB3DA0A9E147 | ZE-B | 814871BC-7162-4925-9D75-65536B8FEABE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ZUHEWS25_ZE-B.pdf | SBO3ZUHEWS25_ZE-B.pdf | Yes |  | Uploads\814871bc-7162-4925-9d75-65536b8feabe.pdf | Exist
Atikah | Yes | 81330C6F-679A-4D20-B516-96482DC5D378 | 9DE0DA65-6375-4296-9AFF-CC56082D01F1 | BESTARI-1 | D3015887-485D-4897-B835-7BBFCFCDD4DD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bestari-1 NOOP.pdf | Bestari-1 NOOP.pdf | Yes |  | Uploads\d3015887-485d-4897-b835-7bbfcfcdd4dd.pdf | Exist
Atikah | Yes | 8021722B-86BA-4B75-B115-F5C08D027772 | 9DE0DA65-6375-4296-9AFF-CC56082D01F1 | BESTARI-1 | 0FE66C30-26F7-4000-879D-470B2C42A46B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bestari-1 v1_FWR.pdf | Bestari-1 v1_FWR.pdf | Yes |  | Uploads\0fe66c30-26f7-4000-879d-470b2c42a46b.pdf | Exist
Atikah | Yes | 31EC4BC9-50C4-479B-BB69-F3D57E90BA7A | 3D4EBF80-9D1F-446F-96B9-CC6B0BD6845A | BERGADING-A2(C) | ED5501A0-B708-4670-8A6D-E87B12DD702D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BGDGWS39_BERGADING_A2.pdf |  | No |  | Uploads\ed5501a0-b708-4670-8a6d-e87b12dd702d.pdf | Exist
Atikah | Yes | 1303411D-CD14-4ACA-9E03-0FB2F9F7955B | 3D4EBF80-9D1F-446F-96B9-CC6B0BD6845A | BERGADING-A2(C) | 7A9E6E29-97A8-4CE7-B11C-78179023CA5A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading A-2 (C) FINAL_SIGNED.pdf | Bergading A-2 (C) FINAL_SIGNED.pdf | Yes |  | Uploads\7a9e6e29-97a8-4ce7-b11c-78179023ca5a.pdf | Exist
Atikah | Yes | 854310EF-8771-4652-82C0-0FDC030128C3 | 9FE60610-DBF2-4C34-8A75-CCB430B5B6FE | D18 107ST1 | D3BBC28A-63E1-4A45-BA97-84F9EE514002 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-107 ST1 FWR.pdf | D18-107 ST1 FWR.pdf | Yes |  | Uploads\d3bbc28a-63e1-4a45-ba97-84f9ee514002.pdf | Exist
Atikah | Yes | E800A4CD-CC28-41C4-AE94-574780E4E49D | 9FE60610-DBF2-4C34-8A75-CCB430B5B6FE | D18 107ST1 | 33A5D9E4-145F-4DAB-912B-5B35DE786174 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WI-XX_(107 ST1) NOOP.pdf |  | No |  | Uploads\33a5d9e4-145f-4dab-912b-5b35de786174.pdf | Exist
Atikah | Yes | 9100752F-A2C4-4E16-A6B3-434F6549D74C | 4D8C3099-B89F-43BD-A0FF-CD35F5E21368 | SJ-105A | D43AA217-375B-487B-8E15-154C862158CA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-105A (PCSB JV) EOWR.pdf | SJ-105A (PCSB JV) EOWR.pdf | Yes |  | Uploads\d43aa217-375b-487b-8e15-154c862158ca.pdf | Exist
Atikah | Yes | 39F23491-71B5-40D0-9819-E21BBC889890 | 4D8C3099-B89F-43BD-A0FF-CD35F5E21368 | SJ-105A | 9C0199FA-79BF-4176-8603-8E6B2A5BEA01 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-105A NOOP for MPM.pdf | SJ-105A NOOP for MPM.pdf | Yes |  | Uploads\9c0199fa-79bf-4176-8603-8e6b2a5bea01.pdf | Exist
Atikah | Yes | 4B43E9F8-3227-46A1-9100-988FD4979D8E | A799AE8A-50BE-4838-9CDA-CD5228BA076B | KNDW-D15 | 751A6236-8A38-4CC1-A537-79E8045C43B1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KNDW D15.pdf | EOWR KNDW D15.pdf | Yes |  | Uploads\751a6236-8a38-4cc1-a537-79e8045c43b1.pdf | Exist
Atikah | Yes | B83698FD-6785-4072-A74B-81B7B7C92A12 | A799AE8A-50BE-4838-9CDA-CD5228BA076B | KNDW-D15 | F3EB5906-AA25-4774-B544-B32F87E706B7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D15 NOOP_Final.pdf | KNDW-D15 NOOP_Final.pdf | Yes |  | Uploads\f3eb5906-aa25-4774-b544-b32f87e706b7.pdf | Exist
Atikah | Yes | B3828AE0-3214-402F-8B14-860D99B06304 | 84561E2C-DE1A-4212-B6F3-CD5F7A69914E | D18-207A | FC81BD4E-767F-4AA6-AF7D-34D422C25CC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-GL27_D18-207A_PCSB_NOOP.pdf | SKO3D18-GL27_D18-207A_PCSB_NOOP.pdf | Yes |  | Uploads\fc81bd4e-767f-4aa6-af7d-34d422c25cc6.pdf | Exist
Atikah | Yes | 2F595A58-ED09-45D1-9EB8-CF5C29FEF60B | 84561E2C-DE1A-4212-B6F3-CD5F7A69914E | D18-207A | 0E4E0388-E6A5-4C68-8F66-EDF1A1E55EA7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D-18 207A Final Well Report 207A-WI6 Signed.pdf | D-18 207A Final Well Report 207A-WI6 Signed.pdf | Yes |  | Uploads\0e4e0388-e6a5-4c68-8f66-edf1a1e55ea7.pdf | Exist
Atikah | Yes | F89B18A4-1E13-45B5-81FF-BD4B6F1DB603 | B646107F-6683-442C-ACF8-CD847E5BAC89 | AJK-A2 | B55FC51A-F1C5-440E-92A0-280560B8C002 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ANJKWS05_AJK-A2.pdf | SKO3ANJKWS05_AJK-A2.pdf | Yes |  | Uploads\b55fc51a-f1c5-440e-92a0-280560b8c002.pdf | Exist
Atikah | Yes | 57CE8F67-191F-43C4-B688-A2E576AF5B16 | B646107F-6683-442C-ACF8-CD847E5BAC89 | AJK-A2 | 24F9D5DE-891B-4203-983E-5FBDB1E9EC1F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ANJKWS07_AJK-A2.pdf | SKO3ANJKWS07_AJK-A2.pdf | Yes |  | Uploads\24f9d5de-891b-4203-983e-5fbdb1e9ec1f.pdf | Exist
Atikah | Yes | 5D3E8C6A-CB07-4D91-9CE1-CCD8E1F29476 | C87C829B-CF43-4494-BD56-CD976586C7E4 | SAPA-10 | 3583F42F-414C-4C78-B1C8-A19409811E96 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SK311 South Acis (SAPA) Revisit I Phase II.pdf |  | No |  | Uploads\3583f42f-414c-4c78-b1c8-a19409811e96.pdf | Exist
Atikah | Yes | A4AB9A79-A927-4E46-B164-D6A9E8833FEF | C87C829B-CF43-4494-BD56-CD976586C7E4 | SAPA-10 | E585BFB9-41E0-4B75-A167-BBFCE8A06613 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-10ST1 EOWR Rev A.pdf | SAPA-10ST1 EOWR Rev A.pdf | Yes |  | Uploads\e585bfb9-41e0-4b75-a167-bbfce8a06613.pdf | Exist
Atikah | Yes | 708C23B0-29D5-4244-BF0B-0B70F648555E | DDF507E4-A8E1-41A8-847B-CDAACFF5E65C | GK-P528C | 6901882A-1C55-4B88-99B9-094567582378 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR - GK-P528C.pdf | EOWR - GK-P528C.pdf | Yes |  | Uploads\6901882a-1c55-4b88-99b9-094567582378.pdf | Missing
Atikah | Yes | D906DE56-95BA-41F8-A309-18607996FA44 | DDF507E4-A8E1-41A8-847B-CDAACFF5E65C | GK-P528C | 51E23266-F585-4F28-B6E1-E30E2E388EFB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-P528C NOOP.pdf | GK-P528C NOOP.pdf | Yes |  | Uploads\51e23266-f585-4f28-b6e1-e30e2e388efb.pdf | Missing
Atikah | Yes | 406C9CD8-DA31-45A4-B2EC-12ABBDED9419 | DAAB29EE-4094-4DAF-BB2D-CDAF79AC60A5 | D18-207B | CB582993-95D3-4A68-BE91-19419397E10C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-GL28_D18-207B_PCSB_NOOP.pdf | SKO3D18-GL28_D18-207B_PCSB_NOOP.pdf | Yes |  | Uploads\cb582993-95d3-4a68-be91-19419397e10c.pdf | Missing
Atikah | Yes | FE4501D2-6FB4-470E-8725-A8317F4EFDE0 | DAAB29EE-4094-4DAF-BB2D-CDAF79AC60A5 | D18-207B | 4F2AF25E-19E3-4871-A5B8-48D1DF4E9B7B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS2K_D18-207B_PCSB_FWR.pdf | D-18 207B Final Well Report 207B-WI7 Signed.pdf | No |  | Uploads\4f2af25e-19e3-4871-a5b8-48d1df4e9b7b.pdf | Missing
Atikah | Yes | F6334507-4B81-4E47-AB72-311E11313B3B | DB830B84-3BD6-46B1-9B1A-CDFFDBD6DEA9 | DELIMA-1 | 15F44A94-F267-4D74-B6C3-ADAB21EA0C9F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20150424 DELIMA-1 NOTICE OF OPERATIONS_CONOCOPHILLIPS_final.pdf |  | No |  | Uploads\15f44a94-f267-4d74-b6c3-adab21ea0c9f.pdf | Exist
Atikah | Yes | 720B937D-B02A-4FA4-8139-D4289C43CF9C | DB830B84-3BD6-46B1-9B1A-CDFFDBD6DEA9 | DELIMA-1 | 10D684FA-CBF1-4329-9834-E8BC727C7D05 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Delima-1_EndofWellReport.pdf | Delima-1_EndofWellReport.pdf | Yes |  | Uploads\10d684fa-cbf1-4329-9834-e8bc727c7d05.pdf | Exist
Atikah | Yes | 527D79C8-EE2F-43D4-803D-10C1626527BA | CDF1F978-F3EE-4BDE-91D6-CEA1D267A381 | EC-A07 | CF53E468-A5CE-4280-BC50-4645322119DE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EC-A07 Final Well Report signed.pdf | EC-A07 Final Well Report signed.pdf | Yes |  | Uploads\cf53e468-a5ce-4280-bc50-4645322119de.pdf | Exist
Atikah | Yes | 0F356601-B6D2-4C35-99A8-7BFA2E606D9F | CDF1F978-F3EE-4BDE-91D6-CEA1D267A381 | EC-A07 | 20A75067-7FCA-4D05-9175-09912D4C0E4C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ECN-GEN-D-0005_Rev.00 NOTICE OF OPERATIONS - WELL EC-A07 (Slot 4A ECW-A Platform) signed AAWAZ_SFR_DS (002).pdf | ECN-GEN-D-0005_Rev.00 NOTICE OF OPERATIONS - WELL EC-A07 (Slot 4A ECW-A Platform) signed AAWAZ_SFR_DS (002).pdf | Yes |  | Uploads\20a75067-7fca-4d05-9175-09912d4c0e4c.pdf | Exist
Atikah | Yes | B0D161C6-DD36-42F3-B16C-64DD60EF79B4 | 57D4B290-A09F-474B-8C16-CEAF45B9E08E | GAYONG DEEP-1 | CFFA6FB6-C812-4018-AD0D-63E28D8F8074 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3GAYDWS01_GAYONG DEEP-1_PCSB_NOOP.pdf | PMO3GAYDWS01_GAYONG DEEP-1_PCSB_NOOP.pdf | Yes |  | Uploads\cffa6fb6-c812-4018-ad0d-63e28d8f8074.pdf | Exist
Atikah | Yes | 113E39D0-5098-4C0D-AEE2-6027391F7CB3 | 57D4B290-A09F-474B-8C16-CEAF45B9E08E | GAYONG DEEP-1 | 9E217076-C378-496F-87DF-16B9223BB9E5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3GAYDWS05_GAYONG DEEP-1_PCSB_FWR.pdf | PMO3GAYDWS05_GAYONG DEEP-1_PCSB_FWR.pdf | Yes |  | Uploads\9e217076-c378-496f-87df-16b9223bb9e5.pdf | Exist
Atikah | Yes | 88147EAF-E41B-4FE6-AF59-3CE792BD5DAE | 98AD43CF-C826-4428-8A73-CED963DA230B | PANGKIN-1 | EB391ECA-7B20-44A9-B874-2E93619E5A47 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pangkin-1_Internal _FINAL NOOP.pdf | Pangkin-1_Internal _FINAL NOOP.pdf | Yes |  | Uploads\eb391eca-7b20-44a9-b874-2e93619e5a47.pdf | Exist
Atikah | Yes | FCA2D60E-937D-4976-A620-59A5B02E4F64 | 98AD43CF-C826-4428-8A73-CED963DA230B | PANGKIN-1 | 59CB4B06-26A8-4149-B533-8D0886BB9B91 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3PGKNGL6664_PANGKIN-1_PCSB_FWR.pdf | SKO3PGKNGL6664_PANGKIN-1_PCSB_FWR.pdf | Yes |  | Uploads\59cb4b06-26a8-4149-b533-8d0886bb9b91.pdf | Exist
Atikah | Yes | D1EBAA11-3085-416A-9317-69F5ABE0D7DF | BA31F9B1-0F5B-493B-993C-CF54A583A66F | D21-A9 | 451FFC23-92EB-4669-B20D-7815579CE6C8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A09 NOOP.pdf |  | No |  | Uploads\451ffc23-92eb-4669-b20d-7815579ce6c8.pdf | Exist
Atikah | Yes | 338623CE-3429-4E5E-98BE-A6FCB66FE0A0 | BA31F9B1-0F5B-493B-993C-CF54A583A66F | D21-A9 | 45CAFB72-9766-408E-8B68-9B2E6F9E550D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A09 EOWR.pdf |  | No |  | Uploads\45cafb72-9766-408e-8b68-9b2e6f9e550d.pdf | Exist
Atikah | Yes | 021E0C8D-FA2D-4DE1-A968-357F98D9F569 | 5A9F8AFC-82BB-425D-9C5C-CF57AA04566C | GK-P527BS1 | 73B41788-5CFC-40B2-B0B5-02CA0D3140CA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR - GK-P527BS1.pdf | EOWR - GK-P527BS1.pdf | Yes |  | Uploads\73b41788-5cfc-40b2-b0b5-02ca0d3140ca.pdf | Exist
Atikah | Yes | 207F347D-78AA-47F2-8B64-D7AEA3182F9E | 5A9F8AFC-82BB-425D-9C5C-CF57AA04566C | GK-P527BS1 | 8485B87B-7D3D-46DD-AACA-D912A57A88C6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-P527B NOOP.pdf |  | No |  | Uploads\8485b87b-7d3d-46dd-aaca-d912a57a88c6.pdf | Exist
Atikah | Yes | 36EF4B2A-4106-4F75-9422-BCFAEC0A279C | 31F4E967-B7FF-4136-8695-CF57CAFCC42B | KMSE-A2 | E00646D7-089A-41CD-9E03-0641207D9038 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KMSE A2_NOOP_2013_SK.pdf |  | No |  | Uploads\e00646d7-089a-41cd-9e03-0641207d9038.pdf | Exist
Atikah | Yes | E9A79EA1-7C5D-4443-A355-C650796006F8 | 31F4E967-B7FF-4136-8695-CF57CAFCC42B | KMSE-A2 | 15BBB10A-94D1-4F85-8298-297DD1F49FEC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FINAL WELL REPORT KMSE-A2.pdf |  | No |  | Uploads\15bbb10a-94d1-4f85-8298-297dd1f49fec.pdf | Exist
Atikah | Yes | 629702FE-AC70-45C4-9299-E3627EEF8B1A | FDFE0DFB-0F9F-4701-A9EB-CFB61E24611D | BN-85 | 5DBAC3FA-139F-4986-99A1-D8E560EBA2B7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-85-FINAL.pdf | NOOP BN-85-FINAL.pdf | Yes |  | Uploads\5dbac3fa-139f-4986-99a1-d8e560eba2b7.pdf | Exist
Atikah | Yes | B117F520-1158-4939-A694-B0723B0F0CC6 | FDFE0DFB-0F9F-4701-A9EB-CFB61E24611D | BN-85 | ACE35BE1-9357-4AEB-A3A4-B779465EC948 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN85_Petronas Final Well Report_Signed Pack (002) TR.pdf | BN85_Petronas Final Well Report_Signed Pack (002) TR.pdf | Yes |  | Uploads\ace35be1-9357-4aeb-a3a4-b779465ec948.pdf | Exist
Atikah | Yes | 61BF17C2-6470-4217-8CF2-50E04CF890FD | EFB4314E-E60C-4E50-B165-D0473795D54F | BAYAN-C314 | 3E984EBA-014F-4416-8473-DF7BA2A2A152 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-314 Final Well Report - Signed.pdf |  | No |  | Uploads\3e984eba-014f-4416-8473-df7ba2a2a152.pdf | Exist
Atikah | Yes | 8EBB3B2C-8C61-4F26-89F8-2370DF1FEBFB | EFB4314E-E60C-4E50-B165-D0473795D54F | BAYAN-C314 | 48EE1797-CBFC-4143-92E5-A3482C4953A6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BY-314 Notice of Operations_APPROVED.pdf |  | No |  | Uploads\48ee1797-cbfc-4143-92e5-a3482c4953a6.pdf | Exist
Atikah | Yes | 5151CE0E-BA77-4FF7-AAA6-2EB4BDE35D50 | 8EEEA3AF-C907-41E9-9C87-D053367B86E0 | CECIL-1 | 872CCAE7-A0A7-43E0-87FC-467D48BB8293 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - Cecil-1_Internal.pdf | NOOP - Cecil-1_Internal.pdf | Yes |  | Uploads\872ccae7-a0a7-43e0-87fc-467d48bb8293.pdf | Exist
Atikah | Yes | E8D993CF-69C1-4C9C-BBFF-4045140B7E18 | 8EEEA3AF-C907-41E9-9C87-D053367B86E0 | CECIL-1 | C6397455-9CD7-44EC-B086-C894E5739217 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report - Cecil-1.pdf | Petronas Final Well Report - Cecil-1.pdf | Yes |  | Uploads\c6397455-9cd7-44ec-b086-c894e5739217.pdf | Exist
Atikah | Yes | 3E59B688-F2A3-4500-B71D-4704A7D65535 | 66E6CF83-E057-4133-A584-D0D1B739945B | D35B-216 | 844AA02B-DA30-44AC-BB20-CC8B1DC7A124 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-216 Well NOOP_Rev0_100718 Signed (final).pdf |  | No |  | Uploads\844aa02b-da30-44ac-bb20-cc8b1dc7a124.pdf | Exist
Atikah | Yes | 9E54A8B5-ABB0-40B8-B7E2-8F5EBCC6D82A | 66E6CF83-E057-4133-A584-D0D1B739945B | D35B-216 | 6CAB0092-0BA8-4D8A-AAFB-35D9415B7298 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-216 End Of Well Report.pdf | D35B-216 End Of Well Report.pdf | Yes |  | Uploads\6cab0092-0ba8-4d8a-aafb-35d9415b7298.pdf | Exist
Atikah | Yes | 2BDD8967-6DE5-43C6-BEEF-BBC8D3373323 | D1609D53-CF80-4F9C-B5B5-D0D52DAA4453 | BOC-29 | A78ABBF4-6673-489B-9383-9A7FEA743113 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-29&29ST1 6B EOWR_Final signed.pdf | BOC-29&29ST1 6B EOWR_Final signed.pdf | Yes |  | Uploads\a78abbf4-6673-489b-9383-9a7fea743113.pdf | Exist
Atikah | Yes | E7B25C77-C16D-41B6-A04F-B694CEBA19C9 | D1609D53-CF80-4F9C-B5B5-D0D52DAA4453 | BOC-29 | 685405AB-7CEB-446A-A833-20857D4EFA9A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-29 (6B) Oil Producer NOOP_Signed.pdf | BOC-29 (6B) Oil Producer NOOP_Signed.pdf | Yes |  | Uploads\685405ab-7ceb-446a-a833-20857d4efa9a.pdf | Exist
Atikah | Yes | 5E8C861D-8BF9-4B47-BC54-EB766184BE3D | 99AE4D1C-FF40-44D9-9F05-D16F0F21437E | D21-A10 | B30AAB06-3014-403D-BF00-1B36A80F9F0E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A10 NOOP.pdf | D21-A10 NOOP.pdf | Yes |  | Uploads\b30aab06-3014-403d-bf00-1b36a80f9f0e.pdf | Exist
Atikah | Yes | 6D25C76E-3624-460D-B2B9-78FBFB2873E5 | 99AE4D1C-FF40-44D9-9F05-D16F0F21437E | D21-A10 | 91A9308A-BB75-463A-B3FE-0C0907456992 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-A10 End Of Well Report Final.pdf | D21-A10 End Of Well Report Final.pdf | Yes |  | Uploads\91a9308a-bb75-463a-b3fe-0c0907456992.pdf | Exist
Atikah | Yes | D122AA7C-7999-4301-8F30-55A2761657A2 | 60956CE0-C79D-4D3D-A505-D192B85604FF | BEKOK-AA18 | 1B88D12D-5251-4DB8-800E-16D8280F5620 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report Bekok AA-18_final.pdf | Petronas Final Well Report Bekok AA-18_final.pdf | Yes |  | Uploads\1b88d12d-5251-4db8-800e-16d8280f5620.pdf | Exist
Atikah | Yes | A01057F6-2254-4ACB-A294-3146DFD45FDD | 60956CE0-C79D-4D3D-A505-D192B85604FF | BEKOK-AA18 | F4EE7189-B4AC-48D1-A577-057216FE9E27 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA18 Approved [internal].pdf | NOOP Bekok AA18 Approved [internal].pdf | Yes |  | Uploads\f4ee7189-b4ac-48d1-a577-057216fe9e27.pdf | Exist
Atikah | Yes | 6758F7B2-B4BE-45CB-A99D-42D3BF6C83CB | F0EA80B3-CFD0-40AD-A0BB-D1E1213AB49D | SIMPOH BELUDU-1 | 105593C0-2CDD-4EC6-927D-290C25684458 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Simpoh Beludu-1 PM407 NOOP.pdf | Simpoh Beludu-1 PM407 NOOP.pdf | Yes |  | Uploads\105593c0-2cdd-4ec6-927d-290c25684458.pdf | Exist
Atikah | Yes | 65695616-B927-4270-8279-7DB0D03BF1D1 | F0EA80B3-CFD0-40AD-A0BB-D1E1213AB49D | SIMPOH BELUDU-1 | FE9FF80F-8063-4F15-9811-5FDACF79FA8D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BLDUGL6226_Pttep_Simpoh_Beludu-1.pdf | PMO3BLDUGL6226_Pttep_Simpoh_Beludu-1.pdf | Yes |  | Uploads\fe9ff80f-8063-4f15-9811-5fdacf79fa8d.pdf | Exist
Atikah | Yes | E9FE806E-2AF8-4784-9493-A7E6C8F4110E | 282777C9-BA5E-4D57-A7FC-D23875862FCD | S-SW1-P9 | 72DF61AB-F8B9-47C8-9FEA-5277B0A8BD6A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | S-SW1-P9 Petronas and Carigali_Drilling and Completion EOWR.pdf | S-SW1-P9 Petronas and Carigali_Drilling and Completion EOWR.pdf | Yes |  | Uploads\72df61ab-f8b9-47c8-9fea-5277b0a8bd6a.pdf | Exist
Atikah | Yes | 70538079-1959-4379-BF3A-B88BAEEB0680 | 282777C9-BA5E-4D57-A7FC-D23875862FCD | S-SW1-P9 | BC478AAE-D280-4BDF-ACC3-A29CB5DE715C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | S-SW1-P9 Petronas and Carigali_Drilling and Completions NOOP.pdf | S-SW1-P9 Petronas and Carigali_Drilling and Completions NOOP.pdf | Yes |  | Uploads\bc478aae-d280-4bdf-acc3-a29cb5de715c.pdf | Exist
Atikah | Yes | 8A1C8620-8D4E-4C78-8DD2-7C7B9FFF66E3 | 13EEDA25-BDFE-46DE-9DB8-D2723EDE8BDC | BUNGA TERATAI-3 | 9BB8381D-F9B5-4ECC-B099-74391C057618 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAIWS17_BUNGA_TERATAI-3.pdf |  | No |  | Uploads\9bb8381d-f9b5-4ecc-b099-74391c057618.pdf | Exist
Atikah | Yes | 5F03386A-C989-4CFB-AE1D-205DB843023E | 13EEDA25-BDFE-46DE-9DB8-D2723EDE8BDC | BUNGA TERATAI-3 | 0A8DA2EA-1F10-4189-8B59-5B36E2BF915A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BTAIWS17_BUNGA_TERATAI-3.pdf |  | No |  | Uploads\0a8da2ea-1f10-4189-8b59-5b36e2bf915a.pdf | Exist
Atikah | Yes | 0703066F-23BE-4E4D-93BA-7193FD1371A9 | ED112CC4-DEFF-4262-8C58-D2E952A2CA97 | SCDR-A6 | FA1431B7-ABDF-4242-9A21-B0293B21F66D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SCDR-A6.pdf | NOOP SCDR-A6.pdf | Yes |  | Uploads\fa1431b7-abdf-4242-9a21-b0293b21f66d.pdf | Exist
Atikah | Yes | E8FCE3C6-38B1-4B80-8615-C7693C68FE06 | ED112CC4-DEFF-4262-8C58-D2E952A2CA97 | SCDR-A6 | 27EB3FA2-B5AA-49FF-818E-A790B534069A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report SCDRA6 (FINAL).pdf | Petronas Final Well Report SCDRA6 (FINAL).pdf | Yes |  | Uploads\27eb3fa2-b5aa-49ff-818e-a790b534069a.pdf | Exist
Atikah | Yes | C3D78A37-F9AF-49A4-9E93-ECDF6FF67FCA | A86EC53E-80AD-46B9-B05E-D37F104F4DED | SADOK-1 | 56141712-D66C-42BC-B316-4CD2B160CFF7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SADOK-1 FWR.pdf | SADOK-1 FWR.pdf | Yes |  | Uploads\56141712-d66c-42bc-b316-4cd2b160cff7.pdf | Exist
Atikah | Yes | 15BDABC0-DD2C-4D80-A857-AAE7CD218946 | A86EC53E-80AD-46B9-B05E-D37F104F4DED | SADOK-1 | C2F2BDF1-9DC2-4BE7-92B1-8B6FF4FFEF96 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sadok-1 NOOP_Rev3.pdf | Sadok-1 NOOP_Rev3.pdf | Yes |  | Uploads\c2f2bdf1-9dc2-4be7-92b1-8b6ff4ffef96.pdf | Exist
Atikah | Yes | B182099C-2AE3-4C08-A5A7-2D545A0D1767 | A890609B-9DA5-4E69-BAD5-D3AD0A497E53 | D35C-303ST1 | 9376BFF7-117C-41B7-AB3C-3BE31F9779EF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-303ST1 Well NOOP Final.pdf | D35C-303ST1 Well NOOP Final.pdf | Yes |  | Uploads\9376bff7-117c-41b7-ab3c-3be31f9779ef.pdf | Exist
Atikah | Yes | 01726A95-7425-464E-9E2F-B804C16DBB57 | A890609B-9DA5-4E69-BAD5-D3AD0A497E53 | D35C-303ST1 | 266105B1-AA93-4E39-BA97-675CEB4B10EE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35C-303ST1 End Of Well Report.pdf | D35C-303ST1 End Of Well Report.pdf | Yes |  | Uploads\266105b1-aa93-4e39-ba97-675ceb4b10ee.pdf | Exist
Atikah | Yes | 87492DE1-B7A0-4348-A4D2-CF47FBDE2D9C | 3609F22B-DDFD-4391-9939-D3D86862823B | KNDW-D12 | 8D4D9DE6-556B-499B-9D54-B30FE1248360 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D12 EOWR Final.pdf | KNDW-D12 EOWR Final.pdf | Yes |  | Uploads\8d4d9de6-556b-499b-9d54-b30fe1248360.pdf | Exist
Atikah | Yes | A2B41DBD-E6DE-4D64-B148-B3884DA7817D | 3609F22B-DDFD-4391-9939-D3D86862823B | KNDW-D12 | E24F265E-5B78-457F-B1E4-257781386BB6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-12 NOOP .pdf | KNDW D-12 NOOP .pdf | Yes |  | Uploads\e24f265e-5b78-457f-b1e4-257781386bb6.pdf | Exist
Atikah | Yes | 3E2EC455-8C2C-4F94-9C29-B23AA0D4AABB | 58398C6E-44A6-4972-B5F7-D3E9369CBD69 | BEKOK DEEP-1RDR1 | 0B6939EB-6DF0-4CEB-B7D0-C80A812EB84B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Approved FWR BD1RDR1.pdf |  | No |  | Uploads\0b6939eb-6df0-4ceb-b7d0-c80a812eb84b.pdf | Exist
Atikah | Yes | 4AED1897-A9FF-487F-B8C7-CBE98578989B | 58398C6E-44A6-4972-B5F7-D3E9369CBD69 | BEKOK DEEP-1RDR1 | 109F69D4-44A4-4EF7-9EDE-2FF3E7DE33B2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bekok Deep-1 - NOOP.pdf |  | No |  | Uploads\109f69d4-44a4-4ef7-9ede-2ff3e7de33b2.pdf | Exist
Atikah | Yes | C2A9E3D9-7E4F-450A-BB64-917D706FE784 | 2A28E6C6-E8F8-4D35-9D1C-D3EE421AE334 | CD-B16 | 41F0E5DF-7CCA-4F98-9F4D-FFEBA9AF6D1B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-B16 REV.02 CP2-GEN-D-0002_NOOP WELL .pdf | CD-B16 REV.02 CP2-GEN-D-0002_NOOP WELL .pdf | Yes |  | Uploads\41f0e5df-7cca-4f98-9f4d-ffeba9af6d1b.pdf | Exist
Atikah | Yes | 80FB8102-5F9E-472A-A099-5C9AE41B68EC | 2A28E6C6-E8F8-4D35-9D1C-D3EE421AE334 | CD-B16 | F98D14E7-E89D-4710-8605-9C8660EA8140 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-B16 Final Well Report_Signed.pdf | CD-B16 Final Well Report_Signed.pdf | Yes |  | Uploads\f98d14e7-e89d-4710-8605-9c8660ea8140.pdf | Exist
Atikah | Yes | 055E6BF5-00A5-4EAD-9A6D-B37BC8242669 | 2745EF5E-7C77-449A-A0BF-D445E24F4BDC | BESAR-A4 | E16F8045-74DF-464F-B553-A7336332E109 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Besar A4_Petronas Final Well Report.pdf | Besar A4_Petronas Final Well Report.pdf | Yes |  | Uploads\e16f8045-74df-464f-b553-a7336332e109.pdf | Exist
Atikah | Yes | 2488ECE4-7520-4141-9590-FC0DE7F46A84 | 2745EF5E-7C77-449A-A0BF-D445E24F4BDC | BESAR-A4 | 5C5E2BFD-FF8C-423A-872C-6F7CAD57498B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Besar A4 (submission for MPM).pdf | NOOP Besar A4 (submission for MPM).pdf | Yes |  | Uploads\5c5e2bfd-ff8c-423a-872c-6f7cad57498b.pdf | Exist
Atikah | Yes | C857C8C7-9B4D-47A8-9074-8D689FD6218D | 32BEB894-ABF8-4195-BF7B-D45F2F29FE4D | PRPA-06 | E57849F9-BB4F-4D52-92F2-CF777E494B98 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 6 PERMAS REVISIT 1 PHASE 3 PRPA-06 NOOP_Rev 0.pdf | PRPA 6 PERMAS REVISIT 1 PHASE 3 PRPA-06 NOOP_Rev 0.pdf | Yes |  | Uploads\e57849f9-bb4f-4d52-92f2-cf777e494b98.pdf | Exist
Atikah | Yes | 5BEFA57C-A2D6-421D-AE47-369338934F2E | 32BEB894-ABF8-4195-BF7B-D45F2F29FE4D | PRPA-06 | 039E89E1-BFCC-4C03-9519-9826063D5526 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-06 EOWR.pdf | PRPA-06 EOWR.pdf | Yes |  | Uploads\039e89e1-bfcc-4c03-9519-9826063d5526.pdf | Exist
Atikah | Yes | FD77F437-1B31-466F-B58C-4BA7BB1A2EC6 | 33CA72D3-E59A-40B6-8A34-D4787D003C1E | SIRUNG-2 | 51071689-660C-4AC8-BCE3-D40FAED5A24D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK405B_Sirung-2_End_Of_Well_Report - Approved.pdf | SK405B_Sirung-2_End_Of_Well_Report - Approved.pdf | Yes |  | Uploads\51071689-660c-4ac8-bce3-d40faed5a24d.pdf | Exist
Atikah | Yes | 9F6F6CDE-B56B-4AA2-8D36-C6BEAB912370 | 33CA72D3-E59A-40B6-8A34-D4787D003C1E | SIRUNG-2 | 42DF46F9-4766-4959-B6CC-D36DA8B3DA90 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sirung-2 Notice of Operation (NOOP) (2023).pdf | Sirung-2 Notice of Operation (NOOP) (2023).pdf | Yes |  | Uploads\42df46f9-4766-4959-b6cc-d36da8b3da90.pdf | Exist
Atikah | Yes | FEEE61D0-2ECF-4284-B5DC-3B6092BC9B31 | E3943D6A-C9D2-4226-BE7D-D47E74C05CD1 | BERTAM A-19 | 844E4871-A0D1-4DEE-AC10-579B01147C1B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-19 NOOP.pdf | Bertam A-19 NOOP.pdf | Yes |  | Uploads\844e4871-a0d1-4dee-ac10-579b01147c1b.pdf | Exist
Atikah | Yes | C3CEB38B-A471-4AB7-9F15-641F65A629BA | E3943D6A-C9D2-4226-BE7D-D47E74C05CD1 | BERTAM A-19 | C1A0669C-4B77-43DC-B994-DC253781AF78 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-19 EOWR.pdf | Bertam A-19 EOWR.pdf | Yes |  | Uploads\c1a0669c-4b77-43dc-b994-dc253781af78.pdf | Exist
Atikah | Yes | 06B7D0CC-07A3-4F42-828E-262887AEFB0B | 741C2229-8D33-4648-987D-D508BBF5D07B | KASAWARI-A1 | C2F446F3-8F9B-47C7-8934-963BBC8BE31D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kasawari A1 Petronas Final Well Report - For Signature PSS MM FK.pdf | Kasawari A1 Petronas Final Well Report - For Signature PSS MM FK.pdf | Yes |  | Uploads\c2f446f3-8f9b-47c7-8934-963bbc8be31d.pdf | Exist
Atikah | Yes | F01B91F5-52AD-40FC-A054-EF400A6E659D | 741C2229-8D33-4648-987D-D508BBF5D07B | KASAWARI-A1 | 226B6AE5-0DA6-4122-8D6A-57BA148B48F1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kasawari-A1 NOOP_Final.pdf | Kasawari-A1 NOOP_Final.pdf | Yes |  | Uploads\226b6ae5-0da6-4122-8d6a-57ba148b48f1.pdf | Exist
Atikah | Yes | 2AC2F095-871F-4A78-8B3E-DBE267293838 | 4807D6C8-C8C8-436C-B4EB-D56B97FC3705 | BPA-6 | DF98C00D-8E58-4B62-9EE0-E0BE75D446F8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-6 EOWR.pdf | BPA-6 EOWR.pdf | Yes |  | Uploads\df98c00d-8e58-4b62-9ee0-e0be75d446f8.pdf | Exist
Atikah | Yes | 7B8E4978-A96D-4D18-9299-92E6AB5529A8 | 4807D6C8-C8C8-436C-B4EB-D56B97FC3705 | BPA-6 | 5EA05AEA-CEF6-482A-80BD-F41CB67E87E9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-6 NOOP.pdf | BPA-6 NOOP.pdf | Yes |  | Uploads\5ea05aea-cef6-482a-80bd-f41cb67e87e9.pdf | Exist
Wadi | Yes | 97BE8443-0D2C-4A53-8158-084B8E7C9749 | 77354141-283F-4F46-822F-D56CCCF8927A | SASA-05 | 5EFF1D74-709B-4EDC-BA10-C26AC4949439 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK311-SASA PHASE 1 NOOP_Rev 1.pdf |  | No |  | Uploads\5eff1d74-709b-4edc-ba10-c26ac4949439.pdf | Exist
Atikah | Yes | F582A1C0-7220-493F-B4AC-5CC10947D2AC | 77354141-283F-4F46-822F-D56CCCF8927A | SASA-05 | D89D0CD7-9C6A-43C6-B6B1-296AD4ED492D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA-05 EOWR.pdf | SASA-05 EOWR.pdf | Yes |  | Uploads\d89d0cd7-9c6a-43c6-b6b1-296ad4ed492d.pdf | Exist
Atikah | Yes | 93C34B87-E1AC-4206-98E4-A263FAAD7F4F | 309A39BD-9772-4E04-A5BC-D5904DBE6453 | DAMAR-A4 | 9740B910-9AC8-4AE1-B955-D17968130170 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARGL04_DAMAR-A4.pdf |  | No |  | Uploads\9740b910-9ac8-4ae1-b955-d17968130170.pdf | Exist
Atikah | Yes | 747E542F-34A1-4C28-B365-EACB45297E37 | 309A39BD-9772-4E04-A5BC-D5904DBE6453 | DAMAR-A4 | B45B6C01-E299-4EEB-96D3-6DB337337411 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DAMAR-A4 EOWR.pdf | DAMAR-A4 EOWR.pdf | Yes |  | Uploads\b45b6c01-e299-4eeb-96d3-6db337337411.pdf | Exist
Atikah | Yes | 5EC0CA73-3199-4448-ABEB-65284AEA7A31 | 4F2285A2-018A-42CD-AC45-D614E978FD94 | BRB-11ST1 | E1F8A58A-8D6C-4793-BB6C-AB4946DC6890 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRB-11ST1_ST2 (LL) NOOP_FINAL_signed.pdf | BRB-11ST1_ST2 (LL) NOOP_FINAL_signed.pdf | Yes |  | Uploads\e1f8a58a-8d6c-4793-bb6c-ab4946dc6890.pdf | Exist
Atikah | Yes | 553CB9EF-8DF1-4A69-BE6C-347C5E1030A0 | 4F2285A2-018A-42CD-AC45-D614E978FD94 | BRB-11ST1 | C9930C74-E38E-44C1-BE68-85EC77ACC93B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR. BRB-11 ST1 ST2 (LL) Well .pdf | EOWR. BRB-11 ST1 ST2 (LL) Well .pdf | Yes |  | Uploads\c9930c74-e38e-44c1-be68-85ec77acc93b.pdf | Exist
Atikah | Yes | 48364F4D-F98C-4C11-8E98-353941BA914B | 5A83C5F6-68E2-416C-A82D-D616C1B61E99 | TEMU-1 | 83FD81BE-A13D-412F-8CD5-2D07C125665F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temu-1 and Temu-1S1- SMEP MLNG Exploration - EOWR -.pdf | Temu-1 and Temu-1S1- SMEP MLNG Exploration - EOWR -.pdf | Yes |  | Uploads\83fd81be-a13d-412f-8cd5-2d07c125665f.pdf | Exist
Atikah | Yes | DCFCBD73-DA2D-4892-B707-E4DF293922AA | 5A83C5F6-68E2-416C-A82D-D616C1B61E99 | TEMU-1 | B6A61DA8-6585-4798-B171-3979109A5827 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temu-1 MLNGx_NOOP.pdf | Temu-1 MLNGx_NOOP.pdf | Yes |  | Uploads\b6a61da8-6585-4798-b171-3979109a5827.pdf | Exist
Atikah | Yes | A592F78C-D708-4306-B15F-5D158CF7588F | 346354FF-84C4-4809-8B89-D696EE8740C2 | D18-309 | 515B8CEB-A4F1-415A-AEBD-7F3042754298 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18-C309 NOOP.pdf | SKO3D18-WS75_D18-309_PCSB.pdf | No |  | Uploads\515b8ceb-a4f1-415a-aebd-7f3042754298.pdf | Exist
Atikah | Yes | E319302E-EA20-46DF-B903-886F80D3282D | 346354FF-84C4-4809-8B89-D696EE8740C2 | D18-309 | C7A1FDE9-7BBC-42B0-98D9-462F74654010 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS2N_D18-309_PCSB.pdf | SKO3D18-WS2N_D18-309_PCSB.pdf | Yes |  | Uploads\c7a1fde9-7bbc-42b0-98d9-462f74654010.pdf | Exist
Atikah | Yes | 8905696C-9D91-493F-BD7A-70DCE2AFA152 | 52A17A66-4A3E-4102-941E-D6AA0E192F0A | BA-33 ST1 | 7A1BA64B-BD72-49D2-9235-F71CC7A37BF0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BARMWS6K_BA-33ST_PCSB_FWR.pdf |  | No |  | Uploads\7a1ba64b-bd72-49d2-9235-f71cc7a37bf0.pdf | Exist
Atikah | Yes | 530CC28D-3636-4CF5-B886-C55FA5927F8F | 52A17A66-4A3E-4102-941E-D6AA0E192F0A | BA-33 ST1 | A8A00BB3-9FE9-413C-AFEC-5C10CB8A3D37 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BADP-B BA-33SR (BA39).pdf |  | No |  | Uploads\a8a00bb3-9fe9-413c-afec-5c10cb8a3d37.pdf | Exist
Atikah | Yes | 6733BDA3-038D-4075-AFE2-6F8CC5BDF2BD | 1003C2D3-0D36-44C7-9824-D6AF8ABE2A83 | ANGSI-E14 | 6EEABD26-31A0-475D-89FA-0D87D6399E8C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ANGSI E-14 NOOP Final Signed.pdf | ANGSI E-14 NOOP Final Signed.pdf | Yes |  | Uploads\6eeabd26-31a0-475d-89fa-0d87d6399e8c.pdf | Exist
Atikah | Yes | 2B041A0C-083C-4655-913E-0C9D9614518C | 1003C2D3-0D36-44C7-9824-D6AF8ABE2A83 | ANGSI-E14 | DE4FE26E-0D09-4217-BC4C-A7D7A71B82B5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report ANGSI E-14 Complete Signed.pdf | Final Well Report ANGSI E-14 Complete Signed.pdf | Yes |  | Uploads\de4fe26e-0d09-4217-bc4c-a7d7a71b82b5.pdf | Exist
Atikah | Yes | 667CCD85-8EE3-45CA-AEC2-2955B6A6C988 | 5AEE4837-1368-4676-AADB-D6C0B3EB2D1E | BANGSAWAN-1 | EA7365A9-025E-4D1C-B0F5-7324A7C44B9A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bangsawan-1_Final_Well_Report_(Drilling)_Rev0.pdf | Bangsawan-1_Final_Well_Report_(Drilling)_Rev0.pdf | Yes |  | Uploads\ea7365a9-025e-4d1c-b0f5-7324a7c44b9a.pdf | Exist
Atikah | Yes | D1FCFC64-7C00-4B2B-8E7C-D6752248EC48 | 5AEE4837-1368-4676-AADB-D6C0B3EB2D1E | BANGSAWAN-1 | 4FF7B3D3-D264-45EF-BA94-F039CAF295B2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bangsawan-1 NOOP.pdf | Bangsawan-1 NOOP.pdf | Yes |  | Uploads\4ff7b3d3-d264-45ef-ba94-f039caf295b2.pdf | Exist
Atikah | Yes | C0A20009-1FBA-4798-80C6-BB23E27D50BC | 7722A2F3-7188-4653-8975-D729BBD67BDA | ANGSI-E16 | 21C65391-8F59-4416-BD26-0366495B436A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report ANGSI E-16 Complete Signed.pdf | Final Well Report ANGSI E-16 Complete Signed.pdf | Yes |  | Uploads\21c65391-8f59-4416-bd26-0366495b436a.pdf | Exist
Atikah | Yes | 3E0DAB5E-A175-4473-986A-E2263D2C5F74 | 7722A2F3-7188-4653-8975-D729BBD67BDA | ANGSI-E16 | FC784E37-B9E9-4ABF-85CA-AD5A54D26DD8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Angsi E-16 Final Signed.pdf | NOOP Angsi E-16 Final Signed.pdf | Yes |  | Uploads\fc784e37-b9e9-4abf-85ca-ad5a54d26dd8.pdf | Exist
Atikah | Yes | 42C0A987-86D7-490C-8B53-68B0CE9302AA | F00781F4-F70C-4CB5-87D3-D7B1FDE63CF8 | BPA-2 | 9E001072-7211-4095-A663-FAACE1E492E5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-2 EOWR.pdf | BPA-2 EOWR.pdf | Yes |  | Uploads\9e001072-7211-4095-a663-faace1e492e5.pdf | Exist
Atikah | Yes | 29F103D9-194B-44ED-8847-977EBCB9A0F0 | F00781F4-F70C-4CB5-87D3-D7B1FDE63CF8 | BPA-2 | 16FD759E-3618-47FA-A376-2FAF023C1607 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BPKMGL04_BPA_2.pdf | PMO3BPKMGL04_BPA_2.pdf | Yes |  | Uploads\16fd759e-3618-47fa-a376-2faf023c1607.pdf | Exist
Atikah | Yes | 6B2EF015-F7DF-4BE8-9F5F-2C7EDB3F5251 | AE431A54-67D0-455A-815F-D7F18A337044 | TBK-A5 | 37A6DA1B-A32D-4054-8386-062113FBDA08 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TBK-A5.pdf | NOOP TBK-A5.pdf | Yes |  | Uploads\37a6da1b-a32d-4054-8386-062113fbda08.pdf | Exist
Atikah | Yes | 7687F6C9-7CA6-4690-AD2D-36A5F958CC27 | AE431A54-67D0-455A-815F-D7F18A337044 | TBK-A5 | 26CBF2AF-FD45-419B-B8CA-869A6BFC38E5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A5 Final Well Report final.pdf | TBK-A5 Final Well Report final.pdf | Yes |  | Uploads\26cbf2af-fd45-419b-b8ca-869a6bfc38e5.pdf | Exist
Atikah | Yes | D5587320-07FA-4E0E-AC35-B64E2A27CE9E | 11656015-D892-44C3-BA64-D7FDFD959B9A | PATAWALI-1 | FF04976B-E9D3-4ACF-A7A7-72C8BD545A30 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-WL4-DRL-PROCE-051 PATAWALI-1 NOOP.pdf |  | No |  | Uploads\ff04976b-e9d3-4acf-a7a7-72c8bd545a30.pdf | Exist
Atikah | Yes | FD62C32E-9A98-48AC-8C45-D7A5FF004C3B | 11656015-D892-44C3-BA64-D7FDFD959B9A | PATAWALI-1 | 896918AB-A334-4E7F-BEC3-8A6478A0828F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Patawali-1 Drilling End of Well Report.pdf | Patawali-1 Drilling End of Well Report.pdf | Yes |  | Uploads\896918ab-a334-4e7f-bec3-8a6478a0828f.pdf | Exist
Atikah | Yes | 098132C0-F182-4615-8927-B5656773B5DB | 48C04D50-5DA6-4567-B550-D80E0846B188 | SUMANDAK SELATAN-B20 | 0F04D3D4-9B2B-45AA-A430-DD3F702F1BE2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B20 NOOP (Final) 261018.pdf | Sumandak Selatan B20 NOOP (Final) 261018.pdf | Yes |  | Uploads\0f04d3d4-9b2b-45aa-a430-dd3f702f1be2.pdf | Exist
Atikah | Yes | F69BC2EF-0377-41DE-A148-64A86285A805 | 48C04D50-5DA6-4567-B550-D80E0846B188 | SUMANDAK SELATAN-B20 | FF71EDA0-5F6D-46FC-B4F2-2488320AC017 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B20 FWR 17 Jan 2019.pdf | Sumandak Selatan B20 FWR 17 Jan 2019.pdf | Yes |  | Uploads\ff71eda0-5f6d-46fc-b4f2-2488320ac017.pdf | Exist
Atikah | Yes | 8DB2F0F3-98DC-4C3F-AECE-787EBF1EF4F5 | C4D30470-5C52-4678-B3B1-D893BC1C75EA | GANSAR-1 | CA442432-EB98-41F5-A920-BDD49C305021 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3GNSRWS01_GANSAR-1.pdf | PMO3GNSRWS01_GANSAR-1.pdf | Yes |  | Uploads\ca442432-eb98-41f5-a920-bdd49c305021.pdf | Exist
Atikah | Yes | D878A87A-E5A5-4529-AF68-EC18DACB37FF | C4D30470-5C52-4678-B3B1-D893BC1C75EA | GANSAR-1 | 07A48C49-A42E-4BD7-81AB-F40373F37611 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3GNSRWS10_GANSAR-1.pdf | PMO3GNSRWS10_GANSAR-1.pdf | Yes |  | Uploads\07a48c49-a42e-4bd7-81ab-f40373f37611.pdf | Exist
Atikah | Yes | B18AEBA1-24A5-44FE-BCB4-74839F18DF34 | 2F64DF72-FD4D-4F66-9015-D8A5FF6B56E9 | SM-113 | 5AB5F57F-D2A1-473A-9FB2-1B036D96B5EF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL45_SM_113.pdf | SBO3SMRGGL45_SM_113.pdf | Yes |  | Uploads\5ab5f57f-d2a1-473a-9fb2-1b036d96b5ef.pdf | Exist
Atikah | Yes | BD25958D-356F-414E-BC5B-508F1AABEE72 | 2F64DF72-FD4D-4F66-9015-D8A5FF6B56E9 | SM-113 | 38DDC0CC-BA78-475E-8680-12E3E6F884D3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSEW_SM_113.pdf | SBO3SMRGWSEW_SM_113.pdf | Yes |  | Uploads\38ddc0cc-ba78-475e-8680-12e3e6f884d3.pdf | Exist
Atikah | Yes | 2B2D5D39-FEF1-497E-BA96-78A29500DA07 | 7A5A14C0-176C-40E0-860D-D8BE199DA109 | BUAH KERAS-1 | B7F1ED07-AFBC-4A33-9897-A728CE59A3DB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Buah Keras 1NOOP.pdf | Buah Keras 1NOOP.pdf | Yes |  | Uploads\b7f1ed07-afbc-4a33-9897-a728ce59a3db.pdf | Exist
Atikah | Yes | CD18CA9D-8BD8-4496-8D18-5DAB7E192C1D | 7A5A14C0-176C-40E0-860D-D8BE199DA109 | BUAH KERAS-1 | 866A9484-7916-4400-82DC-F7DBD1F71488 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Buah Keras-1_EOWR FINAL.pdf | Buah Keras-1_EOWR FINAL.pdf | Yes |  | Uploads\866a9484-7916-4400-82dc-f7dbd1f71488.pdf | Exist
Atikah | Yes | 5EADF08E-47AD-4A63-9740-00AD85C719F8 | 335BA423-AB4B-491D-A56D-D8BFB7688E06 | TBK-B3 | BD1449A4-853F-4F23-B1EE-E1A08EA5E178 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B3 Final Well Report.pdf | TBK-B3 Final Well Report.pdf | Yes |  | Uploads\bd1449a4-853f-4f23-b1ee-e1a08ea5e178.pdf | Exist
Atikah | Yes | 051021F0-1A20-4735-9195-CBFDF82B15F0 | 335BA423-AB4B-491D-A56D-D8BFB7688E06 | TBK-B3 | 013F0481-E16D-43AB-9451-8C4EFB000F64 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B3.pdf | TBK-B3.pdf | Yes |  | Uploads\013f0481-e16d-43ab-9451-8c4efb000f64.pdf | Exist
Atikah | Yes | AB543230-0574-4BFD-A871-372B64BD6249 | E95B6E21-BE42-4DCB-B0B9-D8F4543D35D9 | D21-A8 | 25D09A9B-0F17-4FF6-B9FD-5D15040DD87C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21 U2 (A8) EOWR.pdf |  | No |  | Uploads\25d09a9b-0f17-4ff6-b9fd-5d15040dd87c.pdf | Exist
Atikah | Yes | C4208CEF-360D-422B-AB8D-3C71B60C6FDB | E95B6E21-BE42-4DCB-B0B9-D8F4543D35D9 | D21-A8 | 66EDF2D0-0EB8-442E-9412-06AE58548F73 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-C2A-FB4b(D21-A8) NOOP.pdf | D21-C2A-FB4b(D21-A8) NOOP.pdf | Yes |  | Uploads\66edf2d0-0eb8-442e-9412-06ae58548f73.pdf | Exist
Atikah | Yes | 6CC95D6B-8671-4446-B10B-835BC5CBBC42 | 8A36B982-D107-4666-BA90-D999E46EBC01 | SM-119ST1 | 83FF14B6-7103-4263-B88C-8F7630DF4415 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM-119-119ST EOWR.pdf |  | No |  | Uploads\83ff14b6-7103-4263-b88c-8f7630df4415.pdf | Exist
Atikah | Yes | 4D05E319-205B-4161-BEE6-9061C73D1A8A | 8A36B982-D107-4666-BA90-D999E46EBC01 | SM-119ST1 | 9C5986D8-3889-4CB6-9034-B456942ED818 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM119 w Signature Rev.2 (1).pdf |  | No |  | Uploads\9c5986d8-3889-4cb6-9034-b456942ed818.pdf | Exist
Atikah | Yes | 3BCA7DF1-6354-4FA4-BC4F-B122279946A0 | 432EF50A-45AD-4B4D-9804-D9A31EF402E2 | WD-A16 | 9BABC058-8FCD-461B-9D18-CB917BB7B231 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3WDESWS47_WD-A16.pdf | PMO3WDESWS47_WD-A16.pdf | Yes |  | Uploads\9babc058-8fcd-461b-9d18-cb917bb7b231.pdf | Exist
Atikah | Yes | 3601C53A-1A63-429C-9A05-BE0AAF1C511F | 432EF50A-45AD-4B4D-9804-D9A31EF402E2 | WD-A16 | F032BEE0-0391-4A62-9C6E-7BA5C643888A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 3. WD-A16 (WI-06) NOOP.pdf |  | No |  | Uploads\f032bee0-0391-4a62-9c6e-7ba5c643888a.pdf | Exist
Atikah | Yes | 93DDBE21-CD9B-4661-A0A7-A9AAF9CFB9CA | 5CFBCAC6-54E4-4B13-8621-D9D0A5C117D1 | GEMILANG-1 | 0794F8D5-5147-4412-B1BF-AC694CF56E5A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gemilang-1 GMG-1 NOOP_Final.pdf | Gemilang-1 GMG-1 NOOP_Final.pdf | Yes |  | Uploads\0794f8d5-5147-4412-b1bf-ac694cf56e5a.pdf | Exist
Atikah | Yes | 1F2AF4FC-4CE0-4DDE-A24E-69FDE21785E9 | 5CFBCAC6-54E4-4B13-8621-D9D0A5C117D1 | GEMILANG-1 | F128D3B6-FF34-4AE4-8148-E5E0EDF70DB5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gemilang-1_EOWR.pdf | Gemilang-1_EOWR.pdf | Yes |  | Uploads\f128d3b6-ff34-4ae4-8148-e5e0edf70db5.pdf | Exist
Atikah | Yes | A4563B36-01A8-4BB2-A43C-AF2BEC166A21 | 9AABF721-710C-491A-BCF7-DA24688B0666 | TBK-A2 | DD84CCE2-F7FB-4D06-BA69-8B42B5AD7462 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A2 Final Well Report.pdf |  | No |  | Uploads\dd84cce2-f7fb-4d06-ba69-8b42b5ad7462.pdf | Exist
Atikah | Yes | 69C24B8D-E504-43C0-A575-0B36AAF325F2 | 9AABF721-710C-491A-BCF7-DA24688B0666 | TBK-A2 | E97B8772-69A9-45A9-BA99-5FB060871613 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TMBKWS14_TBK-A2_NOOP_VESTIGO.pdf | PMO3TMBKWS14_TBK-A2_NOOP_VESTIGO.pdf | Yes |  | Uploads\e97b8772-69a9-45a9-ba99-5fb060871613.pdf | Exist
Atikah | Yes | 535A28D8-C9CE-4F3A-887B-2198DA50D652 | 75668F3E-28BF-438B-83A0-DA590A22A155 | TBK-B2 | 0FD8A164-771A-41B4-8B80-F0B8CE026E2A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B2 Final Well Report.pdf |  | No |  | Uploads\0fd8a164-771a-41b4-8b80-f0b8ce026e2a.pdf | Exist
Atikah | Yes | 61B73D65-9F44-41E5-9EF0-FE1FFDC688CB | 75668F3E-28BF-438B-83A0-DA590A22A155 | TBK-B2 | 777FE4CD-4E40-420B-A782-F0F88BF0FDEF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B2.pdf | TBK-B2.pdf | Yes |  | Uploads\777fe4cd-4e40-420b-a782-f0f88bf0fdef.pdf | Exist
Atikah | Yes | B9878C5F-6DD1-46A3-872D-D08FFA9DCF4E | B43BDAF0-59CF-40AF-B993-DAAF9FC013D4 | BN-74 | F8D2C75A-D77C-46AF-B548-F054D8FDA54E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-74 FWR.pdf | BN-74 FWR.pdf | Yes |  | Uploads\f8d2c75a-d77c-46af-b548-f054d8fda54e.pdf | Exist
Atikah | Yes | 785D0704-4147-4073-BD4E-5A5E7CAAE3A3 | B43BDAF0-59CF-40AF-B993-DAAF9FC013D4 | BN-74 | 084CEC60-5431-4140-9F7B-B9F0264BF819 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BN-74 NOOP for Top Section - FINAL.pdf | BN-74 NOOP for Top Section - FINAL.pdf | Yes |  | Uploads\084cec60-5431-4140-9f7b-b9f0264bf819.pdf | Exist
Atikah | Yes | E2A4668A-9B4D-439D-AFBC-B3A9E1711A7C | 82611FAF-7B97-4AD8-915E-DB540F7D1ED5 | SEC-33ST1 | 5A2F5A0B-537A-4094-9125-CDE0BCB8B620 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeC-33ST_1_1A_2 Development Well Final.pdf | Final Well Report SeC-33ST_1_1A_2 Development Well Final.pdf | Yes |  | Uploads\5a2f5a0b-537a-4094-9125-cde0bcb8b620.pdf | Exist
Atikah | Yes | 69DA9FAD-2871-417D-A7EE-C599747AFE13 | 82611FAF-7B97-4AD8-915E-DB540F7D1ED5 | SEC-33ST1 | 2952D3F9-3053-485A-85AF-0E402DA8D4BB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SeC-33ST1 ST2 Notice of Operation (NOOP) C1.pdf | SeC-33ST1 ST2 Notice of Operation (NOOP) C1.pdf | Yes |  | Uploads\2952d3f9-3053-485a-85af-0e402da8d4bb.pdf | Exist
Atikah | Yes | E48E55FC-E948-45DB-89B7-F61AA49A9A92 | BA6A1797-CE97-412D-9DBE-DB74F2497832 | DANUM-1 | 10F97CF3-26C0-41FB-AD4A-D3541615065A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Danum1 Signed Version 04 April 2013.pdf | Danum1 Signed Version 04 April 2013.pdf | Yes |  | Uploads\10f97cf3-26c0-41fb-ad4a-d3541615065a.pdf | Exist
Atikah | Yes | 7D839E7D-DAAD-43EC-90C1-273C7B5FF8C0 | BA6A1797-CE97-412D-9DBE-DB74F2497832 | DANUM-1 | 960B637B-B40F-4EB9-A698-237F8ED2AFC0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3DNUMWS04_DANUM-1_FWR.pdf | SBO3DNUMWS04_DANUM-1_FWR.pdf | Yes |  | Uploads\960b637b-b40f-4eb9-a698-237f8ed2afc0.pdf | Exist
Atikah | Yes | 71D71835-EA50-436F-84D9-52A63FEF9F23 | D4E25A87-349A-4A7B-A374-DB7BCCE1B6D1 | WEST BELUMUT A-04 | 02FC4C2F-3821-4091-92A2-3A892219D486 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WBA-04 EOWR FINAL.pdf |  | No |  | Uploads\02fc4c2f-3821-4091-92a2-3a892219d486.pdf | Exist
Atikah | Yes | 76664B5B-6FB3-4935-A84C-DD767985EA29 | D4E25A87-349A-4A7B-A374-DB7BCCE1B6D1 | WEST BELUMUT A-04 | 00EFCB77-2873-4454-AC5D-412EA06FB064 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A04-signed.pdf |  | No |  | Uploads\00efcb77-2873-4454-ac5d-412ea06fb064.pdf | Exist
Atikah | Yes | 02F677B1-40A2-4922-BD1C-CB6A5C2EB557 | 2CDDC602-67CA-47BA-ACC4-DC47808BB32D | AJK-A2ST1 | 5227B7E9-D732-4860-A049-7C44BC511483 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report_AJK-A2 ST1.pdf | Final Well Report_AJK-A2 ST1.pdf | Yes |  | Uploads\5227b7e9-d732-4860-a049-7c44bc511483.pdf | Exist
Atikah | Yes | 14CA8B59-00B6-4905-BD08-1665568D5314 | 2CDDC602-67CA-47BA-ACC4-DC47808BB32D | AJK-A2ST1 | 401FE867-AD47-44E9-A784-8B9C677202D8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | AJK-A2 ST1.pdf | AJK-A2 ST1.pdf | Yes |  | Uploads\401fe867-ad47-44e9-a784-8b9c677202d8.pdf | Exist
Atikah | Yes | 2528CBE7-E1C9-4B08-B54D-D6CAA840DE37 | C9B1018D-FF29-43C9-A7CE-DCCFEB4848C7 | BL-P1 | 17D51C45-AC06-4A16-85F0-A5F12903499B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BL-P1_EOWR.pdf | BL-P1_EOWR.pdf | Yes |  | Uploads\17d51c45-ac06-4a16-85f0-a5f12903499b.pdf | Exist
Atikah | Yes | 006F6A96-5CC6-4F72-9B97-C3DADB8BCC18 | C9B1018D-FF29-43C9-A7CE-DCCFEB4848C7 | BL-P1 | EEAE3E6A-7C2C-4B57-A364-0858180A9392 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_Block H Phase 1A Development Notice of Operation Rev0.pdf |  | No |  | Uploads\eeae3e6a-7c2c-4b57-a364-0858180a9392.pdf | Exist
Atikah | Yes | CFF4E94C-2817-4EC0-98C7-3CDBC206FDE5 | 9C91EEFD-A36D-4889-9023-DD218325FE17 | RT-P2 | 1E53C05D-CBD1-4ADA-949E-E2FB6ECDF0E5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | RT-P2_EOWR.pdf | RT-P2_EOWR.pdf | Yes |  | Uploads\1e53c05d-cbd1-4ada-949e-e2fb6ecdf0e5.pdf | Exist
Atikah | Yes | F03AB4BD-A086-4233-B0CA-A1B1E088721F | 9C91EEFD-A36D-4889-9023-DD218325FE17 | RT-P2 | A1454949-9AC3-4C74-8A84-9C7EB5F8E3F3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_Block H Phase 1A Development Notice of Operation Rev0.pdf |  | No |  | Uploads\a1454949-9ac3-4c74-8a84-9c7eb5f8e3f3.pdf | Exist
Atikah | Yes | ADEE0CFD-B158-44DF-9FD8-073C36F01C8B | D82177C4-1938-4329-AC61-DD6EF1CB3D48 | SJ-609B | 0E68663B-52B9-4B9D-A074-E1A799769704 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609B EOWR_MPM.pdf | SJ-609B EOWR_MPM.pdf | Yes |  | Uploads\0e68663b-52b9-4b9d-a074-e1a799769704.pdf | Exist
Atikah | Yes | 50BDF4FF-8506-4B98-A8CC-C944930F943F | D82177C4-1938-4329-AC61-DD6EF1CB3D48 | SJ-609B | 3B898071-C589-496F-ACBB-2E3A7C053B9A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SJ-609B NOOP - MPM Drilling.pdf | SJ-609B NOOP - MPM Drilling.pdf | Yes |  | Uploads\3b898071-c589-496f-acbb-2e3a7c053b9a.pdf | Exist
Atikah | Yes | 5D6FB694-81E2-463B-B078-C89BEBE5A51F | D8257B85-2C04-44A2-95C7-DD7FCC3298B4 | GK-W526C | 4C557DD2-CDBE-434C-90FC-E32A5DBDC889 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR GK-W526C.pdf | EOWR GK-W526C.pdf | Yes |  | Uploads\4c557dd2-cdbe-434c-90fc-e32a5dbdc889.pdf | Exist
Atikah | Yes | 30E0888A-23D3-4BCB-92E0-230F4502033B | D8257B85-2C04-44A2-95C7-DD7FCC3298B4 | GK-W526C | EB7C37C7-F748-4049-BB5F-608AFA5E66B3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-W526C NOOP.pdf | GK-W526C NOOP.pdf | Yes |  | Uploads\eb7c37c7-f748-4049-bb5f-608afa5e66b3.pdf | Exist
Atikah | Yes | 20F2B637-0BC5-44F6-9CB0-2CFE4C320FBC | B01349A9-3FE6-49E1-A2D9-DDD3BCC97C6F | PEKAKA-1 | 9A5C7949-B0B8-4504-910C-3878BE78B5DC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Pekaka-1 Well_Completion Report.pdf | Pekaka-1 Well_Completion Report.pdf | Yes |  | Uploads\9a5c7949-b0b8-4504-910c-3878be78b5dc.pdf | Exist
Atikah | Yes | 93D20514-A5C0-41EA-AC6E-9353253CE4B3 | B01349A9-3FE6-49E1-A2D9-DDD3BCC97C6F | PEKAKA-1 | 49BD18B4-9484-43A9-94BC-10DCE5EA7CD8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Pekaka-1 uDW Exploration_FINAL.pdf | NOOP_Pekaka-1 uDW Exploration_FINAL.pdf | Yes |  | Uploads\49bd18b4-9484-43a9-94bc-10dce5ea7cd8.pdf | Exist
Atikah | Yes | 1FE5CAE5-6C51-42B2-85A8-0076123EED9C | 40216F1E-85FA-46D9-B1DE-DDFCD25ABA77 | EB A-19ST1 | 0F769B76-2121-497F-9FD1-F85F54D9EC50 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-19ST1 End of Well Report Final.pdf | EB A-19ST1 End of Well Report Final.pdf | Yes |  | Uploads\0f769b76-2121-497f-9fd1-f85f54d9ec50.pdf | Exist
Atikah | Yes | 809BF3F9-D0C2-4467-84C5-BEFCFFF1F3C3 | 40216F1E-85FA-46D9-B1DE-DDFCD25ABA77 | EB A-19ST1 | A1E173A4-73A2-4319-8CF3-0C14E66BBE54 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-19ST1 Rev.pdf | EB A-19ST1 Rev.pdf | Yes |  | Uploads\a1e173a4-73a2-4319-8cf3-0c14e66bbe54.pdf | Exist
Atikah | Yes | DCE1E522-C747-4C17-B30C-FD3D40CD8145 | 963C7B47-9960-45DF-B371-DE36E75FCF9B | UNGGUL-1 | 298371E9-8FB0-42A4-9C3B-046558239121 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | UNGGUL-1 NOOP_INTERNAL.pdf | UNGGUL-1 NOOP_INTERNAL.PDF | Yes |  | Uploads\298371e9-8fb0-42a4-9c3b-046558239121.pdf | Exist
Atikah | Yes | C6BF58F7-CA86-4ED6-9F03-92D9D38FDE82 | 963C7B47-9960-45DF-B371-DE36E75FCF9B | UNGGUL-1 | 1297B483-EB3E-4E7D-8D7C-C0BD4DAAB5D2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Unggul-1 FWR.pdf | Unggul-1 FWR.pdf | Yes |  | Uploads\1297b483-eb3e-4e7d-8d7c-c0bd4daab5d2.pdf | Exist
Atikah | Yes | 7F963C23-0846-41DE-867D-FA928E694514 | 25E3B85B-5174-4B0A-B6E4-DE50E61B69EF | BARAM-H16 | 7FBD8703-CB33-4DCE-8784-6F7678375191 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram-H16 H16ST1 Final Well Report Final-Approved.pdf | Baram-H16 H16ST1 Final Well Report Final-Approved.pdf | Yes |  | Uploads\7fbd8703-cb33-4dce-8784-6f7678375191.pdf | Exist
Atikah | Yes | D93EB7CA-6A7C-4431-ADA0-D44BC162FE5E | 25E3B85B-5174-4B0A-B6E4-DE50E61B69EF | BARAM-H16 | C346B82D-FE9D-44CB-8E7A-9B552398178D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram South BARAM-H16 NOOP (Approved) Internal.pdf | Baram South BARAM-H16 NOOP (Approved) Internal.pdf | Yes |  | Uploads\c346b82d-fe9d-44cb-8e7a-9b552398178d.pdf | Exist
Atikah | Yes | 7D77A3AE-20E7-4746-9EED-7541758C428C | 80EF47FA-CED9-4320-8880-DEAA2D9365AF | KANOWIT-SS1 | FEE33F59-6DDC-49FD-BC7D-618764D49727 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KNWTGL03_KANOWIT-SS1_PCSB_NOOP.pdf | SKO3KNWTGL03_KANOWIT-SS1_PCSB_NOOP.pdf | Yes |  | Uploads\fee33f59-6ddc-49fd-bc7d-618764d49727.pdf | Exist
Atikah | Yes | E8A2D93A-1310-4CA7-A87D-58818D2F860E | 80EF47FA-CED9-4320-8880-DEAA2D9365AF | KANOWIT-SS1 | 166A1258-2944-43BF-8D50-59A541D59311 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KNWTWS11_KANOWIT-SS1_PCSB_FWR.pdf | SKO3KNWTWS11_KANOWIT-SS1_PCSB_FWR.pdf | Yes |  | Uploads\166a1258-2944-43bf-8d50-59a541d59311.pdf | Exist
Atikah | Yes | CFBE57D3-5097-4893-8193-04058977AA71 | A3E2A328-4583-40F6-99F8-DED33D894BAA | TE-80 | 6270F944-D295-4665-ACF6-CA34A9C5FE87 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TEMANA-80 FWR.pdf |  | No |  | Uploads\6270f944-d295-4665-acf6-ca34a9c5fe87.pdf | Exist
Atikah | Yes | 596AAC0D-0098-47FB-BA44-62388A6CC98E | A3E2A328-4583-40F6-99F8-DED33D894BAA | TE-80 | 8150C4E8-53C8-4BB3-A964-DE989C6EADDC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temana EMP 1.0 TE-80 NOOP Final.pdf | Temana EMP 1.0 TE-80 NOOP Final.pdf | Yes |  | Uploads\8150c4e8-53c8-4bb3-a964-de989c6eaddc.pdf | Exist
Atikah | Yes | 2C39991C-2EFB-41AD-9B7E-97B700565232 | A85B8B7C-3851-421F-89E7-DF8A0CA001F4 | F14-105 | 9511567D-B9E2-4FC4-B511-0EF971BC5D7A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-105 FDCR (EOWR).pdf | F14-105 FDCR (EOWR).pdf | Yes |  | Uploads\9511567d-b9e2-4fc4-b511-0ef971bc5d7a.pdf | Exist
Atikah | Yes | 4B6FAEDC-78FF-476C-AB9D-1A5F37A00330 | A85B8B7C-3851-421F-89E7-DF8A0CA001F4 | F14-105 | 7F4774DA-DE0E-44E7-AD60-EA732D6106C6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F14-GL02_F14-A104, F14-A105, F14-A107_SHELL_NOOP.pdf |  | No |  | Uploads\7f4774da-de0e-44e7-ad60-ea732d6106c6.pdf | Exist
Atikah | Yes | 70F0739B-A56E-4DBA-9DC2-0E4319CC14F6 | DE16D1A6-8AB9-4D2C-9855-E0046AE38E1A | SUMANDAK SELATAN-B02ST1 | F079ED3C-7E63-4449-AE07-2461BAF232CC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B02 ST1 NOOP_20181214_Final.pdf | Sumandak Selatan B02 ST1 NOOP_20181214_Final.pdf | Yes |  | Uploads\f079ed3c-7e63-4449-ae07-2461baf232cc.pdf | Exist
Atikah | Yes | 08924971-2F4B-4DD5-9E81-A3C27607A992 | DE16D1A6-8AB9-4D2C-9855-E0046AE38E1A | SUMANDAK SELATAN-B02ST1 | 48E1F709-27CD-4726-820A-15BA8EB2C34B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PETRONAS Final Well Report_B02 ST1_Final.pdf | Sumandak Selatan B02 ST1_Final.pdf | No |  | Uploads\48e1f709-27cd-4726-820a-15ba8eb2c34b.pdf | Exist
Atikah | Yes | B95D3B45-1963-4128-AA74-640E2B1269F0 | 4374E891-7E29-489F-AB49-E254D295EC3A | PEGAGA-2 | 4234194E-9D26-4335-8524-732BBC57E955 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3PGGAGL03_Pegaga-2.pdf | SKO3PGGAGL03_Pegaga-2.pdf | Yes |  | Uploads\4234194e-9d26-4335-8524-732bbc57e955.pdf | Exist
Atikah | Yes | 548D7A77-819E-46CF-BE94-CA7B8C7F496F | 4374E891-7E29-489F-AB49-E254D295EC3A | PEGAGA-2 | F76702AF-C95B-418D-98B3-F4583CF19357 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3PGGAWS09_Pegaga-2.pdf | Pegaga-2 FWR_Mudlogging.pdf | No |  | Uploads\f76702af-c95b-418d-98b3-f4583cf19357.pdf | Exist
Atikah | Yes | 0D38B422-6223-41CB-A7C0-096D9234C049 | 32FA6C90-15E7-4361-A009-E2759AE5F2AC | SAMARANG EAST-1 | 2906E941-8D84-43CF-9158-B2B0F1A2378F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSDT_SAMARANG EAST-1_PCSB_NOOP.pdf | SBO3SMRGWSDT_SAMARANG EAST-1_PCSB_NOOP.pdf | Yes |  | Uploads\2906e941-8d84-43cf-9158-b2b0f1a2378f.pdf | Exist
Atikah | Yes | 71EBD10E-7D96-4AB9-A5BB-1B19EEE28524 | 32FA6C90-15E7-4361-A009-E2759AE5F2AC | SAMARANG EAST-1 | E20F85A9-C7B1-4916-953F-A11754568B59 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMREWS01_SAMARANG EAST-1_PCSB_FWR.pdf | SBO3SMREWS01_SAMARANG EAST-1_PCSB_FWR.pdf | Yes |  | Uploads\e20f85a9-c7b1-4916-953f-a11754568b59.pdf | Exist
Atikah | Yes | BA506E4A-FA15-4252-996A-1B2BA646BAF0 | 0B222A40-62B1-4687-BCD6-E30A89A2FF77 | DULANG-A33ST2 | 9E7DB911-9732-42D2-8F99-A66A887A4C6E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Dulang A33 Final.pdf |  | No |  | Uploads\9e7db911-9732-42d2-8f99-a66a887a4c6e.pdf | Exist
Atikah | Yes | 5707C648-1168-461B-B4E4-D177E6CBF6D7 | 0B222A40-62B1-4687-BCD6-E30A89A2FF77 | DULANG-A33ST2 | 7F3A515C-677F-41D1-8463-CF7142614586 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang A33ST2_A33ST3 FWR.pdf | Dulang A33ST2_A33ST3 FWR.pdf | Yes |  | Uploads\7f3a515c-677f-41d1-8463-cf7142614586.pdf | Exist
Atikah | Yes | 7156DC0C-9168-4407-B023-51E611FC65E4 | 31A6F8D7-5F87-42EA-907C-E3A229137606 | TNGB-A9 | 6C4DCF78-4643-4614-8BB6-846812307AC8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS70_TNGB-A9_PCSB.pdf | PMO3TNGBWS70_TNGB-A9_PCSB.pdf | Yes |  | Uploads\6c4dcf78-4643-4614-8bb6-846812307ac8.pdf | Exist
Atikah | Yes | C2CDB044-190F-4BEC-9367-666C94D0AC51 | 31A6F8D7-5F87-42EA-907C-E3A229137606 | TNGB-A9 | 06DB9581-48ED-4EE0-8BBA-EDB4B7949177 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS69_TNGB-A9_PCSB.pdf | PMO3TNGBWS69_TNGB-A9_PCSB.pdf | Yes |  | Uploads\06db9581-48ed-4ee0-8bba-edb4b7949177.pdf | Exist
Atikah | Yes | 6B35105E-1AB2-455A-8543-132600EDCCE5 | 24A0A485-5182-474F-8E59-E4447C0F5A00 | BUJANG D2-1 | B03B34A5-98D0-4034-A312-C89E5E0AD611 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BJD2WS01_BUJANG D2-1.pdf | PMO3BJD2WS01_BUJANG D2-1.pdf | Yes |  | Uploads\b03b34a5-98d0-4034-a312-c89e5e0ad611.pdf | Exist
Atikah | Yes | 35F4E0D6-1BE7-4DC8-A172-F2E6B4DD0FAF | 24A0A485-5182-474F-8E59-E4447C0F5A00 | BUJANG D2-1 | A37E1181-96A4-4714-B4C4-D54503B9B058 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3BJD2WS04_BUJANG D2-1.pdf | Bujang D2-1 FWR_FINAL [22.01.201].pdf | No |  | Uploads\a37e1181-96a4-4714-b4c4-d54503b9b058.pdf | Exist
Atikah | Yes | 8C4840E7-9051-4480-BB89-C3A66D9CF680 | 08437D19-F91E-4428-BFCC-E44CCB729BAA | BO-F606 | 5EDCCC32-5250-455C-9EA0-1A261E623E70 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BOKOR-F606 FINAL rev2.0 SIGNED.pdf |  | No |  | Uploads\5edccc32-5250-455c-9ea0-1a261e623e70.pdf | Exist
Atikah | Yes | E11F814A-697F-4D27-8C5E-B1BEF9E4941A | 08437D19-F91E-4428-BFCC-E44CCB729BAA | BO-F606 | DE40CD0A-3ACE-4EF8-A954-602D2D6BBD9B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report (FWR) BO-F606_APPROVED.pdf | Final Well Report (FWR) BO-F606_APPROVED.pdf | Yes |  | Uploads\de40cd0a-3ace-4ef8-a954-602d2d6bbd9b.pdf | Exist
Atikah | Yes | 4CEF32DC-C3AD-44FE-A88B-17F9BD4B03FE | 4813A532-577C-4A41-9CFA-E4C9A1B9A8C4 | D18 208B | A568D685-B8FB-4E20-A55C-DD39854B4248 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | OP3A (208B) NOOP Rev 0 D18-EMP-EXE-PMT-JTB-DRL-NOP-0001.pdf |  | No |  | Uploads\a568d685-b8fb-4e20-a55c-dd39854b4248.pdf | Exist
Atikah | Yes | 0967B994-353C-428F-B930-C1607D97542E | 4813A532-577C-4A41-9CFA-E4C9A1B9A8C4 | D18 208B | BD7E78D9-5E5C-4252-AD1B-7A7B877E44CB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D-18 208B FWR.pdf | D-18 208B FWR.pdf | Yes |  | Uploads\bd7e78d9-5e5c-4252-ad1b-7a7b877e44cb.pdf | Exist
Atikah | Yes | 2E3EED24-1AA3-4109-BEFF-E4C6F7580FEF | 4A654F01-18F6-4A74-9B6C-E5478C86DCA0 | LARUT-A31ST2 | B309CEAF-5D49-4CA5-8196-6FB6FD254572 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-31ST2 (OP8) Final Well Report_RevB.pdf | LARUT A-31ST2 (OP8) Final Well Report_RevB.pdf | Yes |  | Uploads\b309ceaf-5d49-4ca5-8196-6fb6fd254572.pdf | Exist
Atikah | Yes | 12EB4035-79A2-414F-B5C5-519322701AB3 | 4A654F01-18F6-4A74-9B6C-E5478C86DCA0 | LARUT-A31ST2 | 682FB1C0-8DB7-43A3-8732-0A443A3D1176 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LARUT A-31ST1 (NOOP_OP8)-Rev2.pdf |  | No |  | Uploads\682fb1c0-8db7-43a3-8732-0a443a3d1176.pdf | Exist
Atikah | Yes | B1EB607D-A91E-4B21-B46D-4AAF2BA4FAEE | 7695D2C9-323B-43B8-84C8-E58F633DC9F4 | BERGADING-B3(O) | 5C9D8CF9-10F4-48AF-9426-281452D54CD0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading B-3(O) ST1 - signed.pdf | EOWR_Bergading B-3(O) ST1 - signed.pdf | Yes |  | Uploads\5c9d8cf9-10f4-48af-9426-281452d54cd0.pdf | Exist
Atikah | Yes | FE7489B4-7C18-4F31-9D75-E1412C95D26A | 7695D2C9-323B-43B8-84C8-E58F633DC9F4 | BERGADING-B3(O) | 92530C2A-F016-4069-A88F-ECF63F38FB06 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRGB-3(O), Bergading B-3(O).pdf | NOOP - BRGB-3(O), Bergading B-3(O).pdf | Yes |  | Uploads\92530c2a-f016-4069-a88f-ecf63f38fb06.pdf | Exist
Atikah | Yes | 96E210A2-6C52-4261-ABD0-CD99C99A737C | DB624338-5249-4F47-A3F3-E66B03274C5B | SEC-39 | 081E5F7E-D3A0-4325-B63A-4F89E52852DE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Se-C39 Work Over NOWOP Rev0.pdf | Se-C39 Work Over NOWOP Rev0.pdf | Yes |  | Uploads\081e5f7e-d3a0-4325-b63a-4f89e52852de.pdf | Exist
Atikah | Yes | CAE8A14F-9F9D-49AD-9478-991E59DC7A4D | DB624338-5249-4F47-A3F3-E66B03274C5B | SEC-39 | 6DBE6B79-03C8-456E-ABF3-276D52254836 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeC-39 Development Well.pdf | Final Well Report SeC-39 Development Well.pdf | Yes |  | Uploads\6dbe6b79-03c8-456e-abf3-276d52254836.pdf | Exist
Atikah | Yes | 96DCF341-AD7F-4F85-BDE1-8DE9E54ED5D2 | 7DBFEDF7-21D3-4D13-877E-E6AF274F899B | D35A-106ST1 | 5606DC4F-4B7B-440D-86E0-0DEF9B129199 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35A-106ST1 Well NOOP Final.pdf | D35A-106ST1 Well NOOP Final.pdf | Yes |  | Uploads\5606dc4f-4b7b-440d-86e0-0def9b129199.pdf | Exist
Atikah | Yes | D50055C2-A7AF-49E4-B25A-ACE4A476E937 | 7DBFEDF7-21D3-4D13-877E-E6AF274F899B | D35A-106ST1 | 2CC15620-8B9C-4807-9AF1-A3E053499021 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35DPA-106ST1 End Of Well Report Final.pdf | D35DPA-106ST1 End Of Well Report Final.pdf | Yes |  | Uploads\2cc15620-8b9c-4807-9af1-a3e053499021.pdf | Exist
Atikah | Yes | C6A4DDF6-E21E-469B-8126-40194152B050 | 9D7AFFB6-1343-4D12-8F06-E78E8D327D80 | KN-B1 | C7A85D70-8A39-444F-8B43-C2107C3CCF97 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLWS3G_KN_B1.pdf | SBO3KNBLWS3G_KN_B1.pdf | Yes |  | Uploads\c7a85d70-8a39-444f-8b43-c2107c3ccf97.pdf | Exist
Atikah | Yes | B996586D-0787-4D98-B20B-0BB2DD3E55AC | 9D7AFFB6-1343-4D12-8F06-E78E8D327D80 | KN-B1 | F3FFF794-4B51-44F3-A1FD-49EBE30D77CA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KNBLGL57_KN_B1.pdf | SBO3KNBLGL57_KN_B1.pdf | Yes |  | Uploads\f3fff794-4b51-44f3-a1fd-49ebe30d77ca.pdf | Exist
Atikah | Yes | 92FB3745-35B6-4265-8A2D-475770519196 | B399A667-2675-41D8-8FC2-E878BBE0E298 | TNGB-A11 | C5A808E5-7D8C-476D-9956-29A8A0593251 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS73_TNGB-A11_PCSB_NOOP.pdf | PMO3TNGBWS73_TNGB-A11_PCSB_NOOP.pdf | Yes |  | Uploads\c5a808e5-7d8c-476d-9956-29a8a0593251.pdf | Exist
Atikah | Yes | 60D7991F-62B8-402D-8CC8-95D47093DA90 | B399A667-2675-41D8-8FC2-E878BBE0E298 | TNGB-A11 | 6691F0AF-134A-401A-A38E-415B7427E21B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS1D_TNGB-A11_PCSB_FWR.pdf | PMO3TNGBWS1D_TNGB-A11_PCSB_FWR.pdf | Yes |  | Uploads\6691f0af-134a-401a-a38e-415b7427e21b.pdf | Exist
Atikah | Yes | E4832344-8770-4A66-AB04-1DCE05D79619 | ADECCDD6-D59C-4C2F-A8E8-E977048F15AE | BUNGA KANGSAR A-3 | E06550DD-775E-4281-8E16-F124F4F7B638 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A3 EOWR.pdf |  | No |  | Uploads\e06550dd-775e-4281-8e16-f124f4f7b638.pdf | Exist
Atikah | Yes | F26075C7-4DD6-44B2-B409-1D500F38E3C7 | ADECCDD6-D59C-4C2F-A8E8-E977048F15AE | BUNGA KANGSAR A-3 | 7385FF13-5E8F-467C-9300-FCEE2989A85D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BKG-A3 NOOP - signed off_signed.pdf |  | No |  | Uploads\7385ff13-5e8f-467c-9300-fcee2989a85d.pdf | Exist
Atikah | Yes | 368709AD-EA8A-4F74-9F9C-C0472C0643A8 | 29175183-B78E-4089-BB4B-E9FA5FC1188F | JITANG-1 | 9A7A0D6E-D981-42BF-A9B5-285F6BC883D7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JITANG-1 Final (signed).pdf | JITANG-1 Final (signed).pdf | Yes |  | Uploads\9a7a0d6e-d981-42bf-a9b5-285f6bc883d7.pdf | Exist
Atikah | Yes | 600DED5D-A584-48FF-90C2-DF7F45675497 | 29175183-B78E-4089-BB4B-E9FA5FC1188F | JITANG-1 | 0178ED02-5925-40A8-9C5F-1497FA298832 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jitang-1 NOOP_Internal.pdf | Jitang-1 NOOP_Internal.pdf | Yes |  | Uploads\0178ed02-5925-40a8-9c5f-1497fa298832.pdf | Exist
Atikah | Yes | B47B1A80-0EB2-4674-A4B9-37739D2C04F4 | B6E3869A-0D0C-4EB5-8E2C-EA9EAA514DAE | KEKEK-1 | 17871D5C-76A8-431D-92D3-30BF55D49C1A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KEKEK-1 EOWR.pdf | KEKEK-1 EOWR.pdf | Yes |  | Uploads\17871d5c-76a8-431d-92d3-30bf55d49c1a.pdf | Exist
Atikah | Yes | 73C8CDC7-C0FF-41DC-BBAA-949849CDA540 | B6E3869A-0D0C-4EB5-8E2C-EA9EAA514DAE | KEKEK-1 | 5EB6F6B4-B261-4D19-8957-4D832F9FC879 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KEKKGL02_KEKEK-1_SHELL_NOOP.pdf |  | No |  | Uploads\5eb6f6b4-b261-4d19-8957-4d832f9fc879.pdf | Exist
Atikah | Yes | 730D5F59-086C-4B8E-94B8-5FB0EC8BA4D9 | F9BB1B95-88ED-4EB7-A6F8-EB39BB279E8D | E06-102 | DC95A3FC-3817-45F1-844D-C22D2EBED007 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-102 (S4) NOOP.pdf | E06-102 (S4) NOOP.pdf | Yes |  | Uploads\dc95a3fc-3817-45f1-844d-c22d2ebed007.pdf | Exist
Atikah | Yes | 2ACA1654-FFF5-41FF-81FA-D0406DD16645 | F9BB1B95-88ED-4EB7-A6F8-EB39BB279E8D | E06-102 | 78A51C3E-9021-4B57-9FFE-9B094721F877 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | E06-102 End of Well Report FINAL.pdf | E06-102 End of Well Report FINAL.pdf | Yes |  | Uploads\78a51c3e-9021-4b57-9ffe-9b094721f877.pdf | Exist
Atikah | Yes | 59231D39-FB14-43BF-AA9C-719520ED3FFF | 82657D83-9E72-4C0B-9766-EB4877EFAFAC | BAYAN-222 | 99951430-0400-44AA-824B-270FD7A571B1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BYANWSH3_BAYAN-222_NOOP_PCSB.pdf | SKO3BYANWSH3_BAYAN-222_NOOP_PCSB.pdf | Yes |  | Uploads\99951430-0400-44aa-824b-270fd7a571b1.pdf | Exist
Atikah | Yes | A925CD5C-94F2-4444-8BC6-90A371CE06D5 | 82657D83-9E72-4C0B-9766-EB4877EFAFAC | BAYAN-222 | D1F57976-EDFC-4FCC-8231-A3EE8EAD6C94 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAYAN-222ST2 FWR.pdf |  | No |  | Uploads\d1f57976-edfc-4fcc-8231-a3ee8ead6c94.pdf | Exist
Atikah | Yes | 46678D2A-2DDF-4DF0-9DC4-93FB14D7BC05 | 4BF5A9B2-5119-4497-B538-EBA8BB2B056A | KNDW-D06 | DD4B2759-A59D-4029-90B9-D535D948ADB7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW-D06_End of Well Report.pdf | KNDW-D06_End of Well Report.pdf | Yes |  | Uploads\dd4b2759-a59d-4029-90b9-d535d948adb7.pdf | Exist
Atikah | Yes | 34EE218C-9017-4207-B040-C336DA73BA52 | 4BF5A9B2-5119-4497-B538-EBA8BB2B056A | KNDW-D06 | BB8C96CE-FBE0-4AC5-BF45-A857C9F9507D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KNDW D-06 NOOP-Final.pdf | KNDW D-06 NOOP-Final.pdf | Yes |  | Uploads\bb8c96ce-fbe0-4ac5-bf45-a857c9f9507d.pdf | Exist
Atikah | Yes | 0F597065-91A6-4FF2-BB6D-A69DD6BE11B5 | 37A88E82-182E-4006-B102-EBB5D73E388F | SF30-13 | 78D15AB0-916C-401D-9934-730839C9C0D8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-13 NOOP (MPM Drilling).pdf | SF30-13 NOOP (MPM Drilling).pdf | Yes |  | Uploads\78d15ab0-916c-401d-9934-730839c9c0d8.pdf | Exist
Atikah | Yes | 15401185-9E9B-44D1-B14C-355829A1BD72 | 37A88E82-182E-4006-B102-EBB5D73E388F | SF30-13 | C9DF9B89-DD94-4EAF-A5B9-CB21E0C681DB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF30-13 EOWR_MPM Drilling.pdf | SF30-13 EOWR_MPM Drilling.pdf | Yes |  | Uploads\c9df9b89-dd94-4eaf-a5b9-cb21e0c681db.pdf | Exist
Atikah | Yes | 69A22222-97EE-46E7-AF08-29BCC75E528C | 76B02702-5743-484E-9847-EBB620760D9D | BENTARA-A2 | 8B5C0997-86E4-40C4-AFEB-11781691A8B3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bentara-A2_Signed_rev01.pdf | NOOP Bentara-A2_Signed_rev01.pdf | Yes |  | Uploads\8b5c0997-86e4-40c4-afeb-11781691a8b3.pdf | Exist
Atikah | Yes | 090F0E01-C777-4A05-8897-99ED987B8694 | 76B02702-5743-484E-9847-EBB620760D9D | BENTARA-A2 | 56D0F7F5-BCA0-4E62-A695-5940152BE15A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bentara-A2 Final Well Report_.pdf | Bentara-A2 Final Well Report_.pdf | Yes |  | Uploads\56d0f7f5-bca0-4e62-a695-5940152be15a.pdf | Exist
Atikah | Yes | 62015AE3-306B-4FC5-BFF5-47B78C631548 | 75B7E268-C552-4EE0-8C47-EBB978B06D8E | BERTAM A-17 | F75D418E-D69E-416F-8957-C083A8C98F58 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-17 EOWR_Part 1 of 2.pdf | Bertam A-17 EOWR_Part 1 of 2.pdf | Yes |  | Uploads\f75d418e-d69e-416f-8957-c083a8c98f58.pdf | Exist
Atikah | Yes | 4FE86FA6-2E6C-47D0-868A-EB7C3A58CAC3 | 75B7E268-C552-4EE0-8C47-EBB978B06D8E | BERTAM A-17 | 618CF84F-A629-4769-9E53-119021DC90F3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam A-17 Notice of Operations 20171102 SAA.pdf | Bertam A-17 Notice of Operations 20171102 SAA.pdf | Yes |  | Uploads\618cf84f-a629-4769-9e53-119021dc90f3.pdf | Exist
Atikah | Yes | 92295F51-5BE2-452C-A271-0DE0A601BE3E | 9F67EB45-3596-4098-84F2-EBCF1876CB5C | BOC-24 (RR) | BC39B8F0-C711-4036-AE53-CA9D67CBBF87 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BOC-24 (RR) NOOP_Final_Signed.pdf | BOC-24 (RR) NOOP_Final_Signed.pdf | Yes |  | Uploads\bc39b8f0-c711-4036-ae53-ca9d67cbbf87.pdf | Exist
Atikah | Yes | A378C468-FB52-453E-B1B1-81025A0391FE | 9F67EB45-3596-4098-84F2-EBCF1876CB5C | BOC-24 (RR) | 6C8B7E22-ECB6-4CA8-8C80-935338227EE0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR BOC-24 (RR).pdf | EOWR BOC-24 (RR).pdf | Yes |  | Uploads\6c8b7e22-ecb6-4ca8-8c80-935338227ee0.pdf | Exist
Atikah | Yes | 504A146E-FF91-4F1F-8D1A-037F20360621 | 779082AA-2824-48E9-8A80-EC421F9B1004 | S-CN1-P4 | 646B7711-44CE-4C0B-8C95-A87824F3EDF6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPDR20_S-CN1-P4.pdf | SBO3SKNPDR20_S-CN1-P4.pdf | Yes |  | Uploads\646b7711-44ce-4c0b-8c95-a87824f3edf6.pdf | Exist
Atikah | Yes | 7166D3E1-8261-4B44-80BB-20AE9BD67317 | 779082AA-2824-48E9-8A80-EC421F9B1004 | S-CN1-P4 | DF0F6318-F2AE-4082-9833-0979DA7C41A7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SBO-WS7F_S-CN1-P4.pdf | SBO3SBO-WS7F_S-CN1-P4.pdf | Yes |  | Uploads\df0f6318-f2ae-4082-9833-0979da7c41a7.pdf | Exist
Atikah | Yes | 82049264-1C27-4270-BDEF-16F3769C1D64 | DF25D0AB-D34F-48A4-ACA4-EE67DA9B7D3E | BEKOK-AA16ST2 | 16D0F013-3179-4EC1-929D-E10910C6C9DF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bekok AA16 Approved [Internal].pdf | NOOP Bekok AA16 Approved [Internal].pdf | Yes |  | Uploads\16d0f013-3179-4ec1-929d-e10910c6c9df.pdf | Exist
Atikah | Yes | CEFE9607-260C-4595-9E58-95D5DDFAD973 | DF25D0AB-D34F-48A4-ACA4-EE67DA9B7D3E | BEKOK-AA16ST2 | DBB06A8D-5C51-41E7-A2CA-601355A4BFCD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bekok-AA16ST2 Final Well Report_.pdf | Bekok-AA16ST2 Final Well Report_.pdf | Yes |  | Uploads\dbb06a8d-5c51-41e7-a2ca-601355a4bfcd.pdf | Exist
Atikah | Yes | B54F8777-D1EA-40AC-8B51-374EDC02C215 | 14322389-83BF-4939-90AE-EEAB334308D8 | MAYONG-1 | F29F2526-8749-4938-862C-16ED26CB5984 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3MYNGWS04_MAYONG-1_PCSB.pdf | Mayong-1 FWR.pdf | No |  | Uploads\f29f2526-8749-4938-862c-16ed26cb5984.pdf | Exist
Atikah | Yes | 76AEB528-9FD2-4357-B0D7-B414B0D08EB5 | 14322389-83BF-4939-90AE-EEAB334308D8 | MAYONG-1 | D398BBC0-3C8F-4664-AD88-9297E25C0626 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3MYNGWS02_MAYONG-1.pdf | SKO3MYNGWS02_MAYONG-1.pdf | Yes |  | Uploads\d398bbc0-3c8f-4664-ad88-9297e25c0626.pdf | Exist
Atikah | Yes | A5557E88-04A5-4181-8426-E489BC3626A8 | FBE2EDCB-C794-4CE8-9D0A-EED34577A5A6 | BENUM-1 | B7514D11-6B8D-4FB2-8FED-A47069226328 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Benum-1_Drilling End of Well Report.pdf | Benum-1_Drilling End of Well Report.pdf | Yes |  | Uploads\b7514d11-6b8d-4fb2-8fed-a47069226328.pdf | Exist
Atikah | Yes | 7FC3892E-A9AE-48B6-8AB2-76CF62EC20AE | FBE2EDCB-C794-4CE8-9D0A-EED34577A5A6 | BENUM-1 | F3981AE0-1395-4704-A613-8A53E167A265 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Benum-1 NOOP.pdf | Benum-1 NOOP.pdf | Yes |  | Uploads\f3981ae0-1395-4704-a613-8a53e167a265.pdf | Exist
Atikah | Yes | E9FF1FB3-B0F6-49F5-891C-4CE7186765B9 | E4FC82DA-5584-4648-BCBB-F083BCA08C81 | DULANG-D31 | E5EB8504-B484-4A56-9153-695941D016F1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSYI_DULANG_D31.pdf | PMO3DULGWSYI_DULANG_D31.pdf | Yes |  | Uploads\e5eb8504-b484-4a56-9153-695941d016f1.pdf | Exist
Atikah | Yes | 61DEC5B1-95BD-4479-9C7A-D753E4D95E72 | E4FC82DA-5584-4648-BCBB-F083BCA08C81 | DULANG-D31 | EDB5D0A8-D8EA-4B7C-9BD6-3FE1E7CCFB6F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DULGWSXP_DULANG_D31.pdf | PMO3DULGWSXP_DULANG_D31.pdf | Yes |  | Uploads\edb5d0a8-d8ea-4b7c-9bd6-3fe1e7ccfb6f.pdf | Exist
Atikah | Yes | 5792322B-E2F6-41E8-982F-BA0FFC381F8C | 90EBC067-6482-42C4-B601-F08B6380B438 | BUNGA ZETUNG A-1(A) | 816CB7C7-ABF9-4DF2-A52B-9635E7A16399 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BZA_Rev0_Final.pdf |  | No |  | Uploads\816cb7c7-abf9-4df2-a52b-9635e7a16399.pdf | Exist
Atikah | Yes | 71E0E7CC-ABE2-4159-BE17-48EA6DC78F9E | 90EBC067-6482-42C4-B601-F08B6380B438 | BUNGA ZETUNG A-1(A) | 03540A87-6282-4BD4-BE7A-FD01F84EA845 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NMB-DRI-RPT-01166.pdf |  | No |  | Uploads\03540a87-6282-4bd4-be7a-fd01f84ea845.pdf | Exist
Atikah | Yes | CDAC0890-02B7-454D-8093-89F04A42D101 | E4459C06-CEF6-49DB-8EC0-F0BDC12F3B55 | DULANG-D13ST1 | 535E1C86-737E-4C4A-BF74-5C9402247774 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang EMP D13ST1 - OP3 Final 20Sept2017.pdf |  | No |  | Uploads\535e1c86-737e-4c4a-bf74-5c9402247774.pdf | Exist
Atikah | Yes | 825E8B5F-5E21-4B65-B611-ECFB234308CD | E4459C06-CEF6-49DB-8EC0-F0BDC12F3B55 | DULANG-D13ST1 | A8F9A782-FC00-4C78-98A3-AD3AF1BD2E31 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang D13ST1 OP3 FWR Complete Attachment.pdf | Dulang D13ST1 OP3 FWR Complete Attachment.pdf | Yes |  | Uploads\a8f9a782-fc00-4c78-98a3-ad3af1bd2e31.pdf | Exist
Atikah | Yes | 15AF6560-4D28-4783-9322-2822C764F8AE | E6357E34-BCA5-4297-BECD-F0C159FF2DF3 | SM-118 | 24765C9C-867D-4827-AE88-A83B6AA9D1DD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM 118 SM-2EOR-PCLO-DRL-JE-DRL-20-2018.pdf | SM 118 SM-2EOR-PCLO-DRL-JE-DRL-20-2018.pdf | Yes |  | Uploads\24765c9c-867d-4827-ae88-a83b6aa9d1dd.pdf | Exist
Atikah | Yes | 26AB6958-FA00-4055-B1AF-105B91013E51 | E6357E34-BCA5-4297-BECD-F0C159FF2DF3 | SM-118 | 9742FD06-80C6-47CB-AE3E-E6EE49A2B335 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM118 w Signature (1).pdf | SM118 w Signature (1).pdf | Yes |  | Uploads\9742fd06-80c6-47cb-ae3e-e6ee49a2b335.pdf | Exist
Atikah | Yes | B2293E65-1962-4004-AAEF-577E7904B0A2 | E840260D-A71D-4091-B767-F0EBD95A629D | EB A-18ST2 | FBC116C2-900E-4CEB-A286-B0578A4F7584 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-18ST2 EOWR.pdf | EB A-18ST2 EOWR.pdf | Yes |  | Uploads\fbc116c2-900e-4ceb-a286-b0578a4f7584.pdf | Exist
Atikah | Yes | CE1FC207-E6D2-4256-9D0C-A0D810E9934A | E840260D-A71D-4091-B767-F0EBD95A629D | EB A-18ST2 | B1CEC6D6-614F-4054-B7B2-918984A1B91B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB-A18ST2 Rev 1.pdf | EB-A18ST2 Rev 1.pdf | Yes |  | Uploads\b1cec6d6-614f-4054-b7b2-918984a1b91b.pdf | Exist
Atikah | Yes | 49DAB1F4-D186-4348-9664-1968CD080853 | 8377E8C1-5E1B-4B93-9425-F10AFC81806E | TIMI-1 | 910FCF8D-029D-4720-BE3B-946BFCDEB9A2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Timi-1 NOOP.pdf | Timi-1 NOOP.pdf | Yes |  | Uploads\910fcf8d-029d-4720-be3b-946bfcdeb9a2.pdf | Exist
Atikah | Yes | 52C951C0-8CBF-4018-83DE-D68A01CF4CD4 | 8377E8C1-5E1B-4B93-9425-F10AFC81806E | TIMI-1 | BA84ADA7-4A62-4487-BE8A-E61640C69AB0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Timi-1 EOWR.pdf | Timi-1 EOWR.pdf | Yes |  | Uploads\ba84ada7-4a62-4487-be8a-e61640c69ab0.pdf | Exist
Atikah | Yes | B9F6B984-0B32-4687-8C6C-FDB31EEBA379 | D4B84545-D383-4EF8-9996-F11A9E1FCD94 | RUKU RUKU-1 | BD1A0C90-353D-4A04-8F42-9EEFB4389141 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Ruku Ruku-1 Shell MLNG Exploration - EOWR.pdf | Ruku Ruku-1 Shell MLNG Exploration - EOWR.pdf | Yes |  | Uploads\bd1a0c90-353d-4a04-8f42-9eefb4389141.pdf | Exist
Atikah | Yes | 8F816685-851B-455B-A944-08A7085FB60C | D4B84545-D383-4EF8-9996-F11A9E1FCD94 | RUKU RUKU-1 | 11ECCBEF-D320-430D-BED5-CAA841A965C8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Ruku Ruku-1_Final NOOP.pdf | Ruku Ruku-1_Final NOOP.pdf | Yes |  | Uploads\11eccbef-d320-430d-bed5-caa841a965c8.pdf | Exist
Atikah | Yes | A96D6EF9-5051-452D-BA55-9A6A00F52C5F | 37E8BB80-B92D-4337-A7E0-F1961C5677CE | SUMANDAK SELATAN-B12ST1 | EEEF15B1-BE78-49C0-9233-15CDD86BA3D2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B12ST1 NOOP.pdf | Sumandak Selatan B12ST1 NOOP.pdf | Yes |  | Uploads\eeef15b1-be78-49c0-9233-15cdd86ba3d2.pdf | Exist
Atikah | Yes | 0FEF9AB7-86F2-4E22-AC35-748644E52074 | 37E8BB80-B92D-4337-A7E0-F1961C5677CE | SUMANDAK SELATAN-B12ST1 | 5CCAAD66-F793-4C2B-ACD8-DAAC75617719 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sumandak Selatan B12 ST1 FWR.pdf | Sumandak Selatan B12 ST1 FWR.pdf | Yes |  | Uploads\5ccaad66-f793-4c2b-acd8-daac75617719.pdf | Exist
Atikah | Yes | 5DA3B276-064E-49FD-B8D0-62FC1267B489 | E1742586-A8C2-48A7-9D9A-F29EB34F98BF | SUJT-C05 | 58BC52F7-14E3-4059-B521-103961A5891A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SUMANDAK TEPI C05 ST1_NOOP_2014_SB.pdf |  | No |  | Uploads\58bc52f7-14e3-4059-b521-103961a5891a.pdf | Exist
Atikah | Yes | 7D7EF960-9FDA-4540-B5ED-928BF3F8CCCE | E1742586-A8C2-48A7-9D9A-F29EB34F98BF | SUJT-C05 | 6EC63FE0-3123-4087-8CC6-F873EAE4F71C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMDPWS17_SUJT-C05_PCSB_FWR.pdf | SBO3SMDPWS17_SUJT-C05_PCSB_FWR.pdf | Yes |  | Uploads\6ec63fe0-3123-4087-8cc6-f873eae4f71c.pdf | Exist
Wadi | Yes | C2B939FD-EAD3-4C9F-AD8F-CDB6D2D30757 | 15867950-46F0-46E5-AA23-F2AEC34DB6EB | BERGADING-D3 (D) | 6A7184CB-D105-4C1F-87CC-F00201103A2B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading D-3_ Rev0_21062017 - PETRONAS SUBMISSION_FINAL.pdf |  | No |  | Uploads\6a7184cb-d105-4c1f-87cc-f00201103a2b.pdf | Exist
Atikah | Yes | 32613EEC-C282-4D69-8C1F-C083E81C29BA | 15867950-46F0-46E5-AA23-F2AEC34DB6EB | BERGADING-D3 (D) | 8CFD6FE9-4A07-451A-8395-BF7E1C6BF3D3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading D-3 (D) R0_FINAL.pdf | Bergading D-3 (D) R0_FINAL.pdf | Yes |  | Uploads\8cfd6fe9-4a07-451a-8395-bf7e1c6bf3d3.pdf | Exist
Atikah | Yes | 91246B29-2362-4910-B489-85D6806BD647 | 7F5FC836-1F78-46E7-AE3B-F2C85C7A791D | PUTERI BASEMENT-1 | E91C25F6-2E92-4110-9C31-5D83019D611F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Puteri Basement-1 PCSB FWR with Attachment Signed.pdf | Puteri Basement-1 PCSB FWR with Attachment Signed.pdf | Yes |  | Uploads\e91c25f6-2e92-4110-9c31-5d83019d611f.pdf | Exist
Atikah | Yes | AAD1CFB0-B10E-4D36-A622-0E8366277866 | 7F5FC836-1F78-46E7-AE3B-F2C85C7A791D | PUTERI BASEMENT-1 | 4AAC5A5A-13D3-414F-B20E-5396E0AE85BE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Puteri Basement-1 NOOP Final Signed (1).pdf | Puteri Basement-1 NOOP Final Signed (1).pdf | Yes |  | Uploads\4aac5a5a-13d3-414f-b20e-5396e0ae85be.pdf | Exist
Wadi | Yes | 769B6486-60E3-4A8E-A563-6F0B13D1F080 | E01D4699-FAC1-4E5F-9C68-F32B21995A6F | PESA-04 | 2D610B5E-7A01-4E8F-8767-ABF120DDE46F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PESA-4 EOWR FINAL (APPROVED).pdf |  | No |  | Uploads\2d610b5e-7a01-4e8f-8767-abf120dde46f.pdf | Exist
Wadi | Yes | 6A948F4D-E0ED-4966-A8E9-6C638C229AD2 | E01D4699-FAC1-4E5F-9C68-F32B21995A6F | PESA-04 | A0CF7A10-1941-49C0-8AD9-4A3BD4469C54 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PEMANIS PESA-1, PESA-2, PESA-3 and PESA-4 NOOP Revised.pdf |  | No |  | Uploads\a0cf7a10-1941-49c0-8ad9-4a3bd4469c54.pdf | Exist
Atikah | Yes | 2320EA42-C7DC-4BB6-ABA4-719BA852D6F4 | 2CFEB1E5-4BA3-4BCA-9DA5-F3D1FD26718A | EW-123ST2 | 8DBEE637-A9AE-4466-A1B3-5BF13BFD5B9E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas FWR EW-123 ST2_Final-signed.pdf | Petronas FWR EW-123 ST2_Final-signed.pdf | Yes |  | Uploads\8dbee637-a9ae-4466-a1b3-5bf13bfd5b9e.pdf | Exist
Atikah | Yes | FEC80EBE-D22B-4BA5-937A-D0C1A6FB34D5 | 2CFEB1E5-4BA3-4BCA-9DA5-F3D1FD26718A | EW-123ST2 | 3D5FD160-474E-47D7-AFCF-7A4B4358243F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Erb West EW123 ST2 NOOP_FINAL.pdf | Erb West EW123 ST2 NOOP_FINAL.pdf | Yes |  | Uploads\3d5fd160-474e-47d7-afcf-7a4b4358243f.pdf | Exist
Atikah | Yes | DFB9D6FD-3C15-4274-B27A-D8779A55C404 | 05A68438-4CAD-43AB-8C70-F464F384EB27 | BESA-11 | 6DCFC77F-92C4-4488-A128-AD53221A3582 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-69-DNC-RP-0004-00_BESA-11 EOWR.pdf | MOM-SK309-69-DNC-RP-0004-00_BESA-11 EOWR.pdf | Yes |  | Uploads\6dcfc77f-92c4-4488-a128-ad53221a3582.pdf | Missing
Atikah | Yes | B77C8350-3796-4580-9AF4-236D74882544 | 05A68438-4CAD-43AB-8C70-F464F384EB27 | BESA-11 | DBC2B5AE-43D3-47A1-9B59-8891E7D18AA9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | SKO3BLUMWS16_BESA-01_BESA-02_BESA-03_BESA-11_BESA-12.pdf | No |  | Uploads\dbc2b5ae-43d3-47a1-9b59-8891e7d18aa9.pdf | Missing
Wadi | Yes | BC248618-585C-457B-B1CD-3B01430CB509 | 66563E73-6D89-47D6-A0B4-F4CDBE17FBAB | SASA-13 | D3A5BB1C-A6C1-4EB1-818D-E359B403DFE7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Ph1_BATCH 2 NOOP.pdf |  | No |  | Uploads\d3a5bb1c-a6c1-4eb1-818d-e359b403dfe7.pdf | Exist
Atikah | Yes | 2550AEF5-B058-411F-8C95-B3DA6CA16696 | 66563E73-6D89-47D6-A0B4-F4CDBE17FBAB | SASA-13 | 03FC669B-F4CA-49EA-83A4-B0D4DC4F110D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA-13 EOWR.pdf | SASA-13 EOWR.pdf | Yes |  | Uploads\03fc669b-f4ca-49ea-83a4-b0d4dc4f110d.pdf | Exist
Atikah | Yes | 5B160A86-99CC-43DF-B5A3-8F4EA5193325 | E3C0ABE3-FF0E-49E9-BFDB-F5417AF5278F | BUNGA ZETUNG A-4 (C) | 1435249C-A846-442A-9651-882B01D00EB5 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BZA_Rev0_Final.pdf |  | No |  | Uploads\1435249c-a846-442a-9651-882b01d00eb5.pdf | Exist
Atikah | Yes | 9F06C4F9-C734-41A4-A108-E946EBB09252 | E3C0ABE3-FF0E-49E9-BFDB-F5417AF5278F | BUNGA ZETUNG A-4 (C) | 4CC669F2-109C-4398-85E8-ABF8871D4C0A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bunga Zetung A-4C.pdf | EOWR_Bunga Zetung A-4C.pdf | Yes |  | Uploads\4cc669f2-109c-4398-85e8-abf8871d4c0a.pdf | Exist
Atikah | Yes | 3BDC5399-0EA8-401D-83B8-BC94A7D7547D | 4811A89C-2F89-460C-90D1-F5EA823EFDAE | GINSENG-1 | 59EEC20C-FB5E-4B35-8232-8717DC6FFE36 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Ginseng-1 NOOP.pdf | Ginseng-1 NOOP.pdf | Yes |  | Uploads\59eec20c-fb5e-4b35-8232-8717dc6ffe36.pdf | Exist
Atikah | Yes | C56D9257-F005-487F-98AA-2F24832A00C5 | 4811A89C-2F89-460C-90D1-F5EA823EFDAE | GINSENG-1 | 8AADE213-91BA-4237-8F39-0F96A0E4D7FB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Ginseng-1 Final Well Report.pdf | Ginseng-1 Final Well Report.pdf | Yes |  | Uploads\8aade213-91ba-4237-8f39-0f96a0e4d7fb.pdf | Exist
Atikah | Yes | DCE5CA9C-5D05-4240-8228-19EBC611BE2D | 78BA28A5-BF57-4255-A6F5-F61C539B2F5C | MLK-113 | 8549EB46-BED2-4973-8555-B4A917850B58 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-113 EOWR_Petronas version.pdf | MLK-113 EOWR_Petronas version.pdf | Yes |  | Uploads\8549eb46-bed2-4973-8555-b4a917850b58.pdf | Exist
Atikah | Yes | 1898C761-76D5-4E4D-AB58-9954383078D8 | 78BA28A5-BF57-4255-A6F5-F61C539B2F5C | MLK-113 | C254A9A0-FB5E-4BD5-89BE-FCC9DA1A0E94 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-113 P402 NOOP_Final for Issue.pdf | MLK-113 P402 NOOP_Final for Issue.pdf | Yes |  | Uploads\c254a9a0-fb5e-4bd5-89be-fcc9da1a0e94.pdf | Exist
Atikah | Yes | D721DA66-9A0A-4C59-9CD9-72FB81E59F60 | 0EDAF336-3A62-419F-AA25-F63B1471C432 | GOREK-104 | 5CD8A746-E796-4837-9B45-CC98E04C667C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gorek-104 (NE) NOOP_Final_Rev2.pdf | Gorek-104 (NE) NOOP_Final_Rev2.pdf | Yes |  | Uploads\5cd8a746-e796-4837-9b45-cc98e04c667c.pdf | Exist
Atikah | Yes | BD30F829-16CA-4DDE-A179-B8377C732881 | 0EDAF336-3A62-419F-AA25-F63B1471C432 | GOREK-104 | EF81E746-AB3A-4A5B-A80F-BD3395AD7047 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gorek-104 FDCR_EOWR_Final_Rev0.0_S.pdf | Gorek-104 FDCR_EOWR_Final_Rev0.0_S.pdf | Yes |  | Uploads\ef81e746-ab3a-4a5b-a80f-bd3395ad7047.pdf | Exist
Atikah | Yes | DC2C930A-7EE5-4221-8A83-5DE4B5098AF5 | 6A0110E4-7F12-4A98-BD54-F6669B8DB406 | SIRIH-1 | 2B363CD7-9BB6-4721-9123-6BB270965572 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRIHWS01_SIRIH_1.pdf | SKO3SRIHWS01_SIRIH_1.pdf | Yes |  | Uploads\2b363cd7-9bb6-4721-9123-6bb270965572.pdf | Exist
Atikah | Yes | EEDCE4B0-1910-4918-8A26-42886E7A5DC2 | 6A0110E4-7F12-4A98-BD54-F6669B8DB406 | SIRIH-1 | 7437F00B-13CF-47B0-9849-B51900D2EB25 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Sirih-1 FWR.pdf | Sirih-1 FWR.pdf | Yes |  | Uploads\7437f00b-13cf-47b0-9849-b51900d2eb25.pdf | Exist
Atikah | Yes | C2D1C526-A539-499E-AA5B-66E57F8A31B6 | C17B2C05-6636-4282-9FE1-F72F7906F533 | REALGAR-2 | 41EBF622-7636-4683-89CC-2312A050D2D0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Realgar 2_Notice of Operation PETRONAS (NOOP) Rev 1.pdf | Realgar 2_Notice of Operation PETRONAS (NOOP) Rev 1.pdf | Yes |  | Uploads\41ebf622-7636-4683-89cc-2312a050d2d0.pdf | Exist
Atikah | Yes | EBF56C5B-37AC-445E-9530-D1AC1380FD8D | C17B2C05-6636-4282-9FE1-F72F7906F533 | REALGAR-2 | 7EDEE6BF-D787-4FA3-AD3E-52FF30C13049 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Realgar-2 EOWR.pdf | Realgar-2 EOWR.pdf | Yes |  | Uploads\7edee6bf-d787-4fa3-ad3e-52ff30c13049.pdf | Exist
Atikah | Yes | AAD994E5-ACCD-442D-A0DE-7FD1695041B5 | EC745227-99A5-4C51-8D93-F7724F9CF833 | BERGADING-A7(O) | E0081435-2B32-4F99-9190-F3A6300A72DA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERGADING-A7 FWR.pdf | BERGADING-A7 FWR.pdf | Yes |  | Uploads\e0081435-2b32-4f99-9190-f3a6300a72da.pdf | Exist
Atikah | Yes | 216F3B80-A592-4AF5-B716-14BED6BB4608 | EC745227-99A5-4C51-8D93-F7724F9CF833 | BERGADING-A7(O) | 529F6B77-7017-4D72-9580-D85714243DC6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRG A-7(O) - FINAL SIGNED.pdf | NOOP - BRG A-7(O) - FINAL SIGNED.pdf | Yes |  | Uploads\529f6b77-7017-4d72-9580-d85714243dc6.pdf | Exist
Atikah | Yes | 9931BA3F-572E-4C37-98B3-84BE0CB05D97 | 995E27D7-238C-4FA8-9061-F7B49063329D | BPA-4 | 0B338BEA-2C32-4BFF-B994-D13FA36467D2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-4 EOWR.pdf | BPA-4 EOWR.pdf | Yes |  | Uploads\0b338bea-2c32-4bff-b994-d13fa36467d2.pdf | Exist
Atikah | Yes | E6F69585-3E95-49DC-AF6E-7B9AD74D1C76 | 995E27D7-238C-4FA8-9061-F7B49063329D | BPA-4 | C082F4E0-7702-423B-A0DB-4641A832096C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-4 NOOP.pdf | BPA-4 NOOP.pdf | Yes |  | Uploads\c082f4e0-7702-423b-a0db-4641a832096c.pdf | Exist
Atikah | Yes | 5745A42E-862E-49A0-B5AB-877BA7FCDF10 | EFCEEB6A-4644-47DC-8BF3-F84BCB3E9BE7 | TBK-B1 | 148591C3-1130-43BB-A0C3-4A2BC6700282 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B1.pdf | TBK-B1.pdf | Yes |  | Uploads\148591c3-1130-43bb-a0c3-4a2bc6700282.pdf | Exist
Atikah | Yes | 25A8264D-1044-4D1A-B9B4-16C4CDE239D8 | EFCEEB6A-4644-47DC-8BF3-F84BCB3E9BE7 | TBK-B1 | 77DE2F8D-25BD-408C-857F-0A522014658E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-B1 Final Well Report.pdf | TBK-B1 Final Well Report | No |  | Uploads\77de2f8d-25bd-408c-857f-0a522014658e.pdf | Exist
Atikah | Yes | 6BB64B34-7E76-49C7-B588-05AFD09CE3D4 | 774C6005-69D0-4D46-92D7-F90316946C09 | JTG-A3 | 0AE37EC9-2C37-479D-A538-7F8100C82446 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | JTG-A3 Final Well Report_2020_01_23.pdf | JTG-A3 Final Well Report_2020_01_23 | No |  | Uploads\0ae37ec9-2c37-479d-a538-7f8100c82446.pdf | Exist
Atikah | Yes | FC451BF4-40FB-49A9-8794-C38A8CDA9674 | 774C6005-69D0-4D46-92D7-F90316946C09 | JTG-A3 | 34CFCA4D-6712-4AC8-85D0-21EDC9CA06C9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP JTG-A3.pdf | NOOP JTG-A3 | No |  | Uploads\34cfca4d-6712-4ac8-85d0-21edc9ca06c9.pdf | Exist
Atikah | Yes | F574097A-947F-47CB-84C2-1EF31C9B3492 | DBBAADF9-E3A9-4A7C-A76E-F922E213409B | S-SW1-W1 | A7730616-DB1F-4DAE-882C-4FDE2245AC62 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SBO-WS7R_S-SW1-W1_PTTEP_NOOP.pdf | SBO3SBO-WS7R_S-SW1-W1_PTTEP_NOOP.pdf | Yes |  | Uploads\a7730616-db1f-4dae-882c-4fde2245ac62.pdf | Exist
Atikah | Yes | B9A670D8-F05C-4A30-BA21-89F5CC731385 | DBBAADF9-E3A9-4A7C-A76E-F922E213409B | S-SW1-W1 | B25CF660-A2A6-476D-ABA5-9504044F89EF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SKNPWS66_S-SW1-W1_PTTEP_FWR.pdf | SBO3SKNPWS66_S-SW1-W1_PTTEP_FWR | No |  | Uploads\b25cf660-a2a6-476d-aba5-9504044f89ef.pdf | Exist
Atikah | Yes | C45EF3C4-07B4-44BE-88CF-437AC6537B7C | F851E81F-F989-4B28-AEDD-F94E72EA048C | D18-8 | 68C57862-0F2E-4F80-972E-DFBD68143A7C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-WS1G_D18-8.pdf | SKO3D18-WS1G_D18-8.pdf | Yes |  | Uploads\68c57862-0f2e-4f80-972e-dfbd68143a7c.pdf | Exist
Atikah | Yes | 17E3C364-36C8-4C50-B091-D70BCDE00DD7 | F851E81F-F989-4B28-AEDD-F94E72EA048C | D18-8 | C89ABFD8-8A4C-4E09-AF0E-1D026BF36FA3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D18-GL12_D18-8.pdf | SKO3D18-GL12_D18-8.pdf | Yes |  | Uploads\c89abfd8-8a4c-4e09-af0e-1d026bf36fa3.pdf | Exist
Atikah | Yes | 78268B71-B0D6-49F8-BC45-D7AFB76D5458 | D98B00EB-9DFE-4A3D-94B6-FA3B13751E8F | MLK-121 | F55B28AF-24F0-4A0A-8EA7-8697171C15F8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-121S1 FINAL.pdf | EOWR Malikai-121S1 FINAL.pdf | Yes |  | Uploads\f55b28af-24f0-4a0a-8ea7-8697171c15f8.pdf | Exist
Atikah | Yes | DF94C736-E12A-4537-8CE2-9229E879F91F | D98B00EB-9DFE-4A3D-94B6-FA3B13751E8F | MLK-121 | 575CACDD-5AB1-4A6C-8F17-BDC086AF39C1 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-121 S1 KMU2 WI - NOOP v2.pdf | MLK-121 S1 KMU2 WI - NOOP v2.pdf | Yes |  | Uploads\575cacdd-5ab1-4a6c-8f17-bdc086af39c1.pdf | Exist
Atikah | Yes | 960289B1-7630-4E06-9DD0-4D449097F683 | A28FA296-32AE-4194-8858-FA81DAF5F066 | INAS-8 | 8D839A25-B9DD-4F16-917E-1F0D3E7AC181 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3INASWS44_INAS-8.pdf | PMO3INASWS44_INAS-8.pdf | Yes |  | Uploads\8d839a25-b9dd-4f16-917e-1f0d3e7ac181.pdf | Exist
Atikah | Yes | C05E6C2C-1C45-4BA6-91F5-F6A114F0C4F4 | A28FA296-32AE-4194-8858-FA81DAF5F066 | INAS-8 | 6C619DEE-FC19-4B41-A5EF-375503168187 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3INASWS42_INAS-8_NOOP.pdf | PMO3INASWS42_INAS-8_NOOP | No |  | Uploads\6c619dee-fc19-4b41-a5ef-375503168187.pdf | Exist
Atikah | Yes | A4476F22-7A68-4568-B126-9725E4078428 | 8032D158-960F-4168-9D3C-FAC7F475D7F2 | NOSONG-3 | EB543DE0-DB55-48EC-9B06-BEAF5B2D7F91 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3NSNGWS11_NOSONG-3_FWR.pdf | SBO3NSNGWS11_NOSONG-3_FWR.pdf | Yes |  | Uploads\eb543de0-db55-48ec-9b06-beaf5b2d7f91.pdf | Exist
Atikah | Yes | 16121B87-8685-4E3A-BD9F-9E7B96EE0592 | 8032D158-960F-4168-9D3C-FAC7F475D7F2 | NOSONG-3 | EEC7AA84-9B13-4261-A4E4-6911A2648BE3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP NOSONG-3_PCSB.pdf | NOOP NOSONG-3_PCSB.pdf | Yes |  | Uploads\eec7aa84-9b13-4261-a4e4-6911a2648be3.pdf | Exist
Atikah | Yes | DAA41139-FD62-4074-B35A-E79E39223823 | 6F69F265-5A93-4C77-BF06-FAEAF0BFEDA1 | BERGADING-A10(P) | 53DEEEBE-CE7E-4969-8439-AF446C9D7777 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bergading A-10ST1.pdf | Bergading A-10ST1.pdf | Yes |  | Uploads\53deeebe-ce7e-4969-8439-af446c9d7777.pdf | Exist
Atikah | Yes | 09F78FD9-3A6F-4F70-ACEB-C44B212DC6D8 | 6F69F265-5A93-4C77-BF06-FAEAF0BFEDA1 | BERGADING-A10(P) | F77F7171-1E29-41E9-BE6A-6E800E6C5E73 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRG A-10(P).pdf | BRG A-10(P).pdf | Yes |  | Uploads\f77f7171-1e29-41e9-be6a-6e800e6c5e73.pdf | Exist
Atikah | Yes | 3EE6303A-292E-4375-AA34-732C7D305170 | 6D34B4B6-36A0-4E54-BC5D-FAF89ABA4FE7 | TNGB-A3 | CB96C60B-1CC6-4D00-B47E-61B8A4F8E456 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TANGGA BARAT A03-NOOP_2011_PM.pdf | TANGGA BARAT A03-NOOP_2011_PM.pdf | Yes |  | Uploads\cb96c60b-1cc6-4d00-b47e-61b8a4f8e456.pdf | Exist
Atikah | Yes | 33DFC83A-2E30-430D-91C0-6DBDADBBA811 | 6D34B4B6-36A0-4E54-BC5D-FAF89ABA4FE7 | TNGB-A3 | 3357AC51-E686-4B3F-BD6D-6E3880BF6CD2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3TNGBWS50_TNGB-A3_FWR.pdf | PMO3TNGBWS50_TNGB-A3_FWR.pdf | Yes |  | Uploads\3357ac51-e686-4b3f-bd6d-6e3880bf6cd2.pdf | Exist
Atikah | Yes | ECF53ABC-7BE3-4F75-837C-45887AD18482 | 12C3F4BA-E2AA-4DEA-9333-FB4A5436F1DA | SM-111 | E57E1705-F77F-4BD7-BD2A-A07849A23094 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSES_SM-111_PCSB_FWR.pdf | SBO3SMRGWSES_SM-111_PCSB_FWR.pdf | Yes |  | Uploads\e57e1705-f77f-4bd7-bd2a-a07849a23094.pdf | Exist
Atikah | Yes | 48BF97CE-3213-46DE-B3BB-10CD5DC449A5 | 12C3F4BA-E2AA-4DEA-9333-FB4A5436F1DA | SM-111 | 96BC68A0-5BD9-460E-9309-CC423699F7F8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL37_SM-111_PCSB_NOOP.pdf | SBO3SMRGGL37_SM-111_PCSB_NOOP.pdf | Yes |  | Uploads\96bc68a0-5bd9-460e-9309-cc423699f7f8.pdf | Exist
Atikah | Yes | 64D82929-E643-4A1A-8630-74171C2D10ED | 77EA99A7-1504-432F-AD53-FBD817747544 | BEKOK-BB20 | BA3C843E-B7A7-4B54-B8CA-54A0EFF5977A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 2. NOOP Bekok BB20.pdf | 2. NOOP Bekok BB20.pdf | Yes |  | Uploads\ba3c843e-b7a7-4b54-b8ca-54a0eff5977a.pdf | Exist
Atikah | Yes | F3E6143D-D711-4471-BEE7-BC4F2F9B13C4 | 77EA99A7-1504-432F-AD53-FBD817747544 | BEKOK-BB20 | D183FC72-B63C-4B5E-9BF6-22A0B91935D1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BB20 Final Well Report Final REV6.pdf | BB20 Final Well Report Final REV6.pdf | Yes |  | Uploads\d183fc72-b63c-4b5e-9bf6-22a0b91935d1.pdf | Exist
Atikah | Yes | A571A023-D53F-4F83-B468-F919F35EE549 | 2A7EACCC-8D6B-4A0B-A024-FBF692993476 | JERUN-A2 | 0EF6B98A-727E-4D76-9368-0C3A3DFB1CE6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Jerun-A2 Final Well Report R1.pdf | SK408 Jerun-A2 Final Well Report R1.pdf | Yes |  | Uploads\0ef6b98a-727e-4d76-9368-0c3a3dfb1ce6.pdf | Exist
Atikah | Yes | 943FA87E-00F1-446E-B406-7ED165518691 | 2A7EACCC-8D6B-4A0B-A024-FBF692993476 | JERUN-A2 | C4ABEE95-BCC1-466C-B42C-802885A8937E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\c4abee95-bcc1-466c-b42c-802885a8937e.pdf | Exist
Atikah | Yes | 171E3E84-8B6A-4C65-8F87-6BFC84049703 | C33D88BB-FEC9-4A6C-BE47-FC3E4094E4B5 | MERANTI M3 | 2DDABE9C-B1BE-4A53-9744-629BFFBB75CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MRNTWS17_MERANTI M1_M2_M3.pdf | PMO3MRNTWS17_MERANTI M1_M2_M3.pdf | Yes |  | Uploads\2ddabe9c-b1be-4a53-9744-629bffbb75cd.pdf | Exist
Atikah | Yes | 4A430F83-E7D5-43B5-910A-FFE577EFB143 | C33D88BB-FEC9-4A6C-BE47-FC3E4094E4B5 | MERANTI M3 | 56EDA4A0-611D-4386-8779-F0DF381C52FF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3MRNTWS14_MERANTI-M3.pdf | PMO3MRNTWS14_MERANTI-M3.pdf | Yes |  | Uploads\56eda4a0-611d-4386-8779-f0df381c52ff.pdf | Exist
Atikah | Yes | 709FF21F-9802-4C0D-B0AE-B92357C2E819 | 8F27B3DE-FF98-4F4B-89CC-FD33944756EA | BA-41 SR | 397B146E-1445-4AB5-83CC-02347470628D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARAM-41SR FWR.pdf | BARAM-41SR FWR.pdf | Yes |  | Uploads\397b146e-1445-4ab5-83cc-02347470628d.pdf | Exist
Atikah | Yes | 15AFADE5-1931-43DB-9174-D5B400E21CC2 | 8F27B3DE-FF98-4F4B-89CC-FD33944756EA | BA-41 SR | 572AD258-59E1-4E02-96AF-D13D414540B8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BARMWS5L_BA-41 SR.pdf | SKO3BARMWS5L_BA-41 SR.pdf | Yes |  | Uploads\572ad258-59e1-4e02-96af-d13d414540b8.pdf | Exist
Atikah | Yes | EF077543-52EB-4E21-AE3A-97C349F98417 | 3B4B7714-7679-4930-ACB2-FD3F854E2D01 | KAYU SUGI-1 | 834FDE9D-8D13-44A5-95F4-AA51B6B55CB4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kayu Sugi-1 Internal Copy.pdf | Kayu Sugi-1 Internal Copy.pdf | Yes |  | Uploads\834fde9d-8d13-44a5-95f4-aa51b6b55cb4.pdf | Exist
Atikah | Yes | DD7584A8-7C09-4BC9-8355-95A3D1A814C8 | 3B4B7714-7679-4930-ACB2-FD3F854E2D01 | KAYU SUGI-1 | 3BC0DFA5-3817-4C70-975E-A61F8D806674 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KAYU SUGI-1 FWR WITH ATTACHMENT.pdf | KAYU SUGI-1 FWR WITH ATTACHMENT.pdf | Yes |  | Uploads\3bc0dfa5-3817-4c70-975e-a61f8d806674.pdf | Exist
Atikah | Yes | 91936226-19A3-499F-BEC3-1F76DE87FA54 | DFB2A8CE-182F-4379-95DA-FD4603FABA1F | JERUN-A3 | A02A7691-87CD-421F-8A46-86FFBB02DF96 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK408 Jerun-A3 Final Well Report_FINAL.pdf | SK408 Jerun-A3 Final Well Report_FINAL.pdf | Yes |  | Uploads\a02a7691-87cd-421f-8a46-86ffbb02df96.pdf | Exist
Atikah | Yes | 680C1BDE-A30B-4727-B57B-46DB90226A47 | DFB2A8CE-182F-4379-95DA-FD4603FABA1F | JERUN-A3 | 8DA351FC-F990-4529-A885-9AE4D8FAEF34 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | SapuraOMV SK408 Jerun Development NOOP_FINAL_R1 1.pdf | Yes |  | Uploads\8da351fc-f990-4529-a885-9ae4d8faef34.pdf | Exist
Atikah | Yes | DC8711DC-39B1-48A4-B00A-394344653E71 | 5C36FD56-EAAB-4212-9131-FDEE74C2DD4B | BESA-12 | D95EC534-B495-413D-AE37-0060090BB427 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | Yes |  | Uploads\d95ec534-b495-413d-ae37-0060090bb427.pdf | Exist
Atikah | Yes | 95BCFA37-460F-4A9A-B7A1-DECF595B2E76 | 5C36FD56-EAAB-4212-9131-FDEE74C2DD4B | BESA-12 | 308F03E2-EB10-431B-8715-0A9B055AD611 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-69-DNC-RP-0005-00_BESA-12 EOWR.pdf | MOM-SK309-69-DNC-RP-0005-00_BESA-12 EOWR.pdf | Yes |  | Uploads\308f03e2-eb10-431b-8715-0a9b055ad611.pdf | Exist
Atikah | Yes | 6AC42EAE-6F91-4843-9763-04B15F93ECDE | C6C11A41-EC14-42C5-A90E-FE1C4C30F1C9 | CD-C12 | 3256251C-2868-420A-8DDF-E767F9077B25 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-C12 Final Well Report.pdf | CD-C12 Final Well Report.pdf | Yes |  | Uploads\3256251c-2868-420a-8ddf-e767f9077b25.pdf | Exist
Atikah | Yes | 0070D97F-BBA0-439C-B9D4-7AF7A03AF2E9 | C6C11A41-EC14-42C5-A90E-FE1C4C30F1C9 | CD-C12 | 0D9D7CC8-1C77-497F-AD60-42D2582BADF4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | CD-C12 (Slot 6A CDW-C Platform) SIGNED NOOP.pdf | CD-C12 (Slot 6A CDW-C Platform) SIGNED NOOP.pdf | Yes |  | Uploads\0d9d7cc8-1c77-497f-ad60-42d2582badf4.pdf | Exist
Atikah | Yes | F4EFAECE-ED63-489F-A1A0-16B18FED5B58 | 63CFEDFE-1073-488A-A04E-FE6C7837869E | BEDUK-1 | 73A96D4A-EA1B-4991-928F-2D7F2F1879CF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Beduk-1 End of Well Report.pdf | Beduk-1 End of Well Report.pdf | Yes |  | Uploads\73a96d4a-ea1b-4991-928f-2d7f2f1879cf.pdf | Exist
Atikah | Yes | D0146883-2920-49EC-94EA-2A52C6F5D4AE | 63CFEDFE-1073-488A-A04E-FE6C7837869E | BEDUK-1 | E39E2DF0-9744-4410-AD1F-FAF771600C9F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Beduk-1 NOOP.pdf | Beduk-1 NOOP.pdf | Yes |  | Uploads\e39e2df0-9744-4410-ad1f-faf771600c9f.pdf | Exist
Atikah | Yes | EC9DEAD8-8D93-41BF-8577-5345A02F774B | 7C7D1D3D-AA19-4A90-A294-FE753BB073A0 | MERAPUH-05 | 7CBC47D0-ACFC-47B5-90CF-5B99AB355042 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3KUMSWS02_MERAPUH-5_NOOP_PTTEP.pdf | SKO3KUMSWS02_MERAPUH-5_NOOP_PTTEP.pdf | Yes |  | Uploads\7cbc47d0-acfc-47b5-90cf-5b99ab355042.pdf | Exist
Atikah | Yes | 6CA98EAC-AAA8-4957-9481-D3FDD758210D | 7C7D1D3D-AA19-4A90-A294-FE753BB073A0 | MERAPUH-05 | ED60DD2D-BD15-45AC-8D33-AFC327F92A7A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Merapuh-5 EOWR.pdf | Merapuh-5 EOWR.pdf | Yes |  | Uploads\ed60dd2d-bd15-45ac-8d33-afc327f92a7a.pdf | Exist
Atikah | Yes | 14FCDA34-9181-4A8C-992A-4CCCDF6D92AF | 0310E566-2E9A-49E4-B772-FE8298B34F67 | BESA-02 | 90C7CB09-8456-4D92-9A0B-85729B442500 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | SKO3BLUMWS16_BESA-01, BESA-02, BESA-03, BESA-11, BESA-12_PTTEP_NOOP.pdf | Yes |  | Uploads\90c7cb09-8456-4d92-9a0b-85729b442500.pdf | Exist
Atikah | Yes | 5E43E28C-E396-438C-90F6-1E89CDAC9C23 | 0310E566-2E9A-49E4-B772-FE8298B34F67 | BESA-02 | 5A4C304D-0504-49B3-8738-1D1AF8190EB8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-69-DNC-RP-0002-00_BESA-02 EOWR.pdf | MOM-SK309-69-DNC-RP-0002-00_BESA-02 EOWR.pdf | Yes |  | Uploads\5a4c304d-0504-49b3-8738-1d1af8190eb8.pdf | Exist
Atikah | Yes | F14EAC29-A3AC-44F0-9D46-3DB7CCFDF8CE | 182F0787-6A25-4456-A20C-FF00B85E7852 | TE-81 | 31BD8B2C-8DEE-42A8-A118-9D500CDC041F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TEMANA-81ST2 FWR.pdf | TEMANA-81ST2 FWR.pdf | Yes |  | Uploads\31bd8b2c-8dee-42a8-a118-9d500cdc041f.pdf | Exist
Atikah | Yes | 0C6FAA45-52B4-4623-9F78-E465BE2964B7 | 182F0787-6A25-4456-A20C-FF00B85E7852 | TE-81 | D662D3C0-2611-4570-B345-A1F75F9F3163 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Temana EMP 1.0 TE-81 NOOP Final with KPI.pdf | Temana EMP 1.0 TE-81 NOOP Final with KPI.pdf | Yes |  | Uploads\d662d3c0-2611-4570-b345-a1f75f9f3163.pdf | Exist
Atikah | Yes | B8571EDF-D513-4F2A-822A-8B9DAB0D5F79 | 855F11AD-F260-4F1C-B7E8-FF2691F1EBA6 | WPPB-17 | 30237C3F-4914-412F-B264-B3B3721E8B50 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3WPPBGL6374_WPPB_17.pdf | SKO3WPPBGL6374_WPPB_17.pdf | Yes |  | Uploads\30237c3f-4914-412f-b264-b3b3721e8b50.pdf | Exist
Atikah | Yes | F3DBCD0F-A2DB-40F1-80DD-AFC7DE11101E | 855F11AD-F260-4F1C-B7E8-FF2691F1EBA6 | WPPB-17 | C7D0209F-FAA6-4B67-8567-A2C7BAF35E8C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf | MOM-SK309-61-DR-PR-0001-00_WPPB_INFILL_NOOP.pdf | Yes |  | Uploads\c7d0209f-faa6-4b67-8567-a2c7baf35e8c.pdf | Exist
Atikah | Yes | 43276DBE-507E-4A1C-B61E-62B26FE4FE34 | 851C4D55-D8C1-407B-B33F-FF28B7D46305 | BERANANG WEST-1 | E934F20C-EFAF-48A4-AAF7-4D2A4E401052 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERANANG WEST-1_NOOP_2013_PM.pdf | BERANANG WEST-1_NOOP_2013_PM.pdf | Yes |  | Uploads\e934f20c-efaf-48a4-aaf7-4d2a4e401052.pdf | Exist
Atikah | Yes | 8BDAC901-7E3D-4F1F-9E43-4CC38DE38D2A | 851C4D55-D8C1-407B-B33F-FF28B7D46305 | BERANANG WEST-1 | B0EDFAB8-BAEA-4BE6-B992-5307BD4277FE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Beranang West-1 FWR.pdf | Beranang West-1 FWR.pdf | Yes |  | Uploads\b0edfab8-baea-4be6-b992-5307bd4277fe.pdf | Exist
Atikah | Yes | 384A1CE2-26FF-490A-A42C-335D704525F4 | EA1898FC-F109-41F4-BC15-FFB490A1BB26 | ZAITUN-1 | 586C3531-5F16-4A2B-A58E-89AE48AA44E8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Zaitun-1 Notice of Operations Rev 3.pdf | Zaitun-1 Notice of Operations Rev 3.pdf | Yes |  | Uploads\586c3531-5f16-4a2b-a58e-89ae48aa44e8.pdf | Exist
Atikah | Yes | 4C563412-8A41-4269-B8C4-B5F7D5D224C5 | EA1898FC-F109-41F4-BC15-FFB490A1BB26 | ZAITUN-1 | B82F0D9B-3883-4B49-99B8-00C7A9777B77 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Zaitun 1 and ST1_V2 EOWR.pdf | Zaitun 1 and ST1_V2 EOWR.pdf | Yes |  | Uploads\b82f0d9b-3883-4b49-99b8-00c7a9777b77.pdf | Exist
Atikah | Yes | B029DF50-AE04-47EA-B3D2-3B305DD25C67 | 9BF6A158-1C21-42C7-971F-FFED774A063C | TUKAU-E42ST1 | 5B47D144-9462-4E6E-8A01-F04F31E12C88 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TK-42 ST1 FINALIZED Petronas Final Well Report.pdf | TK-42 ST1 FINALIZED Petronas Final Well Report.pdf | Yes |  | Uploads\5b47d144-9462-4e6e-8a01-f04f31e12c88.pdf | Exist
Atikah | Yes | 3878F3F1-8CEB-4DEB-8258-AF85DA15C17C | 9BF6A158-1C21-42C7-971F-FFED774A063C | TUKAU-E42ST1 | A3A59DFF-DD03-4F66-B0B0-5C025213C752 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP TK-42 ST1 (Rev1)_Approved.pdf | NOOP TK-42 ST1 (Rev1)_Approved.pdf | Yes |  | Uploads\a3a59dff-dd03-4f66-b0b0-5c025213c752.pdf | Exist
Mursyid | Yes | 7E52094C-557B-4592-8F97-13BAACBA7D45 | 003597D2-FEE8-4979-976B-051D135F3849 | B15-A1 | 9BB1CD70-0EC6-43ED-B3C5-C7D8C72CEB6F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SK310 B15-A1ST1 End of Well Report W Appendix (Signed).pdf | SK310 B15-A1ST1 End of Well Report W Appendix (Signed).pdf |  |  | Uploads\9bb1cd70-0ec6-43ed-b3c5-c7d8c72ceb6f.pdf | Exist
Mursyid | Yes | 80C6B0AF-22B6-44FA-9744-1DAE96A0B5C3 | 003597D2-FEE8-4979-976B-051D135F3849 | B15-A1 | BBC5F68B-A4D5-4F1E-971F-F255358AC289 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | B15 A1 NOOP.pdf | B15 A1 NOOP.pdf |  |  | Uploads\bbc5f68b-a4d5-4f1e-971f-f255358ac289.pdf | Exist
Mursyid | Yes | CBDEC4A4-E34F-48F6-8E43-C0A1F47F7974 | AFB775F1-FBE5-4A1A-BCBB-3C8213A0EC1E | BARAM-H14 | A621AE1F-8B41-4B21-966A-05CF3A2978A9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3BARSGL6000_BARAM-H14_PCSB.PDF | SKO3BARSGL6000_BARAM-H14_PCSB.PDF |  |  | Uploads\a621ae1f-8b41-4b21-966a-05cf3a2978a9.pdf | Exist
Mursyid | Yes | 659C0FCE-A48F-4F03-BD15-1F6E8FEBBC76 | AFB775F1-FBE5-4A1A-BCBB-3C8213A0EC1E | BARAM-H14 | A68AF565-8908-46B2-B590-04B944B808F8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Baram-H14 Final Well Report_Approved.pdf | Baram-H14 Final Well Report_Approved.pdf |  |  | Uploads\a68af565-8908-46b2-b590-04b944b808f8.pdf | Exist
Atikah | Yes | 4743641A-5E6C-4E47-A145-4496E0267442 | 50DD4A19-DE9D-460C-9EA9-CBB61E98DB15 | BAYAN-221 | D33ACB04-58E4-499B-8287-16B9491F9E42 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 3 BAYAN-221ST1 NOOP.pdf | 3 BAYAN-221ST1 NOOP.pdf |  |  | Uploads\d33acb04-58e4-499b-8287-16b9491f9e42.pdf | Exist
Atikah | Yes | E0A1A3DA-791E-4314-A2B7-FCE4EBDB3483 | 50DD4A19-DE9D-460C-9EA9-CBB61E98DB15 | BAYAN-221 | 442C8CF9-5A8F-40A7-B85A-2B03BB8D543D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BAYAN-221ST1 FWR.pdf | BAYAN-221ST1 FWR.pdf |  |  | Uploads\442c8cf9-5a8f-40a7-b85a-2b03bb8d543d.pdf | Exist
Atikah | Yes | DD749711-CD72-4813-B7A3-6F74DF528E67 | D5F89637-88D2-4A38-B540-B962C03FBC7A | BEKOK-BB18ST1 | E594BED1-3154-47EC-9EE6-9277672CFD2A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BB18_Final Well Report_Final_021222.pdf |  |  |  | Uploads\e594bed1-3154-47ec-9ee6-9277672cfd2a.pdf | Exist
Atikah | Yes | 05A7E223-B024-49F1-B55C-945F85C8B7C2 | 3D38880F-EE2D-47FA-869F-F8FBAA32D4EE | BERGADING-A4(E) | 526CFB1C-C5C8-4648-A27D-7B4465A26586 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BRG A-4(E) - FINAL_signed.pdf |  |  |  | Uploads\526cfb1c-c5c8-4648-a27d-7b4465a26586.pdf | Exist
Atikah | Yes | BD4D368D-4587-4D49-8CD0-177519EDAE15 | 3D38880F-EE2D-47FA-869F-F8FBAA32D4EE | BERGADING-A4(E) | A6BCCF60-A75B-4E21-BEEA-25EE07065B26 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading A-4_ Rev0_Final.pdf |  |  |  | Uploads\a6bccf60-a75b-4e21-beea-25ee07065b26.pdf | Exist
Atikah | Yes | B3584006-6D20-46EB-8758-DC80CC489E26 | 445148DE-5448-49B7-AF99-84833F2C9F58 | BERGADING-A5(N) | 8E0ED3C8-1D53-46D2-8277-D28378BBFE8F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRG A-5(N) ST1 - FINAL Signed.pdf |  |  |  | Uploads\8e0ed3c8-1d53-46d2-8277-d28378bbfe8f.pdf | Exist
Atikah | Yes | DEA5B402-FEFE-48EE-8837-AB41975DAA6E | 445148DE-5448-49B7-AF99-84833F2C9F58 | BERGADING-A5(N) | F1040679-5E90-4242-A98F-C1E5F9CF9A47 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading A-5_ Rev0 (sign).pdf |  |  |  | Uploads\f1040679-5e90-4242-a98f-c1e5f9cf9a47.pdf | Exist
Atikah | Yes | 08D8931D-1CB6-45D9-A1BB-A5F446C2EA4E | 6CC7D346-AE70-40E3-B637-E5459335E0F1 | BERGADING-B2(N) | EC67E791-0A3C-4A8A-AE78-CA2EF358EA35 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP - BRGB-2(N), Bergading B-2(N).pdf | NOOP - BRGB-2(N), Bergading B-2(N).pdf |  |  | Uploads\ec67e791-0a3c-4a8a-ae78-ca2ef358ea35.pdf | Exist
Atikah | Yes | 1F9D565D-8D8E-4D55-9E5C-A833FAC22380 | 6CC7D346-AE70-40E3-B637-E5459335E0F1 | BERGADING-B2(N) | 39E91751-BAF9-43F6-9227-48CCD201A775 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading_B-2(N)_Signed.pdf | EOWR_Bergading_B-2(N)_Signed.pdf |  |  | Uploads\39e91751-baf9-43f6-9227-48ccd201a775.pdf | Exist
Mursyid | Yes | 04345485-AC72-49C3-B772-2543B82D7DDD | A0EABB05-ED7F-4889-B347-5B89FFB6DFD9 | BERGADING-D2 (B) | 61E43EE4-6139-4429-9BA5-0B82DC5CC55F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_Bergading D-2_ Rev0_20062017 - PETRONAS SUBMISSION_FINAL.pdf |  |  |  | Uploads\61e43ee4-6139-4429-9ba5-0b82dc5cc55f.pdf | Exist
Mursyid | Yes | 3B62FCAA-72B1-4CB6-BDDD-90C1693F8464 | A0EABB05-ED7F-4889-B347-5B89FFB6DFD9 | BERGADING-D2 (B) | A6DCF833-03B0-41FA-9DF9-3B0F43610BA9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Bergading D-2 (B) R0_FINAL.pdf | NOOP Bergading D-2 (B) R0_FINAL.pdf |  |  | Uploads\a6dcf833-03b0-41fa-9df9-3b0f43610ba9.pdf | Exist
Atikah | Yes | 5947248F-C7C8-4AB8-A618-EBC417254D16 | C7E33BCF-D1F1-4A2F-A726-7309B46B0EBA | BERTAM A-1 | 6B07F9E8-801D-457B-88C1-54472327F295 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A01 NOOP (with Cover Letter PCSB).pdf | PMO3BTAMWS25_BERTAM A-12_IPC_LUNDIN_NOOP.pdf |  |  | Uploads\6b07f9e8-801d-457b-88c1-54472327f295.pdf | Exist
Atikah | Yes | FCC6AA93-9B74-46C2-8775-7FA9676A5AA8 | C7E33BCF-D1F1-4A2F-A726-7309B46B0EBA | BERTAM A-1 | 52D7ED56-7EAC-4015-9182-71160DB7020C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A1 EOWR.pdf | BERTAM-A1 EOWR.pdf |  |  | Uploads\52d7ed56-7eac-4015-9182-71160db7020c.pdf | Exist
Atikah | Yes | 4D567009-8EB9-4590-B824-25091C889FB0 | F49A8ED3-C363-4FD8-9D9F-D4559C75CB27 | BERTAM A-7 | 2A58FD62-A8AE-4674-8275-55D9E887E681 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A07ST1 EOWR (Final_Resize_Part4).pdf |  |  |  | Uploads\2a58fd62-a8ae-4674-8275-55d9e887e681.pdf | Exist
Atikah | Yes | 6B2D57C6-EA04-4579-937B-9D740800B397 | F49A8ED3-C363-4FD8-9D9F-D4559C75CB27 | BERTAM A-7 | C25E8A48-1C6F-4B8E-8F6F-5489A3CA8966 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BERTAM-A07ST1 NOOP (signed_resize).pdf |  |  |  | Uploads\c25e8a48-1c6f-4b8e-8f6f-5489a3ca8966.pdf | Exist
Mursyid | Yes | 02812D1A-32F2-42EA-8DC0-66F362FE6ECD | 031F5CAA-39DB-418C-B712-642A63D23261 | BERTAM-5 | 3C223331-A319-4488-8465-F71E2CD9F18A | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam-5 EOWR_Final_Complete.pdf | Bertam-5 EOWR_Final_Complete.pdf |  |  | Uploads\3c223331-a319-4488-8465-f71e2cd9f18a.pdf | Exist
Mursyid | Yes | D2DAC8E5-2CC2-4E63-B2E0-8C956473377C | 031F5CAA-39DB-418C-B712-642A63D23261 | BERTAM-5 | 2080A70B-2D52-4AD3-B563-B0F51F50E044 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bertam-5 NOOP.pdf | Bertam-5 NOOP.pdf |  |  | Uploads\2080a70b-2d52-4ad3-b563-b0f51f50e044.pdf | Exist
Mursyid | Yes | 830ECFDE-3E91-4ABC-840B-4FA1FA0096AE | 343B8821-12B4-497D-8124-1BBFA41F106D | BN-81 | CEA9C702-2D81-4E1B-9699-70071F0D9B0F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN-81 [Internal] (1).pdf | NOOP BN-81 [Internal] (1).pdf |  |  | Uploads\cea9c702-2d81-4e1b-9699-70071f0d9b0f.pdf | Exist
Mursyid | Yes | 49064D4B-98C7-4801-9143-055CCC61FBF7 | 343B8821-12B4-497D-8124-1BBFA41F106D | BN-81 | 95DF375B-02C1-4EDD-87B9-1EDBC2EB0C16 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BARONIA-K81 FWR.pdf |  |  |  | Uploads\95df375b-02c1-4edd-87b9-1edbc2eb0c16.pdf | Exist
Atikah | Yes | CA060AAA-B58D-40A2-B1F0-D63DBF1B142F | 5B701195-9418-4CC7-8F98-93E377E1CDFF | BN-82ST1 | 5DAAE239-066F-4A46-B05B-BDDA09F3B0AE | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR BN-82ST1 FINAL - for submission.pdf | FWR BN-82ST1 FINAL - for submission.pdf |  |  | Uploads\5daae239-066f-4a46-b05b-bdda09f3b0ae.pdf | Exist
Atikah | Yes | 0F3AF969-F7D8-484A-93A9-C446B2E8C748 | 5B701195-9418-4CC7-8F98-93E377E1CDFF | BN-82ST1 | EF03C598-2F8E-4C2D-9075-773823A0BD8A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP BN82-ST1 FINAL SIGNED.pdf | NOOP BN82-ST1 FINAL SIGNED.pdf |  |  | Uploads\ef03c598-2f8e-4c2d-9075-773823a0bd8a.pdf | Exist
Mursyid |  | CA9C75A8-2F3B-4E5F-A065-AF98F144CBAF | D022734A-B47B-48D4-8B02-38E872DB24C7 | BOKOR-E507 | E126CD1C-368C-456A-85DC-00DA1DFC5209 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 |  |  |  |  | Uploads\e126cd1c-368c-456a-85dc-00da1dfc5209.pdf | Exist
Atikah |  | 1789CF62-8D6E-4EDC-A675-543DC088F238 | 063194FF-7716-437C-8C91-B69ECD61A421 | BPA-1 | 9C3CA7EC-2D21-4942-BE66-1F2CFF70B2E7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 |  |  |  |  | Uploads\9c3ca7ec-2d21-4942-be66-1f2cff70b2e7.pdf | Exist
Atikah | Yes | CCD04C02-7FC9-4B73-B048-B24C4D227145 | 063194FF-7716-437C-8C91-B69ECD61A421 | BPA-1 | 3FD81BEE-A9BD-4C1A-969D-257D368DC357 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | BPA-1 EOWR_Rev1.pdf | BPA-1 EOWR_Rev1.pdf |  |  | Uploads\3fd81bee-a9bd-4c1a-969d-257d368dc357.pdf | Exist
Atikah | Yes | 2449661A-5689-41F9-97C9-0162FCDD901D | 8DFFC9E2-762A-4C49-92CA-9EF3A6BE6549 | BUNGA TERATAI 5 | 1FBCEFFA-5A37-45E7-8467-279C0B13754E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR_B. Teratai 5_signed.pdf |  |  |  | Uploads\1fbceffa-5a37-45e7-8467-279c0b13754e.pdf | Exist
Atikah | Yes | 5F21E568-713B-464D-B43D-F9DF695FE1F3 | 8DFFC9E2-762A-4C49-92CA-9EF3A6BE6549 | BUNGA TERATAI 5 | B4556C3A-9D90-4A50-9493-4499F81442EB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Teratai BT5(NW)_NOOP signed.pdf |  |  |  | Uploads\b4556c3a-9d90-4a50-9493-4499f81442eb.pdf | Exist
Mursyid | Yes | 050D4CF4-B4B6-40C7-9854-0E997EABABCB | CB23DF5A-31D7-430D-ACEE-309A2379F0A8 | BUNGA TERUNTUM-1 | 4C0111CD-FF69-4133-A794-B1CBE0A5322B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Teruntum-1 NOOP.pdf | Bunga Teruntum-1 NOOP.pdf |  |  | Uploads\4c0111cd-ff69-4133-a794-b1cbe0a5322b.pdf | Exist
Mursyid | Yes | DC934416-DFB0-40C3-AB2E-805F78E5E709 | CB23DF5A-31D7-430D-ACEE-309A2379F0A8 | BUNGA TERUNTUM-1 | BB7645A4-DFCD-475F-B4A6-7A27346BF314 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Bunga Teruntum-1 EoWR.pdf | Bunga Teruntum-1 EoWR.pdf |  |  | Uploads\bb7645a4-dfcd-475f-b4a6-7a27346bf314.pdf | Exist
Atikah | Yes | 44878C2D-7D42-4C92-942C-9C446C5479EF | A37402F1-B3FF-4702-A443-B7DB08F247D1 | CD-C08 | ED1A1CAD-D4DC-4FCE-AAA4-5345561EE242 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CDORWS3S_CD-C08.pdf | PMO3CDORWS3S_CD-C08.pdf |  |  | Uploads\ed1a1cad-d4dc-4fce-aaa4-5345561ee242.pdf | Exist
Atikah | Yes | C89AE0C8-9AB5-4270-98C7-040A7CAD6F9D | A37402F1-B3FF-4702-A443-B7DB08F247D1 | CD-C08 | D324C280-F630-4FD4-832A-A00A0A5652A7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP CD-C08 PML – PR – D – 0345 Rev 00.pdf | NOOP CD-C08 PML – PR – D – 0345 Rev 00.pdf |  |  | Uploads\d324c280-f630-4fd4-832a-a00a0a5652a7.pdf | Exist
Atikah | Yes | E0387304-98EB-42B9-A533-78EC077F5152 | EAB81BD2-AF45-4791-89BB-88293A3F08B3 | CHENANG-2 | 4280C8C7-2F98-4FF2-8A3B-416B29387139 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3CHENWS01_CHENANG-2_VESTIGO_NOOP.pdf | PMO3CHENWS01_CHENANG-2_VESTIGO_NOOP.pdf |  |  | Uploads\4280c8c7-2f98-4ff2-8a3b-416b29387139.pdf | Exist
Atikah | Yes | C853D8D5-B168-4643-8288-AA4303C1D39E | EAB81BD2-AF45-4791-89BB-88293A3F08B3 | CHENANG-2 | 570237CB-D78C-44ED-9CB5-8D1A82F8A57E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Chenang2 Final Well Report.pdf | Chenang2 Final Well Report.pdf |  |  | Uploads\570237cb-d78c-44ed-9cb5-8d1a82f8a57e.pdf | Exist
Mursyid | Yes | 68975D4A-D933-4B35-951B-58FB05DB3CB5 | 265823A3-08D8-48A1-AC18-55A131762C8C | D12-101A | 5133E5D4-5D73-4C92-99E7-9CCFE6A80509 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D12-101A NOOP (PMU).pdf |  |  |  | Uploads\5133e5d4-5d73-4c92-99e7-9ccfe6a80509.pdf | Exist
Mursyid | Yes | D96305E1-96E4-40DB-ABDD-544EB33CB624 | 265823A3-08D8-48A1-AC18-55A131762C8C | D12-101A | 4611239E-7667-44A6-BD7D-42A4329AC6B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3D12-WS16_D12-101A_SHELL_FWR.pdf | SKO3D12-WS16_D12-101A_SHELL_FWR.pdf |  |  | Uploads\4611239e-7667-44a6-bd7d-42a4329ac6b7.pdf | Exist
Atikah | Yes | 02C52700-A3F3-4B0A-B7BA-629D9085BD36 | EB5FDC02-2058-4181-8941-EB58D018BB4D | D18 401 | 10342966-3567-47EA-ABAB-209129A7CD64 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 401 FWR-signed.pdf | D18 401 FWR-signed.pdf |  |  | Uploads\10342966-3567-47ea-abab-209129a7cd64.pdf | Exist
Atikah | Yes | D2EDD656-9EEF-4DF4-9433-EC63038A19D4 | EB5FDC02-2058-4181-8941-EB58D018BB4D | D18 401 | 64E41A39-A96B-4726-8613-234D1BEF764A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D18 JT-D 401 (OP-AA) NOOP.pdf |  |  |  | Uploads\64e41a39-a96b-4726-8613-234d1bef764a.pdf | Exist
Mursyid | Yes | 0494F188-BC53-4166-89A9-E9269532E40B | 2578F522-2D38-4CDA-91A1-2E0D028C0DED | D21-P1 | B1785E67-D923-4E93-8E14-CB0D8F7AF763 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21-C2A-FB5 (P1)(D21-A5).pdf |  |  |  | Uploads\b1785e67-d923-4e93-8e14-cb0d8f7af763.pdf | Exist
Mursyid | Yes | 09133EC7-8550-4A6A-AE76-18379A9EA424 | 2578F522-2D38-4CDA-91A1-2E0D028C0DED | D21-P1 | 991337AC-142F-4877-8658-52C38AE418C4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D21 P1 (A5) EOWR.pdf | D21 P1 (A5) EOWR.pdf |  |  | Uploads\991337ac-142f-4877-8658-52c38ae418c4.pdf | Exist
Mursyid | Yes | E835CE09-6F19-485F-8DC4-D4DB0E9ECC7E | 02942886-B496-4CEE-BCFA-2BFACB57D7CE | D35-218ST1 | 986B35D7-CB51-4742-B22B-6D1F245E047F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-218ST1 End Of Well Report.pdf |  |  |  | Uploads\986b35d7-cb51-4742-b22b-6d1f245e047f.pdf | Exist
Mursyid | Yes | DF509827-15BE-42D7-AD9B-0265811B8AF2 | 02942886-B496-4CEE-BCFA-2BFACB57D7CE | D35-218ST1 | 53BEAB96-9080-4B40-9D79-800FBB1F94C6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-218ST1 Well NOOP.pdf | D35-218ST1 Well NOOP.pdf |  |  | Uploads\53beab96-9080-4b40-9d79-800fbb1f94c6.pdf | Exist
Atikah | Yes | 0F2B2369-CD03-4F66-B78A-803F5C53C80E | 45CAD953-71C1-45F5-BAD0-70958D147AF8 | D35B-217 ST2 | B6C6C6AB-1023-4099-AA8E-43F799C6781A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35-217ST2 Signed Final NOOP.pdf |  |  |  | Uploads\b6c6c6ab-1023-4099-aa8e-43f799c6781a.pdf | Exist
Atikah | Yes | 604E3B4D-8D9C-4EC5-BC47-0B8584152DCC | 45CAD953-71C1-45F5-BAD0-70958D147AF8 | D35B-217 ST2 | 6F438704-23C6-4BB6-BACB-FC752D4A1196 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | D35B-217 End Of Well Report Final.pdf |  |  |  | Uploads\6f438704-23c6-4bb6-bacb-fc752d4a1196.pdf | Exist
Atikah | Yes | 65CC308D-C16C-43DE-A502-341F3F487777 | F93F61F6-37D4-4896-9F0C-AC4FF3CDF63C | DAMAR-A07 | BAFC37E3-2778-4237-82C8-B2E078547917 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARGL05_DAMAR-A07.pdf | PMO3DMARGL05_DAMAR-A07.pdf |  |  | Uploads\bafc37e3-2778-4237-82c8-b2e078547917.pdf | Exist
Atikah | Yes | C9A6BBEF-2B23-406E-B316-8738F306C5EC | F93F61F6-37D4-4896-9F0C-AC4FF3CDF63C | DAMAR-A07 | EE5152DF-5DED-488A-A0A9-E383F2AB139E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report Damar A-7.pdf |  |  |  | Uploads\ee5152df-5ded-488a-a0a9-e383f2ab139e.pdf | Exist
Mursyid | Yes | 2223A6CA-9E63-411D-A7FF-83D96493C3DD | 2A5F353C-846F-4174-94D9-080CBA107E4B | DAMAR-A10 | 222956CB-DFD5-4E67-ABE1-FDA51A3C1B43 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Damar A-10 FWR.pdf | Damar A-10 FWR.pdf |  |  | Uploads\222956cb-dfd5-4e67-abe1-fda51a3c1b43.pdf | Exist
Mursyid | Yes | F5413BE3-65DF-45A4-AE73-C983CEB76222 | 2A5F353C-846F-4174-94D9-080CBA107E4B | DAMAR-A10 | F50C0257-AFB9-41DF-BDEA-848293662763 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARWS21_DAMAR-A10.pdf | PMO3DMARWS21_DAMAR-A10.pdf |  |  | Uploads\f50c0257-afb9-41df-bdea-848293662763.pdf | Exist
Atikah | Yes | 86819660-FA4E-4A18-A4C9-888E21284C45 | BFBE4FEC-5F6B-4F47-A5F7-8DB8420FCF44 | DAMAR-A14 | ED170685-91FF-4138-8C35-894E5F6214D3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PMO3DMARGL03_DAMAR-A14_EMEPMI.pdf | PMO3DMARGL03_DAMAR-A14_EMEPMI.pdf |  |  | Uploads\ed170685-91ff-4138-8c35-894e5f6214d3.pdf | Exist
Atikah | Yes | 441C8005-F3B1-42F6-ADDC-451ED9EC09E6 | BFBE4FEC-5F6B-4F47-A5F7-8DB8420FCF44 | DAMAR-A14 | 998F5C83-E1A4-4AB9-9653-5C26BD15573C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Damar A-14 FWR.pdf | Damar A-14 FWR.pdf |  |  | Uploads\998f5c83-e1a4-4ab9-9653-5c26bd15573c.pdf | Exist
Atikah | Yes | A08E00FC-F6F6-421C-AF34-20B8A33AD86C | D129E4F9-E245-47D2-870E-9EE95990046E | DULANG-A23ST2 | 3C855226-23C2-4738-A436-EB1CC50000F4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Dulang A23ST2.pdf |  |  |  | Uploads\3c855226-23c2-4738-a436-eb1cc50000f4.pdf | Exist
Atikah | Yes | F6302314-D5B8-48C0-A4F3-78765C9A673D | D129E4F9-E245-47D2-870E-9EE95990046E | DULANG-A23ST2 | EA379082-EAA1-4D12-B811-237B3208FAD3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_DULANG-A23ST2.pdf |  |  |  | Uploads\ea379082-eaa1-4d12-b811-237b3208fad3.pdf | Exist
Mursyid | Yes | F60CDF04-D9FD-4892-9D80-80BB8AA8A272 | 023391AD-E6D7-4CEB-8D9D-0EAD859B7723 | DULANG-B25ST2 | 69CC3127-018B-4CDA-B878-637ACD786C45 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Dulang B25ST4_Signedcopy.pdf |  |  |  | Uploads\69cc3127-018b-4cda-b878-637acd786c45.pdf | Exist
Mursyid | Yes | C1B2D2AA-2DD8-4EB6-97CA-A751E96712F7 | 023391AD-E6D7-4CEB-8D9D-0EAD859B7723 | DULANG-B25ST2 | CA13E320-8560-47EE-B730-AC7ABCCF76FD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_Dulang B25ST2 Final.pdf | NOOP_Dulang B25ST2 Final.pdf |  |  | Uploads\ca13e320-8560-47ee-b730-ac7abccf76fd.pdf | Exist
Atikah | Yes | A51FF042-4A48-4257-B289-543C2CB0FD0A | 1B569C44-3CE7-4152-B323-AEFE508FA396 | DULANG-D20ST1 | 139E1C54-B427-4A87-9092-4059E0D7A0C5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Dulang D20ST1 OP1 FWR Complete Attachment.pdf | Dulang D20ST1 OP1 FWR Complete Attachment.pdf |  |  | Uploads\139e1c54-b427-4a87-9092-4059e0d7a0c5.pdf | Exist
Atikah | Yes | 2AE3E7C6-BAAA-41FD-98B5-E636587A1AEB | 1B569C44-3CE7-4152-B323-AEFE508FA396 | DULANG-D20ST1 | 6E458DA4-6C85-491F-9183-2E873315E68C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | DULANG-D20ST1 NOOP ADDENDUM.pdf | DULANG-D20ST1 NOOP ADDENDUM.pdf |  |  | Uploads\6e458da4-6c85-491f-9183-2e873315e68c.pdf | Exist
Atikah | Yes | 8240355F-FC80-4B8F-9826-A09176FA2BE2 | 21C457AF-ED37-4514-80FE-763F8EA2F8D1 | EB A-04ST1 | 60C695B6-EF10-4837-8DD9-81ED3CFEA899 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-04ST1 FWR.pdf | EBA-04ST1 FWR.pdf |  |  | Uploads\60c695b6-ef10-4837-8dd9-81ed3cfea899.pdf | Exist
Atikah | Yes | 0599A83E-C2E8-4BCF-8E8C-622AAE59A054 | 21C457AF-ED37-4514-80FE-763F8EA2F8D1 | EB A-04ST1 | EB139035-52E6-4625-8070-071A0A96BAD2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-04ST1 Final.pdf | EBA-04ST1 Final.pdf |  |  | Uploads\eb139035-52e6-4625-8070-071a0a96bad2.pdf | Exist
Mursyid | Yes | C2934F73-2A92-428B-89F0-85AF7BA6FCDC | D919DC7D-75DD-44DD-B35E-668DB396068A | EB A-09ST2 | 7C754630-04D2-46D3-BA94-BAD58411C2DE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB-A09ST2 NOOP Final.pdf |  |  |  | Uploads\7c754630-04d2-46d3-ba94-bad58411c2de.pdf | Exist
Mursyid | Yes | A73593E0-A99C-483F-8D7E-43D0AE7D2FD5 | D919DC7D-75DD-44DD-B35E-668DB396068A | EB A-09ST2 | D51455B6-EB49-409F-9640-D013D49131A6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB-A09ST2 FWR (1).pdf |  |  |  | Uploads\d51455b6-eb49-409f-9640-d013d49131a6.pdf | Exist
Atikah | Yes | F9C3E66E-1D7C-4233-8E0E-DB621595CAAF | 392F26ED-0990-4C5A-B4E2-92CDA72211C1 | EB A-11ST1 | B2ACE185-BDE3-4ECB-84E4-216678A087EA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-11ST1 NOOP FINAL APPROVED.pdf | EB A-11ST1 NOOP FINAL APPROVED.pdf |  |  | Uploads\b2ace185-bde3-4ecb-84e4-216678a087ea.pdf | Exist
Atikah | Yes | 9AFC6B44-DEE4-454E-BF58-F465D91859AE | 392F26ED-0990-4C5A-B4E2-92CDA72211C1 | EB A-11ST1 | FBDF0BDF-E4DB-4F69-A98C-64AC677B0DAD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EBA-11 ST1 FWR.pdf | EBA-11 ST1 FWR.pdf |  |  | Uploads\fbdf0bdf-e4db-4f69-a98c-64ac677b0dad.pdf | Exist
Mursyid | Yes | F83649C9-3E0A-4549-98CF-75B5897D4D8D | 119EC196-002B-442F-B0B0-0313AFEB6AD1 | EB A-14ST2 | 6C8722A7-925F-4A11-850B-326CA184AD45 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-14ST2 FWR.pdf | EB A-14ST2 FWR.pdf |  |  | Uploads\6c8722a7-925f-4a11-850b-326ca184ad45.pdf | Exist
Mursyid | Yes | 829C0C5E-1FBA-42E8-B398-7CAF4FA306F4 | 119EC196-002B-442F-B0B0-0313AFEB6AD1 | EB A-14ST2 | C3106FE3-8E61-40CE-92E2-D11330D20D0A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EB A-14ST2 NOOP FINAL APPROVED.pdf | EB A-14ST2 NOOP FINAL APPROVED.pdf |  |  | Uploads\c3106fe3-8e61-40ce-92e2-d11330d20d0a.pdf | Exist
Atikah | Yes | E6AD07D8-997E-4290-9FE2-FD4BF748AD0F | 04A6940F-D391-48DB-AB08-B08CFA5ED404 | ERB WEST 120 ST2 | 89F6415A-AF6A-40A4-96CD-0A0324D37916 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Petronas Final Well Report EW-120 ST2_Rev2_Final.pdf |  |  |  | Uploads\89f6415a-af6a-40a4-96cd-0a0324d37916.pdf | Exist
Atikah | Yes | 1E7E7D64-0F09-4F30-83A1-2BEE0D24DF43 | 04A6940F-D391-48DB-AB08-B08CFA5ED404 | ERB WEST 120 ST2 | DE42C9B3-1FEC-46D8-BA97-3D7443F01A7B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20190515_Erb West EW120 ST2 NOOP.pdf |  |  |  | Uploads\de42c9b3-1fec-46d8-ba97-3d7443f01a7b.pdf | Exist
Mursyid | Yes | A9B20D6F-A596-4FC6-B3A5-A89B5138E487 | A7E25A29-A854-401F-A781-6304B56218DD | EW-119 ST2 | F820FD73-ABAB-4521-9D47-995CB7414EFA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 20190515_Erb West EW119 ST2 NOOP.pdf | 20190515_Erb West EW119 ST2 NOOP.pdf |  |  | Uploads\f820fd73-abab-4521-9d47-995cb7414efa.pdf | Exist
Mursyid | Yes | 5E32C5A2-4B44-4992-A0BE-181A1DF3EBCA | A7E25A29-A854-401F-A781-6304B56218DD | EW-119 ST2 | 828C02BA-C962-4B9C-8982-EEB060A442F1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EW-119 ST2_Rev3 Final Well Report.pdf | EW-119 ST2_Rev3 Final Well Report.pdf |  |  | Uploads\828c02ba-c962-4b9c-8982-eeb060a442f1.pdf | Exist
Atikah | Yes | 31D52FD8-D581-40EC-927C-1856AE494D7C | 699A79D8-A81F-4D6E-A701-E5893B7129A4 | EW-124 ST3 | 4FF38C49-2262-4560-A3B7-37BB01FF2E07 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EW-124ST3 FWR.pdf | EW-124ST3 FWR.pdf |  |  | Uploads\4ff38c49-2262-4560-a3b7-37bb01ff2e07.pdf | Exist
Atikah | Yes | 135D2E5F-CC51-417B-A5AE-197B8DDB8AD3 | 699A79D8-A81F-4D6E-A701-E5893B7129A4 | EW-124 ST3 | 5E5B55BA-08DE-40D1-A685-0349FA75C4D6 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ERB WEST EW-124 ST3 NOOP.pdf | ERB WEST EW-124 ST3 NOOP.pdf |  |  | Uploads\5e5b55ba-08de-40d1-a685-0349fa75c4d6.pdf | Exist
Atikah | Yes | AB00F78D-088E-4566-A4B2-3E5F33AD5292 | 3890D466-4107-490A-ABF7-DC1D80921ECF | F14-109 | 2ECF8CC2-CBFF-47BD-A041-1974A234F065 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | F14-109 NOOP_Rev1.pdf | F14-109 NOOP_Rev1.pdf |  |  | Uploads\2ecf8cc2-cbff-47bd-a041-1974a234f065.pdf | Exist
Atikah | Yes | 401FA399-633B-4057-B80A-822B8865E646 | 3890D466-4107-490A-ABF7-DC1D80921ECF | F14-109 | B9CE9192-7CBA-46CD-A77C-40CC72FF6E06 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FDCR F14-109.pdf | FDCR F14-109.pdf |  |  | Uploads\b9ce9192-7cba-46cd-a77c-40cc72ff6e06.pdf | Exist
Atikah | Yes | 60E26562-C9F3-48CE-90AB-1729CC524EBE | A01869F5-7262-4EF4-AB5B-AABD3DCA6D8E | F9-A5 | BA97E232-6C85-4DCB-A061-76E4BE5D54B5 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F9--WS39_F9-A5_PCSB.pdf | SKO3F9--WS39_F9-A5_PCSB.pdf |  |  | Uploads\ba97e232-6c85-4dcb-a061-76e4be5d54b5.pdf | Exist
Atikah | Yes | E8ED9523-6C85-47BE-9A29-AF5CF34F5E51 | A01869F5-7262-4EF4-AB5B-AABD3DCA6D8E | F9-A5 | 66211EA0-BC30-4A8C-8943-5628D43D69A3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3F9--WS30_F9-A5_PCSB.pdf | SKO3F9--WS30_F9-A5_PCSB.pdf |  |  | Uploads\66211ea0-bc30-4a8c-8943-5628d43d69a3.pdf | Exist
Mursyid | Yes | 94B06AFA-DBAD-42DD-8F17-2C8E4277E5AF | EBD53DAE-BA96-4B8A-BCDE-2969D2B47AA7 | GARANTUNG-1 | ADBE6B2E-3409-49E0-8C5F-EBB081B3FD53 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Garantung-1_Final (002).pdf | FWR Garantung-1_Final (002).pdf |  |  | Uploads\adbe6b2e-3409-49e0-8c5f-ebb081b3fd53.pdf | Exist
Mursyid | Yes | D0FBABAD-3C51-47A5-8ABB-E4A14A449310 | EBD53DAE-BA96-4B8A-BCDE-2969D2B47AA7 | GARANTUNG-1 | 1D9A4732-EE3E-4CF7-B355-14B32B4C095B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Garantung-1 Final NOOP.pdf | Garantung-1 Final NOOP.pdf |  |  | Uploads\1d9a4732-ee3e-4cf7-b355-14b32b4c095b.pdf | Exist
Mursyid | Yes | 2B05E368-C601-4177-9E8B-AAE83614C6D2 | ACDA5BB7-207A-4331-87DB-11836924EAA3 | GK-W614B | BCCFE8AA-4AF4-4E55-A522-3FF3A1625BB7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FINAL EOWR GK W614B.pdf | FINAL EOWR GK W614B.pdf |  |  | Uploads\bccfe8aa-4af4-4e55-a522-3ff3a1625bb7.pdf | Exist
Mursyid | Yes | 0676BF23-C552-455B-82F0-337D4A242B16 | ACDA5BB7-207A-4331-87DB-11836924EAA3 | GK-W614B | E59BBCD5-5DD0-4485-8B99-F58760491970 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GK-W614B NOOP.docx |  |  |  | Uploads\e59bbcd5-5dd0-4485-8b99-f58760491970.pdf | Exist
Mursyid | Yes | 9EE4BE66-A6A2-4393-AA9C-84F7E09E2756 | 3AC62FFB-EAE6-441A-8658-43846A8F148F | GUNTONG-C05ST1 | D9E86A27-1E0C-4AD5-99B7-FE7352C6094D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GUNTONG-C05ST1 (C33) EOWR (MPM).pdf | GUNTONG-C05ST1 (C33) EOWR (MPM).pdf |  |  | Uploads\d9e86a27-1e0c-4ad5-99b7-fe7352c6094d.pdf | Exist
Mursyid | Yes | E84D66CE-B44A-4FC6-9310-638F47E63621 | 3AC62FFB-EAE6-441A-8658-43846A8F148F | GUNTONG-C05ST1 | 7D79FDD4-2D0C-4FE7-A794-EE33D1936F8F | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GUNTONG-C05ST1 (C33) NOOP (PCSB) - Updated.pdf |  |  |  | Uploads\7d79fdd4-2d0c-4fe7-a794-ee33d1936f8f.pdf | Exist
Atikah | Yes | 112F6DCB-0C24-44B4-8F78-E82142D396AE | 6CA01943-5FEE-47B0-B7A1-C28116113337 | GUNTONG-C10 | DF2F0DB5-B84D-442E-B426-9C5FFCBB31C9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GuC 10ST1 (34) NOOP - MPM.pdf |  |  |  | Uploads\df2f0db5-b84d-442e-b426-9c5ffcbb31c9.pdf | Exist
Atikah | Yes | CBB7CA45-F207-47F4-923D-33EE754D6DD9 | 6CA01943-5FEE-47B0-B7A1-C28116113337 | GUNTONG-C10 | 37D9DC19-FAEC-48E2-A880-E336F46B099D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | GUNTONG-C10ST1 (C34) EOWR.PDF | GUNTONG-C10ST1 (C34) EOWR.PDF |  |  | Uploads\37d9dc19-faec-48e2-a880-e336f46b099d.pdf | Exist
Atikah | Yes | E9D86036-AF16-42CF-A79B-E092981B16F3 | B3137327-0B2A-4FF8-9881-E4E456B79486 | J4-A09 | 445B60AB-4291-4C03-AD5E-8B46781930D4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4 A09ST2 (P) EOWR_Signed.pdf | J4 A09ST2 (P) EOWR_Signed.pdf |  |  | Uploads\445b60ab-4291-4c03-ad5e-8b46781930d4.pdf | Exist
Atikah | Yes | 2F8C6019-E7E1-41A0-BC1C-EDDAEF0E8869 | B3137327-0B2A-4FF8-9881-E4E456B79486 | J4-A09 | DC117495-CE10-4996-9AC2-81BF00BCC6FE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | J4-A09ST2 (P) Well.pdf | J4-A09ST2 (P) Well.pdf |  |  | Uploads\dc117495-ce10-4996-9ac2-81bf00bcc6fe.pdf | Exist
Atikah | Yes | FB879EC0-76F5-4F75-9AE0-8139F1E0ED97 | 26ED7E20-879A-4CC3-8C4B-960FE91372E8 | JERUN-1 | 301391A5-B45F-46FD-9CB0-2ACE2D7BA6EA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jerun-1 Final Well Report - 22 Dec 2015.pdf | Jerun-1 Final Well Report - 22 Dec 2015.pdf |  |  | Uploads\301391a5-b45f-46fd-9cb0-2ace2d7ba6ea.pdf | Exist
Atikah | Yes | 98669A2E-BD05-499E-80E0-11A18BC3AC21 | 26ED7E20-879A-4CC3-8C4B-960FE91372E8 | JERUN-1 | E699726E-5584-4DFB-9154-35CAA7A54B8E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3JRUNWS01_JERUN-1_SAPURA OMV_NOOP.pdf | SKO3JRUNWS01_JERUN-1_SAPURA OMV_NOOP.pdf |  |  | Uploads\e699726e-5584-4dfb-9154-35caa7a54b8e.pdf | Exist
Mursyid | Yes | D4C28E70-7900-4787-9508-B09CF2A776DC | B6D0BF7E-E08B-48F2-9735-222BEA385639 | KBB-A02 | DBE6A52C-41E7-4CB2-8650-3F25281B1D17 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A02 .pdf | EOWR KBB PH-1 KBB-A02 .pdf |  |  | Uploads\dbe6a52c-41e7-4cb2-8650-3f25281b1d17.pdf | Exist
Mursyid | Yes | 7309EEE9-3F6C-49AD-81D6-3DEA835629E6 | B6D0BF7E-E08B-48F2-9735-222BEA385639 | KBB-A02 | ECEF5197-65DE-4A1B-8E6C-20E9A31CB3F4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\ecef5197-65de-4a1b-8e6c-20e9a31cb3f4.pdf | Exist
Atikah | Yes | 5BF4FA02-127F-457B-ABC7-EE78D8DA7476 | 354EAE43-CE4A-444C-964C-FA26AE6DB29F | KBB-A03 | 826C2CB8-D6D9-47D5-95DB-EB33B82D1D43 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\826c2cb8-d6d9-47d5-95db-eb33b82d1d43.pdf | Exist
Atikah | Yes | 030DC33F-AF32-4E73-8C16-611FC2DB3A1F | 354EAE43-CE4A-444C-964C-FA26AE6DB29F | KBB-A03 | B2C639D5-437E-4C56-8BB5-17F33A2E5D06 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A03 ST2 .pdf | EOWR KBB PH-1 KBB-A03 ST2 .pdf |  |  | Uploads\b2c639d5-437e-4c56-8bb5-17f33a2e5d06.pdf | Exist
Mursyid | Yes | C2945279-8611-4B09-927F-7B69CC592902 | ACC074C1-B332-445E-B540-6578C5F91C2E | KBB-A05 | 4C07CB8E-6089-4D4B-BD2F-857674DEACA7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 02.pdf |  |  |  | Uploads\4c07cb8e-6089-4d4b-bd2f-857674deaca7.pdf | Exist
Mursyid | Yes | F7239CF6-5354-465C-BD58-CD9F08852ECB | ACC074C1-B332-445E-B540-6578C5F91C2E | KBB-A05 | A2667187-B204-46B2-BFF5-50F58739C354 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A05.pdf | EOWR KBB PH-1 KBB-A05.pdf |  |  | Uploads\a2667187-b204-46b2-bff5-50f58739c354.pdf | Exist
Atikah | Yes | DC32F65A-936D-4AAB-9E29-4B79BFC5F17C | 47BAE4C3-FA65-48EC-A1A3-74892ECF2969 | KBB-A06 | 29CA2237-EBBA-402A-9525-24B1587AA3E2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A06.pdf | EOWR KBB PH-1 KBB-A06.pdf |  |  | Uploads\29ca2237-ebba-402a-9525-24b1587aa3e2.pdf | Exist
Atikah | Yes | 42980550-ACFE-43BA-9E6D-07C97FF4EAAF | 47BAE4C3-FA65-48EC-A1A3-74892ECF2969 | KBB-A06 | E26E5CE6-D69E-42DE-86CC-F98AEAA008B4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\e26e5ce6-d69e-42de-86cc-f98aeaa008b4.pdf | Exist
Atikah | Yes | 30B1479B-2ECF-4300-87EA-00314E105478 | 18770B8C-432D-480E-B726-F9D21985EDDA | KBB-A07 | 86BBA504-3B96-45E6-AB3C-A11ED8C45814 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\86bba504-3b96-45e6-ab3c-a11ed8c45814.pdf | Exist
Atikah | Yes | D90EDCCC-E672-42DA-9C06-F18471D19164 | 18770B8C-432D-480E-B726-F9D21985EDDA | KBB-A07 | 3F6FE652-C55F-4399-90E5-73B1511F9F35 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A07 .pdf | EOWR KBB PH-1 KBB-A07 .pdf |  |  | Uploads\3f6fe652-c55f-4399-90e5-73b1511f9f35.pdf | Exist
Mursyid | Yes | A15292DB-8C9B-4A66-A578-87A458AD7BB7 | ED0F577B-8265-47D8-8DF0-34909D9719FC | KBB-A13 | BAB2A176-6316-4A98-AA01-B10860A39269 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A13 .pdf | EOWR KBB PH-1 KBB-A13 .pdf |  |  | Uploads\bab2a176-6316-4a98-aa01-b10860a39269.pdf | Exist
Mursyid | Yes | 5CE1F215-E7B3-466E-9E97-21E33CBAE775 | ED0F577B-8265-47D8-8DF0-34909D9719FC | KBB-A13 | 6468793F-0A39-4E02-A1DD-72EDC1597052 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\6468793f-0a39-4e02-a1dd-72edc1597052.pdf | Exist
Mursyid | Yes | 255F845B-8D36-4396-82B4-1874B963F395 | 4B65492B-8DD7-4992-9805-26F9DC83338A | KBB-A20 | 0C202CD9-DBEF-4C94-B0BD-AD90FF5BEAA6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR KBB PH-1 KBB-A20.pdf | EOWR KBB PH-1 KBB-A20.pdf |  |  | Uploads\0c202cd9-dbef-4c94-b0bd-ad90ff5beaa6.pdf | Exist
Mursyid | Yes | D2F6D6C2-1CE9-40B8-A022-682ACEBE73AD | 4B65492B-8DD7-4992-9805-26F9DC83338A | KBB-A20 | 2B35D748-11D6-4725-93DD-B74EF5848720 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP KBB PH-1 DEV WELLS - BATCH 01.pdf |  |  |  | Uploads\2b35d748-11d6-4725-93dd-b74ef5848720.pdf | Exist
Atikah | Yes | 7AA79111-6416-46D2-A33A-F4B84D9BACEF | 07C58230-335A-44A7-B361-F4A22F5D88EC | KECUPU-1 | 0E90609F-E06D-4738-920A-032F2B728704 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kecupu-1-NOOP_MLNGx_.pdf | Kecupu-1-NOOP_MLNGx_.pdf |  |  | Uploads\0e90609f-e06d-4738-920a-032f2b728704.pdf | Exist
Atikah | Yes | D6481B3A-132A-4479-946E-F879DBB00912 | 07C58230-335A-44A7-B361-F4A22F5D88EC | KECUPU-1 | E5B3FCB7-BB1A-4C44-9ADC-58CE96749B66 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SMEP MLNG Exploration - EOWR - Kecupu-1 (Final).pdf | SMEP MLNG Exploration - EOWR - Kecupu-1 (Final).pdf |  |  | Uploads\e5b3fcb7-bb1a-4c44-9adc-58ce96749b66.pdf | Exist
Atikah | Yes | 08E4CD22-5984-47C8-B9F0-6D6F6EADA3FD | 409E5B44-331E-449F-81D0-737EDD024A98 | KITABU-1 | 73AB805D-DA15-4CC6-9BA9-72FD34BEC80D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Kitabu-1 NOOP.pdf | Kitabu-1 NOOP.pdf |  |  | Uploads\73ab805d-da15-4cc6-9ba9-72fd34bec80d.pdf | Exist
Atikah | Yes | C64E35DE-2981-4852-BFAA-460962017607 | 409E5B44-331E-449F-81D0-737EDD024A98 | KITABU-1 | BC6C76F1-71B7-4B40-9F03-BAFA581F7CA3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KITABU-1_EOWR.pdf | KITABU-1_EOWR.pdf |  |  | Uploads\bc6c76f1-71b7-4b40-9f03-bafa581f7ca3.pdf | Exist
Atikah | Yes | 6DDD5FDE-33C6-4E6E-9C47-BA9118158297 | 4B2AF34C-4528-46DA-A6B8-FE3EAF7C2ECF | KME-2 | A7F30962-6669-49A6-BCC9-66CEB74228B2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3KAMEGL06_KME_2.pdf | SBO3KAMEGL06_KME_2.pdf |  |  | Uploads\a7f30962-6669-49a6-bcc9-66ceb74228b2.pdf | Exist
Atikah | Yes | A9D2E479-2547-4E9D-A97C-CF7FDA893936 | 4B2AF34C-4528-46DA-A6B8-FE3EAF7C2ECF | KME-2 | 12092A66-80BA-48F1-80EB-C0D47A45951B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | KME-2_EOWR.pdf | KME-2_EOWR.pdf |  |  | Uploads\12092a66-80ba-48f1-80eb-c0d47a45951b.pdf | Exist
Mursyid | Yes | 65AF3EDC-B3D8-48A5-9AC8-60D8C0C2181B | D92ED4FA-E257-44CC-85CF-351A9DFE74F7 | LA-102 | 0644830E-1FF0-48A8-82C0-52E42395E219 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAILA-102 NOOP (Final).pdf | LAILA-102 NOOP (Final).pdf |  |  | Uploads\0644830e-1ff0-48a8-82c0-52e42395e219.pdf | Exist
Mursyid | Yes | 57709D95-9DDA-4AEA-819C-7555BEDB05CE | D92ED4FA-E257-44CC-85CF-351A9DFE74F7 | LA-102 | E9DEAC10-355A-4BA6-9A4D-47DAA4DEA934 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAILA-102 EOWR (Drilling_Completion).pdf | LAILA-102 EOWR (Drilling_Completion).pdf |  |  | Uploads\e9deac10-355a-4ba6-9a4d-47daa4dea934.pdf | Exist
Atikah | Yes | F510376F-497A-49D1-9731-268FA09BB643 | F60D4FE3-CF76-4C82-9051-C60C0CBA59E1 | LA-104 | 81B6D8DC-A4F0-488D-A652-5BBB9F13CEBA | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3LAILWS12_LA-104_SHELL_NOOP.pdf | SKO3LAILWS12_LA-104_SHELL_NOOP.pdf |  |  | Uploads\81b6d8dc-a4f0-488d-a652-5bbb9f13ceba.pdf | Exist
Atikah | Yes | 439E66CC-5526-4DC7-A444-7983480D1660 | F60D4FE3-CF76-4C82-9051-C60C0CBA59E1 | LA-104 | 767E839D-D8E1-4976-8ACA-3564DB2539FB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAILA-104 EOWR (Drilling_Completion).pdf | LAILA-104 EOWR (Drilling_Completion).pdf |  |  | Uploads\767e839d-d8e1-4976-8aca-3564db2539fb.pdf | Exist
Atikah | Yes | 0B0E9DA6-DE6E-4898-8246-093597FA47BF | 85B4A84F-7CE5-41C6-89F4-76122E291AB3 | LAYANG-2 | DFD77C4E-844D-4C5C-B434-9CDD0ED6B419 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAYANG NOOP.pdf |  |  |  | Uploads\dfd77c4e-844d-4c5c-b434-9cdd0ed6b419.pdf | Exist
Atikah | Yes | BA1152A6-FCF9-4A4C-855B-F47BC9988C3E | 85B4A84F-7CE5-41C6-89F4-76122E291AB3 | LAYANG-2 | BC807481-BA7A-4978-9813-EEBC7C580A2B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | LAYANG-2RD EOWR (1).pdf | LAYANG-2RD EOWR (1).pdf |  |  | Uploads\bc807481-ba7a-4978-9813-eebc7c580a2b.pdf | Exist
Mursyid | Yes | D57DA2F2-8D57-414E-B01E-8F3FE4160812 | 7D6971AD-D028-4DF5-A6E4-02A2CB87E5EF | MENAWAN-1ST1 | 6A294B6B-7E90-4C44-B8C5-BFDA22A696FB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MENAWAN-1 NOOP (Signed) (1)_Menawan-1NOOP.pdf |  |  |  | Uploads\6a294b6b-7e90-4c44-b8c5-bfda22a696fb.pdf | Exist
Mursyid | Yes | 422DB9CC-8950-4087-865D-D3D79EBE6268 | 7D6971AD-D028-4DF5-A6E4-02A2CB87E5EF | MENAWAN-1ST1 | 18F4DF9C-B6AA-4250-BA6D-EB19B768241B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3MEWNWS03_MENAWAN_1ST1.pdf | SBO3MEWNWS03_MENAWAN_1ST1.pdf |  |  | Uploads\18f4df9c-b6aa-4250-ba6d-eb19b768241b.pdf | Exist
Mursyid | Yes | 756FDC5E-41F9-4A35-96E6-BD6561FF38E3 | EC8D0065-156D-4B15-87AB-1515701D4FBF | MLK-103 | 5EA3B09F-3467-4435-BFDF-53584B4BCFB9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-103 (KMU1) NOOP (FINAL SIGNED).pdf | MLK-103 (KMU1) NOOP (FINAL SIGNED).pdf |  |  | Uploads\5ea3b09f-3467-4435-bfdf-53584b4bcfb9.pdf | Exist
Mursyid | Yes | 56CC9101-F36A-4A3D-8E94-E226C613ADBB | EC8D0065-156D-4B15-87AB-1515701D4FBF | MLK-103 | 85363EA4-A2DF-4A86-AB36-8B88285F74EC | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-103 EOWR 180402 (FINAL).pdf | MLK-103 EOWR 180402 (FINAL).pdf |  |  | Uploads\85363ea4-a2df-4a86-ab36-8b88285f74ec.pdf | Exist
Mursyid | Yes | 5A1DA5D2-D04E-418E-8ED4-811E21A2D2B2 | BD7B239F-2C8D-4484-B669-197D0396A34B | MLK-104 | D5FE050D-7620-4B70-A279-9F110CF131ED | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-104 P401 NOOP_Final.pdf | MLK-104 P401 NOOP_Final.pdf |  |  | Uploads\d5fe050d-7620-4b70-a279-9f110cf131ed.pdf | Missing
Mursyid | Yes | 5CB5AF52-A133-4DA9-8477-A9D3EC90FD5F | BD7B239F-2C8D-4484-B669-197D0396A34B | MLK-104 | BA0C594F-6A84-4F71-B1F8-61322C66D626 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Malikai-104 EOWR.pdf |  |  |  | Uploads\ba0c594f-6a84-4f71-b1f8-61322c66d626.pdf | Missing
Mursyid | Yes | 0A89BE0D-31B6-4141-B652-DC84EFC1FBDB | ACBA5E74-2F8B-49BE-A0A4-4AD557E34287 | MLK-106 | ECDC3406-1750-4B24-8F87-668D075BA56E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-106 FINAL.pdf |  |  |  | Uploads\ecdc3406-1750-4b24-8f87-668d075ba56e.pdf | Exist
Mursyid | Yes | 4F3FE6FA-2BA1-40B0-919A-EE2C05B7DA7F | ACBA5E74-2F8B-49BE-A0A4-4AD557E34287 | MLK-106 | E410089E-1A98-446E-8DB8-531B5EFB2217 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-106 Pink North WI - NOOP v2.pdf | MLK-106 Pink North WI - NOOP v2.pdf |  |  | Uploads\e410089e-1a98-446e-8db8-531b5efb2217.pdf | Exist
Mursyid | Yes | A6B63961-0E4F-43EF-9DDB-F3A5BB884B4D | 91C72E3A-D5C4-4CFE-B470-504A5F6CAF4A | MLK-115 | 328011A8-01EC-45BC-9E38-A8E31A736C35 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | 01. Malikai MLK-115 P300 NOOP_Rev1.pdf | 01. Malikai MLK-115 P300 NOOP_Rev1.pdf |  |  | Uploads\328011a8-01ec-45bc-9e38-a8e31a736c35.pdf | Missing
Mursyid | Yes | 52C3D75F-33BE-43D1-8CEA-CB0762A9EA91 | 91C72E3A-D5C4-4CFE-B470-504A5F6CAF4A | MLK-115 | 66ACA337-4385-4224-BE5C-9ACEE8F6BCAB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MALIKAI-115 EOWR DRILLING AND COMPLETION.pdf |  |  |  | Uploads\66aca337-4385-4224-be5c-9acee8f6bcab.pdf | Missing
Atikah | Yes | E9156F2B-1025-49C3-8989-D3CFB8C906A9 | 893188BF-05E3-4FA4-9BD5-D94821997833 | MLK-121 S1 | 02B64A17-E828-4A51-B628-69CBA160EE56 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MLK-121 S1 KMU2 WI - NOOP v2.pdf | MLK-121 S1 KMU2 WI - NOOP v2.pdf |  |  | Uploads\02b64a17-e828-4a51-b628-69cba160ee56.pdf | Exist
Atikah | Yes | F484F1A0-FD63-4038-845B-5F74F0847878 | 893188BF-05E3-4FA4-9BD5-D94821997833 | MLK-121 S1 | 3CD6FC28-2665-4080-8D53-C7B8FCBE235F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR Malikai-121S1 FINAL.pdf |  |  |  | Uploads\3cd6fc28-2665-4080-8d53-c7b8fcbe235f.pdf | Exist
Atikah | Yes | 52F1C50F-5EC8-45CA-8DD9-3CCD7A447619 | F91D56E8-D8BA-4DF9-A27E-C11ECC06B37A | NC3-A5 | 0A1E3013-A800-4012-B5FE-D7978E0251E4 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NC3 A5 FWR final signed.pdf | NC3 A5 FWR final signed.pdf |  |  | Uploads\0a1e3013-a800-4012-b5fe-d7978e0251e4.pdf | Exist
Atikah | Yes | BF5C37DA-2DD7-423F-B111-E9923BCEEF24 | F91D56E8-D8BA-4DF9-A27E-C11ECC06B37A | NC3-A5 | 477BED9F-A93E-4566-A448-31941BB15A14 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP NC3-A5 external.pdf | NC3 A5 FWR final signed.pdf |  |  | Uploads\477bed9f-a93e-4566-a448-31941bb15a14.pdf | Exist
Atikah | Yes | 4F68F4A2-CB8A-46B2-90BF-8EA9B64DEA88 | E95D2FE6-7929-47FB-BF1E-F447DDFCF843 | PATAWALI-2 | DF8DAE21-2A06-4FE1-B3AA-4C19C7200BC4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Patawali-2 Notice of Operations.pdf | Patawali-2 Notice of Operations.pdf |  |  | Uploads\df8dae21-2a06-4fe1-b3aa-4c19c7200bc4.pdf | Exist
Atikah | Yes | 67B95795-7958-4BED-A85C-0E501652E9E5 | E95D2FE6-7929-47FB-BF1E-F447DDFCF843 | PATAWALI-2 | 22BE5D78-3656-4285-B8F1-FC77D6BE63F9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Patawali-2 and Patawali-2 RDR1 Drilling End of Well Report.pdf | Patawali-2 and Patawali-2 RDR1 Drilling End of Well Report.pdf |  |  | Uploads\22be5d78-3656-4285-b8f1-fc77d6be63f9.pdf | Exist
Mursyid | Yes | 2584C48F-2490-48D7-B30D-DE5EAC727703 | 59DD6203-0713-4E5E-A14D-6A53BAA951DC | PENDEKAR-1 | 082F9EA0-DB01-44D3-A221-3AFE8354ECD7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PENDEKAR-1 ST-1 FWR.pdf | PENDEKAR-1 ST-1 FWR.pdf |  |  | Uploads\082f9ea0-db01-44d3-a221-3afe8354ecd7.pdf | Exist
Mursyid | Yes | DAF930DC-E4BE-4225-8825-AFA30A1F84C0 | 59DD6203-0713-4E5E-A14D-6A53BAA951DC | PENDEKAR-1 | CE0BCE1A-00E3-407D-B25F-211C4E3AF559 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3PDKRWS01_PENDEKAR_1.pdf | SBO3PDKRWS01_PENDEKAR_1.pdf |  |  | Uploads\ce0bce1a-00e3-407d-b25f-211c4e3af559.pdf | Exist
Atikah | Yes | 6C2BCC7F-0058-4D50-BFD2-E3DDFB329D10 | 326DD87B-49E3-44A9-93BB-A99B7CBF162E | PRPA-02 | 6B106B65-B2AE-4AAF-89C8-BCF5A99B7EFA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA-02 EOWR.pdf | PRPA-02 EOWR.pdf |  |  | Uploads\6b106b65-b2ae-4aaf-89c8-bcf5a99b7efa.pdf | Exist
Atikah | Yes | 3242A3B2-F5BA-4BF5-A33B-4F3CF5427F1A | 326DD87B-49E3-44A9-93BB-A99B7CBF162E | PRPA-02 | 2C5F4D74-674B-4979-AF8B-C06A572D94FE | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PRPA 1,2,3,4,5 PERMAS REVISIT 1 PHASE 2 NOOP_Rev 0.pdf |  |  |  | Uploads\2c5f4d74-674b-4979-af8b-c06a572d94fe.pdf | Exist
Mursyid | Yes | D9051A0A-4305-49B5-A504-2231FB2159C3 | D9B5C4E3-0A09-40F5-99B2-24966B9F1FB5 | PUDING EMAS -1 | B1BD81A6-36E8-4FBB-ADCF-C038F9052AFF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Puding Emas-1 FWR.pdf | Puding Emas-1 FWR.pdf |  |  | Uploads\b1bd81a6-36e8-4fbb-adcf-c038f9052aff.pdf | Exist
Mursyid | Yes | FD6CF58A-D268-4245-A7E9-870C52A0C130 | D9B5C4E3-0A09-40F5-99B2-24966B9F1FB5 | PUDING EMAS -1 | E3A0D085-9BB2-4DDB-9D20-7825A21EFD35 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Puding Emas rev.01.pdf |  |  |  | Uploads\e3a0d085-9bb2-4ddb-9d20-7825a21efd35.pdf | Exist
Mursyid | Yes | 6DDFCECA-3C5F-45A7-A1F2-38FDB0882E10 | 546C5E2D-446E-4B54-B1F3-670BE4A8E424 | REMUJUNG-01 | 0197B407-3A09-4A39-A3EF-833D33E4654F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Remujung-1 EoWR FINAL.pdf |  |  |  | Uploads\0197b407-3a09-4a39-a3ef-833d33e4654f.pdf | Exist
Mursyid | Yes | D2E63691-66CD-4181-8664-A64E018AA1E2 | 546C5E2D-446E-4B54-B1F3-670BE4A8E424 | REMUJUNG-01 | 91C77280-37B4-449B-B18D-55C0846B3689 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Remujung-1_NOOP -FINAL.pdf |  |  |  | Uploads\91c77280-37b4-449b-b18d-55c0846b3689.pdf | Exist
Atikah | Yes | F6BCD384-01C2-4B61-8C8B-4C1BD81A06EB | BF799B1A-654D-45CC-A983-A4FB147076D6 | ROSMARI-1 | 1894F8CA-2C9E-4D01-92FE-A85E48D9204B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Rosmari-1_NOP_FINAL23122013.pdf | Rosmari-1_NOP_FINAL23122013.pdf |  |  | Uploads\1894f8ca-2c9e-4d01-92fe-a85e48d9204b.pdf | Exist
Atikah | Yes | 2127BCAB-C9B4-4701-9733-9F9C8C4CA401 | BF799B1A-654D-45CC-A983-A4FB147076D6 | ROSMARI-1 | CFC72CE6-58E0-4AB7-9679-20C946274894 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Rosmari-1 ST1 EOWR final.pdf | Rosmari-1 ST1 EOWR final.pdf |  |  | Uploads\cfc72ce6-58e0-4ab7-9679-20c946274894.pdf | Exist
Mursyid | Yes | DFD4DC92-F8BC-44C2-AFAA-633508E7BFDC | 72474A49-33C9-4642-A858-2597E9875720 | ROTAN RP-1 | 39B89933-B363-49B2-B927-2202A25220CD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Rotan RP-1 Petronas and Carigali_Drilling NOOP.pdf | Rotan RP-1 Petronas and Carigali_Drilling NOOP.pdf |  |  | Uploads\39b89933-b363-49b2-b927-2202a25220cd.pdf | Exist
Mursyid | Yes | EDF6FDA0-A1B1-47EA-8675-A8955B3D9296 | 72474A49-33C9-4642-A858-2597E9875720 | ROTAN RP-1 | 84151615-BDD1-4FC0-9B42-9E5186FF01FD | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ROTAN RP-1 EOWR.pdf | ROTAN RP-1 EOWR.pdf |  |  | Uploads\84151615-bdd1-4fc0-9b42-9e5186ff01fd.pdf | Exist
Mursyid | Yes | BC8DE237-2581-480A-9661-2F83B9DCDB43 | C0EFB543-C8D3-4A2F-9C3F-12E4DAA186DB | SALAM-1 | 75B6FBBE-2A7A-4E80-8D3D-7776B2537177 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SALAM-1 FWR.pdf | SALAM-1 FWR.pdf |  |  | Uploads\75b6fbbe-2a7a-4e80-8d3d-7776b2537177.pdf | Exist
Mursyid | Yes | C15C4A5D-348D-460D-BBC6-06882EE9EE53 | C0EFB543-C8D3-4A2F-9C3F-12E4DAA186DB | SALAM-1 | E0C8E689-AA4D-4925-8DC8-00882342E68C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SALAM-1 NOOP.pdf | SALAM-1 FWR SIGNED.pdf |  |  | Uploads\e0c8e689-aa4d-4925-8dc8-00882342e68c.pdf | Exist
Atikah | Yes | EF0BFE36-78CD-491E-9489-ACCDDB50E9DD | E5860A6F-D730-4928-8CA1-76F87B7908C0 | SAPA-01ST2 | 7251A495-DA7D-43CD-B574-3C11E297592C | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_NOWOP SAPA-01,SAPA-03,SAPA-17.pdf |  |  |  | Uploads\7251a495-da7d-43cd-b574-3c11e297592c.pdf | Exist
Atikah | Yes | 2FD0042E-1FD3-4102-A82E-B5F09D6D9A27 | E5860A6F-D730-4928-8CA1-76F87B7908C0 | SAPA-01ST2 | D2336055-ED1A-445A-941E-CB1586F2F72B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3ACISGL26_SAPA-01ST2_PTTEP_fwr.pdf | SAPA-01ST2_ST3 EOWR.pdf |  |  | Uploads\d2336055-ed1a-445a-941e-cb1586f2f72b.pdf | Exist
Mursyid | Yes | 423A4678-7731-42D6-B798-EF5DB5D770F0 | C922890E-E48C-4436-BC27-0D14AFA061EC | SAPA-03 | FE6556CB-70DB-41C5-9C93-08F530F01595 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_NOWOP SAPA-01,SAPA-03,SAPA-17.pdf | NOOP_NOWOP SAPA-01,SAPA-03,SAPA-17.pdf |  |  | Uploads\fe6556cb-70db-41c5-9c93-08f530f01595.pdf | Exist
Mursyid | Yes | EB075983-9089-43E1-8ABB-977623C2486E | C922890E-E48C-4436-BC27-0D14AFA061EC | SAPA-03 | DB8F903F-39D5-48E5-8345-8DC1F6DA702B | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-03_ST1 EOWR.pdf | SAPA-03_ST1 EOWR.pdf |  |  | Uploads\db8f903f-39d5-48e5-8345-8dc1f6da702b.pdf | Exist
Mursyid | Yes | 001131EF-0604-4533-B26A-6D2AEF1C8CA3 | 28D03F09-D465-4BC9-B2AB-6729E62D9C7D | SAPA-08 | 185B9654-AB51-4E79-95B9-F7F77F661B11 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-08 EOWR.pdf | SAPA-08 EOWR.pdf |  |  | Uploads\185b9654-ab51-4e79-95b9-f7f77f661b11.pdf | Missing
Mursyid | Yes | C88B019C-CC64-45AB-942C-5C4B9AED404F | 28D03F09-D465-4BC9-B2AB-6729E62D9C7D | SAPA-08 | 8F60AE69-520E-4BA4-A1BD-6449355DC1FF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-08 & SAPA-09 NOOP.pdf | SAPA-08 & SAPA-09 NOOP.pdf |  |  | Uploads\8f60ae69-520e-4ba4-a1bd-6449355dc1ff.pdf | Missing
Atikah | Yes | 03AA92E1-D663-465C-BFEF-1777EBC0B2AD | A16E705C-9817-4894-B831-DFB10BB9591A | SAPA-12 | ED2D243B-0AAC-49B8-9895-15077D882048 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SK311 South Acis (SAPA) Revisit I Phase II.pdf |  |  |  | Uploads\ed2d243b-0aac-49b8-9895-15077d882048.pdf | Exist
Atikah | Yes | 5BF66F35-4229-4F64-AE02-B78BDFB8FC68 | A16E705C-9817-4894-B831-DFB10BB9591A | SAPA-12 | 8DE70906-AE21-4914-AE8C-86997622F6C0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-12 EOWR Rev A.pdf | SAPA-12 EOWR Rev A.pdf |  |  | Uploads\8de70906-ae21-4914-ae8c-86997622f6c0.pdf | Exist
Atikah | Yes | 9DE6BA6F-F69B-47B3-8197-34EEF653F4C6 | C4730ECC-D73C-4E57-9E44-DB5CB13EF068 | SAPA-14 | 3087B1EA-AAF5-49F7-86BB-1B31235D9CA9 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-14ST1 EOWR Rev A.pdf | SAPA-14ST1 EOWR Rev A.pdf |  |  | Uploads\3087b1ea-aaf5-49f7-86bb-1b31235d9ca9.pdf | Exist
Atikah | Yes | 2C8D9716-2341-4126-B53C-B96EC138A713 | C4730ECC-D73C-4E57-9E44-DB5CB13EF068 | SAPA-14 | BA44511F-FE39-4853-828B-B9C17ED3C706 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SK311 South Acis (SAPA) Revisit I Phase II.pdf |  |  |  | Uploads\ba44511f-fe39-4853-828b-b9c17ed3c706.pdf | Exist
Mursyid | Yes | 060ED13A-A8C0-4314-9204-08FC2AE203D6 | 04F3711E-852A-48E4-A2AA-49734D88A89D | SAPA-17ST1 | 1CF8DE34-FEA7-40D7-B126-6904AB4AA8C6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-17ST1 EOWR.pdf | SAPA-17ST1 EOWR.pdf |  |  | Uploads\1cf8de34-fea7-40d7-b126-6904ab4aa8c6.pdf | Exist
Mursyid | Yes | 2449E12F-00B4-4723-9D47-BF499B0C6850 | 04F3711E-852A-48E4-A2AA-49734D88A89D | SAPA-17ST1 | 1F7F0AE8-FFD9-4DEE-917D-B31AF788051D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP_NOWOP SAPA-01,SAPA-03,SAPA-17.pdf |  |  |  | Uploads\1f7f0ae8-ffd9-4dee-917d-b31af788051d.pdf | Exist
Atikah | Yes | AFAB7328-861C-45E3-9ECD-EC57D0F48A93 | 46ED5D15-DD43-461D-A7E8-EB78441F64C4 | SAPA-19ST1 | A1723179-8862-402B-8536-B436DD235E4D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK311-91-DR-TN-0001-00_SAPA Revisit 1 Phase I NOOP_Rev 0.pdf |  |  |  | Uploads\a1723179-8862-402b-8536-b436dd235e4d.pdf | Exist
Atikah | Yes | 67490DE7-AB53-44AD-B5B8-70EF915792CA | 46ED5D15-DD43-461D-A7E8-EB78441F64C4 | SAPA-19ST1 | 032A7DAC-7237-48A6-9BCE-1FB30D3147A6 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-19ST1 EOWR (2).pdf | SAPA-19ST1 EOWR (2).pdf |  |  | Uploads\032a7dac-7237-48a6-9bce-1fb30d3147a6.pdf | Exist
Mursyid | Yes | 55279608-4A42-42DB-8247-1BF94D606CE4 | C9962888-F805-430A-822E-34C74521BEE2 | SAPA-22 | 39CF4EB3-32B7-4C46-86F6-D5B8159891BD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK311-91-DR-TN-0001-00_SAPA Revisit 1 Phase I NOOP_Rev 0.pdf |  |  |  | Uploads\39cf4eb3-32b7-4c46-86f6-d5b8159891bd.pdf | Exist
Mursyid | Yes | 3BE8B206-B865-45B9-876C-3580B69197AF | C9962888-F805-430A-822E-34C74521BEE2 | SAPA-22 | 8E1FE020-3BB1-449C-914F-4DF2637E170E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-22 EOWR Rev A.pdf | SAPA-22 EOWR Rev A.pdf |  |  | Uploads\8e1fe020-3bb1-449c-914f-4df2637e170e.pdf | Exist
Atikah | Yes | B4F42DC0-ABC3-45F7-BCF0-D609C832275C | 9491699B-48DC-4A6E-91BC-ECFB60769EBB | SAPA-24 | 9A27DE90-9491-458C-AE6D-B6138A5223C1 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAPA-24 EOWR.pdf | SAPA-24 EOWR.pdf |  |  | Uploads\9a27de90-9491-458c-ae6d-b6138a5223c1.pdf | Exist
Atikah | Yes | E5A4447E-22E0-4D12-9BF9-A9EFA4082CD7 | 9491699B-48DC-4A6E-91BC-ECFB60769EBB | SAPA-24 | EDE73689-2DA6-40A4-BCF9-F22C939820E8 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK311-91-DR-TN-0001-00_SAPA Revisit 1 Phase I NOOP_Rev 0.pdf |  |  |  | Uploads\ede73689-2da6-40a4-bcf9-f22c939820e8.pdf | Exist
Atikah | Yes | C9E2DF00-8A3E-4EAB-BDAF-461017E94A9C | 2A9AA0FA-89FB-48B4-BD0C-D536B650DD2F | SASA-17 | 31BFCC9D-E9E5-457F-8338-4F78A0221C47 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SASA Infill Campaign EOWR.pdf |  |  |  | Uploads\31bfcc9d-e9e5-457f-8338-4f78a0221c47.pdf | Exist
Atikah | Yes | FFED991E-914A-42BD-AF2E-E7E106A893D2 | 2A9AA0FA-89FB-48B4-BD0C-D536B650DD2F | SASA-17 | 2E4D03A4-03A8-407E-8292-6F3D6A128D0B | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK311-92-DR-PR-0002-00_South_Acis_Drilling__Completion_Campaign_NOOP Rev1.pdf |  |  |  | Uploads\2e4d03a4-03a8-407e-8292-6f3d6a128d0b.pdf | Exist
Atikah | Yes | 4E59D674-DDB1-4245-A570-2351AAE61759 | 6C9C6125-E5E8-4355-9A9D-A56828AFF396 | S-CN1-P14 | EB5C22DB-3F66-4A13-9BDA-01A883C36B0A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf |  |  |  | Uploads\eb5c22db-3f66-4a13-9bda-01a883c36b0a.pdf | Exist
Atikah | Yes | 608E804A-1601-4B8D-8966-05CBDE306ADA | 122AAB7F-D761-409E-8FF5-94D811CEECFA | SEE-32 | 3A02C46F-7F17-473D-9228-C760715A50E7 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Jambu Well (SeE-32) Drilling Programme.pdf | Jambu Well (SeE-32) Drilling Programme.pdf |  |  | Uploads\3a02c46f-7f17-473d-9228-c760715a50e7.pdf | Exist
Atikah | Yes | 4F25380E-DF2B-40CF-BFC7-69A4A70CF320 | 122AAB7F-D761-409E-8FF5-94D811CEECFA | SEE-32 | 2882EB9D-4DBE-45C1-A6BB-DBCE2BFA3E47 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeE-32 32ST1 C1 Scanned.pdf | Final Well Report SeE-32 32ST1 C1 Scanned.pdf |  |  | Uploads\2882eb9d-4dbe-45c1-a6bb-dbce2bfa3e47.pdf | Exist
Atikah | Yes | F7206FBE-ADE5-48D9-A531-3F3C37B5B1C0 | 0AA52DA5-5F6E-45AB-8435-72921388C76C | SEE-33 | A1FC1F18-C87A-4317-A1B2-3C14061917F7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Final Well Report SeE-33 C1.pdf | Final Well Report SeE-33 C1.pdf |  |  | Uploads\a1fc1f18-c87a-4317-a1b2-3c14061917f7.pdf | Exist
Atikah | Yes | 9740BC43-26B8-49FC-AEBF-F4D6CC1AFA3B | 0AA52DA5-5F6E-45AB-8435-72921388C76C | SEE-33 | B5A012BC-7CAF-419A-B8F8-1F17C7BAE4D0 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Gedabu Well (SeE-33) Notice of Operation (NOOP) C1.pdf | Gedabu Well (SeE-33) Notice of Operation (NOOP) C1.pdf |  |  | Uploads\b5a012bc-7caf-419a-b8f8-1f17c7bae4d0.pdf | Exist
Mursyid | Yes | A9FC2474-B878-48E2-8CBC-0DBF212B435F | DB640D63-F2F9-4B74-9F42-41E591168AF2 | SEPA-10ST1 | FCDFE639-61A7-4F3A-A754-D7B610FE2AA3 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP SEPA-10,SEPA-12.pdf |  |  |  | Uploads\fcdfe639-61a7-4f3a-a754-d7b610fe2aa3.pdf | Exist
Mursyid | Yes | 4D2C19F1-B5CE-48C0-9056-2E9A68A34ACD | DB640D63-F2F9-4B74-9F42-41E591168AF2 | SEPA-10ST1 | 59A8C0C0-CC6C-4059-B246-498CCDC396BB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SEPA10ST2 EOWR_FINAL (APPROVED).pdf |  |  |  | Uploads\59a8c0c0-cc6c-4059-b246-498ccdc396bb.pdf | Exist
Atikah | Yes | 2DDBE7C4-30A7-49CC-909E-ECDB644004B9 | 401D3D9F-FAFE-4363-A78F-81B44EFC4BBF | SEPAT-11 | 61E47A4B-AA9B-40DE-908C-A5AD1EE4E3B7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | FWR Sepat-11_Part1_signed.pdf | FWR Sepat-11_Part1_signed.pdf |  |  | Uploads\61e47a4b-aa9b-40de-908c-a5ad1ee4e3b7.pdf | Exist
Atikah | Yes | F0510A4E-5E10-4573-A9F2-E3E05D7763A2 | 401D3D9F-FAFE-4363-A78F-81B44EFC4BBF | SEPAT-11 | F9A17236-5786-4BD2-A2B8-D301EF8A4748 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Sepat-11 submitted to MPM with Signtures.pdf | NOOP Sepat-11 submitted to MPM with Signtures.pdf |  |  | Uploads\f9a17236-5786-4bd2-a2b8-d301ef8a4748.pdf | Exist
Mursyid | Yes | 6E6CEF3C-8223-4753-9CD9-56CE1DC168E2 | D135C790-7F61-4C11-B2F8-2D3AE4E00BEB | SEPAT-A11 | B0FB23B2-6B59-4091-B317-B53B542B701E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | NOOP Sepat A11 FINAL (1).pdf | NOOP Sepat A11 FINAL (1).pdf |  |  | Uploads\b0fb23b2-6b59-4091-b317-b53b542b701e.pdf | Exist
Mursyid | Yes | 92701F34-9C91-4E27-AD63-A0F7FDAB3D55 | D135C790-7F61-4C11-B2F8-2D3AE4E00BEB | SEPAT-A11 | 60DEAA5E-10BB-4C21-BF9E-E930293811E2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SUBMISSION OF FINAL WELL REPORT FOR SEPAT A11.pdf | SUBMISSION OF FINAL WELL REPORT FOR SEPAT A11.pdf |  |  | Uploads\60deaa5e-10bb-4c21-bf9e-e930293811e2.pdf | Exist
Mursyid | Yes | 86188B1B-C9A6-4B7B-BEB2-F3A3F233BFC6 | 04D32FB5-5240-4A1B-B76D-5AAAD1017712 | SF-15 | 3E231D06-DADC-4A5A-88CB-DCF4CEE190CB | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SOUTH FURIOUS-A15 NOOP.pdf |  |  |  | Uploads\3e231d06-dadc-4a5a-88cb-dcf4cee190cb.pdf | Exist
Mursyid | Yes | 11322CEF-0A93-488A-A86B-31D76AAB92BE | 04D32FB5-5240-4A1B-B76D-5AAAD1017712 | SF-15 | F944F64C-2A87-4B09-9BF9-332332CBFDB3 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SF15S2 EOWR FINAL.pdf | SF15S2 EOWR FINAL.pdf |  |  | Uploads\f944f64c-2a87-4b09-9bf9-332332cbfdb3.pdf | Exist
Mursyid | Yes | 9F2E9040-4F32-495B-9538-97C614876BF7 | 31BCA2B5-F24C-4EEE-A2CB-5CEAFBF909EE | SF-16S2 | 9E0AFA2C-8435-423D-A02D-89E76C32C5FD | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SOUTH FURIOUS-A16ST2 NOOP.pdf |  |  |  | Uploads\9e0afa2c-8435-423d-a02d-89e76c32c5fd.pdf | Exist
Mursyid | Yes | 1272E71A-B940-4229-9D58-257BC2132556 | 31BCA2B5-F24C-4EEE-A2CB-5CEAFBF909EE | SF-16S2 | 54503CA9-8175-4C64-9F1E-095407A48C0D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SOUTH FURIOUS-16S3 EOWR (Final).docx |  |  |  | Uploads\54503ca9-8175-4c64-9f1e-095407a48c0d.pdf | Exist
Mursyid | Yes | EF12D796-5A79-4533-9109-6486B83BE39A | BD6E1DBC-E75F-41DC-A12E-56C2370FA36E | SJ-105C | 8BC9C01F-2BBC-477A-8A11-F44BE1B9A753 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Hibiscus North Sabah St Joseph Well SJ-105C NOOP.pdf | Hibiscus North Sabah St Joseph Well SJ-105C NOOP.pdf |  |  | Uploads\8bc9c01f-2bbc-477a-8a11-f44be1b9a753.pdf | Exist
Mursyid | Yes | 87A8D86C-75EB-4ACA-89D4-D35AB39B7EBF | BD6E1DBC-E75F-41DC-A12E-56C2370FA36E | SJ-105C | B716CB17-54F4-493A-A437-8145D89E2184 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | EOWR letter SJ-105C (PCSB JV).pdf | EOWR letter SJ-105C (PCSB JV).pdf |  |  | Uploads\b716cb17-54f4-493a-a437-8145d89e2184.pdf | Exist
Mursyid | Yes | B44F97D2-0455-4008-8015-7AA9F96DE142 | 27BE6365-67EA-478B-A75B-1EC511901425 | SM-47ST | 416AC92A-D298-4DB7-B799-F40DA9CFF056 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM47ST NOOP SM-2EOR-DD-DRL-DB-DRL-PRC-8-2018 (1).pdf | SM47ST NOOP SM-2EOR-DD-DRL-DB-DRL-PRC-8-2018 (1).pdf |  |  | Uploads\416ac92a-d298-4db7-b799-f40da9cff056.pdf | Exist
Mursyid | Yes | D1DB9324-8B8C-4F0A-93B2-A485ED84401C | 27BE6365-67EA-478B-A75B-1EC511901425 | SM-47ST | D838B195-C15E-4860-8234-51DC75560ADF | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B47ST1 FWR.pdf |  |  |  | Uploads\d838b195-c15e-4860-8234-51dc75560adf.pdf | Exist
Mursyid | Yes | 464AC890-C08B-4903-9AD4-42D8841B2EB7 | 191A5DEA-81BF-4DFA-AFE8-00D71CC1DCE3 | SM-49ST | 46FFFAF0-DD71-4B8E-AC02-343A92103152 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGWSEM_SM_49ST.pdf | SBO3SMRGWSEM_SM_49ST.pdf |  |  | Uploads\46fffaf0-dd71-4b8e-ac02-343a92103152.pdf | Exist
Mursyid | Yes | 0A3CBB55-E3C8-4039-A5D2-4C935686EA93 | 191A5DEA-81BF-4DFA-AFE8-00D71CC1DCE3 | SM-49ST | 0BEAAE56-C3F3-409A-90A9-1F8F49D24A9E | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3SMRGGL53_SM49T.pdf |  |  |  | Uploads\0beaae56-c3f3-409a-90a9-1f8f49d24a9e.pdf | Exist
Mursyid | Yes | CEA4735A-8952-4E24-BFC7-8C42364B183D | F521DE06-4EF1-4C38-B09E-481549E72089 | SM-50ST2 | C15E0BC1-4CF6-45E9-8316-BDAC6AE9EDDF | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SM50ST2.pdf | SM50ST2.pdf |  |  | Uploads\c15e0bc1-4cf6-45e9-8316-bdac6ae9eddf.pdf | Exist
Mursyid | Yes | B68A81DA-AF53-424C-9DB8-0D4FCB90D273 | F521DE06-4EF1-4C38-B09E-481549E72089 | SM-50ST2 | 3D5DA490-800C-4532-B43F-97FABBC1F131 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SAMARANG-B50ST2 FWR.pdf |  |  |  | Uploads\3d5da490-800c-4532-b43f-97fabbc1f131.pdf | Exist
Mursyid | Yes | 2801401B-B021-4C88-8652-5F3C448E9768 | 987D85DE-0D85-46AE-B621-649A633309BD | SNPA-07 | 57D4F7F2-E7FA-48B5-8175-03FBDE26EC18 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0001-00_SNPA Dev Project Revisit 2 Phase I - NOOP.pdf |  |  |  | Uploads\57d4f7f2-e7fa-48b5-8175-03fbde26ec18.pdf | Exist
Mursyid | Yes | C269E77F-330D-4B26-805E-101986E6D394 | 987D85DE-0D85-46AE-B621-649A633309BD | SNPA-07 | C5F63EE9-E9C5-4D72-97B4-9BA1F805C8FB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0013-00_SNPA-07ST1 EOWR Final.pdf | MOM-SK309-72-DNC-RP-0013-00_SNPA-07ST1 EOWR Final.pdf |  |  | Uploads\c5f63ee9-e9c5-4d72-97b4-9ba1f805c8fb.pdf | Exist
Mursyid | Yes | D518552B-B885-47C0-AC9E-84CDD47CAB4C | D0231564-9AF8-47B1-B98F-437CAE4EC3FB | SNPA-08 | D8C788A3-5D9A-4C1F-8912-5435EDBEC3E8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-68-DNC-RP-0014-00_SNPA-08ST1 EOWR Final.pdf | MOM-SK309-68-DNC-RP-0014-00_SNPA-08ST1 EOWR Final.pdf |  |  | Uploads\d8c788a3-5d9a-4c1f-8912-5435edbec3e8.pdf | Exist
Mursyid | Yes | 88E134DA-AF51-4625-87BE-95F5A44DF57D | D0231564-9AF8-47B1-B98F-437CAE4EC3FB | SNPA-08 | 7F315164-E214-45EC-8621-AC05DCC7A9A9 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0001-00_SNPA Dev Project Revisit 2 Phase I - NOOP.pdf |  |  |  | Uploads\7f315164-e214-45ec-8621-ac05dcc7a9a9.pdf | Exist
Mursyid | Yes | FC6DBCC4-6EBB-4874-8E7F-939C0E1BF007 | C46D0433-CC0A-4579-AC10-449E5A5E3C40 | SNPA-10 | 8724FB71-139B-46EE-93DF-C3A2F59B48BC | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf |  |  |  | Uploads\8724fb71-139b-46ee-93df-c3a2f59b48bc.pdf | Exist
Mursyid | Yes | D896BAAB-CE10-4E1F-B30F-F9BFD14837C2 | C46D0433-CC0A-4579-AC10-449E5A5E3C40 | SNPA-10 | F2189B41-C9B2-4E61-A35D-C1AF75E2C1AB | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SKO3SRDHWS99_1_SNPA-10.pdf | SKO3SRDHWS99_1_SNPA-10.pdf |  |  | Uploads\f2189b41-c9b2-4e61-a35d-c1af75e2c1ab.pdf | Exist
Mursyid | Yes | 63B9F890-ECD8-4F6A-9B8E-74E1AF8BE9FA | 3F08DF2D-BADD-4CAC-88AE-02D195FB997B | SNPA-11 | 74D516A0-C1C8-43DA-92BD-7868825EE537 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf |  |  |  | Uploads\74d516a0-c1c8-43da-92bd-7868825ee537.pdf | Exist
Mursyid | Yes | F65DBC87-E983-44CE-BA8C-2639D110BF1D | 3F08DF2D-BADD-4CAC-88AE-02D195FB997B | SNPA-11 | 73E1CA07-D268-4AEB-988F-8B8D17ECB3F8 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SNPA-11 EOWR.pdf | SNPA-11 EOWR.pdf |  |  | Uploads\73e1ca07-d268-4aeb-988f-8b8d17ecb3f8.pdf | Exist
Mursyid | Yes | 08467B7C-F0D0-4813-AB2A-81CB45979B84 | CCD39497-7DDF-4FED-8507-26E3E4C0667B | SNPA-12 | C714BC50-D625-4B95-A2E7-E5327F36BFB2 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-SOW-0005-00_NOOP for SNPA Dev Project Revisit 2 Phase II.pdf |  |  |  | Uploads\c714bc50-d625-4b95-a2e7-e5327f36bfb2.pdf | Exist
Mursyid | Yes | A9491482-5119-4633-A759-0A640540F9E2 | CCD39497-7DDF-4FED-8507-26E3E4C0667B | SNPA-12 | 31FF9CDA-27AD-4E3A-8FCB-4F73CE354E73 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0017-00_SNPA-12ST1 EOWR.pdf | MOM-SK309-72-DNC-RP-0017-00_SNPA-12ST1 EOWR.pdf |  |  | Uploads\31ff9cda-27ad-4e3a-8fcb-4f73ce354e73.pdf | Exist
Atikah | Yes | 63A9BABD-0515-43B8-A9AA-9F0517285CC6 | 980C5EE9-7FBC-4D39-8B05-85D64E85577F | SNPA-24 | 55C66FCC-7392-4963-917C-5A051294A333 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DR-TN-0002-00_1_SNPA 23_24_Revisit 2 Phase 3_Rev 1.pdf |  |  |  | Uploads\55c66fcc-7392-4963-917c-5a051294a333.pdf | Exist
Atikah | Yes | 4FC57FF6-4E8A-4660-8430-3D3DB6F32F82 | 980C5EE9-7FBC-4D39-8B05-85D64E85577F | SNPA-24 | D190D03F-19C0-49E3-8AA1-520FD4904CC2 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MOM-SK309-72-DNC-RP-0021-00_SNPA-24 EOWR.pdf | MOM-SK309-72-DNC-RP-0021-00_SNPA-24 EOWR.pdf |  |  | Uploads\d190d03f-19c0-49e3-8aa1-520fd4904cc2.pdf | Exist
Atikah | Yes | 600AD254-2C6C-4C63-9E09-0D62DE53911E | F3F395E0-621B-46C9-805F-BF0574D82277 | S-SW1-P17 | 5F647512-66F8-4296-8471-FBB531894DA4 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-H-10-DR-RP-0001-00_SNP Phase 2 Dev_NOOP.pdf |  |  |  | Uploads\5f647512-66f8-4296-8471-fbb531894da4.pdf | Exist
Mursyid | Yes | 9CB6903F-D74A-436E-91DA-1DB4788D0F5B | C82C1197-20FD-4687-B19A-16BEAE6043D8 | TBK-A4 | 2FEC604B-ABD5-474E-92B6-F6698BB51902 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK-A4 Final Well Report Rev 1 (Final to MPM).pdf | TBK-A4 Final Well Report Rev 1 (Final to MPM).pdf |  |  | Uploads\2fec604b-abd5-474e-92b6-f6698bb51902.pdf | Exist
Mursyid | Yes | 3048173B-0F02-4361-8606-8CD23EB4EEF0 | C82C1197-20FD-4687-B19A-16BEAE6043D8 | TBK-A4 | 6AABC5A6-FBCB-4A28-86F0-7B98EE11CD14 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TBK_A4 MPM.pdf | TBK_A4 MPM.pdf |  |  | Uploads\6aabc5a6-fbcb-4a28-86f0-7b98ee11cd14.pdf | Exist
Mursyid | Yes | 807D34D0-D9FB-424E-9B61-772BECEA6085 | 4B4420B8-A6A6-41EF-BBA0-5E8D4AA59E0D | TELOK-B6 | 58E53CB8-82C4-4EE6-B784-123F480C368A | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | TELOK-B5_TELOK B6_NOOP.pdf | TELOK-B5_TELOK B6_NOOP.pdf |  |  | Uploads\58e53cb8-82c4-4ee6-b784-123f480c368a.pdf | Exist
Mursyid | Yes | 8F942681-854B-4BAF-BA99-FFA2A7BAC65D | 4B4420B8-A6A6-41EF-BBA0-5E8D4AA59E0D | TELOK-B6 | BCCC701F-B26D-4F33-97FD-16CB97C8B1D0 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Telok B6 Final Well Report (MPM Submission).pdf | Telok B6 Final Well Report (MPM Submission).pdf |  |  | Uploads\bccc701f-b26d-4f33-97fd-16cb97c8b1d0.pdf | Exist
Mursyid | Yes | 08DBF9D9-E9BC-4340-ADCA-9F486F89F6A7 | 251CE7CE-B71F-43EC-96F6-67D770233F6C | WEST BELUMUT A-06 | BFE95857-B47B-45E7-BD9A-F48BC1FF4529 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WB A06 - signed.pdf |  |  |  | Uploads\bfe95857-b47b-45e7-bd9a-f48bc1ff4529.pdf | Exist
Mursyid | Yes | 8A795706-6937-4DE6-8467-F3A6B49EF57D | 251CE7CE-B71F-43EC-96F6-67D770233F6C | WEST BELUMUT A-06 | 73B64099-2870-40B5-A090-299E1AD37D4F | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | WBA-06 FWR.pdf |  |  |  | Uploads\73b64099-2870-40b5-a090-299e1ad37d4f.pdf | Exist
Mursyid | Yes | 9CFA87D7-12C3-4C04-B72B-65EDD44A7F53 | CCB99400-EBD9-4E9D-8237-32F0C84D0D76 | WPPB-15/15ST1 | 13FB0770-1627-49AD-9F77-AD9E033F752D | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK309-61-DNC-RP-0001-00_WPPB Infill Campaign EOWR.pdf |  |  |  | Uploads\13fb0770-1627-49ad-9f77-ad9e033f752d.pdf | Exist
Mursyid | Yes | 1A55BFBE-414C-49FE-B95B-DED357C03FA9 | 85DC6FD1-123F-4457-962A-4609A35E14C5 | WPPB-16 | 2E35C8BD-2362-46A7-B1B1-B270121A197C | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | MY-SK309-61-DNC-RP-0001-00_WPPB Infill Campaign EOWR.pdf |  |  |  | Uploads\2e35c8bd-2362-46a7-b1b1-b270121a197c.pdf | Exist
Atikah | Yes | 01E68037-6417-49F8-8828-4719137C9302 | 59F4723D-8526-491F-A007-A75B56ECED7A | ZUHAL EAST-A | 65E5258A-83A8-4341-AE25-E92852423BFA | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ZUHEWS24_ZUHAL-EAST-A_PCSB.pdf | SBO3ZUHEWS24_ZUHAL-EAST-A_PCSB.pdf |  |  | Uploads\65e5258a-83a8-4341-ae25-e92852423bfa.pdf | Exist
Atikah | Yes | 09C2E817-1364-43AA-9D37-DF19AF7727C6 | 59F4723D-8526-491F-A007-A75B56ECED7A | ZUHAL EAST-A | E839296F-FCF2-4275-82AA-769E96FCD897 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ZUHAL EAST- A NOOP (NEW TARGET).pdf | ZUHAL EAST- A NOOP (NEW TARGET).pdf |  |  | Uploads\e839296f-fcf2-4275-82aa-769e96fcd897.pdf | Exist
Atikah | Yes | C7B5866F-A929-4307-B31D-9667260DCF50 | CA14383C-C7FF-4F16-AA21-AD275883457E | ZUHAL EAST-C | AA36B26B-72F8-4A04-900A-97B05865776E | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | SBO3ZUHEWS26_ZUHAL-EASTC_PCSB.pdf | SBO3ZUHEWS26_ZUHAL-EASTC_PCSB.pdf |  |  | Uploads\aa36b26b-72f8-4a04-900a-97b05865776e.pdf | Exist
Atikah | Yes | F5038E5D-AF14-4415-A4B5-97300EFC13C1 | CA14383C-C7FF-4F16-AA21-AD275883457E | ZUHAL EAST-C | BC8916DE-765F-4EB5-BA2E-87C1D0781E3D | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | ZUHAL EAST-C NOOP (NEW TARGET).pdf | ZUHAL EAST-C NOOP (NEW TARGET).pdf |  |  | Uploads\bc8916de-765f-4eb5-ba2e-87c1d0781e3d.pdf | Exist
Atikah | Yes | 118E50AF-6DED-4146-9AB1-8CF0BCA7ACFF | 3D223E44-04C8-488E-A76E-F6FF00B0A020 | ZUHAL SOUTH-1 | FBBC47B7-2DDD-48D7-8ACA-F890DDD51CE7 | 1 | FWR | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | PCSB FWR (Zuhal South-1) Final 04122017.pdf | PCSB FWR (Zuhal South-1) Final 04122017.pdf |  |  | Uploads\fbbc47b7-2ddd-48d7-8aca-f890ddd51ce7.pdf | Exist
Atikah | Yes | 0DA56119-F2B8-4F45-A72E-7CCF1EA42A85 | 3D223E44-04C8-488E-A76E-F6FF00B0A020 | ZUHAL SOUTH-1 | 4C4460C2-4F3F-43B5-9D23-6F04ABBD7497 | 1 | NOOP | application/pdf | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 0 | Zuhal South-1 NOOP (Final).pdf | Zuhal South-1 NOOP (Final).pdf |  |  | Uploads\4c4460c2-4f3f-43b5-9d23-6f04abbd7497.pdf | Exist